## Slide 1
J. G. Weisend II
Deputy Head of Accelerator Projects
April 2, 2014
Actions at ACCSYS Resulting from the Recommendations of the Annual Review

## Slide 2: Methodology
A total of 9 recommendations from the Annual Review addressed ACCSYS issues (including 1 in the Annual Review’s top ten worries)
One of these recommendations (concerning the communication of radiation protection issues to the public) was reassigned to the Communication Division
Each of the remaining 8 recommendations was:
  Interpreted for clarity by ACCSYS
  Assigned actions and deliverables
  Assigned to a staff member
The deliverables were to either be completed by or have their status reviewed at this TAC Meeting

## Slide 3: Recommendation 2013-1 (Top 10 Worry #3)
Original Recommendation:
Basic assumption of 1 W/m used as Level 1 requirement with major implications inter alia on licensing, shielding and operation; needs to be confirmed by realistic end-to-end beam simulations including errors, showing sufficient margin. Normal operation envelope should include beam loss scenarios.
Interpretation
Verify that ESS accelerator can provide average beam power of 5 MW with beam loss less than 1 W/m Verify the shielding is adequate for 1 W/m

## Slide 4: Recommendation 2013-1 (Top 10 Worry #3)
Status
Verify that ESS accelerator can provide average beam power of 5 MW with beam loss less than 1 W/m
Analysis is ongoing. See Talk by M. Eshraqi
Verify shielding is adequate for 1 W/m
Tech Note is under review. See Talk by L. Tchelidze

## Slide 5: Recommendation 2013-1 (Top 10 Worry #3)

## Slide 6: Recommendation 2013-2
Original Recommendation
Accidental beam loss: need to establish “worst case” scenarios based on risk analysis and to conduct simulations to determine appropriate shielding (interface with CF) and system interlocks for personnel protection
Interpretation
Establish and document worst case beam loss scenarios to use for shielding analysis

## Slide 7: Recommendation 2013-2
Status
Done - Tech Note has been written and been reviewed. It should be submitted to EPG for final approval before the end of March – See Talk by L. Tchelidze

## Slide 8: Recommendation 2013-4
Original Recommendation
Reassess beam instrumentation based on effective strategy of commissioning and needs of operation
Interpretation
Review the type, location, number and performance of beam-line instruments for: · Sequence for beam commissioning . Operations mode . Maintenance mode

## Slide 9: Recommendation 2013-4
Status
Draft Tech Note on Commissioning Plans and Diagnostics has been written and is under review
Additional information will be developed during a beam commissioning workshop In April
- See Talk by M. Muñoz
Beam Diagnostics retreat was held and additional beam diagnostic optimization is on going
– See Talk by A. Jansson

## Slide 10: Recommendation 2013-5
Original Recommendation
Recommend push for faster prototyping of all accelerating structures and raster magnet system
Interpretation
Review the schedule to determine if the strategy for prototyping is time-efficient, and to determine which if any activity durations can be shortened and milestones moved forward. Analyze what dependent activities are impacted and how they are impacted, and change the plan if necessary. Analyze changes to risks - new risks, changed risk assessments (probability or impact), or changed risk mitigation.

## Slide 11: Recommendation 2013-5
Status
Done - Excel spreadsheet listing all prototypes, possibility of speeding them up and impact of such changes is complete along with a covering report
Results: Almost all prototyping is technically limited and can’t be sped up. The exception is the raster magnets and associated power supplies. Their prototypes will be completed 6 – 8 months sooner in the new schedule.

## Slide 12: Recommendation 2013-5

## Slide 13: Recommendation 2013-6
Original Recommendation
Establish criteria for success and formalize decision process in advance for decision of IOTs (end 2017)
Interpretation
Same as above
Status
Done: These captured in the following document
“Selection Criteria for the High Power Source for the High Beta section of the ESS Linac“ ESS-00008307 in CHESS

## Slide 14: Recommendation 2013-7
Original Recommendation
Analyze and develop IKC potential for beam instrumentation
Interpretation
Same as above
Status
Beam instrumentation planning (including a dedicated offsite retreat) has been changed to include significantly more IKC opportunities.
Meetings have been held with a number of interested countries on possible contributions. Areas of particular interest include: MEBT (Spain), LEBT ( France), BPM/BCM (Germany) and BLM (joint procurement with CERN)
See Talk by A. Jansson

## Slide 15: Recommendation 2013-9
Original Recommendation
Translate high-level requirements for reliability and availability into performance figures for elementary components and systems, identify discrepancies with state-of-the-art and implement corrective / mitigating actions (overcapacity, redundancy, reparability, “hot” spares, etc.)
Interpretation
Develop requirements to L4 for, as a minimum, availability and for reliability. Trace requirements to L1 availability and reliability requirements to ensure the breakdown is mathematically correct.

## Slide 16: Recommendation 2013-9
Status
Recently hired a reliability engineer (E. Bargallo’) with experience in accelerator facilities
He has begun a detailed analysis of systems (starting with the RF) to investigate which failures would have the most impact on beam performance and from that which mitigations would have the most impact
Place holders for L4 reliability requirements have been created but defining these requirements and tracing their impact back up to L1 is dependent on the completion of these more detailed studies

## Slide 17: Recommendation 2013-10
Original Recommendation
Integrate utilities into reliability/availability studies
Interpretation
Same as above
Status
This effort is underway. Reliability of utilities is defined as part of the Conventional Facilities Project but is integrated into the rest of ES via the Cross Functional Working Group on Reliability/Availability.

## Slide 18: Summary
ACCSYS has a total of 8 recommendations from the 2013 Annual Review
All are being addressed
Currently:
  3 are complete (Recommendations 2, 5 and 6)
  3 more will be complete by May (Recommendations 1, 4 & 7)
  2 (Recommendations 9 and 10) require further work and should be completed by the end of 2014
ACCSYS has benefited from all of these recommendations