## Slide 1: Integrated Control Systems Status and Plans
Garry Trahern
Head of ICS Division
www.europeanspallationsource.se
TAC 9, 3rd April, 2014, ESS, Lund

## Slide 2: Overview
ICS Project status
In Kind status
Staffing status
CS Services Framework Agreement decision
PSS progress
TAC 9 Questions

## Slide 3: ICS Project Status I
WBS
  WBS scrubbed post review, bottom-up costing under way
Interfaces
  Ion Source, LEBT control specification developing with Saclay
  Cryogenic plant control specification for plant tender completed
  RF Cell interlock architecture and control interfaces developing
  CF control architecture and interfaces being developed
  SLA with NSS on motion control and sample environment
Hardware and Integration
  Integration: BCM, Wire Scanner, LLRF, DoD/PostMortem, Timing, Detector Bulk Data, Motion Control
  PLC test stand
  Timing System
Core software and Applications
  SDD for ESS/EPICS community roadmap with Tata/ITER, Alarm Strategy with GoalArt
  RBAC, Configuration, Naming, Lattice, Cable databases and related tools with DISCS collaboration
  OpenXAL, Python and Script Execution Environment
MPS BIS architecture
  Initial discussions on hardware collaboration with CERN and DESY occurred March 17-18

## Slide 4: ICS Project Status II
Milestones for 2014
  MPS BIS External Review Q3
  Application framework(s) decision Q3
  Lattice database V2 Q2
  ESS Single PLC decision Q3
  Control Box Platform freeze Q3
  Timing System 2014 Q4
  PSS Preliminary Design Q4
  High level ICDs for Accelerator, Target, NSS, CF Q4

## Slide 5: ICS Construction Phase IKC Potential
WBS Code | WBS Name | Budget (€) | In Kind Potential (%)
14 | Integrated Control Systems 2014-EOC | 72,825,120 | 59
14.1 | Management & Administration | 4,669,200 | 0
14.2 | Applications | 6,514,575 | 53
14.3 | Software Core Components | 8,469,252 | 42
14.4 | Hardware Core Components | 6,989,825 | 74
14.5 | Protection Core Components | 9,186,223 | 12
14.6 | Equipment | 12,257,150 | 74
14.7 | Control System Infrastructure | 4,552,401 | 75
14.8 | Physics | 1,727,335 | 36
14.10 | Accelerator integration support | 6,711,648 | 69
14.11 | Target integration support | 1,675,650 | 70
14.12 | Instruments integration support | 2,763,501 | 67
14.13 | Conventional Facilities integrations support | 2,332,800 | 72
14.14 | Test stands integration support | 1,875,560 | 70

## Slide 6: In Kind status
France / Saclay contribution for NC accelerator control
  Ion Source device specification and detailed plan for control being developed
Hungarian contribution discussed with company Evopro
Institute for Energy (Halden) EOI for control room design on hold while Norwegian contribution is clarified
Discussions with, but nothing definite yet
  Italy (Elettra),
  Spain(ESS Bilbao),
  Switzerland (PSI) ongoing
Not in-kind, but CERN/DESY collaboration on MPS BIS - first meeting completed

## Slide 7: ICS Staffing 2014
Hiring status
  2013 EOY Staff level: 11
  2014 Q1 staff level: 12
  Planned 2014 EOY level: 35
Hiring plan:
  Advertised in Q1
    Deputy Head of Division
    MPS PLC and FPGA developers
    Software Architect (Services, Databases), Senior Software Developer (Applications)
    PSS Lead Engineer
  To be prioritized in Q2
    Physics Lead Developer
    Lead integrators for: Accelerator, Target
    CS Infrastructure Lead Engineer (Networks, Data Centre)
External expertise:
  4 Contracted Integrators present onsite from Q1
  Number will increase when required
  PSS contractor engaged April 2014
  Goal Art for Alarm Strategy

## Slide 8: CS Services Framework Agreement
Decision
  Re-tender of CS services agreement after May 2014
  Current FA will be extended to end of 2014 while tender process is completed
  The new FA can keep awarded companies on board beyond 2019 in principle
Problem
  FA is cash ‘out the door’ regardless of which companies are awarded so a project funding solution for ICS is needed
  Registered top risk that IKC may be insufficient for funding ICS

## Slide 9: Personnel Safety System Status I
Paul Wright (SNS) will join from April 21 for ~6 months to work on PSS design
Short term goal is to clarify scope and prepare project plan by time of mini-review at end of May
PSS lead engineer could join ESS during this period of P. Wright’s stay to collaborate and take over the PSS activity
Other PSS hires will follow successful hire of lead PSS engineer

## Slide 10: Personnel Safety System Status II
From initial discussions scope of the work includes:
  Personnel Safety System – Protects workers from prompt radiation due to beam operations. PSS will be required for the accelerator, target and instruments
  Oxygen Deficiency System - Protects workers from hazards associated with cryogenic gases. ODH systems will be required for the LINAC tunnel and cryogenic plant buildings
  Area Radiation Monitors - Monitors used to protect workers from prompt radiation due to beam operations and activated components (Target building)
  Storage Pit Room Access Control - Protects workers that enter storage pit room from radiation from the Target hot cell
  Environmental Radiation Monitoring – Radiation/sampling systems for central exhaust stack and boundary monitors to comply with environmental regulations

## Slide 11: TAC 9 Questions – ICS perspective
- Are the measures we have proposed to resolve the issues and review / implement the recommendations of the 1st ESS Annual Review adequate and sufficient?
  Yes, there are good plans in place to achieve milestones on schedule
- Are the technical risks of the constructions plans for Controls comfortably low enough of for safely achieving start of initial operation in 2019 on time, budget and performance?
  We have not identified a serious technical risk, but we will leverage existing technologies to mitigate such risks if they arise. Risks that we have identified, e.g., in CF will we have sufficient conduit space for cables and enough space allocated for racks, etc. We are working on this with CF and Accelerator now…
- What intermediate early key milestones are required to be met on the way?
  Control box platform, Single PLC Decision, PSS & MPS designs, Interfaces understood, then Application frameworks and Services in place
- Is there a need to identify / study additional back-up options for securing timely start of initial operations?
  We are open to suggestions!