## Slide 1: Beam Instrumentation for the ESS Accelerator
Andreas Jansson

## Slide 2: Overview
Status of beam diagnostics
  Background on re-scoping
  Status of design work.
Strategy for in-kind contributions
  In-kind/in-house split of efforts
Commissioning plan input
  Number of devices and performance

## Slide 3: Diagnostics (WP7) Team
Name | Role
C. Böhme | Non-invasive profile, Cold Linac & HEBT BI Coordination, Cables and Rack Space Coordination, Mech Designer Coordination (on leave)
B. Cheymol | Emittance, WS, FC, Warm Linac BI Coordination
H. Hassanzadegan | BPMs, BCM, BI Electronics Integration Coordination
A. Jansson | WP7 leader, BI Group Leader
I. Kittelmann | Bunch length/Longitudinal profile
T. Shea | Target Diagnostics, A2T BI Coordination (also ACCSYS lead engineer on 50%)
L. Tchelidze | BLM, Loss simulations (also radiation safety/shielding)
C. Thomas | Target Diagnostics Optics, Controls/EPICs Integration Coordination, Motion Control Integraton Coordination
H. Kocevar | EPICs integration, software
M. Donna | FPGA development (joining soon)
M. Jarosz | oPAC Fellow (oPAC Funded), Beam Loss
C. Roose | oPAC Fellow (oPAC Funded), Non-invasive profile
T Grandsaert | Mechanical Designer (Design Office)
M Puls | Mechanical Designer (Design Office)

## Slide 4: Initial diagnostics scope
Initial diagnostics scope and requirements was based on some simple considerations, e.g.
  Full coverage BLMs
  One BPM per quad (where possible)
  Current measurement between each major linac section.
  Transverse and longitudinal profile measurement at each major optics transition
Requirements developed by diagnostics group, concurred by beam physics
Since then, there was (at least one) major linac redesign and budget crunch.

## Slide 5: Updated diagnostics scope
Task for annual review: reduce BI scope/cost significantly while maintaining possibility to retrofit later (phase I/phase II). Quick solution:
  Maintained NRE (reversible)
  Significantly reduced # profile devices and some FCs. Instrument only every 2nd BPM (one per cell). Cut all dedicated Halo (ie use WS)
  Done in short order with intent to refine later.
Annual review recommended to refine the scope based on a commissioning/operations plan.

## Slide 6: Annual Review
[…]
Reassess beam instrumentation based on effective strategy of commissioning and needs of operation
Analyse and develop IKC potential for beam instrumentation
[…]

## Slide 7: Commissioning planning
Initial draft plan just released (previous presentation), needs to be refined.
Will review diagnostics device counts placement and performance requirements based on this.
Also need to consider operation.
Open questions related to off-site tests & temporary diagnostics.

## Slide 8: Current system counts
 | BLM | BCM | BPM | Slit | Grid | FC | WS | NPM | Img | Halo | BSM
LEBT | 0 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
MEBT | 0 | 4 | 6 | 1 | 1 | 1 | 4 | 2 | 0 | 0 | 1
DTL | 15 | 7 | 15 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 1
Spk | 39 | 0 | 26 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
MB | 27 | 1 | 18 | 0 | 0 | 1 | 3 | 3 | 0 | 0 | 1
HB | 63 | 1 | 42 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
UHB | 67 | 2 | 44 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 1
A2T | 19 | 2 | 11 | 0 | 1 | 0 | 3 | 3 | 2 | 3 | 0
DmpL | 6 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
TOTAL | 236 | 21 | 165 | 2 | 4 | 5 | 17 | 12 | 3 | 4 | 4
Note: Unchanged since review. WILL CHANGE based on e.g.
commissioning planning output.

## Slide 9: Linac/Beamline Layout
For lack of a better tools, have so far maintained our own diagnostics layouts.
Diagnostics is now in BLED, along with the latest (Optimus+) lattice
Working to make CHESS/Catia global model consistent with this.
In the process, clarifying responsibility boundaries and procedures.
Regular beamline integration meetings to start soon.

## Slide 10: Linac Warm Sections

## Slide 11: Racks, Cables, IOCs & PVs
Have cable and rack lists, working to put into database.
List of IOCs and PVs provided to ICS (will eventually also go in DB).

## Slide 12: BLM
Plan to use LHC style ionization chamber as main detector
Procurement with CERN, along with last spare run.
Have electronics requirements, investigating implementation options.
Simulation of beam loss patterns as oPAC Fellow project.

## Slide 13: BCM
Plan to use ACCTs.
Developed first prototype electronics with differential current functionality (collaboration with ICS /CosyLab).
  Test case for FPGA coding framework.
Discussing FPGA and analog front end development with DESY.
  RTM to include MIS interface

## Slide 14: Differential BCM

## Slide 15: BPM
Working with DESY on cold linac button BPMs (have first prototype).
INFN Legnaro to do DTL BPMs
Discussion with Bilbao on MEBT BPMs
Working with SLAC on analog front end development (and general uTCA.4 knowledge transfer)
  also coordinating with LLRF.
Working with DESY for FPGA development on SIS8300

## Slide 16: Cold BPM prototypes

## Slide 17: BPM Electronics
uTCA.4 prototyping platform.
Major players: SLAC and DESY
(collaborating with both)
Caveat: No potential IKC partners
(other than DESY) use uTCA.4 fully.
uTCA
test setup

## Slide 18: Buttons vs striplines

## Slide 19: Emittance Monitor
Early in-kind from Saclay on LEBT Allison Scanner (similar to IFMIF).
Simulations of multiple scattering and space charge effects ongoing for MEBT slit/grid system. Discussing on in-kind for mechanical design with Bilbao.
LIPAC Allison emittance scanner

## Slide 20: Faraday Cups
Conceptual/thermal studies done for most FCs.
  LEBT: Full power capable (commercially available)
  MEBT: In progress
  DTL (tank 2-5): Dual degraders needed. Difficulty handling full current diagnostics pulse 100us @1Hz. 10us @ 14Hz OK.

## Slide 21: Wire Scanners/Halo
Warm Linac:
  Carbon Wire, SE signal readout
  Single actuator at 45 degrees
  Thermal load limit 62mA pulse to 50us in MEBT and 100us in DTL at 1Hz rep rate.
Cold linac:
  Tungsten Wire, SE signal readout in spokes, Scintillator downstream of spokes
  Dual actuators, shorter travel
  Thermal load limits to 62mA pulse to 100us at 1Hz
HEBT & A2T
  Fast wire scanners (single pulse). Looking at recent CERN design
  Capable of full beam operation
Wire scanners also used for Halo
CERN fast wire scanner

## Slide 22: Non-invasive profile
Tool for high power operation.
Ionization profile monitors for cold linac, luminescence for warm sections.
Co-located with wire scanners.
Plan for optical PMT readout w/o MCP. Ion to photon conversion efficiency studies done at Stockholm Uni.
Started discussion with RAL on HV tests

## Slide 23: Stockholm tests

## Slide 24: Longitudinal Profile
Standard Feschenko monitor works well in MEBT and DTL.
New method needed in HEBT. Looking into e.g. OTR light + streak camera.
Intermediate energy (after frequency jump) method under study.

## Slide 25: Monolith and beam image
Notes: Individually replaceable parts, could be replaced with blanks.
Working on reducing waste, tighter integration etc. Optimize aperture for optical line of sight.
Very tightly coupled with Target Division.
Nex step is value engineering

## Slide 26: Target Diagnostics
Dedicated diagnostics plug between window and target.
Integrated effort with target and beam instrumentation group.
Plan for optical imaging, halo thermocouples and dedicated raster scanning BPM.
Not upgradable area, so including possible future devices in layout (may be replaced by blank plugs).
Investigating collaborations with Stony Brook/University West, PSI

## Slide 27: Monolith Diagnostics Plug
Modularity
Cooling
Waste minimization
Lifetime
Material restrictions
Thermo-mechanical issues
IFMIF concept

## Slide 28: Optical Imaging
Have initial optical design for PBW viewing system.

## Slide 29: In-kind strategy
Re-structuring WP7 plan to better fit in-kind contributions (negotiations)
  Previously, NRE grouped by system (e.g. BPM) and production costs grouped by linac section.
  Now grouping by unique systems (beamline components or electronics)
Generally, a fraction of the NRE (up to 50%) and small fraction (~10%) of production kept in Lund.

## Slide 30: System synergies/dependencies
Repackaging to be done by mid-april (for 2014), updated cost estimates once
new system counds and requirements are know.

## Slide 31: Potential collaborators
Note: incomplete list
Note II: many small IKC contracts

## Slide 32: Summary
Re-organizing the plan for in-kind
Start re-planning number of devices, and possibly performance requirements, based on ongoing commissioning planning activity
Maintain a strong team in Lund
  Conceptual design involvement
  Oversight of detailed design and production
  Handover, commissioning and operation

## Slide 33: BI Schedule Highlights
2010
14
11
12
13
15
19
16
17
18
20
21
22
23
Start LWU Installation
Injector test at Saclay
Early access to tunnel
SC linac 570 MeV ready
First protons to target
Source Test Catania
NC linac ready
LEBT Diagnostics needed
MEBT Diagnostics needed
Readout Electronics Needed
Most beamline devices needed
Target Diagnostics needed
Proton Beam Instrumentation plug installation

## Slide 34: WP7 (Diagnostics) Cost in primavera
Work Unit Groups | Current
Diagnostics Design (NRE), Integration & Management | 10.9 MEuro
Warm Linac Diagnostics production cost | 3.4 MEuro
SCL & HEBT Diagnostics production cost | 5.7 Meuro
A2T & Dump Diagnostics production cost | 2.6 MEuro
Note: distribution will change.

## Slide 35: Interfaces
Internal:
Lead Engineers (requirements)
Beam Physics (sensitivity studies, input to requirement)
Other WPs (e.g. space allocation)
External:
ICS (integration of devices, split of development responsibilities, MPS)
Target (target diagnostics)
NSS (beam pulse information for experiments)

## Slide 36: In-kind open questions
Is electronics to be provided by the design in-kind partner (preferred), or purchased to spec by the vertical integrator partner?
Vertical integration responsibility?
Many small IKC agreements to put in place. Relatively large overhead (compared to e.g. a cryomodule)