## Slide 1
M. Munoz
April 2, 2014
Beam Commissioning at ESS

## Slide 2: General Organization
Review in Autumn
Losses studies
Beam Commissioning Planning
Working Group
Define goals and procedures
ICS
Requirements:
Beam Instrumentation
Current status

## Slide 3: Planning organization
Working group
Objectives and procedures planning
Extract requirements
  Beam instrumentation
  High level applications collection
Workshop on proton Linac commissioning 8th and 9th of April. Review of our plans.

## Slide 4: Working group
Composition:
  Thomas Shea: L
  Eugene Tanke
  Mohammad Eshraqi
  Rihua Zeng
  Stephen Molloy
  Håkan Danared
  Marc Munoz
The documentation produces is then reviewed including experts from ICS, Beam Instrumentation, RF, Lead engineers, etcs

## Slide 5: ESS commissioning vs Beam Commissioning
Beam commissioning is a part of the global ESS commissioning
Beam commissioning is the verification of the system with proton beam
  Systems testing before beam commissioning
Ready the beam for Target commissioning and Neutron instrument commissioning
When planning the Beam Commissioning we are also identifying some of the steps of the system testings/ESS commissioning

## Slide 6: Commissioning Personnel
Define the ESS personnel and external collaborators to be involved in Beam commissioning
Integration of dedicated Linac operators
Plan the training for the commissioning personnel
Training in the period 2017-2019

## Slide 7: Commissioning and Transition to Operation Steps
Commissioning Phase I
  Normal conducting
  Spoke and medium beta:
  Commissioning to Beam Dump
  Commissioning to Target: Finish by 28 Aug 2019
Start of Initial Operations: September 2019
Phase II
  High beta cryomodules 1-11: Finish by 6 September 2021
Phase II
  High beta cryomodules 12-21: Finish by 22 September 2022
End of Initial Operations: End 2025

## Slide 8: Goals for commissioning and Initial Operations
 | Date | Current | Energy | Power
Phase I (start of Initial Operations) | July 2019 | 6.25 mA | 0.4 GeV | 100 kW
 | May 2021 | 56 mA | 0.571 GeV | 1.26 MW
Phase II | September 2021 | 25 mA | 0.8 GeV | 0.8 MW
 | August 2022 | 50 mA | 1.3 GeV | 2.6 MW
Phase II | September 2022 | 31 mA | 1.6 GeV | 2 MW
End of Initial Operation | End 2025 | 62.5 mA | 2 GeV | 5 MW
In all cases the proton beam should be stable and reliable for Target Commissioning and User operation
Working on a proper definition of stable

## Slide 9: Cartoon of a possible Power Ramping Scenario
Chart: 
| 43651.0 | 43739.0 | 43831.0 | 43891.0 | 44013.0 | 44105.0 | 44197.0 | 44256.0 | 44317.0 | 44470.0 | 44531.0 | 44576.0 | 44621.0 | 44682.0 | 44743.0 | 44835.0 | 44927.0 | 45108.0 | 45292.0 | 45536.0 | 45658.0 | 45748.0 | 45901.0
Energy [GeV] | 0.2 | 0.2477 | 0.29757 | 0.33009 | 0.39622 | 0.44609 | 0.49595 | 0.52794 | 0.561 | 0.561 | 1.3 | 1.3 | 0.8 | 0.91172 | 0.99414 | 1.0766 | 1.1883 | 1.3 | 1.3 | 1.2 | 2 | 2 | 2 | 1.6 | 1.6345 | 1.7024 | 1.7715 | 2 | 2 | 2 | 2
Power [MW] | 0.1001 | 0.12397 | 0.2234 | 0.33042 | 0.49577 | 0.6698 | 0.86879 | 1.0569 | 1.2635 | 1.4039 | 0.32532 | 0.65065 | 0.8008 | 0.91263 | 1.2439 | 1.6164 | 2.0816 | 2.6026 | 2.9279 | 3.003 | 0.5005 | 1.001 | 1.5015 | 2.002 | 2.0452 | 2.5562 | 3.1032 | 4.004 | 4.004 | 4.5045 | 5.005
Current [mA] | 12.5 | 12.5 | 18.75 | 25 | 31.25 | 37.5 | 43.75 | 50 | 56.25 | 62.5 | 6.25 | 12.5 | 25 | 25 | 31.25 | 37.5 | 43.75 | 50 | 56.25 | 62.5 | 6.25 | 12.5 | 18.75 | 31.25 | 31.25 | 37.5 | 43.75 | 50 | 50 | 56.25 | 62.5

## Slide 10: Beam dumps and targets
Beam Destination | Max. power [kW] | Peak Current [mA] | Energy | Pulse Length | Repetition Rate [Hz]
Faraday Cup in the LEBT | 0.63 | 100 | 75 keV | 6 ms | 14
Faraday Cup in the MEBT | 0.3 | 62.5 | 3.6 MeV | 50 µs | 1
Faraday Cup between DTL and spokes. | 0.5 | 62.5 | 90 MeV | 100 µs | 1
Beam up to the beam stop behind the 4th cryo module in the medium beta section. Only for spokes | 10 | 62.5 | 200 MeV | 100 µs | 1
Tuning dump | 12.5, In evaluation | 62.5 62.5 | 2 GeV 2 GeV | 10 µs 2.86 ms | 14 0.1
High power target | 5000 | 62.5 | 2 GeV | 2.86 ms | 14

## Slide 11: Tuning Dump
Evaluation of the need of the Tuning Dump:
  Power,
  Duty factor
  Present design 12.5 kW:
    62.5 mA, 1 Hz, 100 ms, 2 GeV
Evaluated against the need of space
  Alternative 1 kW
    62.5 mA, 1 Hz, 8 ms, 2 GeV
Consequences during Operations:
  Neutron instruments need to access LoS and other areas
  Most Machine Study time will be on Tuning Dump

## Slide 12: Warm Linac Commissioning Steps
Divided by sections:
  IS+LEBT
  RFQ
  MEBT
  DTL
An a final step of the whole NC linac

## Slide 13: IS+LEBT
Fully beam commissioned at in-kind partner
Beam commissioning at ESS:
  Verification of partner commissioning
  Verification of installation at ESS
  Verification of ESS system integration
  Possibility of doing the beam commissioning before installation of the RFQ
    Temporary diagnostic and beam dump

## Slide 14: Ion Source
Objectives:
Verification beam out of the IS
Procedure:
Characterize the beam out of the ion source (IS)
  Beam current: average peak pulse, pulse length, from waveform shape
  Measure transverse emittances
  Measure energy (direct high voltage measurement, other possibilities)
Stability test
  Short term stability: Shot to shot reproducibility, flat top
  Long term (24 hours) stability

## Slide 15: LEBT
Objectives:
Center the beam at the entrance of RFQ
Setup the Chopper
Setup the iris
Characterize beam at entrance of RFQ for a range of current
MPS testing: Beam permit system, Beam abort system
Ramping up transmission

## Slide 16: LEBT-Procedures

## Slide 17: RFQ, MEBT, DTL
Beam commissioning objectives and procedure defined
RFQ: MEBT used a the diagnostic line of the RFQ
  Possibility of temporary diagnostic and beam dump under study after definition of MEBT diagnostic components
MEBT: Not all of the required measurements could be done with the DTL in place:
  Possibility of temporary diagnostic and beam dump under study after definition of MEBT diagnostic components
DTL: Not all of the required measurements could be done without the Spokes diagnostic in place:
  Possibility of temporary diagnostic and beam dump under study

## Slide 18: Warm Linac
Objectives
Fault and Losses test
Transmission optimization
Stability

## Slide 19: Superconducting Part
Initial Operations would be without the High Beta section
Three clear stages of beam commissioning:
  Spokes/Medium beta/HEBT-AT2B: 571 MeV (End of Phase I)
  High beta, modules 1-11: 1.3 GeV
  High beta, modules 12-21: 2 GeV
Target commissioning, Instrument commissioning and user operation between those stages

## Slide 20: Spokes

## Slide 21: Medium Beta to Tuning Dump

## Slide 22: A2T

## Slide 23: Instrumentation Requirements
Name | Description | Number | Location
BLM |  |  | 
BCM |  |  | 
BPM |  |  | 
WS |  |  | 
EMU |  |  | 
NPM |  |  | 
Imaging devices |  |  | 
BSM |  |  | 
Halo |  |  | 

## Slide 24: Example BCTs
 | Location | Nominal Beam | Tuning Beam
Resolution |  |  | 
Accuracy/Stability |  |  | 
Maximum Pulse power |  |  | 

## Slide 25: Application List
Section | Application | Short description
MEBT | Trajectory Correction | 
 | Quadrupole Scan | 
 | Quad Centering | 

## Slide 26: Next steps
Finish the commissioning plan
Extract the requirements for Beam Instrumentation
Extract the requirements for ICS
  Create the list of applications to develop
Detailed plan to follow
  Time schedule
  Resources needed
  Coordination with installation