## Slide 1
Response to TAC8 and Annual Review Recommendations
John Haines
Head of Target Division
www.europeanspallationsource.se
April 2, 2014

## Slide 2: TAC-8 Recommendation (1 of 3)
Recommendation:
Regarding System Engineering Approach:
  Minimize formal constraints to the technical contributors, but be strict of what is mandatory (e.g. quantified progress report).
  Create a high level, readily accessible parameter list immediately.
Response:
SE requirements are being tailored to meet the needs of the Target Project. Near term system engineering expectations and deliverables (Preliminary Design Review and Critical Design Review) identified and communicated to Work Package Leaders. Tailoring of longer term deliverables remains to be done.
Established high level parameter list for Target Station that has been posted to the TAC-9 site (ESS-0010614)

## Slide 3: Excerpt from Target Station Parameters List

## Slide 4: TAC-8 Recommendation (2 of 3)
Observations
The target safety system is not clearly defined.
Recommendations
A credible monitoring system has to be specified, capable to guarantee that “the target is ready for beam”. Early definition of this system is important for the design and control of the target instrumentation.
Response:
Process to derive the set of safety credited controls is in place and being worked (See Linda Coney’s presentation for details) (ca. 2016)
In general, Target MPS items will be identified in P&IDs that will be part of the Preliminary Design Review deliverables (ca. 2014)

## Slide 5: TAC-8 Recommendation (3 of 3)
Recommendation: Prioritize the list of EDD‘s considering the budget constraints; identify what is mandatory or needed, and when.
Response:
  EDD Plan developed and iterated several times to settle on a set of activities that address critical issues in a timely fashion (ESS-0006024)
  Activities are included in Target Project plan with a total budget of approximately 5 M€

## Slide 6: List of approved EDDs included in Performance Measurement Baseline
Target System Gas Flow Erosion (WBS 12.2.2.4)
Target Rotary Seal (WBS 12.2.3.5)
Moderator Neutronics Benchmark (WBS 12.8.2.1)
Test of Remote Handling Procedures (WBS 12.6.2.2)
Tungsten Fatigue Studies (WBS 12.8.6.2)
Helium Purification (WBS 12.2.2.4)
Ortho Hydrogen Fraction in Moderator (WBS 12.8.2.1)

## Slide 7: Recommendations from Nov 2013 Annual Review
Target received seven recommendations from the 1st ESS Annual Review held in Nov 2013
  Responses and final closure of items is being tracked
  The May 2014 Update Review will focus on responses to the recommendations
  A document addressing the current status of these responses was posted to the TAC-9 site and the next seven slides provide a high level summary

## Slide 8: Recommendation 2013-11 and status of response
Recommendation: Only two years are being allowed for the moderator and reflector plug build; this may not be enough. Interactions with vendors may be helpful.
Response:
Activity: Attempt to understand why the SNS plug design and fabrication approach takes so much longer than for similar facilities. Also, seek input from vendors. Document findings.
Deliverable: Report and possible adjustment to plan.
Status: On track for June 2014 completion

## Slide 9: Recommendation 2013-12 and status of response
Recommendation: The price of off-spec steel is important; a supplier should be located and a price negotiated. This is currently in the project schedule for 2015.
Response:
Activity: Better understand the availability, quantities, and cost of off-spec steel available within partner countries. Explore possibility of an in-kind partner supplying steel.
Deliverable: Report and possible adjustment of cost estimate.
Status: On track for May 2014 completion

## Slide 10: Recommendation 2013-13 and status of response
Recommendation: The target/instrument, target/accelerator, and target/conventional facilities interfaces are important and appear to be improving. These need to continue to improve, and a timely decision on the new moderator design is a first test.
Response:
Activity: Work with NSS to finalize moderator concept and establish monthly meetings between interfacing Project Leaders to raise visibility.
Deliverable: Submit moderator design change request package for CCB approval. Monthly Project Leader level interface management meetings established.
Status: Monthly meetings being held. On track for April 30, 2014 decision on moderator concept.

## Slide 11: Recommendation 2013-14 and status of response
Recommendation: Planning of the remote-handling schemes for target & moderator-reflector replacement needs to be completed.
Response:
Activity: Moderator concept will be decided in the spring of 2014. Ease of remote handling is one aspect being considered in this selection process. Following this decision, the remote handling scheme will be established during the preliminary design process for the Moderator-Reflector Plug and Target Wheel.
Deliverable: Report documenting maintenance schemes for Moderator and Reflector Plug and Target Wheel.
Status: On track for completing in Nov 2014

## Slide 12: Recommendation 2013-15 and status of response
Recommendation: Spare components are currently delayed to operations. Make sure to manage this.
Response:
Activity: Compile a list of critical spares and update periodically to be prepared to factor into operations planning. Establish priority for purchasing based on impact on operations, lead time needed to obtain replacement equipment, and probability of failure.
Deliverable: Critical spares list including expected lifetime, probability of premature failure, replacement time, and cost documented and transmitted to Ops, ES&H, and QA Director.
Status: Complete (ESS-0008954, document posted to TAC-9 site)

## Slide 13: Recommendation 2013-16 and status of response
Recommendation: Consider consolidating neutronics and shielding efforts into one group to avoid duplication of efforts.
Response:
Activity: Develop proposal for conducting neutronics and shielding analyses across all projects and establish a well-documented, rigorous process.
Deliverable: Proposal for EPG on organizational aspects and release of document describing rigorous shielding analysis process
Status: EPG approved appointment of Günter Muhrer as ESS Shielding Coordinator and shielding analysis process description nearing completion (See Günter Muhrer’s presentation)

## Slide 14: Recommendation 2013-17 and status of response
Recommendation: The water-cooled target backup study of beam power versus need for emergency coolant is important. This study should be completed as soon as possible.
Response:
Activity: Complete study by May 2014
Deliverable: Report documenting power limit
Status: On track for meeting May 2014 plan (see slide in John Haines presentation on Target Status)