## Slide 1
Status of the French activities
under the responsibility of CEA
Philippe CHOMAZ
Collaboration Board

## Slide 2
Project #1: Beam tests with IPHI

## Slide 3
The SILHI source is ready
Sept 2013: I=65 mA with ESS parameters
Start of the RF conditioning: Q3 2014
The assembling of the RFQ is almost completed !
All manifolds are mounted except one that needs to be repaired (leak on a weld)
All wave guides mounted
The last operations to be performed before the tests:
Water cooling circuit (700 flexible pipes, 1 km, skid).
Cabling of the pumping groups with the C/C system
Three talks by D. Uriot, O. Tusk and F. Peauger at the EUCARD2/ESS workshop on beam commissioning on the proton source, the injector beam commissioning and on the IPHI commissioning plan (April the 8th & 9th).

## Slide 4
Project #2: 352 MHz RF test stand

## Slide 5: Status
The tests stand is ready to host the IPNO bench for the RF power processing of the 2 couplers pairs (4 couplers)

## Slide 6
Projects #3, #5, # 8:
High beta prototypes
Medium beta ECCTD

## Slide 7
First chemical treatments on the high b prototype cavity (ZANON)
Second high b prototype cavity welded (RI)
Redesign of the medium b cavity – dangerous HOM suppressed
Call for tender finalized
ECCTD design study: completion of the cryogenic pipes and first analysis for compliance with PED
Main achievements for the period

## Slide 8
| PAGE 8
    RI cavity welded, and delivered soon
    ZANON cavity: * 2 BCP (80µm in total)
    * tests in VC in April
    2 prototype high beta cavities manufactured
    No HOM coupler on the high beta cavities of the series
    (Prototypes are equipped with HOM coupler ports)
    EUCARD2 SPL b=1 cavity
        cavity delivered to Saclay a few weeks before the first ESS cavity
        2 Electropolishing treatments performed
        Heat treatment for H2 release performed
        Tests in CV in 2 weeks (Pb with He delivery)
SPL cavity electropolishing at Saclay

## Slide 9
    no HOM coupler needed
    Call for tender in progress for 6 medium beta cavities. Order to be launched soon (~ 1 or 2 weeks)
    Last checks before completion of the drawings needed before the Kick-off meeting (once the contract is awarded)
    The general planning of the M-ECCTD ( October 2013) should not be delayed by this modification of the cavity design.
Status of the medium b cavities

## Slide 10
    First meeting with APAVE last February confirmed our first analysis
    Volumes of the helium circuits and vessels < 50 l
    1,431 bars< Working pressure
    Ps can be < 2 bars
    Article 3.3 of PED
    To be confirmed
    Meeting at Lund for PED compliance in April
    Compliance with European
    PED 97/23/EC

## Slide 11
Status on other components and toolings

## Slide 12: Fundamental power coupler
    Call for tender for the ceramic windows and antennas closed. Offers analysed. The order should be launched in few weeks
    Drawings for the outer conductors completed. Preparation of the call for tender in the comming months
    Door-knob: design almost completed. A seal design to be tested before.

## Slide 13
    Coupling box design finalized
Test bench for the pressure compensation system of the power coupler
    First tests performed.
    Modifications in progress (Stronger sping needed, sliding guids, …)
    Preparation of the call for tender in the comming months

## Slide 14
Procurement of all main other components will be preprared before summer and launched before the end of 2014

## Slide 15
  2 rooms: ISO7 & ISO5.
IS0 5
52,69 m2
IS0 7
27,5 m2
Water cleaning
High Pressure Rinsing HPR
    Picture of the clean room last November
    The clean room will be ready for operation in April 2014
The new clean room ISO5 at Saclay

## Slide 16
Preparation of the stand for the RF power tests at 2 K
2000l Dewar delivered. Tests in the coming weeks
Cryogenic line (L > 50 m) delivered in the coming weeks
C/C system: Geobrick system chosen by ESS
The modification of the klystron modulator to increase the pulse length up to the ESS requirements (2ms => 3ms) will start in June (after the 2 SPL coupler processing)
Test stand for the M-ECCTD

## Slide 17
Project #4: TDR contributions

## Slide 18: RF design completed Thermomechanical calculation almost completed
Achievements
Conceptual design review to be organized in June
Objective: launch the procurement of the copper

## Slide 19
Thank you for your attention