## Slide 1: Science Directorate Instrument Technologies division Neutron Chopper Group Update IKON6
Iain Sutton
Neutron Chopper Group Leader
www.europeanspallationsource.se
February 26, 2014
Notes: Good morning
My name is Iain Sutton
I am currently the Group leader for Neutron choppers
And In the following 10mn I will attempt to present the Status and strategy of NG Tech work package

## Slide 2: Science directorate / Neutron technologies division - Interim mechanical workshops -
Skiffervagen 26, 224 78 ,Lund
Space
Building ESS’s capacity to innovate….
CURRENT STATUS
Tools
Equipment

## Slide 3: Neutron technologies workshops
Chopper test cell
Real work is commencing!
Basic machine shop
Prototype assembly area
Optics group test station
Electronic assembly area

## Slide 4: Scope - from Concepts to Construction
Exploration of Requirements
Theoretical studies
Engineering studies
Engineering Specification
Procurement
Exploration of Requirements
Theoretical studies
Engineering studies
Engineering Specification
Instrument Construction
|---------NEUTRON CHOPPER TECHNOLOGIES WP------------------------------|
|--CONSTRUCTION >
TRL 2
TRL 3
TRL 4
TRL 5
TRL 6
TRL 7 - 9
Notes: quick look at the activities we are involved with
All starts with Requirements
Engineering studies
Computer
and Physical prototypes

## Slide 5: DISC CHOPPER – TECH DEMONSTRATOR SMALL ROTOR

## Slide 6: DC-SR
STATUS PROJECT LEADER: Erik Nilsson > Markus Olsson
Current TRL 2 (Design complete)
Current phase 2 Procurement
All principal components on order
Spindle + Control system SKF
  Delivery June
Housing & Dummy rotor CECOM
Integration starts in September
Commisioning in November

## Slide 7: DC-LR
STATUS PROJECT LEADER: Erik Nilsson
Current TRL 1 (Requirements & concept)
Current phase 0 Preliminary Design
Requirements collected
Preliminary specification in progress
Design concepts under study
  Looking for development partner
Design starts in August
Preliminary Design complete by December

## Slide 8: PPSc
STATUS PROJECT LEADER: Darek
Current TRL 1 (Requirements & concept)
Current phase 0 Preliminary Design
Requirements collection in progress
Preliminary specification in progress
Design concepts under study
  Looking for development partner
Design starts in August
Preliminary Design complete by December

## Slide 9: Prompt pulse suppression choppers ‘PPSc’
PPSc
SNS
ISIS
J-Parc
CNCS
?
PA-5-H-S-10
PE-5-V-C
PA-5-H-S
500mm
PA-5-H-S -25/50

## Slide 10: PPSc PA-10-H-S-D-56 concept “Dora”
Performance
  Rotational speeds 7 > 56Hz
  Beam size <= 100x100mm
  Attenuation 10e6 ?
NFR
  Design life 20 years
  MTBF >500k hrs
  Remote handling
  Extreme radiation resistance
Features
  Modular design
  ESS systems compatible
  Operation under vacuum
  Water cooling
  Metallic rotors (Inconel?)
  Magnetic or Contact bearings
Notes:   Rotors d600mm
  Material Inconel
  Mass 600kg ?

## Slide 11: PPSc 2.PA-5-H-S-I-56 concept “Carla”
Back to back In-direct drive variant
2 x 300mm Hammers

## Slide 12: A chopper extraction concept