## Slide 2: Charge
Are all or a sufficient coverage of requirements and specifications for the Jumper Connection including for its interfaces with other systems, documented and communicated to and understood by the Work Unit team?
Does the Jumper Connection design meet requirements and specifications?
Is the design of the combined CM-VB system joined by the proposed Jumper scheme compatible with the adjustable support and fixing of the CM to its stands in TS2 and in the tunnel (ESS-2589636), under nominal load conditions? Does the design account for the full adjustment capability provided by the CM supports?
Have quality assurance and quality control activities been planned?
Have safety issues and technical risks been identified and eliminated or otherwise mitigated for in the detailed design or identified for managing for manufacture, assembly, installation or operation?
Will the delivery include a detailed installation sequence, complete with checklists for fulfilling any needed installation prerequisite, for performing the connection work at the interface of the connecting systems?
Is the schedule for delivery of materials, components and for the manufacture of the Jumper Connection sufficiently understood and in accordance with activities, durations and milestone dates shown in the ACCSYS project plan?
Is the cost of the new design well understood and appropriate?
Are the roles of ESS, WUST and KrioSystem well understood and agreed upon?
Does the work unit team require additional input from ESS or its other partners, or seek additional review, decision or approval from ESS to proceed with all work planed?
Are there any outstanding agreements to be made or other actions necessary to allow the work unit to achieve the Plan?

## Slide 3: Charge
Are all or a sufficient coverage of requirements and specifications for the Jumper Connection including for its interfaces with other systems, documented and communicated to and understood by the Work Unit team?
Generally yes, but we should have a list of updated requirement documents, capturing the content of the presentations
Does the Jumper Connection design meet requirements and specifications?
We think yes, but a better traceability of requirements (see previous points) would confirm it. See comments on installation. Concern on the small clearance between the JC and the RD line, the recommendation is to explore ways to increase it and take into account for deviation from the nominal position of the flanges*. The use of carbon steel components should be avoided.
Is the design of the combined CM-VB system joined by the proposed Jumper scheme compatible with the adjustable support and fixing of the CM to its stands in TS2 and in the tunnel (ESS-2589636), under nominal load conditions? Does the design account for the full adjustment capability provided by the CM supports?
We think yes. The same analysis expert at EIS has produced all simulations. EIS will perform a quick independent check on the consistency of the findings.
* Slightly edited from what was presented as this slipped due to time constraing, but corresponding to the contents delivered verbally.

## Slide 4: Charge
Have quality assurance and quality control activities been planned?
Generally yes. The inspection plan should be revievew by Björn using the current inspection templates.
Have safety issues and technical risks been identified and eliminated or otherwise mitigated for in the detailed design or identified for managing for manufacture, assembly, installation or operation?
No safety concern on design. Procedures for installation (especially at TS2) will be reviewed during the IRR/WO. Another concern is the tight spacing for the RD exchanges in case this happens.
Will the delivery include a detailed installation sequence, complete with checklists for fulfilling any needed installation prerequisite, for performing the connection work at the interface of the connecting systems?
Not yet, but plans are in place for its development. Again IRR/WO.

## Slide 5: Charge
Is the schedule for delivery of materials, components and for the manufacture of the Jumper Connection sufficiently understood and in accordance with activities, durations and milestone dates shown in the ACCSYS project plan?
Schedule needs to be integrated in the P6 plan, with some details (many concurrent activities).
Is the cost of the new design well understood and appropriate?
Priceswise yes, we need a plan for the full 30 items.
Are the roles of ESS, WUST and KrioSystem well understood and agreed upon?
Yes
Does the work unit team require additional input from ESS or its other partners, or seek additional review, decision or approval from ESS to proceed with all work planed?
Just the EIS check by Nick G., OHS, and followup at IRR/WO

## Slide 6: Charge
Are there any outstanding agreements to be made or other actions necessary to allow the work unit to achieve the Plan?
Create a simple document list of the reviewed material, with revision
Integrate new requirements and specs into existing documentation. If necessary, new releases.