## Slide 1
SKADI
Current Status
STAP-Meeting 20.04.2021
April 2021 | Sebastian Jaksch, Alexis Chennevière, Romuald Hanslik, Stefphan Butterweck, Ralf Engels, Uwe Clemens, Sylvain Désert, Pascal Lavie, Teddy Kozielewski, Henrich Frielinghaus et al.

## Slide 2
Sample cave
  Change request for partially non-magnetic cave approved
  Cave design well progressed
  PDR for cave design complete
  Interface with ESTIA will be clarified: Supervised+Inaccessible zone
  Design and construction on track for 2023
Detector interfaces between detector housing and tube ongoing
  No neutrons for testing 
  Interfacing with DMSC+Detector group still challening, but working on it
In-Bunker installation
  Kickoff with SNAG has taken place
  SNAG full until summer, but the installation is simple, a lot of similar parts can be taken from other projects
  Full start in summer
  Construction starting Jan 2022
  Installation ready until mid 2022 for first bunker opening window
Progress Overview

## Slide 3
Progress Overview continued
Chopper kick-off meeting has taken place
  IDR for choppers immanent
Answers to call for tender for collimation and detector tube received.
  Going through the quotes now: Four quotes received
Common collimation wall with ESTIA is progressing
Detector shielding CDR is finalized now, waiting for publication
Collimation shielding will probably go along with detector shielding

## Slide 4: ESS Instrument suite
ZEA-1 | Technology for Excellent Science
Small-K Advanced Diffractometer (SKADI) -
Small-angle neutron scattering (SANS) instrument

## Slide 5
SKADI Complete with the shielding - E3-Port
SKADI layout (short reminder)

## Slide 6
Design progressing well
Floor loading is a potential issue: ESS takes over additional costs – Coordination with ESTIA to achieve common loadspreading
Sample Cave

## Slide 7
Sample Cave continued
MCA components will meet ESS standards, discussions with PSS/safety ongoing
Compartmentalization of walls reflects non-magnetic and carbon steel areas as a cost saving excercise: Simulations now show the systems is capable of handling 15 T non-directional magnets

## Slide 8
Sample Cave continued

## Slide 9
Sample cave layout overview
Detector tube diameter = 2410mm
Detector flange outer diameter = 2590mm
Center of Detector tube is not the neutron beam axis

## Slide 10
Detector and interfaces
CTV passed: 05/10/2020
Call for tender finished, now going through the quotes

## Slide 11
Detector and Interfaces continued
Interface with FZJ:
- Mechanical design is on track
- Need better communication for testing

## Slide 12
Choppers
Name | Chopper Type | Distance to ISCS (m) | Operating speeds max/min (Hz) | Rotor Radius (mm)
BW1 | Single | 15,5 | 14/7 | 310
BW2 | Single | 20,85 | 14/7 | 310

## Slide 13
In-bunker
SNAG won the bid for the tender
Detailed design will start in summer
Production begins in Jan 2022
Heavy shutter interfaces have been designed, heavy shutter already under design – will go through TG process together with the rest of the installation

## Slide 14
Collimator
CTV passed: 27/02/2019
Call for tender finished, now examining quotes

## Slide 15
Collimator Shielding: Impact on ESTIA
CTV passed: 16/11/2018

## Slide 16
Detector Shielding
Detector Shielding CTV scheduled for 22nd of April

## Slide 17
Detector Shielding continued
Shielding size was increase for the detector tube
Allows to walk/work alongside the tube inside the shielding
Access door was also increased in size
Simplified access for removal/maintenance of detector (can be reached with a custom carriage)

## Slide 18
Schedule
Component | Delivery and Installation last STAP | Delivery and Installation current
NBOA | Q1-20 | ???
In-Bunker | Q3-24 | Q2/Q3-22
Polarizer, Fast Shutter | Q1-23 | Q1-23
Choppers | Q3-23 | Q3-23
SCS | Q2-24 | Q2-24
Monitors | Q1-23 | Q1-23
Sample Area | Q2-23 | Q2-23
Hutch Area | Q4-23 | Q4-23
TG3-Full | Q4-21 | Q4-21
TG4-Full | Q2-24 | Q2-24 (the only 2024 component is the detector, which is fully in our hands
TG5-Full | Q3-25 | Q3-25
TG3 in Q4-2021 is a risk due to:
Covid delays
Manufacturer overload
Rehiring of additional engineers
Not under instrument team control, but we are monitoring the situation
Delayed
At risk
On track
Non-critical

## Slide 19
Thank you for your attention

## Slide 20
Advertisement: SANS Special Issue
New instrument designs
Instrument upgrades and fundamental improvements
Sample environment technologies and experimental support
Data treatment
Exemplary experiments on systems that allow a general use, also for other systems
Dedicated different geometries/techniques linked with SANS, such as GISANS
Recent Advance in Small Angle Neutron Scattering
https://www.mdpi.com/journal/applsci/special_issues/small_angle_neutron_scattering#info

## Slide 21
13.6.7.1.1 Beam extraction system
NBOA
Final design review in progress.
Delivery delays caused by Covid-19 pandemic are to be expected.

## Slide 22
13.6.7.1.1 Beam extraction system
Reflector (neutron guide)
with intergrated lifting beam
Bridge beam guide
Vertical heavy shutter

## Slide 23
13.6.7.1.1 Beam extraction system
Overview complete reflector in bunker
Reflector (neutron guide)
with intergrated lifting beam
Bridge beam guide
Vertical heavy shutter

## Slide 24: Heavy Shutter new design
Neutron flux
Shutter
Ca.350kg
Reflector with housing ca.300kg
Linear guides and bearings are lubricant-free.
2530
275
2470

## Slide 25: Heavy Shutter new design
1958
2458
2100
1260
25
1040
900

## Slide 26: Heavy Shutter new design
26
Adjustment elements

## Slide 27: Heavy Shutter overview
Forward view
Rear view
27

## Slide 28: Heavy Shutter with the bunker wall
28
28
39

## Slide 29: Heavy Shutter with the bunker wall
29
It is planned to shield the gap with a shielding cover. This is machined on site in order to avoid concrete tolerance issues.

## Slide 30
13.6.7.1.7 Flight Tube (Feed through bunker wall)
ESS has sent us the modified feed through bunker wall. The feed through was increased in size to provide more room for the previous spacer plates. But this has no effect on our design.

## Slide 31
13.6.7.1.5 Beam Filtering System
Polarizer

## Slide 32
Polarizer
Polarizer
Fast Shutter
Spin Flipper

## Slide 33
13.6.7.1.5 Beam Filtering System
Polarizer
Concept design for Polarizer ready.
Vacuum vessel was calculated by calculation group ZEA-1.
We stopped at that point because we put the prioritization on the bunker inside components.

## Slide 34: Chopper system overview
Name | Chopper Type | Distance to ISCS (m) | Operating speeds max/min (Hz) | Rotor Radius (mm)
BW1 | Single | 15,5 | 14/7 | 310
BW2 | Single | 20,85 | 14/7 | 310

## Slide 35: Chopper assemblies Discs
Discs Radius – 310mm
Discs material - not yet defined. Possible materials:
Alloy | Standard | Note
Aluminium 6061 | ISO 6361 | proposed
GRP (ISOVAL TM) | ISOVOLTA TM V0.7/16 | To be verified
CFRP |  | proposed
Bearing type: Magnetic bearings

## Slide 36
13.6.7.2 Sample Exposure System
Sample Area update
Modified Sample Area Shielding:
  Only one door from the operating side, detector access with pallet jack
  Shielding wall to Estia modified

## Slide 37
13.6.7.2 Sample Exposure System
Sample Area update
Energy chain
More space is needed on the detector housing side in detector tube. So the center of the detector tube is not the center of the beam axis.
For this reason the diameter of the detector tube is larger and the detector tube is shifted to the ESTIA side.

## Slide 38
13.6.7.2 Sample Exposure System
Sample Area
300 mm thick steel walls
Detector tube diameter = 2410mm
Detector flange outer diameter = 2590mm
Center of Detector tube is not the neutron beam axis

## Slide 39
13.6.7.2 Sample Exposure System
Sample Area update
600
300
5300
3000

## Slide 40
13.6.7.2 Sample Exposure System
Sample Area Update

## Slide 41
13.6.7.2 Sample Exposure System
Sample Area Update

## Slide 42
13.6.7.2 Sample Exposure System
Sample Area Update
Stainless steel

## Slide 43: Detector housing
Forward view
Rear view
43
Detector rear view
Detector front view
Front cap
Rear flat head
Trumpet
Lid
656 mm
ᶲ 1740 mm

## Slide 44: Detector housing
Front cap
6 mm thick (Al)
Trumpet
762 mm
ᶲ 1740 mm
Sensor holder (Ti)
- Sensor holder from Ti,
- Another components
from AlMg4,5Mn0,7
- Bolts from Ti
44
Rear flat head
25 mm thick (Al)

## Slide 45: Detector housing
max. 55 mm
6 mm
Detector housing cut
45

## Slide 46: Front cup
Stress limits
membrane stress 
membrane + bending stress 
Front Cap – Linerized stresses at 1.2 bar differential pressure
Sum of membrane and bending stress
Membrane stress

## Slide 47: Front cup
47
Front cup was milled from an aluminum block according to the stress calculations

## Slide 48: Detector cooling
48
Temperature Chips + Boards - First calculations
Die erste Reihe Platinen hat keine Luftschlitze an der Rückseite!

## Slide 49: Detector cooling
49
Lengthened air nozzles
with cooling air
Air outlet
Cooling air inlet
Air buffer chamber

## Slide 50: Detector cooling
50
Lengthened air nozzles
with cooling air

## Slide 51: Test equipment for cooling validation
51
Test device for the verification of the calculation results
Air outlet
Cooling air inlet
Air buffer chamber
520 mm
620 mm
670 mm

## Slide 52: Test equipment for cooling validation
52
Test device for the verification of the calculation results
Air outlet
Cooling air inlet
Air buffer chamber

## Slide 53
Impressions

## Slide 54
First Tests
Mesurement of AgBeh, slits, ….
Semi-transparent beamstops/attenuators not strictly necessary, but improve S/N ratio
Software and hardware work as expected
Improvements on 4-pi scatterer normalization ongoing

## Slide 55
Detector
Air outlet
Cooling air inlet
Air buffer chamber
Tests for full scale cooling being prepared
Up to now, no heat issues (never exceeded 65°C without active cooling)

## Slide 56
Detector
Working on a tender box for simple removal of full detector
Housing will be possible to handle with instrument crane through side access door

## Slide 57: test Housing assembly
ᶲ400
167
265

## Slide 58: Test Housing assembly

## Slide 59: Test Housing assembly

## Slide 60
Detector and Interfaces continued
Hardware works
Tests needed
Tests rely on (partially) working DAQ system

## Slide 61
Detector and Interfaces continued
Front cup was milled from an aluminum block according to the stress calculations