## Slide 1
Jim Nightingale
ISIS Lead Engineer on IMAT instrument
IMAT Design Evolution

## Slide 2
IMAT Design Evolution

## Slide 3
2008 Draft Proposal
Instrument Concept & Layout
Notes: Elliptical guide concept
Curved guide considered but would remove neutrons below 2Å
Straight guide decision

## Slide 4
IMAT position proposal
Instrument Concept & Layout
?
?
?
?
?
?
?
?
Notes: IMAT best placed on coupled hydrogen moderator to maximise neutron flux for imaging
Broad neutron wavelength (0.5 – 10A) effective energy-selective imaging, bragg edge analysis

## Slide 5
Nov 2009 – Feb 2010
Decision on position and length
40m
W5
W8

## Slide 6
Nov 2009 – Feb 2010
Decision on position and length
40m
W5
W8

## Slide 7
Nov 2009 – Feb 2010
Decision on position and length
37m

## Slide 8
Nov 2009 – Feb 2010
Decision on position and length
52m

## Slide 9
Impact:
Increase of instrument cost = £2m
Increased complexity of design & build
Increased timescale for evaluation and sign-off
Kockelmann, W., Zhang, S. Y., Chapon, L. C. (2010) IMAT: performance evaluation report
Jan 2010 - IMAT position decision
Instrument Concept & Layout
Notes: Increase of £2m due to length / building
Process of evaluation / benefit / signoff

## Slide 10
Feb 2010 – First outline design
Instrument Preliminary Design
Notes: Impact of building location:
Facility soak-away needed re-siting
Facility HV supply cable diversion
Extensive existing building water treatment plant alterations
R80 Building structural columns in the way
Section with no overhead crane affecting design, assembly and operations

## Slide 11
Feb 2010 – First outline design
Instrument Preliminary Design
Notes: Horizontally translated pin-hole selector
Early detector array design

## Slide 12
Feb 2010 – First outline design
Instrument Preliminary Design
Notes: Impact of building location:
Facility soak-away needed re-siting
Facility HV supply cable diversion
Extensive existing building water treatment plant alterations
R80 Building structural columns in the way
Section with no overhead crane affecting design, assembly and operations

## Slide 13
May 2010 – Revised outline design
Instrument Preliminary Design
Beamline offset at an angle of 1⁰ in order to avoid clashing with neighbouring instrument and facility structure
Chopper positions altered to suit space restrictions
Building added

## Slide 14
July 2010 – Developed outline design
Instrument Preliminary Design
Evolution:
Realistic shielding space envelope
Access around beamline
Space for instrument control equipment

## Slide 15
Instrument Detail Design

## Slide 16
Instrument Detail Design
Evolution:
Access and operational improvements to chopper pits
Access platforms
Combined front end chopper pit
Detailed design
Notes: Over 500 new pieces of IMAT shielding in this view alone.
With the guide, choppers & monitors – there’s well over 1000 specially designed parts

## Slide 17
Nov 2011 – Detail Design
Increased height to accommodate overhead crane
Main Entrance
R80 Entrance foyer
Increased window coverage
Instrument Detail Design

## Slide 18
Extension Building Design & Build

## Slide 19
Detector/Camera Evolution

## Slide 20
Detector/Camera Evolution

## Slide 21
Detector/Camera Evolution

## Slide 22
Detector/Camera Evolution

## Slide 23
Detector/Camera Evolution

## Slide 24
IMAT Design Evolution
Design continues to change throughout the life of the project
Major obstacles are addressed early on but many minor problems need to be solved throughout the design
Opportunities arise during the design and often need decisive action