## Slide 1
Estia – Project Update
Alessandra Luchini & Sven Schütz :: ESTIA Core Team :: Paul Scherrer Institut
STAP meeting 12/10/2021

## Slide 2
ESTIA instrument overview

## Slide 3
ESTIA instrument overview
FAT NBOA

## Slide 4
ESTIA- NBOA
FAT of the NBOA: test with light source to check focusing properties of the guide
Ready for shipment to ESS in Oct 2021

## Slide 5
ESTIA instrument overview
FAT NBOA
FAT Feeder, Chopper Pit in production

## Slide 6
ESTIA- In-bunker Feeder
FAT of in- bunker feeder support, vacuum chamber and alignment mechanics (May 2021)
FAT of the in-bunker feeder optics (Aug 2021)
Additional pre-installation test at PSI prior to shipment at ESS (Jan/Feb 2022)
Installed at PSI

## Slide 7
ESTIA - Chopper Pit
Chopper Pit Vacuum chamber contains:
Chopper
Virtual source

## Slide 8
ESTIA - Chopper Pit
Chopper Pit Vacuum chamber contains:
Chopper
Virtual source
Chopper:
Chopper disk produced and shipped to ISIS for coating and balancing (Sept 2021)
Spindle tested at ESS and ready for shipment for additional tests at PSI together with the chopper disk (Jan/Feb 2021)

## Slide 9
ESTIA - Chopper Pit
Chopper Pit Vacuum chamber contains:
Chopper
Virtual source
Virtual Source:
Support is mechanically assembled and integration of the motors in TwinCat and Epics is in progress
The 2 L-shaped blades are produced and ready for testing

## Slide 10
ESTIA - Chopper Pit
Test at PSI of the In-buker feeder and Chopper Pit assembly (Oct/Nov 2021):
Mechanical assembly
Vacuum test
Shipment to ESS (Mar/Apr 2022) for early in-bunker installation (Apr-Jun 2022)

## Slide 11
ESTIA instrument overview
FAT NBOA
FAT Feeder, Chopper Pit in production
Selene 1 at ESS, Selene 2 at PSI, MF design

## Slide 12
ESTIA – Selene 1
Selene guide 1 carrier and vacuum vessel are installed at ESS
Currently in progress:
Characterization of the mirrors at PSI with interferometry
Integration in TwinCat and Epics of metrology cart and alignment robot (in progress)
Alignment robot
Metrology cart
Installation of the mirrors and robots at ESS in summer 2022

## Slide 13
ESTIA –Selene 2
Pre-installation of the carrier at PSI
Guide field installation and testing
Integration TwinCat and Epics of metrology cart and alignment robot
preliminary tests (Oct 2021)
Shipment to ESS (Dec 2021)
Installation at ESS (summer 2022)

## Slide 14
ESTIA Middle Focus
Orginal concept: the two polarisers are placed one before and one after the MF
New concept: the two polarisers are both placed before the MF
Advantages:
Similar performances as the orginal concept
Both polarisers are placed on the same motorised support
The spin flipper can be located in correpondance of smaller beam
Reduced costs
Currently in progress: from conceptual design to detailed design

## Slide 15
ESTIA Middle Focus
New concept: the two polarisers are both placed before the MF
Polarisers are Si/Fe supermirrors m=5/5.5
Polarisers have V-shape: logarithmic spiral segment + linear segment. Optimised shape to accommodate large beam divergence.
FOM is Ni-coated Si wafer with logarithmic spiral shape (nuetrons with wavelength above 30 Å are removed)
McStas simulation currently in progress to confirm the results

## Slide 16
ESTIA Middle Focus
FOM
Polarisers
Free Position

## Slide 17
ESTIA – Middle Focus
Design in progress
Mask changer
Polarisers
and FOM
Selene 1
Shutter
Middle Focus
Motorised support:
Moving polarisers or FOM in or out of the beam
Alignment of the polarisers and FOM

## Slide 18
ESTIA – Middle Focus
Design in progress
Mask changer
Polarisers
and FOM
Selene 1
Shutter
Middle Focus
Spin flipper:
Same design as AMOR
Produced at PSI

## Slide 19
ESTIA instrument overview
FAT NBOA
FAT Feeder, Chopper Pit in production
Selene 1 at ESS, Selene 2 at PSI, MF design
Sample Stage and Detector Arm design

## Slide 20
ESTIA – Experimental Cave
Conceptual design finalised
Critical Tender Verification (CTV) Oct 2021
Procurement spring 2022
Top view
Precision floor
False floor

## Slide 21
ESTIA – Sample Stage & Detector Arm
Conceptual design almost finalised

## Slide 22
Sample stage
Hexapod
Omega stage
Example with SE: Warm Bore Magnet
The sample is mounted on the hexapod and can be roated inside the magnet
Solid/liquid sample changer
ESTIA – Sample Stage & Detector Arm

## Slide 23
Sample stage
Hexapod
Omega stage
Solid/liquid sample changer
Sample environment for HC
Solid/liquid cells + sample changer + accessories: the project in collaboration with Prof. Adrian Rannie at Uppsala University
Test on AMOR for divergent beam and standard solid/liquid cells
ESTIA – Sample Stage & Detector Arm

## Slide 24
Sample stage
Hexapod
Omega stage
Solid/liquid sample changer
Sample environment additional projects
SPLICs: Nico Paracini at Malmö University/ ESS
Combined ATR-FTIR, Ellipsometry, NR: Prof. Thomas Ederth, Linköping University
ESTIA – Sample Stage & Detector Arm

## Slide 25
Detector Arm
Analyser ca be placed in and out side of the beam
Design of the detector vessel in progress
Satisfying tests were performed on AMOR for detector prototype
A new detector (same design) will be installed on AMOR in Dec 2021
Spin flipper design similar to MF
ESTIA – Sample Stage & Detector Arm

## Slide 26
ESTIA instrument - Outlooks
NBOA at ESS
Test of the Feeder & Chopper Pit Assembly at PSI
Shipment of Selene 2 to ESS and finalisation of MF design
Finalisation of Sample Stage & Detector Arm design
Start of Common Electrical and Common Utilities Projects

## Slide 27
Thank you for your attention!
Any questions?
Page 27
Notes: 27

## Slide 28
Risk Report
Current Top 5 Risks |  |  |  |  | 
Title | Severity | Category | Responsible | Response | Trend
Activation Analysis | 12 | Cost | PSI | Avoid | Steady
Common Utilities Project | 9 | Schedule | ESS | Observe | New
PSS standards | 9 | Schedule | ESS | Observe | New
Experimental Cave delivery | 6 | Schedule | ESS |  | Falling
Communication to ESS | 6 | Schedule | ESS | Reduce | Steady
09.03.2021 - Top 5 Risks |  |  |  |  | 
Title | Severity | Category | Responsible | Response | Trend
Installation Resources | 16 | Schedule | ESS | Avoid | Steady
Activation Analysis | 12 | Cost | PSI | Avoid | Steady
Communication to ESS | 12 | Schedule | ESS | Reduce | Falling
PSI / ESS scope transfer | 8 | Schedule | ESS |  | Falling
Shared shielding ESTIA/Skadi | 4 | Schedule |  |  | Falling

## Slide 29
Financial Report