## Slide 1: Commissioning of the new CERN SM18 Infrastructure P. Maesen on behalf of BE/RF-SRF section Following : 1. P. Maesen on behalf of BE/RF-SRF section “Upgrade of CERN SM18 Infrastructure ", SLHiPP 4, CERN

## Slide 2: Contents
Finalization of cryogenic distribution in CERN SM18 for the RF
  Horizontal bunker M7, cryo box
Ultra pure water production
HPR commissioning
New Clean Room
Status and timescale

## Slide 3: Horizontal bunker M7
M7
M9
V3
V4
V5
V6
  Cryo connections to :
  LHC cryomodule
  HIE-ISOLDE cryomodule
  And later FCC 400 MHz project
  Cryo connections to :
  SPL half cryomodule
  CRAB cryomodule
  And later LHC 800 MHz project
for HIE-ISOLDE or LHC

## Slide 4: Horizontal bunker M7 today
New end of line bypass
Output towards future valve box
One of the 6 Cryo service modules

## Slide 5
!!! under redesigning !!!
To cope with CRAB module

## Slide 6: Similar dedicated Cryo valve box in M9
Connections
for HIE-ISOLDE or LHC
Installed and welded
Last week 03’2015

## Slide 7: Ultra pure water production
Fully connected and Operational from June ‘14
Maintenance contract for three years

## Slide 8: HPR commissioning
High pressure pumps
High pressure and waste water connections

## Slide 9: Cabinet flow chart supervision

## Slide 10: Cavity loading area
Shower inlet
SPL 5 Cells

## Slide 11: Rinsing recipe
Central positions of the cells

## Slide 12: New Clean Rooms & HPR
15m long Cleanroom for cryomodule assembly
15m long grey room for cryomodule preparation
Cavity HPR & drying
Personnel entrance

## Slide 13: New Clean Rooms accessories
Close follow up of usable

## Slide 14: Cavity rinsing operational
High Pressure Rinsing
Accessories Preparation
High Pressure Rinsing
Possible warm N2 drying
Rinsing
Drying and flanges mounting

## Slide 15: ISO 4 unloading area
Air drying and
flanges mounting area

## Slide 16: Status & timescale (1)
Procurement of equipment:
  Klystron (1x): 1.5 MWp ordered, tested at Thales, delivered at CERN, tested in Bd 112 to be installed mid 2015 in SM18 for Coupler test bench
  Circulator (1x): ordered, delivered OK
  RF loads (3x): 1.5MWp ordered, delivered OK
  Waveguides: special pieces (magic tees, bends, bellows) ordered at Mega Industries (USA) all straight parts from Spain delivered OK
  Modulator: delivered and operational OK
  Electrical power: 3*400V 300A connected from ERD2/M18 OK
  Clean rooms tools and cavity levering up under study to be ordered

## Slide 17: Status & timescale (2)
Key dates:
  From June ’14: Started HPR playing with recipes, see future trans lucid cavity
    High Pressure Rinsing performance increase
  -> End ‘14: CCDTL tests (Linac 4) finished in SM18
  From mid ’15: SPL HPRF system installation : klystron + Coupler test bench
Controls:
  HPRF controls: re-use the PLC system developed and installed for L4 test stand
  Cryomodule:
    RF controls expected to be ready mid 2015 ( L. Arnaudon )
    Cryo controls redefined ( TE/CRG ) for the new multipurpose cryo box ‘2016 !
  Low level ?

## Slide 18: Thanks for your attention
Questions ?