## Slide 1: WP2 at M36 and until M48
29 November 2021
Author: Andy Götz – WP2 leader

## Slide 2: Status of WP2 in M36
According to planning in proposal WP2 finished in M36 with FAIR data policies updated and DMPs implemented and all Deliverables and Milestones achieved
In reality:
  All deliverables have been achieved, 3 milestones achieved
  Last Milestone not achieved because
    not all facilities producing DOIs and Open Data
  Data policies have not been updated (yet) at ESRF, ESS, EuXFEL and ILL
  DMP templates have only been implemented by ESS

## Slide 3: Status of FAIR Data Policies in M36
In reality:
  Situation at ESRF is
    submitted an updated policy to the research directors but it is stalled and the discussion needs to be reactivated
    in the meantime ESRF is minting DOIs for raw and processed data
  ESS discussion has started (AFAIK) but not been formalized yet
  EuXFEL and ILL formal discussions have not started yet (AFAIK)

## Slide 4: Status of DMP templates in M36
In reality:
  Lots of discussion and work has gone into the DMP questions (with ExPaNDS)
  A DMP template tool has been chosen (DS Wizard)
  DMP templates have been implemented by ESS and source code and knowledge base are shared
  ESRF has a prototype of the DMP template using the ESS code
  CERIC, EuXFEL, ELI and ILL have not started implementing DMPs
  Not sure who will actually integrate DMPs in their operations

## Slide 5: WP2 Issues in M36
According to planning in proposal WP2 finished in M36 with FAIR data policies and DMPs implemented
In reality:
  Data policies have not been updated at ESRF, ESS, EuXFEL and ILL
  DMP templates have only been implemented by ESS

## Slide 6: WP2 expected and actual KPIs
KPIs track how many sites are producing DOIs and open data and their use via DOIs
In reality:
  DOIs are not being produced at all sites (CERIC, ELI, ESS?)
  Open Data is not available at all sites yet (CERIC, ELI?)
  Use of DOIs is still not generalised and is not growing

## Slide 7: WP2 activities in M36 to M48
In reality:
  Data policies will be updated at ESRF, ESS, EuXFEL and ILL
  DMP templates will be implemented at CERIC, ELI, ESRF, EuXFEL, ILL
  DOIs will be implemented at all sites (CERIC, ELI todo)
  Users will be trained / incited to cite data DOIs
  Open Data will be available at all sites (CERIC, ELI, ESS todo)

## Slide 8: WP2 activities after PaNOSC
In reality:
  Continue following Data policies and sharing best practices
  Certify data catalogues with CoreTrustSeal
  Work on a common campaign to promote data DOIs in publications
  Register data repositories with publishers

## Slide 9: WP2 collaboration with ExPaNDS
The plan was to work closely with ExPaNDS WP2
In reality:
  Despite good intentions and no blocking issues close collaboration did not really happen with the exception of the PaNOSC DP and DMPs
    ExPaNDS members contributed to PaNOSC Data Policy
    DMPs were discussed in joint meetings however implementations are diverging (DS Wizard vs RDMO)
  Meetings are not attended regularly by both projects
  Two projects should aim to organize joint events for remaining 12M

## Slide 10: It has been great working together with everyone on WP2! WP2 activities will need to continue on a permanent way to really change the culture around research data at our facilities …