## Slide 1: WP8: Future
29th November, 2021
Thomas H. Rod

## Slide 2: Planned versus actual
Planned
Get pan-learning up running in a maintainable and safe fashion
Jupyter integration
Add training content showcasing the different facilities and PaNOSC services
Get all partner facilities to use pan-learning
Organize summer school
Actual
Everything planned to some extent
Made pan-learning an EOSC services
Collaboration with ExPaNDS on joint training portal with catalogue and e-learning
  Merging two web sites into one
  The joint portal should be an EOSC service
Umbrella ID
CPU resources

## Slide 3: Addressing discrepancies
We use unspent PaNOSC resources at ESS to address the ‘EOSC scope creep’ related to EOSC
How do we get partner facilities to provide content and use the platform?

## Slide 4: Issues
We need to have a focused effort from staff at partner facilities – outside meetings (time is an issue) – plan to have 1:1 meetings with all partners
Developing training material is time consuming and often underestimated.
The WP leader is not spending enough time on the WP!
ExPaNDS / PaNOSC collaboration works really well:
  Some questions about the selection of TESS / workflow manager
  Are ExPaNDS partners informed about pan-learning.org?

## Slide 5: Activities for next 12 months
Get the joint ExPaNDS / PaNOSC training portal up running on pan-training.eu / pan.training
Gather and develop content
  For each facility
  For each PaNOSC service (WPs input is required)
Organize and run CPU intensive summer school
D8.1 | Report on lessons learned and future prospects for adopting best practises data stewardship at the PaNOSC facilities | 07.21
D8.2 | Report on lessons learned for adopting the e-learning platform at the PaNOSC facilities, task 8.4 | 05.22
D8.3 | Teaching material for users of PaNOSC services, FAIR principles, and the PaNOSC facilities accessible in the e-learning platform at pan-learning.org, task 8.5-7 | 05.22
D8.4 | Closing report including report from summer school, task 8.8 | 11.22

## Slide 6: Beyond PaNOSC
ESS intend to maintain pan-learning.org (but not the content – relies on course providers)
pan-learning.org will be used in the neutron world, e.g. at summer schools
Will it be used in the photon world?