## Slide 2: ESS ODHDS Plan and Schedule
PRESENTED BY Annika Nordt

## Slide 3: ESS ODH Detection Systems - Overview
ODH Detection System for G04, CTLG, CXH, HCB – In operation
ODH Detection System for Test Stand 2 – In operation
Temporary ODH Detection System for Accelerator – Ready to be taken into operation
ODH Detection System for Accelerator – In design phase
ODH and Hydrogen Detection System for Target – In advanced analysis phase
ODH Detection System for Instruments and NSS – In early analysis phase
Systems Status

## Slide 4: ESS ODH Detection Systems - Dates
ODH Detection System for Accelerator
  Preliminary Design Review – 2022-02 (this review)
  Critical Design Review – 2022-11
  Ready for operation – 2023-05
ODH and Hydrogen Detection System for Target
  Preliminary Design Review – 2023-01
  Critical Design Review – 2023-11
  Ready for operation – 2025-04
ODH Detection System for Instruments and NSS
  Preliminary Design Review – 2024-10
  Critical Design Review – 2025-10
  Ready for operation – 2026-12
Top Level Milestones
Important Note:
ESS is currently adjusting and updating all plans until 2027
The dates presented for ODHDS’s are not yet optimised nor adjusted towards when the systems are really needed, or by when for example pipe installation has to be done
We must establish a realistic agreement with Target and NSS asap

## Slide 5: More Open Points
  Criteria for linking to target and NSS installation plans not established yet
      If ODHDS installation is done too late, the risk is high that retrofitting is needed (e.g. pipes)
      This would translate in a (significant) cost increase
      It is important to refine timelines asap to better understand what is needed and when (analysis, design, piping, operation)
  Handing over an ODHDS to operations / cryo operations
      Is this done at other facilities?