## Slide 1: Target Project Progress and Plans
Eric Pitcher Deputy Head of Target Division 11th TAC Meeting April 1, 2015
www.europeanspallationsource.se

## Slide 2: Outline
Schedule
  Preliminary Design Reviews
  First hardware
Changes in the Target Baseline since TAC-10
Current design assessments
Committee comments from Preliminary Design Reviews
Development of a safety classification process

## Slide 3: Schedule of Preliminary Design Reviews

## Slide 4: First Target hardware to be delivered to the site in October
Concrete embedments for connecting all support rings to be delivered in October and installed in November
Outer ring to be delivered in November and installed in December
Embedments for active cells scheduled to be delivered to the site in February

## Slide 5: Changes approved to date by Target CCB
Number | Proposed Change | Status | Further Action | Outcome
TC-1 | Monolith diameter and position of light shutters | Approved | Take to Programme CCB | Approved
TC-2 | Lower monolith bulk shielding and support structures | Approved | None | 
TC-3 | Monolith helium vessel diameter and upper dome | Rework | Rework | 
TC-4 | Cooling medium for intermediate target cooling | Approved | None | 
TC-5 | Active Cells layout and waste package logistics inside the target station | Approved | Take to Programme CCB | Approved
TC-6 | Modified MR plug configuration and handling concept (Twister) | Approved | Take to Programme CCB | Approved
TC-7 | Operation Pressure Primary Target Cooling System | Approved | None | 
TC-8 | Target Wheel Shroud | Approved | Take to Programme CCB | Approved
TC-9 | Target Shaft Dimension | Approved | None | 
TC-10 | Tuning beam dump installation logistics | Approved | Take to Programme CCB | Approved
TC-11 | Tungsten Configuration | TBA |  | 
TC-12 | Butterfly Moderator Set | Approved | Take to Programme CCB | Approved
TCs since last TCM

## Slide 6: TC-6: “Twister” configuration for the Moderator-Reflector Plug
Relative to the TDR design, Twister offers these advantages:
No direct view of the target during MR-Plug change
Much less material to change (and dispose) each year
Casks reduced in size and weight, simplifying handling
Features of the Twister:
All steps in the replacement sequence can be monitored visually
Several simple contingency options are available in case of problems
The plugs offer flexibility for future arrangements
Up to 2120° flight path openings for both moderators
The support pillar and pipes will need active cooling

## Slide 7: TC-7: Helium coolant pressure for target increased from 3.5 to 10 bar
Benefits:
Reduced helium compressor power and cost
Reduced pressure drop
Reduced helium velocity
Detriments:
Increased helium leakage
  from flanges, valves, etc.
  from shaft seal to helium vessel
Increased stress in shroud

## Slide 8: TC-8: Target wheel shroud thickened and internal helium flow channels added
Top and bottom walls thickened from 5 to 14 mm to accommodate higher internal helium pressure
Flow to the Beam Entrance Window rerouted from the side walls to the top and bottom shroud walls
  Eliminates “hot spots” present in the TDR design
4% neutronic penalty

## Slide 9: TC-9: Target shaft diameter reduced
PDR design
11 ton
TDR design
17 ton
Higher helium operating pressure allows the shaft diameter to be reduced while maintaining low pressure drops through the shaft
Shaft mass reduced by 6 tons
  Lower torque load on motor
  Less load on bearings
Step to address radiation streaming increased from 50 to 135 mm

## Slide 10: TC-10: Tuning beam dump installation
Proposed installation path for the tuning beam dump shielding
  Blocks enter via the transport hall, provisionally 60 pieces of 10 tons ea.
  Blocks lifted up to the high bay, transferred to the hatch upstream of the monolith, and lowered to the floor of the A2T
  A trolley transfers the blocks to the tuning beam dump pit
  A temporary overhead crane lowers blocks into the beam dump pit

## Slide 11: TC-11: Tungsten Configuration
Proposal:
  Change the tungsten geometry from plates to bricks of uniform dimensions, 10 × 30 × 80 mm3
  Change the number of sectors from 33 to an even number
Benefits:
  Reduced stress in tungsten
  Easier to manufacture
Number of bricks in wheel in the range of 7 800 to 6 300
Neutronic penalty of 1.7 – 4%
TDR design: Plate geometry with “S” flow
Proposed design: Brick geometry with highly parallel flow

## Slide 12: TC-12: Butterfly Moderators
Baseline design now consists of two butterfly moderators
  3 cm height
  6 cm height
Enhanced thermal brightness with equal cold brightness relative to the pancake design
Liquid H2
H20
6cm Design
3cm Design

## Slide 13: Highlight of current design assessments
Neutron beam extraction
Target HVAC system
Helium purification
Monolith vessel atmosphere

## Slide 14: Monolith systems Modification of neutron beam extraction system
Uniform 6° angular spacing for N and E sectors
Alternating 5.3°/6.7° angular spacing for S and W sectors
Corner extraction scheme with four different centerline origins, one for each sector, to adapt to optimised moderator design
Double decker inserts for possibility to view either of the upper and lower moderator

## Slide 15: Progress on the Target HVAC System
Hazards analyses are under way, leading to requirements in terms of redundancy and safety function
          Expected levels of airborne contamination in the active cells used to classify zones according to ISO 17873
                Space allocated in the Target Building for supply, extraction and filtering

## Slide 16: Helium purification system will likely be much simpler than the current baseline
Monolith
95 m3, 1 bar
15 kg Helium
Target
20 m3, 10 bar
23 kg Helium
0.23 mg/s
4 μg/s Air
1 g/s
Circulating and cooling system
Circulating and cooling system
80 mg/s
He purification
(getter)
Contaminants
Contaminants
30 mg/s
Purity performance
I2
H2
O2
N2
CO2
H2O
He purity in
Helium loops: >99.99%
(72 g/year)
(6.58 kg/year)
3 kg/s
40 g/s
PCool
MonAtm
Target wheel rotary seal
< 1 ppb
< 1 ppb
< 1 ppb
< 1 ppb
< 1 ppb
< 1 ppb

## Slide 17: Operating the monolith atmosphere in vacuum may eliminate the need for a PBW
Benefits
  No need to replace the Proton Beam Window (PBW) twice per year
    Lower operating costs
    Higher availability
    Reduced radioactive waste stream
    Reduced dose to personnel
  Potentially offers passively safe beam shutdown for target LOCA & LOFA, and stopped wheel
  Lower beam losses on the way to the target
    Potentially reduced neutron background for instruments
    Potentially lower heat load to in-monolith structures surrounding the beamline
As a contingency, PBW and helium atmosphere designs and procurements will proceed regardless of the decision on the monolith atmosphere
monolith vessel

## Slide 18: Summary of Review Committee comments received from first four PDRs
Present a more complete technical description of the design solution
Summarize the value engineering exercises performed to reach the selected design
In some cases important interface requirements have yet to be established
Safety classification of systems and sub-systems must be further developed and integrated into a global approach at the target or ESS project level
Schedule appears to be aggressive

## Slide 19: Safety classification process is under development
No established regulatory framework in Sweden for licensing a high-power spallation source
            ESS is developing a framework to provide clear guidance for the selection of codes and standards to apply
19
Systems/ Components
Safety Function
Actions: (QA, Procedures) Analysis
Materials Manufacturing Installation
Inspection Testing
etc
Risks - Events
Safety
Class
Quality
Class
Code
Class
Design/define the systems and context
Define (enveloping) events and frequency (H1-H5)
Determine and categorize safety functions to prevent events (SaF)
Event Consequences
Calculate dose consequences of events (H1-H5)
Determine safety classification of equipment (SIC)
Determine quality classification of equipment in disciplines, e.g. mechanical
Choose classification in the codes and standards within the disciplines

## Slide 20: Concluding remarks
Project is on schedule to complete the preliminary design of all target systems by Feb 2016
First target hardware to be delivered and installed this year
The change control process is working smoothly and the project is realizing changes in the baseline
Preliminary Design Reviews are providing useful feedback to the project
Development of a safety classification process is under way