## Slide 1: WP 12.3 Moderator & Reflector Systems D. Lyngh, M. Kickulies, J. Ringnér, J. Jurns, M. Andersson, M. Pucilowski, T. Hedlund, A. Olsson
TAC11
Lund, 1st of April 2015
Presenter: Daniel Lyngh, Lead Engineer
Notes: 20+10min

## Slide 2: Outline
Schedule & Cost Update
  Recent Progress
  Schedule (PDR & CDR)
Technical Developments
  Twister
    Foundation Pillar and Rotation Pipes Development
  Butterfly
    Increased Heat Deposition, Flow Pattern
  Questions
    Double or split plug design
    Beam through twister shaft

## Slide 3: Recent Progress
Moderator & Reflector Plugs (MR Plugs)
  Preliminary Design Ongoing
  PDRs planned for June -15
  Detail Engineering, Make Phase and Testing issued for In-Kind Contribution (startup June)
  TC-8 Twister Handling – Approved
  TC-12 2x Butterfly Moderators - Approved
Cryogenic Cooling System
  Preliminary Design Ongoing
  PDRs planned for June -15

## Slide 4: Schedule
MR Plugs
Cold Moderators
Thermal Moderators
Reflectors
Handling System
Structure & Shielding
Liquid Hydrogen System
Concept Phase
Final Design
Make Phase
PDR
PDR
2019
Q1 Q2
2015
Q1 Q2 Q3 Q4
2016
Q1 Q2 Q3 Q4
2017
Q1 Q2 Q3 Q4
2018
Q1 Q2 Q3 Q4
PDR
PDR
PDR
PDR
PDR
SAT
PDR
Cryogenic Cooling System
He Cryoplant
PDR
PDR
PDR
PDR
PDR
PDR
PDR
PDR
PDR
PDR
PDR
PDR
PDR
Delivery
CDR
PDR
PDR
PDR
PDR
Site Inst. & Testing
Site Work
2014
Q3 Q4

## Slide 5: Technical Developments Twister Handling
Developed design of twister moderator handling system
  Water Cooling of Shafts
  Piping Arrangement
  Proton Beam Path
  Double Plug

## Slide 6: Overview
6
Proton beam window
Moderator and reflector plugs
Target wheel
Neutron beam windows
Neutron beam extraction

## Slide 8: Technical Developments Twister Handling Component Overview

## Slide 9: Technical Developments Twister Handling Shaft Cooling
Bearing
Cavities
water

## Slide 10: Technical Developments Twister Handling Bearings

## Slide 11: Technical Developments Twister Handling Piping Arrangement
Service Position
OperatingPosition
Operating Position

## Slide 12: Technical Developments Twister Handling

## Slide 13: Twister Option Proton Beam Path
Beam Cut-out
+Simpler Pipe Design
-Penetrates Foundation Pillar
+Symmetric Thermal Stresses
-Bigger Plugs
(+) Beneficial for 1 double plug (1 rotating shaft)
+Larger flexibility for beam footprint changes
  - Complex Pipe Routing for Bottom Plug
  + Smaller impact on Foundation Pillar design
  - Asymmetric Thermal Stresses
  - Asymmetric Proton Radiation
  - Limited design margins as shaft is restricted between proton beam and neutron extraction path
  - Asymmetric and therefore more challenging to manufacture
Beam Through Foundation Pillar
Proton Beam
Proton Beam

## Slide 14: Twister Option Independent or double Plugs
+ Simplified Piping Arrangement
+ Simplified Plug Structure & Shielding
+ Simplified Rotation Device
Bigger Cask and Handling System
+ Reduced number of moving parts and bearings
+ Independent Replacement
Complicated Piping arrangement for bottom moderator
+ Higher future mission flexibility
Double Integrated Plug
Split Independent Plugs

## Slide 15: Technical Developments
Butterfly Moderator Implementation
  3cm Top Moderator
  6cm Bottom Moderator
  Increased Cryoplant size 20->35 Kw
  Increased Liquid Hydrogen System
  Increased WP Budget (18%) and delayed schedule.

## Slide 16: Butterfly Moderators TC-12 Instrument Performance
[4] K. Andersson, Pancake and Butterfly Moderators, 4-3-2015.
Abstract
Three new moderator assemblies are evaluated and compared to the baseline configuration. Two make use of the new “butterfly” concept, resulting in a significantly higher thermal brightness compared to the water wings of the pancake moderator. The third is a variant of the Optimised Thermal configuration, changing one of the viewed sectors from East to South.
The preferred solution is to replace the top pancake moderator with a butterfly assembly of the same height. This will have a negligible impact on the cold-neutron instruments, while substantially improving the performance of the bi-spectral instruments. Replacing the bottom “optimised thermal” moderator with a butterfly assembly of the same height, viewable in all instrument sectors, will have little effect on the performance of the individual instruments, but will dramatically increase the flexibility of the instrument layout, allowing all instruments to freely choose the optimum moderator for their needs.

## Slide 17: Technical Development Butterfly Moderator Implementation
Top Pre Moderator Alternatives:
Water Wing
Vacuum Gap
Water Cross
Cold Moderator
Water Disc

## Slide 18: Technical Development Butterfly Design
3 Designs for Hydrogen Flow
Parallel Flow with Jet
Serial Star Flow
Serial Zeus
1
3
2

## Slide 19: Technical Development Butterfly Design
3 Designs for Hydrogen Flow
Parallel Flow with Jet
Serial Star Flow
Serial Zeus
1
2
3

## Slide 20: Technical Development Butterfly Design
3 Designs for Hydrogen Flow
Parallel Flow with Jet
Serial Star Flow
Serial Zeus
1
3
2

## Slide 21: Technical Development Butterfly Design
60mm Bottom Moderator

## Slide 22: Technical Development Butterfly Thermal Moderator

## Slide 23: Technical Development Butterfly Design

## Slide 24: Technical Development Butterfly Design

## Slide 25: Technical Development Butterfly Design

## Slide 26: Technical Development Butterfly Design

## Slide 27: Technical Development Butterfly Design

## Slide 28: Technical Development Butterfly Design

## Slide 29: Technical Development Butterfly Design

## Slide 30: Technical Development Butterfly Design

## Slide 31: Technical Development Butterfly Design

## Slide 32: Technical Development Butterfly Design

## Slide 33: Technical Development Butterfly Weld Tests

## Slide 34: Technical Development Butterfly Weld Tests
Ebeam welding
eBeam
“blindfolded”
“blindfolded”
but clear position
guide
eBeam
eBeam
2 lines
Filler wire

## Slide 35: Summary
Changes/Developments:
Twister Change
Butterfly Change
Questions/request for comments:
Proton Beam Path
Double Plug
Upcoming Activities:
Weld Tests
PDRs in June