## Foglio1
VESPA COMPONENTS FOR PROCUREMENT
ITEMS | STATUS UPDATE
NBOA and NBPI: NBOA has been delivered to ESS; NBPI CDR done, October 2021; delivery of NBPI to ESS: summer 2022, waiting for next NBPI/NBOA integration in Lund according to ESS scheduling.
BBGOA: the optic insert has been designed and included in the VESPA neutron guide technical specification; it will be part of the "in-bunker" neutron guide supply, sharing the same requirements in terms of substrate and radiation hardness requirements; procurement: it is envisaged a possible supply from SNAG, the only reference for metal substrate (Al/Cu) optics supply; public tender can be published as soon as the procurement procedure will be activated; installation plan: CTV has not been performed yet; tender procedure can take up to 9 months, possible prioritization for in-bunker early access is possible if supply contract starts Q1-2023. costs increase: for the guide system, as well as for all the systems that need to be procured, a significant costs increase is expected respect to the assigned project budget (year 2016); a strategy/rule to deal with budget overrunning and prioritization of the supplies can support the procurement phase and project planning.
In-bunker neutron guide: the in-bunker guide system specification is fully defined; a single section of 2 m with elliptical profile, is completed with support and alignment system, the rest of the guide will be integrated in choppers, and heavy shutter within the bunker. Procurement: it is envisaged a possible supply from SNAG, the only reference for metal substrate (Al/Cu) optics supply; public tender can be published as soon as the procurement procedure will be activated; installation plan: CTV has not been performed yet; tender procedure can take up to 9 months, prioritization for in-bunker early access is possible if supply contract starts Q1-2023. Costs increase: for the guide system, as well as for all the systems that needed to be procured, a significant costs increase is expected with respect to the assigned project budget (year 2016); a strategy/rule to deal with budget overrunning and prioritization of the supplies can support the procurement phase and project planning.
Pulse Shaping Chopper: The chopper system includes 5 units, three of them operate in-bunker; a VESPA chopper system technical specification has been released with specifications for all the chopper units. Procurement: a change request for the transfer of scope of the chopper system has been made to the ESS, the ESS chopper group will build and install the choppers system; Installation plan: the VESPA choppers "common project" didn't start yet, details on planning are missing, milestones must be agreed, eventually considering if an early access to the bunker is possible (within Q3 2024); Criticalities: very compact unit, 3 double discs in less than 1 meter (@6,5m, 6,8m, 7,36m); large discs (800 mm diameter) fast spinning (154 Hz); costs increase: for the present specifications, since the first offer from ESS in year 2019, the price increased of 18%, that is compatible with the assigned budget though raising concerns on the BAC for the project.
Frame Overlap Chopper: the chopper unit has a single disc with diameter of 700 mm and speed of 28 Hz. It operates in the instrument hall; a VESPA chopper system technical specification has been released with specifications for all the chopper units. Procurement: change request for the transfer of scope of the chopper system to the ESS, the ESS chopper group will build and install the choppers system; installation plan: the VESPA choppers "common project" has not started yet, details on planning are missing, milestones must be agreed, eventually considering if an early access to the bunker is possible (within Q3 2024); costs increase: for the present specifications, since the first offer from ESS in year 2019, the price increased of 18%, that is compatible with the assigned budget though raising concerns on the BAC for the project.
Heavy shutter: the design of the heavy shutter follows the LOKI heavy shutter design, which is matching with VESPA installation space and neutron adsorbing requirements, and for general safety and functional performance; procurement: the supply will be outsourced, a tender will be published according to ESS CTV outcome and CNR procedure; tender procedure can take up to 9 months. Installation plan: the item is in-bunker operating; the early access to the bunker is possible within Q3 2024, that can be compatible with theoretical lead time for manufacturing and delivery if the supply contract starts within Q1 2023; Criticalities: the unit will operate in-bunker, so an early delivery is preferable, though procurement has not started yet, a technical specification can be provided in short time based on LOKI design; the supply can be made by Mirrotron; a market survey aiming to explore early supply opportunities for in bunker components is ongoing (neutron guides, heavy shutter).
Bunker Wall feedthrough: the design of the optics profile for the bunker wall insert is part of the VESPA guide system technical specification; the detailed design of the insert and support pillar is missing. It will be completed by the supplier (metal substrate requirement -> SNAG); the procurement the system will be includede in the "in-bunker" guide system supply, in outsourcing; the final design , manufacturing, and installation at ESS (turn-key supply) will be provided by an external supplier; costs increase: for the guide system, as well as for all the systems that need to be procured, a significant costs increase is expected with respect to the assigned project budget (year 2016); a strategy/rule to deal with budget overrunning and prioritization of the supplies can support the procurement phase and project planning.
Sub Frame Overlap Chopper: the chopper unit has a double disc with diameter 700 mm and speed 42Hz, it operates in the instrument hall; installation plan: the VESPA choppers "common project" has not started yet, details on planning are missing, milestones must be agreed, installation works in the instrument hall for VESPA project are expected in Q2 2024, the installation plan will be updated considering to speed up the in-bunker delivery, being the installation works out of the bunker have less time sheduling constraints.
Out of bunker Neutron Guide: the out-of-bunker guide system specification is fully defined; elliptical profile on both plane (hor. and vert.), glass substrate, total lenght 43 m. Procurement: a tender will be published according to the ESS CTV and CNR procedure; tender procedure can take up to 9 months. Installation plan: the guide system in the instrument hall can be installed according to the original assigned time window Q2 2024, if the lead time for the supply is compatible with the date of signature of the supply contract (expected Q1 2023). Costs increase: for the guide system, as well as for all the systems that need to be procured, a significant costs increase is expected with respect to the assigned project budget (year 2016); a strategy/rule to deal with budget overrunning and prioritization of the supplies can support the procurement phase and project planning.
Beamline Shielding: the system has been preliminary designed along the PHASE 1 of the ESS common project; procurement: a change request for the transfer of scope of the VESPA beamline shielding system has been made to the ESS, ESS will build and install the VESPA beamline shielding system at the facility; installation plan: the VESPA beamline shielding "common project" did not start yet, details on planning are missing, milestones must be agreed, installation works in the instrument hall for VESPA project are expected in Q2 2024, interdependencies with out of bunker neutron guide installation task must be checked. Costs increase: for the beamline shielding system, the price of the ESS supply increased of 60% with respect the first offer from ESS in year 2019, for the same specifications; that is raising concerns on the BAC for the project, and strategy to deal with similar issues for VESPA subs systems procurement.
Experimental Cave & Hutch: the experimental cave design is at a concept stage; all the functional requirements are defined; details on interfaces with the secondary spectrometer, beamline shielding, and SEE are missing; design pending due to lack of staff (CAD model) Procurement: the system will be procured in outsourcing, a tender will be published according to the ESS CTV and CNR procedure; tender procedure can take up to 9 months. Installation plan: the VESPA experimental cave should be the first system to be installed in Q3 2023; CTV expected Q1 2022 did not occur and is not planned yet; delay on TA WP milestones are expected, interdependencies with the out-of-bunker neutron guide installation task must be checked. Criticalities: the system is the first to be delivered according to original project plan; delay on the design of the secondary spectrometer impacted the finalisation of the design; the team CAD capability is almost zero at the moment, an engineer to be hired.
Beam monitors: five beam monitors for diagnostics and normalization purpose are agreed in terms of basic requirements (position, size, pixelling, temporal and spatial resolution). Technical details are under development in collaboration with ISTP-CNR and Univ. Milano-Bicocca (Milan, ITALY).
Vacuum Tank: large Al container (1,300 mm diameter, 900 mm wide) able to host the core components of the secondary spectrometer under vacuum condition and a top-loading large cryostat. It is equipped with 2 flanges for neutron beam, 7 flanges for detector/cold-head, and 6 flanges for equatorial diffraction arms. Conceptual model with a preliminary engineering design agreed. Detailed design pending. Procurement: N/A. Installation plan: this item, as a part of the WP4, is expected to be installed in Q2 2024, anyway being placed within the cave, its installation can be managed all along the installation period after the cave will be built. Criticalities: probable delays on schedule due to lack of staff, waiting for CAD engineer; procurement model not defined, the secondary spectrometer sub-system was originally intended to be built in-house, in partnership with STFC/ISIS. Pre-assembly of components takes time, early procurement to allow enough time between components purchase and sub system delivery to ESS.
Curved analyser: Made by 12×12 mm2 HOPG tiles (3.354 Å d-spacing, 1.5 deg. mosaicity), it selects final energy in the range 3.2 - 4.8 meV, guaranteeing full access to the elastic line and a solid angle coverage of 0.375 sr per module. Conceptual model with a preliminary engineering design agreed. Detailed design pending. Procurement: . Installation plan: this item, as a part of the WP4, is expected to be installed in Q2 2024. Criticalities: Probable delays on schedule due to lack of staff, waiting for CAD engineer; procurement model not defined, the secondary spectrometer sub-system was originally intended to be built in-house, in partnership with STFC/ISIS. Pre-assembly of components takes time, early procurement to allow enough time between components purchase and sub-system delivery to ESS.
Beryllium filter and cold head: six slices of Be (17.1 deg. angled wedge, thickness 147 mm) able to remove, at a working temperature below 77 K, the higher-order harmonics coming from analyser. They are separated by slabs of absorbing material to reduce the background signal on detectors, that are placed at 25 mm from the Be filters. Conceptual model with a preliminary engineering design agreed. Detailed design in progress, completion expected in 2022. Procurement: TG3.2 expected by the end of 2022, not yet planned. Installation plan: this item, as a part of the WP4, is expected to be installed in 2024. Criticalities: probable delays on schedule due to lack of staff, waiting for CAD engineer; procurement model not defined, the secondary spectrometer sub-system was originally intended to be built in-house, in partnership with STFC/ISIS. Pre-assembly of components takes time, early procurement to allow enough time between components purchase and sub system delivery to ESS
Detectors and electronics: conceptual model with a preliminary engineering design agreed. Detailed design in progress, completion expected in 2022. Spectroscopy: 8 mm - 3He tubes (8 per module) with an active height of 300 mm and position sensitiveness, pixeling of 8×8 mm^2. Diffraction, equatorial bank: 8 mm 3He tubes (20 per module as an upper limit) with an active height of 280 mm and position sensitiveness, pixeling of 8×8 mm^2. Procurement: TG3.2 expected by the end of 2022, not yet planned. Installation plan: this item, as a part of the WP4, is expected to be installed in 2024. Criticalities: probable delays on schedule due to lack of staff, waiting for CAD engineer; procurement model not defined, the secondary spectrometer sub-system was originally intended to be built in-house, in partnership with STFC/ISIS. Pre-assembly of components takes time, early procurement to allow enough time between component purchase and sub-system delivery to ESS.
Cryocooler: based on Close Cycle Refrigerator technology (5 K base temperature) with a customized design able to host large and advanced sample environment equipment (CCR with a total lenght of 1800 mm and a sample compartment, 100 mm diameter). A possible supplier (Quantum design Europe) has been identified and showed interest and capability to provide a customized design fitting VESPA application. Subject to TG3 review together with the WP4. Installation plan: this item, as a part of the WP4, is expected to be installed in 2024, though because the nature of the component and interfaces the installation of the components can be managed with some flexibility in the nstllation plan
Sample stick, precision stage and sample changer: details to be defined when the detailed design of WP4 is completed. Criticalities: the implementation of a pre-cooling system for the large capacity, high throughput sample changer is not fully agreed due to budget constraint. The sample environment equipment will be satisfying the instrument requirements and will be based as much as possible on products available on-the-shelf. Integration work must be considered on interfaces within sample tank and analyser.
Electrical Infr., PPS, common utlities: VESPA takes part to the ESS common utility project and will join the electrical infrastructure ESS common project (level 3); preliminary meeting with Stuart Birtch; VESPA will enter into details with the ESS team later on accordingly to the workload and planning for the previous instruments.