## Slide 1: FREIA STAP Update
Jon Elmer & Tom Arnold
3rd May 2022
Notes: Status
Challenges
Schedule

## Slide 2: FREIA Status
Bunker Wall Insert
NBOA
NBOA (S-DH)
FAT completed in Dec
Delivered to ESS
Installation in Q2/Q3
Chopper Discs (ADSF)
Ready for shiping (x4)
Rework underway (x2)
Delivery to RAL Q2
Guide (SNAG)
Design complete
Collimation System
Collimation guides ordered (SNAG)
Vacuum vessel tender complete
Sample Positioning Sys. (Symetrie)
Design complete
LOKI/FRIEA Hutches
Installation complete
In-bunker Guide
Bunker modules 3, 2, & 1
Bunker Modules
Design complete
Chopper housings & WBC discs
Design complete
Slits 1-3 (JJ X-ray)
Design complete
Detector Bench
Detailed design progressing
S1 (JJ X-ray)
Hutch installation
1.3m and 1m Choppers
SPS (Symetrie)
Bunker Wall Insert
Design complete

## Slide 3: NBOA (S-DH)
The first optics for FREIA were delivered to ESS in December ‘21 following successful FAT.
The optics will be installed in 2022 Q2/Q3, pending delivery of the NBPI (port insert) by ESS Target.
Alignment Devices
Assembled NBOA Units
NBOA CAD Model

## Slide 4: Guide (SNAG)
Design completed in Jan ’22, ESS review complete
Delivery of BBG, Heavy Shutter and BWI guides have been prioritised to be ready for earlier installation.
Next steps:
  Coating development (wafer waviness)
  Manufacture of BWI vacuum housing
Horizontal geometry | S-bend R 174 m/R 200 m
Vertical geometry | 2° inclined ellipse 22.8 m focal length
Cross-section | Max 25 cm (h) × 3 cm (w)
Coatings | Top/bottom: m=3.5 to 6 Sides/vanes: m=3.2 or 3
In bunker
Bunker wall
Out of bunker

## Slide 5: Bunker Modules
BEAM
Choppers and guide housings grouped into three independent “modules” to aid installation/ extraction, allowing maintenance activities to be performed outside of the bunker.
Design completed in April ’22 – under review by ESS
Module 1 (WBC1)
Module 2 (WFM1&2, FOC1)
Module 3 (WBC2, FOC2)

## Slide 6: Choppers
Design completed in April ’22 – under review by ESS
Choppers to share common upper housings where possible:
  Type A: ∅1m ISIS or ADSF disc; in-bunker
  Type B: ∅1.3m ADSF disc; in-bunker
  Type C: ∅1.3m ADSF disc; out-of-bunker
  Type D: ∅1m ISIS or ADSF double disc; out-of-bunker
Freia’s Chopper Suite
WBC1
Type A
WFMs, FOC1
Type B
WBC2
Type A
FOC2
Type B
FOC3
Type C
WBC3
Type D

## Slide 7: Chopper Discs (ISIS)
Design completed in April ’22 – under review by ESS
New design for light-weight, single-sided 10B4C coated aluminium disc to be used for WBC1 & WBC3.
Initial coating trials successful, with further trials ongoing.
10B4C powder order significantly delayed, but not impacting manufacture schedule.
WBC1
WBC3

## Slide 8: Chopper Discs (ADSF)
Ready for shipping (x4)
Rework underway (x2)
  WFM1 – additional coating applied
  FOC3 – accidental damage repaired
Delivery to RAL expected Q2
WFM1
WFM2 ✔
FOC1 ✔
FOC2 ✔
FOC3
WBC2 ✔
FOC3 Damage
Repair
WFM1 Post-coating

## Slide 9: Chopper Spindles & Controllers
Ordered from SKF in July 2020, with delivery prioritised according to ESS’ schedule. Delayed substantially due to supplier overload and Covid.
Deliveries delayed:
  2 sets due Nov ‘21
  3 sets due Dec ‘21
  3 sets due Jan ’22
Delivery status:
    4 sets ready Feb ’22 ✔
    4 sets due April ’22

## Slide 10: Heavy Shutter
Mechanical design loosely based on Loki’s heavy shutter, with substantially more mass in the beam dump necessary to sufficiently attenuate the beam.
Various materials evaluated for performance and activation – Copper, Tungsten and Molybdenum.
Met with ESS in September to discuss material selection. Concluded that the presented materials fulfil ESS’ requirements for shutter performance and activation – final material choice will be based on manufacturability & cost.
Design on hold until Q3 pending engineering resource.
Beam dump
Guide
Pneumatic cylinder
Linear rails
Extraction frame
Fixed walls
Top plate
Thermal
Fast
Heavy shutter concept

## Slide 11: Bunker Wall Insert
Design completed in April ’22 – under review by ESS.
Once manufactured, integration trial with the vacuum housing to be completed in 2022 Q4.
Upstream & Downstream Alignment Devices
Steel Shielding
Vacuum Housing (SNAG)
Guide (SNAG)

## Slide 12: Collimation System
Slit 1
Slit 2
Slit 3
Collimation Guides
Contract awarded to SNAG
Vacuum Vessel
Tender complete, award TBC
Sample Position
Fast Shutters (Uppsala)
Beamline tests to be performed at ISIS
Kinetics Slits
Design underway
BEAM

## Slide 13: Collimation Modes
Standard mode
Inverted mode
Kinetics mode

## Slide 14: Slits (JJ X-ray)
Design completed in April ’22 – under review by ESS
Slit 1: YZ, in vacuum
Slit 2: Z, in vacuum
Slit 3: YZ, in air
Slit 1
Slit 2
Slit 3

## Slide 15: Collimation Guides
Reflectometry and Inverting guides ordered from SNAG – partitioned guides to be included in upgrade scope for ⁓30% flux increase.
Reflectometry
Guide 1
Reflectometry
Guide 2
Partitioned Guide 1
Partitioned Guide 2
Inverting Guide

## Slide 16: Fast Shutters
“Flipper” shutter prototype tested in vacuum at Uppsala University.
Offline timing tests to be carried out at ISIS in April, with beamline tests later in ‘22.
Initial vacuum tests show that servo motor operation in vacuum is feasible.
Slow-motion video

## Slide 17: Sample Positioning System (Symetrie)
Design completed in April ’22 – under review by ESS
Hexapod system with integrated Y-translation stage for sample changing.
Protective bellows and gaskets to mitigate against spillages.
Provides mounting for standard interfaces
  L2 – typical use case
  L0 – rare use, no motion
SPS Hexapod
L2
L0

## Slide 18: SPS Vibration Isolation
Active Vibration Isolation Table
Passive Vibration Isolation Pads
Active vibration isolation table to be installed on top of the SPS for horizontal (free-liquid) samples.
Active VI platforms are incompatible with inclined samples, and must be locked or removed before tilting.
Passive VI pads installed beneath the SPS are unlikely to be effective below 60Hz, and may be detrimental.
Plan to test SPS frequency response (impact hammer test) with & without vibration isolation pads to determine best performance for the installed system.

## Slide 19: Detector Bench
+21°
-7.5°
FEA of design outsourced – stresses and deflections well within limits.
Natural frequencies low, implemented changes to stiffen frame and tables by adding cross braces and changing bolted structures to solid machined.
Design of cable management ongoing.

## Slide 20: Beam Monitors (ESS)
6x GEM monitors delivered by ESS Beam Monitors Common Project, designed by Milano-Biccoca.
Segmented GEM foil used to cope with the very high count rates expected at full power.
Concept design to be adapted for in vacuum monitors (BM4 & BM5), using proven PCB based vacuum feedthrough technology.
In bunker monitors locations
on Module 2
BM1
BM2
PCB based vacuum feedthrough
Concept
Design

## Slide 21: Challenges
Collimation Vessel Tender
  First tender failed  budget revised
  Lack of competition  engaged new suppliers
  Second tender complete, award TBC
Resourcing challenges ongoing
  Lost several key members of the instrument team
  Recruitment ongoing + increased reliance on external contractors
Supply chain delays
  Long lead components ordered with significant float
  SKF components +3-4 months
  10B4C (for choppers) +4 months

## Slide 22: Schedule
2019
2020
2021
2022
2023
2024
2025
Shipping
Neutron Guide
Choppers
Bunker Zone Shutters & Feedthrough
Shielding and Structures
Cave Internals
Services
Pre-build/commission
Installation at ESS
Today
TG3.3
TG3.4
TG3.1 ✔
TG3.2
TG3.5
TG3.6

## Slide 23: Thank you Questions?