## Slide 1: Project Planning
12th Technical Board Meeting
Luisella Lari
Head planner for Accelerator & Senior Scientist
In particular I would like to thank L. Gunnarson and all WP managers
www.europeanspallationsource.se
November 20, 2014

## Slide 2: Reminder….
21st - 24th April 2015 review will focus on schedule and transition to operations

## Slide 3: Outline
Present P6 Schedule status
Different levels for different Milestones
The new P6 schedule for Installation
Summary schedules for WPs
“TO DO” before the review
Change Log for Planning
Conclusions

## Slide 4: Present P6 Schedule status
At the end of 2014 AC=PV and BAC
Chart: Grand Total
| 31/12/2013 | 31/12/2014 | 31/01/2015 | 28/02/2015 | 31/03/2015 | 30/04/2015 | 31/05/2015 | 30/06/2015 | 31/07/2015 | 31/08/2015 | 30/09/2015 | 31/10/2015 | 30/11/2015 | 31/12/2015
Earned | 14709401.0002 | 36542846.355 | 33949988.2984
Actuals | 14709401 | 32562929.76 | 34864979.76
Scheduled | 14709401.0002 | 32562927.6533 | 35468021.6284 | 39642798.9533 | 42300365.9788 | 44312164.749 | 46277286.924 | 49043796.5211 | 53284624.1187 | 58291426.8949 | 61778399.6648 | 67298198.6546 | 74929016.5953 | 80039560.7891
2013
2014
After the end of 2014 the PV were normalized to the AC.
JAN 2015

## Slide 5: Present P6 Schedule status
From August 2014 until now a massive re-plan was put in place in the Accelerator Project plan in P6 called 11.
Summarizing:
2 new WPs were created: WP16 (Cooling) and WP17 (Power Converters).
Scope changed for WP06 (Beam Delivery system).
A lot of WBS changes @ WU level i.e. no more totally aligned to the 2013 cost book (see Change Log).
Resource leveling actions put in place for each WP to align them to the Accelerator official staff plan.
Introduction of PDR, CDR, TRR and audit milestones.
Introduction of Ready For Installation (RFI) milestones.

## Slide 6: Different levels for different Milestones
LEVEL1
 1G MS checked @ ESS management level.
LEVEL2
 2G MS checked @ ACCSYS management level.
LEVEL3
 GG MS related to the interface between ACCSYS and other ESS projects e.g. ICS, target, NSS, CF.
LEVEL4
 MS that link different ACCSYS WPs together.
LEVEL5
 MS related to the WP itself e.g. PDR, CDR, TRR or technical WP achievement.

## Slide 7: LEVEL 1 & LEVEL 2 (High level Milestones)
NB: For the Annual Review in the Plenary Section a different template could be imposed by ESS ADM to having a common layout for all the Projects

## Slide 8: LEVEL 2 (Ready For Installation Date)
Klystron Gallery (RFQ Klystron, MEBT RF Amplifiers, DTLs Klystrons, SPKs High Power Amplifier, MB Klystrons, HVCM for RFQ, DTL, SPK, MB, HB, RF Distribution for MEBT+RFQ, DTL, SPK, MB)
Tunnel (NC Linac components, SPK, SPK LWU (TBC), MB CM, MB LWU (TBC), HEDP (TBC), HB, HB LWU (TBC), BI instrumentation (TBC))
NB: These dates are the input data for the installation plan

## Slide 9: Installation Plan in P6
The present Accelerator Project schedule in P6 is called 11. It is a plan spanning over the whole ACCSYS project timeframe from design until beam commissioning, tracking costs & resources allocated.
A new project called 11I (I for Installation) was created in P6. This is a schedule only “space” oriented. The WBS is composed by Tunnel, Gallery, Stubs.

## Slide 10: Installation Plan in P6
Project 11
Project 11I
time
WPs
Areas
ESS-0025901.1
& LinacLego
RFI date e.g. SPK
e.g. Installation SPK
WP04
WP99
SPK region

## Slide 11: Summary schedules for WPs
In the Annual Review, all the schedules have to be extracted from P6.
In the Annual Review - Accelerator Section – Summary Schedules for the WPs to be used by the speakers in-line with P6.
…….Some examples in the following slides

## Slide 12: WP03 Master Schedule

## Slide 13: WP04 Master Schedule

## Slide 14: WP05 Master Schedule

## Slide 15: WP08 Master Schedule
NB: Please let me know if you need one for your presentation, also @ the level of WU.
It is really important that we are coherent with the P6 official and that no different schedules have to be presented!

## Slide 16: “TO DO” before the review
Include some last re-plan actions,
Include cabling costs in WP1,
Some alignment with the staff plan to be finalized,
Check/Review of all the links,
Re-naming action of the MS with respect to their “LEVEL”,
Check/Review of all the lN-Kind tags,
ESS internal procurement contracts to be checked to identify contract > 50 kEUR for 2015 and 2016, and above >200 kEUR
Schedule Analysis & interface with Initial Operation schedule

## Slide 17: ESS-0012700 ACCSYS Project CCB Change Log @ ACCSYS project level and @ WP level i.e. (change control) Classes C and lower within ACCSYS project
Log nr | CR-ID | Class - Approver/Reviewer | WBS | Summary of Change Request (proposed change)
001 | 11.00001.1 | D - WP Ldr | 11.8 | Increased cost for “Reduced scale RML modulator prototype construction” – addendum to CR 11-0.
002 | 11.00002.1 | C - Project Ldr /Project CCB | 11.1; 11.14 | Replanning WP14 due to Accelerator Division reorganization.
003 | 11.00003.1 | C - Project Ldr /Project CCB | 11.8; 11.99 | Revised Installation Waveguide: the installation activities related to the waveguides are moved from WP99 (Installation) to WP8 (RF).
004 | 11.00004.1 | D - WP Ldr | 11.99 | WP99 re-planning at the WU level: The installation activities related to WP99 are redistributed in different WUs.
005 | 11.00005.1 | C - Project Ldr /Project CCB | 11.3; 11.5 see CR for WUs impacted | Replanning CEA parts of WP3 and WP5. In-kind agreement with CEA.
006 | 11.00006.1 | C - Project Ldr /Project CCB | 11.15; 11.16 | New WP16 for water cooling system, detached from WP15 scope.
007 | 11.00007.1 | D - WP Ldr | 11.13 | Change of leader for WP13 Safety & Reliability. WP leader skills in line with the work to be performed in the WP13.
008 | 11.00008.1 | C - Project Ldr /Project CCB | 11.6.65 11.8.8; 11.17 | Creation of a new WP17 for Power Converters. Expert required in the filed of Power Converters.
009 | 11.00009.1 | C - Project Ldr /Project CCB | 11.2 11.6 | New WU for LWU and for radiation hard magnets to be included in WP02 from WP06. WP06 experts will cover only the work related to raster magnets.
011 | 11.00011.1 | D - WP Ldr | 11.12 | Re-plan for WP12

## Slide 18: ESS-0012700 ACCSYS Project CCB Change Log @ ACCSYS project level and @ WP level i.e. (change control) Classes C and lower within ACCSYS project
Log nr | CR-ID | Class - Approver/Reviewer | WBS | Summary of Change Request (proposed change)
010 | 11.00010.1 | D - WP Ldr | 11.6 | Changed scope for WP06 New collaborating partner agreement.
011 | 11.00011.1 | D - WP Ldr | 11.12 | Re-plan for WP12
012 | 11.00012.1 | C - Project Ldr /Project CCB | 11.8 | Update cost according to contracts
013 | 11.00013.1 | A - ESS AB Board | 11 | New budget for 2014.
014 | 11.00014.1 | A - ESS AB Board | 11 | New budget for 2015.
015 | New, 11.00015.1 | C - Project Ldr | 11.1 | Updated budget for cabling in 11.1.
016 | New, 11.00016.1 | C - Project Ldr | 11.1 | Updated budget in Management WP 11.1
017 | New, 11.00017.1 | C - Project Ldr | 11.14 | Updated budget in Management WP 11.14 reflecting the present staff plan
018 | New,11.00018.1 | C - Project Ldr | 11.13 | Updated budget in Management WP 11.13 reflecting the present staff plan and the scope extended for WP13 (Safety)

## Slide 19: Conclusions
An overview of the current status of the ACCSYS schedule and related on-going activities was presented, focusing on the needs for the Annual Review.
Some open actions have still do be fixed before the Annual Review or better before:
Summary schedules extracted from P6 will be produced for Annual Review speakers.
2Oth March 2015
Close change window

## Slide 20: Thanks for your attention!