## Slide 2: DST capital investment projects
Science Directorate Projects Meeting
PRESENTED BY Jesper rude selknæs

## Slide 3: Introduction
  Objectives – what we wish to accomplish
  The goal of the DMSC capital investments projects are to ensure that the hardware, hosting and licensing capacities are in place to ensure:
      Data acquisition, data reduction, data analysis and data storage of experimental data can be achieved in accordance with the requirements set by instrument teams and end user expectations.
      Scientific computing activities required by ESS to support the construction, development and operation of the facility can be executed.
      That scientific computing capacities required by external funded projects (PaNOSC and HighNESS) can be delivered.
DMSC capital investment activities

## Slide 4: Capital investment plan
2022 overview – 973KEUR in total investments
Chart: 
| HPC | InfiniBand | Ethernet | Licenses | Services | Beamline equipment | Miscellaneous equipment
Distribution of investment costs for 2022 | 130000 | 250000 | 275000 | 70000 | 68000 | 100000 | 80000

## Slide 5: Tracking and planning
Methods and tools used
P6 is used on a per-year level – one activity for all investments in a given year
JIRA is used for tracking and planning in a given year:
  One epic for all procurements in a given year
  One story for each tender or batch of small procurements
  Epics and stories are annotated with P6 activities providing a link between P6 and JIRA
  BigPicture is used to monitor the progress of the investment activities – allowing for accurate reporting to planners and management.
An extended Excel spreadsheet is used to keep track of spendings.

## Slide 6: Tracking and planning
  P6 activities
  In the period 2022 to 2027 these activities are planned in P6:
  2022: NSS-A2146967170 Budget value: 973KEUR
  2023: NSS-A2146967230 Budget value: 1842KEUR
  2024: NSS-A2146967240 Budget value: 1970KEUR
  2025: NSS-A2146967250 Budget value: 590KEUR
  2026: NSS-A2146967260 Budget value: 1625KEUR
  2027: NSS-A2146967280 Budget value: 1410KEUR
P6 activities overview

## Slide 7: 2022 investment plan
Status on activities
Investment project | Procurement method | BOM | Publ | Quotes evaluated | Goods recv. | Invoice recv.
HPC replacement nodes | Tender | Done | OCT-384 | Yes | Yes | Yes
InfiniBand switches | Tender | Done | OCT-387 | Yes |  | 
Ethernet equip. | Tender | Done | OCT-402 |  |  | 
Beamline equipment | (Tender) | On-going |  |  |  | 
Licenses | Ad-hoc | On going | Partially | Partially | Partially | Partially
Services | Existing agreements | N/A | N/A | N/A | Yes | Partially
Misc. equipment | RFQs and FWA | On going | On going | Partially | Partially | Partially

## Slide 8: 2022 investment plan
Status on spendings
Investment project | Budgeted costs | Actual accrued costs | Completed
HPC replacement nodes | 130KEUR | 170KEUR | Yes
InfiniBand switches | 250KEUR | 133,3KEUR | No
Ethernet equip. | 275KEUR | - | No
Beamline equipment | 100KEUR | - | No
Licenses | 70KEUR | 8,6KEUR | No
Services | 68KEUR | 41,86KEUR | No
Misc. equipment | 80KEUR | 21 KEUR | No
Total 2022 costs | 973KEUR | 374,76 KEUR | -

## Slide 9: 2022 investment plan
Status on spendings
Chart: DST Capital Investments 2022
| January | February | March | April | May | June | July | August | September | October | November | December
Total Actual | 0 | 25.2 | 41 | 41 | 41 | 57.5 | 57.5 | 195.28 | 377.08 | 377.08
Total Planned | 18.1667 | 36.3333 | 54.5 | 72.6667 | 90.8333 | 339 | 357.1667 | 650.3333 | 693.5 | 736.6667 | 779.8333 | 973
Projection | 377.08 | 675.04 | 973

## Slide 10: Known issues
Inflation, supply chain and schedule
Vendors reports expected price increases between 90% and 100%
Major supply chain issues for all relevant components – specifically on InfiniBand parts and customized workstations.
Implemented mitigation:
We are working with vendors to find ways of avoiding the most severe supply-chain issues.
We are initiating procurements as soon as we are confident that we need a given piece of equipment.
We are adjusting and refining our procurements to limit the budget impact of cost increases.
DST is an active part in talks on adjustments to existing framework agreements on selected parts.
Participation in relevant big-science events and vendor meeting – most recently BSBF2022.

## Slide 11: Actual and tangible progress
New HPC nodes in COBIS server room
20 pcs. 32 cores 512GB memory
4 more underway – delivery late October

## Slide 12: Finish presentation