## ISRC_Interfaces
System A |  |  |  | System B
Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
L3 | ACC.IS | Ion Source | Luigi/INFN | L3 | ACC.LEBT | LEBT | Luigi/INFN | Mechanical interfaces | Drawing | Plasma chamber to extraction column
L3 | ACC.IS | Beam Physics | Mamad/ESS | L3 | ACC.LEBT | Beam Physics | Mammad/ESS | Twiss parameters | Doc/spec | s=0 at the plasma chamber wall | TraceWin file (no field map, simple elements) of the warm linac
L3 | ACC.IS | Vacuum | Marcelo/ESS | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | Flow rate | Doc/spec | Plasma chamber to extraction column | Vacuum simulations for the integrated Warm Linac
L3 | ACC.IS | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the plasma chamber wall in the tunnel | Skeleton, drawing | s=0 + physical dimensions of HV platform with BLS | Skeleton
L4 | ACC.IS.BLS | Mechanical Beam Line Support | Luigi/INFN | L2 | SI | Site Infrastructure | Dave/ESS | Placement in the tunnel (e.g. transport hook on equipment), pre-alignment of support, grounding | Doc/spec, drawing | Embedded EMC grid + copper plate(?) | 3 terminal pads connecting HV cage to embedded EMC grid
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Alignment of plasma chamber (independent of extraction electrodes wo bellows?) | Alignment precision (bellow?)
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L4 | ACC.IS.BLS | Mechanical Beam Line Support | Luigi/INFN | Plasma chamber to HV platform, HV platform to BLS | Drawing | Insulating columns
L4 | ACC.IS.ISS | HV platform | Luigi/INFN | L4 | ACC.IS.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing | Water cooling for magnetron, automatic tuning unit (ATU) and plasma chamber
L4 | ACC.IS.WTRC | Water Cooling | Anton/ESS | L4 | ACC.IS.WTRC | Water Cooling | Anton/ESS | Routing of the pipes & pipe types inside of HV cage | Drawing, Doc/spec
L4 | ACC.IS.ISS | HV platform | Luigi/INFN | L4 | ACC.IS.CNPW | (Signal) Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing to HV platform | Doc/spec, drawing
L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L4 | ACC.IS.CNPW | Cables + power | Lea + Frithoff/ESS | Connectors, cable types + routing | Doc/spec, drawing | HV PS + HV insulation transformer + PS repeller electrode
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L4 | ACC.IS.PBI | Proton beam instrumentation | Benjamin/ESS | tbd | tbd | Current measurement (current proposal to drop in HV)???
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation | Doc/spec
L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | L4 | ACC.IS.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L2 | ICS | Integrated control system | Eugene/ESS | IS control parameters + physical interfaces of controllers | Doc/spec
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Grouning hook, length of extraction column | Doc/spec
L4 | ACC.IS.CNPW | (Signal) Cables + power | Lea + Frithoff/ESS | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Surge arrester + EMC filter | Doc/spec, drawing |  | Shielded, metallic cable trays for (signal) power cables
L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Grounding switch - HV cage | Doc/spec
L4 | ACC.IS.WTRC | Water Cooling | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | The water cooling hoses shall have a total length of 20 meters on the passage between ground potential to HV platform | Doc/spec, drawing
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L5 | ACC.IS.PS.PSS | Personal Safety System | Stuart/ESS | tbd | Doc/spec
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L5 | ACC.IS.PS.MPS | Machine Protection System | Annika/ESS | tbd | Doc/spec
L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L3 | TS.TSS | Target Safety System | Linda/ESS | tbd | Doc/spec

## LEBT_Interfaces
System A |  |  |  | System B
Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
L3 | ACC.IS | Ion Source | Luigi/INFN | L3 | ACC.LEBT | LEBT | Luigi/INFN | Mechanical interfaces | Drawing | Plasma chamber to extraction column
L3 | ACC.LEBT | LEBT | Luigi/INFN | L3 | ACC.RFQ | RFQ | Bruno/CEA | Mechanical interfaces | Drawing | BCT (in-flange), chopper dump (cone) + cooling, repellant electrode -3kV (insulation), bellow, vacuum gauges, gate valve, gas dosing valve
L3 | ACC.IS | Beam Physics | Mamad/ESS | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec | s=0 at the plasma chamber wall | TraceWin file (no field map, simple elements) of the warm linac
L3 | ACC.LEBT | Beam Physics | Mamad/ESS | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec
L3 | ACC.IS | Vacuum | Marcelo/ESS | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | Flow rate | Doc/spec | Plasma chamber to extraction column | Vacuum simulations for the integrated Warm Linac
L3 | ACC.LEBT | Vacuum | Marcelo/ESS | L3 | ACC.RFQ | Vacuum | Marcelo/ESS | Flow rate | Doc/spec | LEBT to RFQ | Vacuum simulations for the integrated Warm Linac
L3 | ACC.LEBT | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the LEBT in the tunnel | Skeleton, drawing |  | Skeleton
L4 | ACC.LEBT.BLS | Mechanical Beam Line Support | Luigi/INFN | L2 | SI | Site Infrastructure | Dave/ESS | Placement in the tunnel (e.g. transport hook on equipment), pre-alignment of support, grounding | Doc/spec, drawing
L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | L4 | ACC.LEBT.BLS | Mechanical Beam Line Support | Luigi/INFN | Iris, BI tank containing Chopper+FC+AS to BLS | Drawing |  | Alignment system
L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.BLS | Mechanical Beam Line Support | Luigi/INFN | Solenoids, HV steerers to BLS | Drawing |  | Alignment system
L4 | ACC.LEBT.PBI | Iris, FC, AS & Chopper dump | Benjamin/ESS | L4 | ACC.LEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.PWRC | Power Supply | Luigi/INFN | PS & HV connectors | Doc/spec
L4 | ACC.LEBT.PWRC | Power Supply | Luigi/INFN | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
L4 | ACC.LEBT.BMD | Chopper HV switch | Luigi/INFN | SI | SI | Site Infrastructure | Dave/ESS | Position of radiation shielding box for chopper HV switch | Doc/spec, drawing | Chopper HV switch inside shielding box
L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation, gate valve position, gas inlets for space charge compensation | Doc/spec, drawing
L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
L4 | ACC.LEBT.PBI | Iris, FC, AS & Repeller | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L5 | ACC.LEBT.PS.PSS | Personal Safety System | Stuart/ESS | HV power supplies | Doc/spec
L4 | ACC.LEBT.BMD | Chopper | Luigi/INFN | L5 | ACC.LEBT.PS.MPS | Machine Protection System | Annika/ESS | Beam emergency stop | Doc/spec
L4 | ACC.LEBT.BMD | Chopper | Luigi/INFN | L3 | TS.TSS | Target Safety System | Linda/ESS | tbd | Doc/spec

## RFQ Interfaces
System A |  |  |  | System B
Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
L3 | ACC.RFQ | RFQ | Bruno/CEA | L3 | ACC.LEBT | LEBT | Luigi/INFN | Mechanical interfaces | Drawing | BCT (in-flange), dump (cone) + cooling, repellant electrode -3kV (insulation), bellow, vacuum gauges, gate valve, gas dosing valve | "Lattice file" (TraceWin file (no field map, simple elements) of the warm linac: center position + length of the last solenoid in the LEBT)
L3 | ACC.RFQ | RFQ | Bruno/CEA | L3 | ACC.MEBT | MEBT | Ibon/ESS Bilbao | Mechanical interfaces | Drawing | Optional BCT (in-flange), bellow, gate valve | "Lattice file" (TraceWin file (no field map, simple elements) of the warm linac: center position + length of the first quadrupole in the MEBT)
L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
L3 | ACC.RFQ | Vacuum | Marcelo/ESS | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
L3 | ACC.RFQ | Vacuum | Marcelo/ESS | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the RFQ in the tunnel | Skeleton, drawing, reference points | Optical+ physical length of the RFQ | TraceWin file (no field map, simple elements) of the warm linac: reference points with center position + flange-to-flange length of the RFQ
L4 | ACC.RFQ.BLS | Mechanical Beam Line Support | Bruno/CEA | L2 | SI | Site Infrastructure | Dave/ESS | Transport & placement in the tunnel (e.g. transport hook, jackscrew, base concrete, coating), Pre-alignment of support | DOORS ACC-SI interface, Doc/spec, drawing
L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L2 | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Alignment of RFQ with support (alignment very sensitive to displacement errors) | RFQ alignment tolerances in the tunnel are required
L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L4 | ACC.RFQ.BLS | Mechanical Beam Line Support | Bruno/CEA | RFQ to support | Drawing
L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | Coupler to waveguide | Drawing
L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | Routing of the waveguides (RFQ to MagicT) | Drawing | Routing of the waveguides should be agreed with ESS
L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L2 | SI | Site infrastructure | Dave/ESS | Position of the MagicT in the tunnel/building | Drawing
L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Yogi/ESS | MagicT to waveguide | Drawing | Half height of full height wave guide | Phasing requirement of RFQ couplers
L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | Flanges for vacuum instrumentation, isolation valves | Doc/spec, drawing |  | Number + type of pumps & isolation valves
L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Cooling of pumps? | Doc/spec
L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L2 | SI | Site infrastructure | Dave/ESS | Position of the water cooling skid in the tunnel/building | Drawing
L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.CNPW | Cables + power | Lea + Frithoff/ESS | Water cooling skid - electrical power for cooling, cable types + connectors | Doc/spec, drawing
L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L2 | SI | Site Infrastructure | Dave/ESS | Water cooling skid - instrument air for actuators? | Doc/spec |  | Air pressure
L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Water cooling skid - water connection types | DOORS, drawing | Supply temp., temp. tolerance, conductivity, flow rate, working pressure, max. allow. pressure drop, max. allowable heat load
L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (water cooling skid to manifold), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of manifold in the tunnel | Drawing
L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Manifold - water connection types | DOORS, drawing
L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (manifold to RFQ), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | Connector type of the pickup | Drawing, Doc/spec
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.CNPW | Cables | Lea/ESS | Connector, cable types + routing (pick-up to LLRF) | Doc/spec
L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L4 | ACC.RFQ.CNPW | Cables | Lea/ESS | Connector, cable types + routing | Doc/spec
L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing (LLRF to RFDS, LLRF to pick-up, LLRF to water cooling skid) | Doc/spec
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | LLRF control parameters + physical interfaces | Doc/spec
L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L2 | ICS | Integrated control system | Eugene/ESS | Water cooling skid control parameters + physical interfaces | Doc/spec
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | Signal pick-up | Doc/spec | Feedback/regulation of RF power
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | Signal dual directional coupler | Doc/spec | Feedback/regulation of RF input power (e.g. dual directional coupler wr2300: http://www.megaind.com/waveguide/wgDirectionalCouplers.php)
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | Signal water cooling | Doc/spec | Feedback/regulation of water cooling

## MEBT_Interfaces
System A |  |  |  | System B
Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
L3 | ACC.RFQ | RFQ | Bruno/CEA | L3 | ACC.MEBT | MEBT | Ibon/Bilbao | Mechanical interfaces | Drawing | Optional BCT (in-flange), bellow, gate valve | TraceWin file (no field map, simple elements) of the warm linac: center position + length of the first quadrupole in the MEBT
L3 | ACC.MEBT | MEBT | Ibon/Bilbao | L3 | ACC.DTL | DTL | Andrea/INFN LNG | Mechanical interfaces | Drawing |  | TraceWin file (no field map, simple elements) of the warm linac
L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec |  | TraceWin file (no field map, simple elements) of the warm linac
L3 | ACC.MEBT | Beam Physics | Mamad/ESS | L3 | ACC.DTL | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec |  | TraceWin file (no field map, simple elements) of the warm linac
L3 | ACC.RFQ | Vacuum | Marcelo/ESS | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | Flow rate | Doc/spec |  | Vacuum simulations for the integrated Warm Linac
L3 | ACC.MEBT | Vacuum | Marcelo/ESS | L3 | ACC.DTL | Vacuum | Marcelo/ESS | Flow rate | Doc/spec |  | Vacuum simulations for the integrated Warm Linac
L3 | ACC.MEBT | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the MEBT in the tunnel | Skeleton, drawing |  | Skeleton
L4 | ACC.MEBT.BLS | Mechanical Beam Line Support | Ibon/Bilbao | L2 | SI | Site Infrastructure | Dave/ESS | Placement in the tunnel (e.g. transport hook on equipment), pre-alignment of support, grounding | Doc/spec, drawing
L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.BLS | Mechanical Beam Line Support | Ibon/Bilbao | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT to BLS | Drawing |  | Alignment system
L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.BLS | Mechanical Beam Line Support | Ibon/Bilbao | Quadrupoles (H+V), Chopper+Dump to BLS | Drawing |  | Alignment system
L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.BLS | Mechanical Beam Line Support | Ibon/Bilbao | Bunchers to BLS | Drawing |  | Alignment system
L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | PS & HV connectors | Doc/spec
L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | PS & HV connectors | Doc/spec
L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
L4 | ACC.MEBT.BMD | Chopper HV switch | Benjamin/ESS | SI | SI | Site Infrastructure | Dave/ESS | Position of radiation shielding box for chopper HV switch | Doc/spec, drawing | Chopper HV switch inside shielding box
L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation, gate valve position | Doc/spec, drawing
L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | Connector type | Doc/spec
L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
L4 | ACC.IS.PWRC | Power supplies | Ibon/Bilbao | L5 | ACC.MEBT.PS.PSS | Personal Safety System | Stuart/ESS | HV power supplies | Doc/spec
L4 | ACC.MEBT.BMD | Chopper | Ibon/Bilbao | L5 | ACC.MEBT.PS.MPS | Machine Protection System | Annika/ESS | Beam emergency stop | Doc/spec
L4 | ACC.MEBT.BMD | Chopper | Ibon/Bilbao | L3 | TS.TSS | Target Safety System | Linda/ESS | tbd | Doc/spec

## DTL Interfaces
System A |  |  |  | System B
Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
L3 | ACC.DTL | DTL | Andrea/INFN LNG | L3 | ACC.MEBT | MEBT | Ibon/ESS Bilbao | Mechanical interfaces | Drawing |  | "Lattice file" (TraceWin file (no field map, simple elements) of the warm linac: center position + length of the last solenoid in the LEBT)
L3 | ACC.DTL | DTL | Andrea/INFN LNG | L3 | ACC.SPK | SPK (LEDP) | Peter/ESS | Mechanical interfaces | Drawing |  | "Lattice file" (TraceWin file (no field map, simple elements) of the warm linac: center position + length of the first quadrupole in the MEBT)
L3 | ACC.DTL | DTL | Andrea/INFN LNG | L3 | ACC.DTL | DTL | Andrea/INFN LNG | Mechanical interfaces of intertank sections | Drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
L3 | ACC.DTL | Beam Physics | Mamad/ESS | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
L3 | ACC.DTL | Beam Physics | Mamad/ESS | L3 | ACC.SPK | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
L3 | ACC.DTL | Vacuum | Marcelo/ESS | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
L3 | ACC.DTL | Vacuum | Marcelo/ESS | L3 | ACC.SPK | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
L3 | ACC.DTL | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the DTLs in the tunnel | Skeleton, drawing, reference points | Optical+ physical length of the DTL tanks | TraceWin file (no field map, simple elements) of the warm linac: reference points with center position + flange-to-flange length of the DTLs
L4 | ACC.DTL.BLS | Mechanical Beam Line Support | Andra/INFN LNG | L2 | SI | Site Infrastructure | Dave/ESS | Transport & placement in the tunnel (e.g. transport hook, jackscrew, base concrete, coating), Pre-alignment of support | DOORS ACC-SI interface, Doc/spec, drawing
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L2 | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Alignment of DTL with support (alignment very sensitive to displacement errors) | DTL alignment tolerances in the tunnel are required
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.BLS | Mechanical Beam Line Support | Andra/INFN LNG | DTL to support | Drawing
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | Coupler to waveguide | Drawing
L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Yogi/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Routing of the waveguides in the tunnel | Drawing | Routing of the waveguides should be agreed with ESS
L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | L2 | SI | Site infrastructure | Dave/ESS | Position of the MagicT in the tunnel/building | Drawing
L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Yogi/ESS | MagicT to waveguide | Drawing | Half height of full height wave guide | Phasing requirement of DTL couplers
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | Flanges for beam instrumentation | Doc/spec, drawing
L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces | Doc/spec
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | Flanges for vacuum instrumentation | Doc/spec, drawing |  | Number + type of pumps & isolation valves
L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Cooling of pumps? | Doc/spec
L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of water cooling skid in the building | Drawing
L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Water cooling skid - electrical power for cooling, cable types + connectors | Doc/spec, drawing
L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L2 | SI | Site Infrastructure | Dave/ESS | Water cooling skid - instrument air for actuators? | Doc/spec |  | Air pressure
L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water cooling skid - water connection types | DOORS, drawing | Supply temp., temp. tolerance, conductivity, flow rate, working pressure, max. allow. pressure drop, max. allowable heat load
L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (water cooling skid to manifold), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of manifold in the tunnel | Drawing
L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Manifold - water connection types | DOORS, drawing
L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (manifold to DTL), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | Connector type of the pick-up(?) | Drawing, Doc/spec
L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.CNPW | Cables | Lea/ESS | Connector, cable types + routing (pick-up(?) to LLRF) | Doc/spec
L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L4 | ACC.DTL.CNPW | Cables | Lea/ESS | Connector, cable types + routing | Doc/spec
L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces | Doc/spec
L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing (LLRF to RFDS, LLRF to pick-up(?), LLRF to water cooling skid) | Doc/spec
L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | LLRF control parameters + physical interfaces | Doc/spec
L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L2 | ICS | Integrated control system | Eugene/ESS | Water cooling skid control parameters + physical interfaces | Doc/spec
L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | Signal pick-up(?) | Doc/spec | Feedback/regulation of RF power
L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | Signal dual directional coupler | Doc/spec | Feedback/regulation of RF input power (e.g. dual directional coupler wr2300: http://www.megaind.com/waveguide/wgDirectionalCouplers.php)
L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | Signal water cooling | Doc/spec | Feedback/regulation of water cooling

## WP99
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L3 | ACC.IS | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the plasma chamber wall in the tunnel | Skeleton, drawing | s=0 + physical dimensions of HV platform with BLS | Skeleton
ISRC | L4 | ACC.IS.BLS | Mechanical Beam Line Support | Luigi/INFN | L2 | SI | Site Infrastructure | Dave/ESS | Placement in the tunnel (e.g. transport hook on equipment), pre-alignment of support, grounding | Doc/spec, drawing | Embedded EMC grid + copper plate(?) | 3 terminal pads connecting HV cage to embedded EMC grid
ISRC | L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
LEBT | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the LEBT in the tunnel | Skeleton, drawing |  | Skeleton
LEBT | L4 | ACC.LEBT.BLS | Mechanical Beam Line Support | Luigi/INFN | L2 | SI | Site Infrastructure | Dave/ESS | Placement in the tunnel (e.g. transport hook on equipment), pre-alignment of support, grounding | Doc/spec, drawing
LEBT | L4 | ACC.LEBT.BMD | Chopper HV switch | Luigi/INFN | SI | SI | Site Infrastructure | Dave/ESS | Position of radiation shielding box for chopper HV switch | Doc/spec, drawing | Chopper HV switch inside shielding box
LEBT | L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
RFQ | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the RFQ in the tunnel | Skeleton, drawing, reference points | Optical+ physical length of the RFQ | TraceWin file (no field map, simple elements) of the warm linac: reference points with center position + flange-to-flange length of the RFQ
RFQ | L4 | ACC.RFQ.BLS | Mechanical Beam Line Support | Bruno/CEA | L2 | SI | Site Infrastructure | Dave/ESS | Transport & placement in the tunnel (e.g. transport hook, jackscrew, base concrete, coating), Pre-alignment of support | DOORS ACC-SI interface, Doc/spec, drawing
RFQ | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L2 | SI | Site infrastructure | Dave/ESS | Position of the MagicT in the tunnel/building | Drawing
RFQ | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L2 | SI | Site infrastructure | Dave/ESS | Position of the water cooling skid in the tunnel/building | Drawing
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L2 | SI | Site Infrastructure | Dave/ESS | Water cooling skid - instrument air for actuators? | Doc/spec |  | Air pressure
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of manifold in the tunnel | Drawing
RFQ | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
MEBT | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the MEBT in the tunnel | Skeleton, drawing |  | Skeleton
MEBT | L4 | ACC.MEBT.BLS | Mechanical Beam Line Support | Ibon/Bilbao | L2 | SI | Site Infrastructure | Dave/ESS | Placement in the tunnel (e.g. transport hook on equipment), pre-alignment of support, grounding | Doc/spec, drawing
MEBT | L4 | ACC.MEBT.BMD | Chopper HV switch | Benjamin/ESS | SI | SI | Site Infrastructure | Dave/ESS | Position of radiation shielding box for chopper HV switch | Doc/spec, drawing | Chopper HV switch inside shielding box
MEBT | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
DTL | L3 | ACC.DTL | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the DTLs in the tunnel | Skeleton, drawing, reference points | Optical+ physical length of the DTL tanks | TraceWin file (no field map, simple elements) of the warm linac: reference points with center position + flange-to-flange length of the DTLs
DTL | L4 | ACC.DTL.BLS | Mechanical Beam Line Support | Andra/INFN LNG | L2 | SI | Site Infrastructure | Dave/ESS | Transport & placement in the tunnel (e.g. transport hook, jackscrew, base concrete, coating), Pre-alignment of support | DOORS ACC-SI interface, Doc/spec, drawing
DTL | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Yogi/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Routing of the waveguides in the tunnel | Drawing | Routing of the waveguides should be agreed with ESS
DTL | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | L2 | SI | Site infrastructure | Dave/ESS | Position of the MagicT in the tunnel/building | Drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of water cooling skid in the building | Drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L2 | SI | Site Infrastructure | Dave/ESS | Water cooling skid - instrument air for actuators? | Doc/spec |  | Air pressure
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of manifold in the tunnel | Drawing
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure

## S&A
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Alignment of plasma chamber (independent of extraction electrodes wo bellows?) | Alignment precision (bellow?)
LEBT | L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
LEBT | L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
RFQ | L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L2 | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Alignment of RFQ with support (alignment very sensitive to displacement errors) | RFQ alignment tolerances in the tunnel are required
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
MEBT | L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
MEBT | L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
DTL | L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L2 | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Alignment of DTL with support (alignment very sensitive to displacement errors) | DTL alignment tolerances in the tunnel are required

## WP15
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | HV platform | Luigi/INFN | L4 | ACC.IS.CNPW | (Signal) Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing to HV platform | Doc/spec, drawing
ISRC | L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L4 | ACC.IS.CNPW | Cables + power | Lea + Frithoff/ESS | Connectors, cable types + routing | Doc/spec, drawing | HV PS + HV insulation transformer + PS repeller electrode
ISRC | L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | L4 | ACC.IS.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
ISRC | L4 | ACC.IS.CNPW | (Signal) Cables + power | Lea + Frithoff/ESS | L5 | ACC.IS.PS.LPS | Local Protection System | Lali | Surge arrester + EMC filter | Doc/spec, drawing |  | Shielded, metallic cable trays for (signal) power cables
LEBT | L4 | ACC.LEBT.PWRC | Power Supply | Luigi/INFN | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
LEBT | L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
LEBT | L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.CNPW | Cables + power | Lea + Frithoff/ESS | Water cooling skid - electrical power for cooling, cable types + connectors | Doc/spec, drawing
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.CNPW | Cables | Lea/ESS | Connector, cable types + routing (pick-up to LLRF) | Doc/spec
RFQ | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L4 | ACC.RFQ.CNPW | Cables | Lea/ESS | Connector, cable types + routing | Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing (LLRF to RFDS, LLRF to pick-up, LLRF to water cooling skid) | Doc/spec
MEBT | L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
MEBT | L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
MEBT | L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
MEBT | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
DTL | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Water cooling skid - electrical power for cooling, cable types + connectors | Doc/spec, drawing
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.CNPW | Cables | Lea/ESS | Connector, cable types + routing (pick-up(?) to LLRF) | Doc/spec
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L4 | ACC.DTL.CNPW | Cables | Lea/ESS | Connector, cable types + routing | Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing (LLRF to RFDS, LLRF to pick-up(?), LLRF to water cooling skid) | Doc/spec

## WP2
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L3 | ACC.IS | Beam Physics | Mamad/ESS | L3 | ACC.LEBT | Beam Physics | Mammad/ESS | Twiss parameters | Doc/spec | s=0 at the plasma chamber wall | TraceWin file (no field map, simple elements) of the warm linac
ISRC | L3 | ACC.IS | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the plasma chamber wall in the tunnel | Skeleton, drawing | s=0 + physical dimensions of HV platform with BLS | Skeleton
LEBT | L3 | ACC.IS | Beam Physics | Mamad/ESS | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec | s=0 at the plasma chamber wall | TraceWin file (no field map, simple elements) of the warm linac
LEBT | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec
LEBT | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the LEBT in the tunnel | Skeleton, drawing |  | Skeleton
RFQ | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L3 | ACC.LEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
RFQ | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
RFQ | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the RFQ in the tunnel | Skeleton, drawing, reference points | Optical+ physical length of the RFQ | TraceWin file (no field map, simple elements) of the warm linac: reference points with center position + flange-to-flange length of the RFQ
MEBT | L3 | ACC.RFQ | Beam Physics | Mamad/ESS | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec |  | TraceWin file (no field map, simple elements) of the warm linac
MEBT | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | L3 | ACC.DTL | Beam Physics | Mamad/ESS | Twiss parameters, emittances | Doc/spec |  | TraceWin file (no field map, simple elements) of the warm linac
MEBT | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the MEBT in the tunnel | Skeleton, drawing |  | Skeleton
DTL | L3 | ACC.DTL | Beam Physics | Mamad/ESS | L3 | ACC.MEBT | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
DTL | L3 | ACC.DTL | Beam Physics | Mamad/ESS | L3 | ACC.SPK | Beam Physics | Mamad/ESS | Twiss parameters, emittances | DOORS, ref. doc/spec
DTL | L3 | ACC.DTL | Beam Physics | Mamad/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of the DTLs in the tunnel | Skeleton, drawing, reference points | Optical+ physical length of the DTL tanks | TraceWin file (no field map, simple elements) of the warm linac: reference points with center position + flange-to-flange length of the DTLs

## WP7
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L4 | ACC.IS.PBI | Proton beam instrumentation | Benjamin/ESS | tbd | tbd | Current measurement (current proposal to drop in HV)???
LEBT | L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
LEBT | L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | L4 | ACC.LEBT.BLS | Mechanical Beam Line Support | Luigi/INFN | Iris, BI tank containing Chopper+FC+AS to BLS | Drawing |  | Alignment system
LEBT | L4 | ACC.LEBT.PBI | Iris, FC, AS & Chopper dump | Benjamin/ESS | L4 | ACC.LEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
LEBT | L4 | ACC.LEBT.PBI | Iris, FC, AS & Repeller | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | ??? | SA | Survey & Alignment | Fabien/ESS | Alignment targets & alignment strategy (access) | Doc/spec, drawing | Elements to be aligned independantly: tbc | Alignment precision (bellow?)
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.BLS | Mechanical Beam Line Support | Ibon/Bilbao | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT to BLS | Drawing |  | Alignment system
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec |  | Alignment system
MEBT | L4 | ACC.MEBT.BMD | Chopper HV switch | Benjamin/ESS | SI | SI | Site Infrastructure | Dave/ESS | Position of radiation shielding box for chopper HV switch | Doc/spec, drawing | Chopper HV switch inside shielding box
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation, gate valve position | Doc/spec, drawing
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
DTL | L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | Flanges for beam instrumentation | Doc/spec, drawing
DTL | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
DTL | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
DTL | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces | Doc/spec

## WP8
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
RFQ | L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | Coupler to waveguide | Drawing
RFQ | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | Routing of the waveguides (RFQ to MagicT) | Drawing | Routing of the waveguides should be agreed with ESS
RFQ | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L2 | SI | Site infrastructure | Dave/ESS | Position of the MagicT in the tunnel/building | Drawing
RFQ | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Yogi/ESS | MagicT to waveguide | Drawing | Half height of full height wave guide | Phasing requirement of RFQ couplers
RFQ | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | L2 | SI | Site infrastructure | Dave/ESS | Position of the water cooling skid in the tunnel/building | Drawing
RFQ | L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | Connector type of the pickup | Drawing, Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.CNPW | Cables | Lea/ESS | Connector, cable types + routing (pick-up to LLRF) | Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing (LLRF to RFDS, LLRF to pick-up, LLRF to water cooling skid) | Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | LLRF control parameters + physical interfaces | Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | Signal pick-up | Doc/spec | Feedback/regulation of RF power
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.RFQ.RFS.RFDS | RF Distribution Systems | Bruno/CEA | Signal dual directional coupler | Doc/spec | Feedback/regulation of RF input power (e.g. dual directional coupler wr2300: http://www.megaind.com/waveguide/wgDirectionalCouplers.php)
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | Signal water cooling | Doc/spec | Feedback/regulation of water cooling
MEBT | L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | Connector type | Doc/spec
MEBT | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
DTL | L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | Coupler to waveguide | Drawing
DTL | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Yogi/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Routing of the waveguides in the tunnel | Drawing | Routing of the waveguides should be agreed with ESS
DTL | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | L2 | SI | Site infrastructure | Dave/ESS | Position of the MagicT in the tunnel/building | Drawing
DTL | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Yogi/ESS | MagicT to waveguide | Drawing | Half height of full height wave guide | Phasing requirement of DTL couplers
DTL | L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | Connector type of the pick-up(?) | Drawing, Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.CNPW | Cables | Lea/ESS | Connector, cable types + routing (pick-up(?) to LLRF) | Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing (LLRF to RFDS, LLRF to pick-up(?), LLRF to water cooling skid) | Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | LLRF control parameters + physical interfaces | Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | Signal pick-up(?) | Doc/spec | Feedback/regulation of RF power
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L5 | ACC.DTL.RFS.RFDS | RF Distribution Systems | Andra/INFN LNG | Signal dual directional coupler | Doc/spec | Feedback/regulation of RF input power (e.g. dual directional coupler wr2300: http://www.megaind.com/waveguide/wgDirectionalCouplers.php)
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | Signal water cooling | Doc/spec | Feedback/regulation of water cooling

## WP12
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L3 | ACC.IS | Vacuum | Marcelo/ESS | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | Flow rate | Doc/spec | Plasma chamber to extraction column | Vacuum simulations for the integrated Warm Linac
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation | Doc/spec
ISRC | L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | L4 | ACC.IS.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
ISRC | L4 | ACC.IS.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
LEBT | L3 | ACC.IS | Vacuum | Marcelo/ESS | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | Flow rate | Doc/spec | Plasma chamber to extraction column | Vacuum simulations for the integrated Warm Linac
LEBT | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | L3 | ACC.RFQ | Vacuum | Marcelo/ESS | Flow rate | Doc/spec | LEBT to RFQ | Vacuum simulations for the integrated Warm Linac
LEBT | L4 | ACC.LEBT.PBI | Iris, BI tank containing Chopper+FC+AS | Benjamin/ESS | L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation, gate valve position, gas inlets for space charge compensation | Doc/spec, drawing
LEBT | L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
LEBT | L4 | ACC.LEBT.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
RFQ | L3 | ACC.RFQ | Vacuum | Marcelo/ESS | L3 | ACC.LEBT | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
RFQ | L3 | ACC.RFQ | Vacuum | Marcelo/ESS | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
RFQ | L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | Flanges for vacuum instrumentation, isolation valves | Doc/spec, drawing |  | Number + type of pumps & isolation valves
RFQ | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Cooling of pumps? | Doc/spec
RFQ | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L4 | ACC.RFQ.CNPW | Cables | Lea/ESS | Connector, cable types + routing | Doc/spec
RFQ | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
MEBT | L3 | ACC.RFQ | Vacuum | Marcelo/ESS | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | Flow rate | Doc/spec |  | Vacuum simulations for the integrated Warm Linac
MEBT | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | L3 | ACC.DTL | Vacuum | Marcelo/ESS | Flow rate | Doc/spec |  | Vacuum simulations for the integrated Warm Linac
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | Vacuum instrumentation, gate valve position | Doc/spec, drawing
MEBT | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing | Doc/spec
MEBT | L4 | ACC.MEBT.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
DTL | L3 | ACC.DTL | Vacuum | Marcelo/ESS | L3 | ACC.MEBT | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
DTL | L3 | ACC.DTL | Vacuum | Marcelo/ESS | L3 | ACC.SPK | Vacuum | Marcelo/ESS | Flow rate | DOORS, ref. doc/spec |  | Vacuum simulations for the integrated Warm Linac
DTL | L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | Flanges for vacuum instrumentation | Doc/spec, drawing |  | Number + type of pumps & isolation valves
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Cooling of pumps? | Doc/spec
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L4 | ACC.DTL.CNPW | Cables | Lea/ESS | Connector, cable types + routing | Doc/spec
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Instrument air for valve actuators | Doc/spec |  | Air pressure
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces | Doc/spec

## WP13
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Grouning hook, length of extraction column | Doc/spec
ISRC | L4 | ACC.IS.CNPW | (Signal) Cables + power | Lea + Frithoff/ESS | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Surge arrester + EMC filter | Doc/spec, drawing |  | Shielded, metallic cable trays for (signal) power cables
ISRC | L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Grounding switch - HV cage | Doc/spec
ISRC | L4 | ACC.IS.WTRC | Water Cooling | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | The water cooling hoses shall have a total length of 20 meters on the passage between ground potential to HV platform | Doc/spec, drawing

## ICS
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L2 | ICS | Integrated control system | Eugene/ESS | IS control parameters + physical interfaces of controllers | Doc/spec
LEBT | L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
LEBT | L4 | ACC.LEBT.PBI | Iris, FC, AS & Repeller | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | LLRF control parameters + physical interfaces | Doc/spec
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L2 | ICS | Integrated control system | Eugene/ESS | Water cooling skid control parameters + physical interfaces | Doc/spec
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
MEBT | L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
MEBT | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces of controllers | Doc/spec
DTL | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces | Doc/spec
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L2 | ICS | Integrated control system | Eugene/ESS | Control parameters + physical interfaces | Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L2 | ICS | Integrated control system | Eugene/ESS | LLRF control parameters + physical interfaces | Doc/spec
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L2 | ICS | Integrated control system | Eugene/ESS | Water cooling skid control parameters + physical interfaces | Doc/spec

## WP16
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | HV platform | Luigi/INFN | L4 | ACC.IS.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing | Water cooling for magnetron, automatic tuning unit (ATU) and plasma chamber
ISRC | L4 | ACC.IS.WTRC | Water Cooling | Anton/ESS | L4 | ACC.IS.WTRC | Water Cooling | Anton/ESS | Routing of the pipes & pipe types inside of HV cage | Drawing, Doc/spec
ISRC | L4 | ACC.IS.WTRC | Water Cooling | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | The water cooling hoses shall have a total length of 20 meters on the passage between ground potential to HV platform | Doc/spec, drawing
LEBT | L4 | ACC.LEBT.PBI | Iris, FC, AS & Chopper dump | Benjamin/ESS | L4 | ACC.LEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
LEBT | L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
RFQ | L4 | ACC.RFQ.VAC | Vacuum | Marcelo/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Cooling of pumps? | Doc/spec
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.CNPW | Cables + power | Lea + Frithoff/ESS | Water cooling skid - electrical power for cooling, cable types + connectors | Doc/spec, drawing
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L2 | SI | Site Infrastructure | Dave/ESS | Water cooling skid - instrument air for actuators? | Doc/spec |  | Air pressure
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Water cooling skid - water connection types | DOORS, drawing | Supply temp., temp. tolerance, conductivity, flow rate, working pressure, max. allow. pressure drop, max. allowable heat load
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (water cooling skid to manifold), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of manifold in the tunnel | Drawing
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Manifold - water connection types | DOORS, drawing
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (manifold to RFQ), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
RFQ | L4 | ACC.RFQ.EMR | RFQ | Bruno/CEA | L4 | ACC.RFQ.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
RFQ | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | L2 | ICS | Integrated control system | Eugene/ESS | Water cooling skid control parameters + physical interfaces | Doc/spec
RFQ | L5 | ACC.RFQ.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.RFQ.WTRC | Water Cooling | Bruno/CEA | Signal water cooling | Doc/spec | Feedback/regulation of water cooling
MEBT | L4 | ACC.MEBT.PBI | BPM, BCT, WS (H+V), Scraper, NPM (H+V), Slit, BSM, Grid, FC, FCT | Benjamin/ESS | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
MEBT | L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
MEBT | L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.WTRC | Water Cooling | Anton/ESS | Water connection types | DOORS, doc/spec, drawing
DTL | L4 | ACC.DTL.PBI | Beam Instrumentation of DTLs + Intertank sections | Benjamin/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
DTL | L4 | ACC.DTL.VAC | Vacuum | Marcelo/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Cooling of pumps? | Doc/spec
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of water cooling skid in the building | Drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.CNPW | Cables + power | Lea + Frithoff/ESS | Water cooling skid - electrical power for cooling, cable types + connectors | Doc/spec, drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L2 | SI | Site Infrastructure | Dave/ESS | Water cooling skid - instrument air for actuators? | Doc/spec |  | Air pressure
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water cooling skid - water connection types | DOORS, drawing | Supply temp., temp. tolerance, conductivity, flow rate, working pressure, max. allow. pressure drop, max. allowable heat load
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (water cooling skid to manifold), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L2 | SI | Site Infrastructure | Dave/ESS | Position of manifold in the tunnel | Drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Manifold - water connection types | DOORS, drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Routing of the pipes (manifold to DTL), pipe types | Drawing, Doc/spec | A maximum allowable pressure drop should be defined, routing and pipe diameter should be agreed with IKC
DTL | L4 | ACC.DTL.EMR | DTL | Andra/INFN LNG | L4 | ACC.DTL.WTRC | Water Cooling | Anton/ESS | Water connector types + sizes | DOORS, drawing
DTL | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | L2 | ICS | Integrated control system | Eugene/ESS | Water cooling skid control parameters + physical interfaces | Doc/spec
DTL | L5 | ACC.DTL.RFS.LLRF | LLRF | Anders J./Lund Univ. | L4 | ACC.DTL.WTRC | Water Cooling | Andra/INFN LNG | Signal water cooling | Doc/spec | Feedback/regulation of water cooling

## WP17
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L4 | ACC.IS.CNPW | Cables + power | Lea + Frithoff/ESS | Connectors, cable types + routing | Doc/spec, drawing | HV PS + HV insulation transformer + PS repeller electrode
ISRC | L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L5 | ACC.IS.PS.LPS | Local Protection System | Lali/ESS | Grounding switch - HV cage | Doc/spec
LEBT | L4 | ACC.LEBT.BMD | Solenoids, HV steerers, Chopper, Repeller electrode | Luigi/INFN | L4 | ACC.LEBT.PWRC | Power Supply | Luigi/INFN | PS & HV connectors | Doc/spec
LEBT | L4 | ACC.LEBT.PWRC | Power Supply | Luigi/INFN | L4 | ACC.LEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
LEBT | L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L5 | ACC.LEBT.PS.PSS | Personal Safety System | Stuart/ESS | HV power supplies | Doc/spec
MEBT | L4 | ACC.MEBT.BMD | Quadrupoles (H+V), Chopper+Dump | Ibon/Bilbao | L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | PS & HV connectors | Doc/spec
MEBT | L4 | ACC.MEBT.EMR | Bunchers | Ibon/Bilbao | L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | PS & HV connectors | Doc/spec
MEBT | L4 | ACC.MEBT.PWRC | Power Supply | Ibon/Bilbao | L4 | ACC.MEBT.CNPW | Cables + power | Lea + Frithoff/ESS | Connector, cable types + routing, power | Doc/spec
MEBT | L4 | ACC.IS.PWRC | Power supplies | Ibon/Bilbao | L5 | ACC.MEBT.PS.PSS | Personal Safety System | Stuart/ESS | HV power supplies | Doc/spec

## MPS_PSS_TSS
| System A |  |  |  | System B
| Level | Interface A | Discipline A | Contact A | Level | Interface B | Discipline B | Contact B | Interfaces | Representation | Baselines | Requirements
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L5 | ACC.IS.PS.PSS | Personal Safety System | Stuart/ESS | tbd | Doc/spec
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L5 | ACC.IS.PS.MPS | Machine Protection System | Annika/ESS | tbd | Doc/spec
ISRC | L4 | ACC.IS.ISS | Ion Source | Luigi/INFN | L3 | TS.TSS | Target Safety System | Linda/ESS | tbd | Doc/spec
LEBT | L4 | ACC.IS.PWRC | Power supplies | Luigi/INFN | L5 | ACC.LEBT.PS.PSS | Personal Safety System | Stuart/ESS | HV power supplies | Doc/spec
LEBT | L4 | ACC.LEBT.BMD | Chopper | Luigi/INFN | L5 | ACC.LEBT.PS.MPS | Machine Protection System | Annika/ESS | Beam emergency stop | Doc/spec
LEBT | L4 | ACC.LEBT.BMD | Chopper | Luigi/INFN | L3 | TS.TSS | Target Safety System | Linda/ESS | tbd | Doc/spec
MEBT | L4 | ACC.IS.PWRC | Power supplies | Ibon/Bilbao | L5 | ACC.MEBT.PS.PSS | Personal Safety System | Stuart/ESS | HV power supplies | Doc/spec
MEBT | L4 | ACC.MEBT.BMD | Chopper | Ibon/Bilbao | L5 | ACC.MEBT.PS.MPS | Machine Protection System | Annika/ESS | Beam emergency stop | Doc/spec
MEBT | L4 | ACC.MEBT.BMD | Chopper | Ibon/Bilbao | L3 | TS.TSS | Target Safety System | Linda/ESS | tbd | Doc/spec