## Slide 1: WP 3 – WP15(electrical support) interfaces
Evangelia Vaena
Electrical Engineer
www.europeanspallationsource.se
23 April 2015

## Slide 2: Outline
Cabling and connectors (design, procurement, installation)
Electronic equipment integration (racks)
Relevant documentation
“Grey Zones”
Identification of interfaces (who is providing what, who is installing what) concerning:

## Slide 3: Provided by WP3 collaborators – to be confirmed
All cables (design, cables lists, procurement of materials) for Ion Source, LEBT, RFQ, MEBT, DTLs (with the exception of vacuum, BI and ICS cables) will be provided by WP3. (Are they included in the budget?)
Crates/devices to be installed in the FEB and gallery racks
Documentation for the above, including specifications, wiring diagrams, manuals, special requirements, inspection test plans, quality forms, etc.
Spare parts/ list of spare parts, list of preferred vendors

## Slide 4: Provided by ESS -To be confirmed
All vacuum electronics/cabling designed by WP12
All beam instrumentation electronics/cabling designed by WP7
All ICS cables
The cables for the above mentioned systems are not only provided, but also installed by ESS and have already been included in ESS budget
Cable trays/ conduits for all the cable plant
Cable integration, segregation between power/signal cables, assistance in estimating the cable quantities
Numbering (name tags) for all the cables and devices

## Slide 5: Provided by ESS -To be confirmed
Racks (2200H-800D-600W) provided and installed by ESS (the electrical works contractor?), with the exception of the Ion Source racks (picture)
Storage area for electrical equipment
Integration/coordination with conventional facilities

## Slide 6: Overlaps- Unidentified borders
Installation: Cables pulled by ESS contractor, but tested and terminated by WP3?
Overlaps: LEBT steerers and solenoids, MEBT quadrupoles power supplies and cables, scope of WP17 or WP3?
RF cables: Scope of WP8 or WP3?
Installation of equipment in racks: scope of ESS or collaborators?
Who will perform the grounding connections?

## Slide 7: THE END
THANK YOU FOR YOUR ATTENTION!

## Slide 8: Back up slide-List of Source &LEBT deliverables

## Slide 9: Back up slide
Some elements are still to be confirmed in the Spare Parts list and the same holds for the excluded items, but the main terms of the agreement have been forwarded to the INFN Executive Board which should discuss them in the meeting of Feb. 11.