## Slide 1: Responses to recommendations of TAC 11 Integrated Control Systems
Henrik Carling
ESS/ICS
Date: 2015-09-30

## Slide 2: Responses to recommendations of TAC 11 Integrated Control Systems
Complete recommendations from TAC 10
  See following slides
Develop and broadly communicate ICS handbook including hardware and software standards, development environment and processes and required documentation
  The work on an ICS Handbook has not progressed since last TAC. The main reason is that the Chief engineer has been overloaded. This action is competing with efforts to secure in-kind collaborations with Switzerland during 2015 and the in-kind activities have been given higher priority.
  The first version of the development environment has been delivered. The solution has been presented to CEA in the summer of 2015 and the environment is being rolled out. It is worth specifically mentioning the effort to replace the old plan (ITER CODAC-based) with the new one. The feedback so far has been positive and even the people who were promoting CODAC earlier agree that the new environment is much better. The primary advantages of the new development environment are:
    Standardized environment for both off- and on-site users and all ICS stakeholder users
    Software is written consistently with a centralized configuration
    The development environment allows more dynamic release cycling
    Integrators do not need to deal with technical details of low-level drivers, etc.
  Standards and procedures are part of the development environment, but some documents still need to be written. The development environment “product” is still evolving as we learn and get feedback from the users. Several tools will be rolled out soon (IOC Factory, CCDB) and will become part of the procedures
  Hardware standards have been documented as far as possible at this stage. Standards have also been communicated to existing in-kind partners where relevant. Going further requires more interaction with ICS stakeholders and decisions about how systems are going to be built

## Slide 3: Responses to recommendations of TAC 11 Integrated Control Systems
Include the ICS Chief Engineer as a member of the Accelerator Integration Group
  The accelerator integration group no longer exists. Instead, the chief engineer has participated in accelerator vertical design reviews.
  The need to work together with Accelerator, Target and NSS has been further highlighted in the effort to create an integrated plan for ESS with global milestones. ICS is looking for forums and venues to establish this collaboration.
All technical systems that interface to the MPS must be subject to design review and approval by the Machine Protection Committee
  The Machine protection committee is active and chaired by Annika Nordt.
  The committee is working well but a reorganization will mean that new people will be involved in the committee
  The MPC is the approving entity for MP relevant systems
Requirements for staged availability of the PSS should be evaluated based on proposed commissioning of the accelerator
  The PSS team is attending regular meetings with Accelerator division to discuss the potentially staged installation and commissioning and equipment conditioning of the accelerator. Even though dates are not yet defined , we have a preliminary description of how the PSS can be installed and worked in with the accelerator installation and commissioning plan
    1) DTL’s installed. A gated shield wall installed at either end of the DTL’s. These walls will tie in with the fences for PSS zone 2 so switches for the gated shield wall will actually be used on the fences at a later date when they are installed. The DTL’s can then be conditioned in complete safety. We will install temporary X-ray/radiation monitors at each of these entrances which will switch off the RF modulators if high levels of radiation/X-rays are detected.
    2) The Proton source, LEBT,RFQ,MEBT (PSS Zone1) can then potentially commissioned be tested with the walls in position
    3) The first temporary wall (at beginning of the DTL’s) removed and beam run up to the end of the DTL’s. One radiation monitor will remain until after the last temporary wall is removed.
    4) The ODH system will need to be commissioned as the Cryo-lines are expected to be commissioned fairly early
    5) Whilst the temporary wall is in position after the DTL’s it is expected that installation can continue further down the tunnel

## Slide 4: Responses to recommendations of TAC 10 Integrated Control Systems
Issue ICS standards for hardware, software, processes and documentation
  See reply to TAC 11 Action #2 above
Develop Interface Control Documents for the technical systems
  We are still trying to define a coherent way to set up the ICD documents. The goal is to have a common structure for the documents. This has however meant holding back the approval in some cases where the previously prepared documentation has not been fit for the purposes.
  In addition, lack of ICS stakeholder resources has in many cases slowed down progress. It is also sometimes not clear who the counterpart is for defining these documents.
  So far, we have
    A preliminary version of an ICD with CF in CHESS. This is the most stable and advanced agreement so far
    A rough agreement with Accelerator as preliminary in CHESS - this is still developing.
      Sub-agreements with the Beam instrumentation, Vacuum and Water cooling groups
    Top-level ICS with Target is under revision with an agreement on what to change
    ICD with NSS, currently titled “Service Level Agreement” is under revision

## Slide 5: Responses to recommendations of TAC 10 Integrated Control Systems
Proactively seek In-kind collaboration agreements with other institutions and work with accelerator subsystem In-kind initiatives to see if these can include an In-kind collaboration of controls
  Developing ICS In-kind collaboration activities has been a high priority since late spring. The map of In-kind initiatives has changed quite dramatically since this period
  The current In-kind strategy is based on continuing already initiated activities (such as those in France and Bilbao) while actively seeking new activities with “smaller accounts” where the likelihood of success is higher
  The current focus for new In-kind activities in 2015 is Switzerland (PSI and ZHAW), upcoming activities 2016 are being planned/discussed with Estonia, Hungary and Poland

## Slide 6: Responses to recommendations of TAC 10 Integrated Control Systems
Finalize decision on ESS standard PLC for ICS
  This has been completed in the summer 2015. ESS has chosen Siemens as the standard PLC supplier through an extensive procurement/technical evaluation process
Fix hardware standards and document, so they are available for in house and IKC developments, by Q4 2014
  See corresponding action from TAC 11
Consider establishing a framework agreement for the provision of IEC61508 support services (examples being, development of processes and documentation, failure-mode analysis studies, fault-tree analysis, design verification)
  This has been completed during 2015. An agreement is in place with ZHAW (Zürich University for Applied Sciences) and initial activities have been identified. We are now working to transform this collaboration into an in-kind activity.
ESS should develop engineering standards and distribute to all collaborators as early as possible. PSS interface, lock-out tag-out (LOTO) standard, electrical safety, X-ray shielding, pressure-vessels standards, RF power leakage, are some of the more important things for such a set of standards. Compliance with such standards should part of the design (PDR and FDR) and inspection of progress of IKCs
  This is being handled at ESS level by the Selection of Sustainable Materials working group, [Malin Åberg]
  ESS has developed documentation giving guidelines for electrical design and electrical drawing.
  These standards and documents will be followed by the ESS PSS design team.