## Slide 1: ICS re-planning, outsourcing/inhouse development strategy and staffing TAC 12 presentation
Henrik Carling
ESS/ICS
Date: 2015-09-30

## Slide 2: Re-planning, outsourcing/inhouse development strategy and staffing
Agenda
  Current situation
    Planning -> Effort estimate -> Competence/capacity roadmap
    The challenge of in-kinding labor
    Management of commercial suppliers
  Issues
  Way forward

## Slide 3: 2016 plan/budget result
A fairly detailed plan/budget for 2016 is available
For some workpackages, it is a major revision of the planning. The most common problem is the low availability of stakeholder requirements meaning uncertain scope
The plans for 2017 and onwards are (with few exceptions) untouched since 2013/2014 timeframe. This means that visibility for activities after 2017 are obscure
Plans for 2016 show that we must produce about twice the value that will be done in 2015
For 2017 another value doubling is planned
The ICS budget envelope for the construction phase shows the monumental challenge of fast rise and fall in capacity over just a few years time

## Slide 4: Employee/consultant ratio
Since it is not currently possible to establish a credible competence / capacity roadmap, some other models can be used to establish the relationship between employees and consultants
One important factor is the size of the ICS team at steady state operations (somewhere in the phase 2019 - 2026)
Based on experience from other facilities and adjusting for ESS Size and complexity, the following model has been used as an estimate for the steady state operations phase

## Slide 5: The challenge of in-kinding labor
The in-kind budget model is particularly difficult for ICS since 80 - 90% of the cost is labor driven
This means that approximately a value of 25 M€ shall be generated from In-kind activities
This corresponds to approximately 231 MY with the ESS Cost-book labor rate
Meaning that approximately 58 in-kind FTE:s shall be fully loaded by ICS activities during 2016-2019
This is very, very difficult
We expect the ”value efficiency” to be quite low for in-kind activities

## Slide 6: Management of commercial suppliers
Competence is one of several important factors for line managers to consider
Social skills and overall team and motivation level are sometimes more important (since skills often can be learned more quickly than behavioural changes)
When extending the line organization, one of the first decision points is if the position is permanent or transient
Permanent positions should be filled with employees considering
  Long term (5 - 10 years) assignment, competence and capacity profile of the team
  Social/teamwork skills
  Competence and experience
  Remuneration and other contractual status
Transient positions can be filled with temporary employees or consultants
  New framework agreements are being created
    Software development services
    Hardware development services
    PLC programming services
    Integration services
The new framework agreements are intended to replace the current ”Epics integration” agreement
  Increase supplier selection
  Provide local support for smaller assignments
  Increase supplier competitiveness
  Lower cost, increase quality

## Slide 7: Technology scope for ICS
The span of technical scope and the competencies needed in ICS is enormous
From analog signals to Java-based high-end, big-data GUI:s in high performance, high availability
PLC systems
Mechanics and Safety/protection systems
Systems integration, Installation
Project management and administration
Electronics hardware
Software
PLC
Mechanics
Analog electronics
Digital electronics
FPGA firmware
Digital communication
PCB, packaging
Test and validation
Industrialization, maintenance
Kernel drivers
Operating systems (RT)
Development environments
EPICS
CSS/Eclipse
Applicatoins (GUI, Web, Services)
Databases
Availability, performance
Test and validation
Safety and protection

## Slide 8: Competence map for ICS
Electronics (Test, general)
Digital systems (FPGA, Firmware)
Automation and control (PLC)
Computer communications (Networking, cabling)
Hardware/software interaction (Low level software)
Core software development (Linux kernel)
Software development (Java)
Database, High availability (Postgres)
Systems integration
Safety and protection systems (IEC61508 etc)

## Slide 9: Software development services framework
Requirements
The European Spallation Source ESS AB is an accelerator-driven neutron spallation source. The Integrated Controls Systems (ICS) is responsible for providing control and monitoring for all parts of the machine (accelerator, target, neutron scattering systems and conventional facilities).
A large part of the construction scope for ICS is to design, develop, test, deploy and maintain software systems. The software for the control system of ESS is distributed over many different products and technologies with a very wide scope. Some examples are:
Control system core functions; the ESS software control system will be based on the open-source standard EPICS [Link] family of projects
Hardware drivers; specialized hardware built specifically for ESS need software drivers, most often drivers in the Linux kernelspace
Database oriented systems for configuration management; most user level ESS projects are built on database technology, common examples use PostgreSQL or similar open database products
Operator environments; Providing ESS operators with a user interface environment for the control system is essential for ICS. We will use the Control System Studio [Link] family of open-source, Eclipse-based products for this purpose
Development environments; in order for ESS stakeholders to be able to integrate efficiently into the EPICS-based control system, ICS will provide ready-made development environments to facilitate integration work
Data acquisition, archiving and analysis; ICS needs be able to register and store signal flow in the control system to be able to debug and analyze/optimize problems in the very complex facility

## Slide 10: Software development services framework
This “OCT” has been issued by ESS AB in order to enter into a Framework Agreement with one supplier, and for a maximum period of 4 years from contract signature, for the following products:
Software development services including the following
  Design
    Requirement breakdown and analysis
    Estimations
    Software architecture, data structure
  Implementation
    Analysis
    Documentation
    Programming
      Java, C, C++
      Linux environments, Embedded environments
      Test driven development
    Database implementation
  Test, validation, verification and integration
    Several different levels (module, system, integration, …)
    Build systems, automated testing
    Continuous integration
    Delivery
  Deployment, maintenance and support
Software methodology services including the following
  Software project management support
    Many methodologies from agile to waterfall
    Planning and structuring software projects
    Coordination of production/deliveries from several sites
    Software architecture
    Coaching and training
  Useability and design support
    User interface design analyses
    User experience design support
The following products are excluded:
Automation software development (PLC)

## Slide 11: Issues
Very difficult to achieve the in-kind goals as labor
Long lead time for framework agreements to come into play
Uncertainties around the steady-state operations staffing situation

## Slide 12: Thank you!
Questions