## Slide 1: Progress and plans for ICS TAC 12 presentation
Henrik Carling
ESS/ICS
Date: 2015-09-30

## Slide 2: Progress and plans for ICS
Agenda
  Progress
    Governance
    Situation and meta-plan
    ICS targets - 2015 and onwards
    Re-planning effort
    ICS organization
  Current status
    Work package summary
    In-kind initiatives
  Major issues ahead
  Summary

## Slide 3: Progress - ICS governance
Operational structure
  Establish functioning (project/line) matrix
  Establish decision mandates for basic roles
Obtain external input - create governance meta plan
  See next slide
Establish communication structure
  Schedule and participation on division, group and individual level
Preliminary in-kind strategy
  Continue existing initiatives
  Find a structured way to explore new initiatives
Commercial supplier strategy
  Create new framework agreements for services needed in ICS

## Slide 4: Meta plan - management and governance
Meta plan created
External input gathered
Management team in place
Preliminary project plan
Process development
Quality plan
Full in-kind strategy
Scope setting/adjustment
Full WBS
Full project plan
Competence/capacity roadmap
Goal setting finalized
ICS identity/climate
Communication structure
Operational structure
Management roles and responsibilities
Analysis
Formation
Goal setting
Performance tuning
Operational exellence
2015-05
2015-07
2015-11
2016-03
2017-06
Commercial supplier strategy
Preliminary in-kind strategy
Initiate recruitments

## Slide 5: Target setting for ICS ICS Priorities 2015
Meanwhile: work with In-kind activities
  Keep already started in-kind activities going
  Identify new in-kind opportunities
  Define an ICS in-kind governance method
  Keep reaching out and create new opportunities
Improve ICS project plan
  Increase detail level of planning
  Balance planning quality/detail across all work packages
  Start looking into 2017-2018 and beyond
  Identify new in-kind opportunities
  Implies work with requirements
  Goal is to have a plan that we feel confident with
Create ICS competence/capacity roadmap
  Reshape organization to fit the plan
  Will help us analyze employments vs consultants
  Will help us set up relevant framework agreements for procured services
  Will help us define what competence is needed also for long-term
Improve and structure ICS governance
  Define management team and principles
  Define ICS goals and how to govern work towards these goals
  Improve/clarify communication and meeting structures
  Improve overall ICS teamwork/collaboration - internally and externally
  Improve spending and cost control
Create ICS identity
  Improve internal ICS climate
  Increase motivation and well-being at the workplace
  Make newcomers feel welcome, oldtimers feel confident and ”at home”

## Slide 6: Re-planning effort
The number one priority for ICS now is to get the project plan in order
Progress was slow during the vacation period, but results were starting to show in September
Pushed by the 2016 budget deadline good progress has been made for the 2016 plan but visibility in 2017 and onwards is still very low
Improve ICS project plan
  Increase detail level of planning
  Balance planning quality/detail across all work packages
  Start looking into 2017-2018 and beyond
  Identify new in-kind opportunities
  Implies work with requirements
  Goal is to have a plan that we feel confident with

## Slide 7: Organization – ICS team H1 2015 Combined view from first half of 2015
Henrik Carling
Anna Gillberg
Annika Nordt
Daniel Piso Fernández
Miha Reščič
Suzanne Gysin
Timo Korhonen
Emanuele Laface
Jaka Bobnar
Karin Rathsman
Leandro Fernandez
Miha Novak
Miha Vicorovic
Miroslav Paleski
Ricardo Fernandes
Richard Fearn
Alexander Söderqvist
Javier Cerejo Garcia
Klemen Strnisa
Niklas Claesson
Urša Rojec
Angel Monera Martinez
Denis Paulic
Manuel Zaera-Sanz
Morteza Mansouri Sharifabad
Riccard Andersson
Stuart Birch
Ben Folsom
Remy Mudingay
Thilo Friedrich
Temporary employee
Employee
Consultant
Consultant off-site
Sunil, Sha
Sekoranja, Matej
Blaz Zupanc
NN
NN
Nick Levchenko
Benedetto Gallese
David Brodrick
Francois Bellorini
Vacant
Technician (vacant)

## Slide 8: Organization – ICS team 2015-10-01
Henrik Carling
Division head
Anna Gillberg
Team assistant
Annika Nordt Safety and protection
Daniel Piso
Hardware and integration
Hector Novella
Deputy project manager
Susanne Regnell
Control Software
Timo Korhonen Chief engineer
Emanuele Laface
Accelerator physicist
Karin Rathsman Senior scientist
Leandro Fernandez Senior software engineer
Ricardo Fernandes Senior software engineer
Vacant
Software engineer
Javier Cerejo Integrator
Angel Monera
FPGA Engineer
Denis Paulic
PLC Engineer
Manuel Zaera-Sanz
PLC Engineer
Morteza Mansouri
Safety Engineer
Riccard Andersson PhD student
Stuart Birch Senior safety engineer
Ben Folsom
PhD student
Remy Mudingay Infrastructure engineer
Thilo Friedrich
PhD Student
Temporary employee
Employee
Consultant
Consultant off-site
Matej Sekoranja
Developer
Nick Levchenko
Integrator
Benedetto Gallese
Integrator
Vacant IEC61508 engineer
?
Deputy chief engineer
(Vacant)
François Bellorini
Integrator
David Brodrick
Integrator
?
IT/Infrastructure ?
(Vacant?)
Position under consideration
Vacant Engineer?
Vacant Engineer?
Vacant Engineer?
Vacant Engineer?
Alexander Söderqvist
Integrator
Klemen Strnisa
Lead integrator
Niklas Claesson Integrator
Urša Rojec
Integrator
Jeong Han Lee Integrator
Consultants
Vacant Engineer?
Vacant Engineer?

## Slide 9: Status - Work package 2 - Software applications
Workpackage scope
  Development Environment and Software Quality: deliver infrastructure, continuous integration, configuration management systems, service and application monitoring, task tracking system and wiki
  Development of applications and frameworks that will be used by the end user to develop applications: CS Studio, Fixed display framework, Scripting framework, Timing sequencer, MPS applications, Diagnostic applications, Electronic checklist
Workpackage status
  2015 focus on software infrastructure and frameworks
  2016 and 2017 will focus on the development of applications
  Excellent feedback from our stakeholders on the systems deployed.
  Current planning will be reviewed in the coming audits.
  Projects and resources might be moved to other work packages, projects might be cancelled, new projects might be identified
Issues
  Lack of requirements and end-user interaction
Next steps
  Continue development in scripting framework

## Slide 10: Status - Work package 3 - Software core
Workpackage scope
  To enable the collection, storage, and distribution of configuration data needed to install, commission and operate ESS control system. More specifically, it will provide data repositories and software tools, documentation, and user training and support to manage the configuration of the control system.
Workpackage status
  Finishing development of the Cable Database for 5th production release.
  Finishing development of the CCDB and the IOC Factory for first production release.
Issues
  Lack of a clear mandate for the applications to be used across the Machine Directorate’s Divisions.
  Lack of requirements from other Machine Directorate’s Divisions.
  Lack of a clear identification of who populates the applications with controls data (the WU is only responsible for providing applications and train/support end-users to use these properly).
Next steps
  Deploy production versions of the Cable Database, CCDB and IOC Factory.
  Involve other stakeholders through the creation of formal meetings/working groups per application.
  Identify/define who is responsible for populating the applications with controls data

## Slide 11: Status - Work package 4 - Hardware core
Workpackage scope
  Hardware platforms for ESS/ICS - 3-level model
  uTCA digital platform, EtherCAT, PLC integration
Workpackage status
    Work Package needs to be completely redone for detail estimates
    uTCA platform ready for deployment in Q3 2016, planned as an in-kind contribution from Switzerland
Issues
  Work Package plan had to be scrapped - previous status was not useful
  Stakeholder buy-in is missing in some parts, prototypes developed without requirements and clear agreement on interfaces should not be considered production-ready.
  uTCA.4 platform issues; Maturity of the standard; Complexity, interoperability; Community issues; Licensing policy of DESY; limited sharing of knowledge and effort
Next steps
  Conceptual design done (Q2, 2015) -> preliminary design in Q3/Q4
  Deploy temporary solutions in Q1/2016 (plan)

## Slide 12: Status - Work package 5 - Machine protection
Workpackage scope
  Machine protection system
    Beam Interlock System, Interlock System for raster magnets, Target Protection System, Magnet Powering Interlock System, Bending Magnet Interlock System, Interlock System for all insertable devices, Run Permit System, Post Mortem System, Software Interlock System, Dependency Analysis
Workpackage status
  All activities with deliveries in 2016 are estimated and planned
Issues
  Missing Requirements for Target Protection System and Run Permit system
  Missing Interface definition for Beam instrumentation systems
Next steps
  Set up of prototypes and lab
  Finalize of all relevant contracts (CERN, ITER, embeX, ZHAW) and staffing plan
  Review 2015-12 on the overall machine protection concept and design of the Beam Interlock System
  Implementation of risk analysis process for detecting risks relevant for machine protection (ESS level) as part of the work within the MPC/ESS level
  Definition of requirements for target protection system, for protection of NSS systems

## Slide 13: Status - Work package 7 - Infrastructure
Workpackage scope
  Control room, Control System Data Centre, Control System Network, Cabling and Wiring
Workpackage status
  Control room - planning for getting the control room implemented and designed as in-kind contribution
  Data Centre - planning and specifications ongoing - exploring a possible in-kind contribution
  Network - planning and specifications ongoing - merger of two work units into one
Issues
  Requirements for all three work units are missing or incomplete
  Uncertain location of the main control room and uncertain security/safety requirements
  Network Security Policy is undefined - how much security is needed?
  Grouped procurement (CF/ICS/NSS/IT)
  ICS Infrastructure group (organizational setup) unclear
Next steps
  Define usecases, gather requirements, continue rolling planning for 2017 - 2019
  Finalize Technical Annex with Norway and start in-kind activity for the control room
  Explore possible in-kind contributions for the Data Centre
  Build and create lab-facilities for Data Centre and Network

## Slide 14: Status - Work package 8 - Physics
Workpackage scope
  Develop the infrastructure for beam physics applications
  Provide the control support for beam commissioning and machine development
  Address all the physics issues related to control
Workpackage status
  Linear model of the accelerator fully benchmarked versus other products (TraceWin, Madx) and published in several conference papers
  Significant improvement of the EPICS Virtual Accelerator achieved
  Successful test of the EPICS communication with a real accelerator (SNS) in collaboration with ACCSYS Beam Physics
  Linear model under investigation against real data from SNS with three measurements
Issues
  Unclear actual scope/budget prioritization compared to other Work packages in ICS
Next steps
  Finalize the data analysis of SNS and summarise in conference papers
  Try to predict the LINAC4, CERN, measurements in the DLT (under definition)
  Continue to work with ACCSYS Beam Physics to simplify the interface and the productivity of OpenXAL
  Continue to extend the model for the linear errors
  continue to extend the model to include the non-linear dynamics (high order multipoles, non-linear space charge)

## Slide 15: Status - Work package 9 - Personnel Safety
Workpackage scope
  Accelerator personnel safety system, oxygen depletion system, radiation monitoring system
  Target personnel safety system, radiation monitoring system, hot cell personnel safety system
  On-site cryomodule test stand personnel safety system
  Neutron Instrument (LOKI, ODIN, NMX) personnel safety systems
Workpackage status
  Fairly robust plans are available for some systems
  Due to staff resource shortages planning has been slow but a full plan will be completed in 2016
  A recent review requested that the PSS team should concentrate on the accelerator design
Issues
  A full set of requirements are still difficult to finalize as the overall designs are still in a state of flux
  Resource availability 25% down on staff so this is now impacting the overall plan
  The original budget was underestimated in 2012 - will not even cover the staff resources
Next steps
  Continue planning
  Continue the Accelerator PSS design
  Continue Cryomodule test stand design, Install and start building PSS test stand
  Start initial meetings for Target PSS, identify Target hazards and interfaces, start design of target PSS
  Explore if installation of cable containment and cables could potentially be in-kind

## Slide 16: Status - Work packages [10..13] - Integration
Workpackage scope
  Control system integration of Accelerator (WP10), Target (WP11), Instruments (WP12) and CF (WP13)
Workpackage status
  Newly formed team is finding their way to manage the integration efforts
  A common integration strategy for all the integration WPs is being put in place
Issues
  Much of the planning needs to be reworked but in some cases this is very complex
  The requirements gathering process has been problematic
  Integration strategy for WP 11, 12 had to refined regarding ICDs and resource allocation.
  In-kind negotiations have to proceed independently of the status of the designs. The two major consequences
    The nature of the in-kind process may increase the final price of the systems
    It is more difficult to have global approaches to ”common problems”
Next steps
  Re-plan work packages and finalize ICDs
  Increase the coordination with Accelerator Division. Specially the coordination with ACCSYS WP3 (Normal Conducting Front End)
  Coordination with Proton Source Controls Project, which is being deployed in Catania in the following weeks
  Prototype activities in WP 10: Beam Instrumentation Prototypes and WP12: Lakeshore temperature controller
  Task for to finalize the integration strategy for CF controls integration

## Slide 17: ICS work package status summary

## Slide 18: EVM Graph
Current progress
A re-planning has been done for 2015 and 2016. For 2015, we have corrected some mistakes and unrealistic planning items. The re-planning exercise has also leveled the quality of the plan between work packages.
Currently, the (calculated) delay for ICS is about 2 months - in reality this is distributed over the different work packages
September 2015
Notes: Schedule variance = Earned – Schedule
Cost Variance = Actuals - Earned
SPI = Earned/Scheduled
CPI = Earned/Actuals

## Slide 19: In-Kind initiatives
The in-kind budget model is particularly difficult for ICS since 80 - 90% of the cost is labor driven
In-kind activities are ongoing with Bilbao, CEA and INFN - total value ~2M€
Activities are being planned with CNRS, IFE, PSI, TUT and ZHAW - total value up to 7 M€
Activities planned with STFC and Uppsala are on hold - total value ~4 M€
Despite improvements in H2 2015, still ICS lacks a structured approach to create and drive in-kind activities

## Slide 20: Major issues
In-kind activities
  Budget model will be difficult to achieve
  Structured approach to create and drive activities is missing
Re-planning
  The ICS plan for 2016 is workable, but visibility in 2017 and onwards is almost non-existant
Collaborative efforts
  ICS attempts to standardize and industrialize controls
  Collaboration with stakeholders is improving but must be improved faster

## Slide 21: Summary
Current focus is on establish a structured governance and an improved project plan giving increased visibility 2017 and onwards
Standardization, industrialization and quality are critical for the sucess of ICS - we will include measures to secure this in our process
Our in-kind status needs significant improvement - we are continuously identifying in-kind activities but lack a structured approach how to manage this

## Slide 22: Thank you!
Questions