## Slide 1: ESS Construction Project
Kent Hedin
Head of Conventional Facilities
www.europeanspallationsource.se
8 October 2015

## Slide 2: CF Scope
CF in numbers
72 hectares
26 buildings, approx. 100 000 m2
50 000 m3 concrete
6 000 tons reinforcement
40 km pipes
Campus Area with Office & Labs – 17 560 m2
Notes: Quote from TDR “Technical design Report”
The term “conventional facilities” refers to
The spaces required to house the ESS research equipment, machines and instruments and to accommodate the human beings who will either make use of the facility directly, or who will support its operation and maintenance, be they ESS staff, guest researchers or visitors. CF is also responsible for the mechanical and electrical services necessary for the proper functioning of the facility.

## Slide 3: CF Overview
Necessary permits obtained in 2014
Contract for construction signed with SKANSKA Feb 2014
Milestone for Ground Break achieved and site works have proceeded according to plan during 2014-2015
Construction works of Accelerator tunnel started ahead of schedule
Construction of Substations and Target building has commenced during 2015
Most critical work this year; piling of Target & Experimental Halls
Campus Area in preliminary design. Contract will be procured beginning 2016
Budget wise still in ramp up. 2016 the most work intense year to come.
Staff level steady and sufficient

## Slide 4: CF Organization

## Slide 5
W | 36 |  | 38 |  | 40 |  | 42 |  | 44 |  | 46 |  | 48 |  | 50 |  | 52 |  | 1 |  | 3 |  | 5 |  | 7 |  | 9 |  | 11 |  | 13 |  | 15 |  | 17 |  | 19 |  | 21 |  | 23 | 
1
3
2
4
1
3
2
4
1
3
2
4
1
3
2
4
MONTH | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
G01, G02,
G04
Accelerator
D02
Target
F03, Shipping
E01, E03, E04, E05
Exp. Halls
D04, 05, 06, 07
TARGET BUILDINGS
H09 SPRINKLER
1. BUILDINGS INVENTORY | 2. RADIATION CALCULATIONS/ ASSESSMENTS | 3. HAZARD ANALYSIS, FINALIZE REQUIREMENT DOCS | 4. APPROVAL OF REQUIREMENT DOCS
2015 | 2016
1
2
3
4
D01, 03, 08, E02
TARGET BUILDINGS
H10 Waste building
CF BASELINE PROGRAMME (INCL. ESS RAD SAFETY ANALYSIS)
SSM Requirements Fixed

## Slide 6: Once upon a time… there was a big green field.
8 May 2014

## Slide 7: Ongoing works
H05
H06
G01
D02
Site Offices
H01
G04
G02

## Slide 8: Accelerator Progress 2015-10-09
G01
Blinding 537 m (100%)
Base slab 537 m (100%)
Walls 316,5 m (59%)
Vaults/top slab 271 m (50%)
CTL tunnel Completed – inc. Fill
HEBT Base slabs completed, walls in progress
FEB Base slabs completed, walls in progress

## Slide 9: Intersection G01 – G02
3,5 m
6 m
5,5 m
15,5 m
10 m
4-11 m

## Slide 10: Recent tunnel pics
Top slab reinforcement
Formwork for walls
19 August 2015

## Slide 11: Stubs
4 June 2015
28 May 2015
23 September 2015
19 August 2015

## Slide 12: Retaining wall
Gable wall
23 September 2015
Formwork 19 August 2015
18 September 2015

## Slide 13: Tunnel vision

## Slide 14: CTL
Blinding – 21 November 2014
12 March 2015
19 May 2015
Inside CTL –
19 August 2015
Bottom slab –
19 December 2014
Refill CTL –
4 August 2015

## Slide 15: HEBT
6 November 2014
15 April 2015
23 September 2015
23 September 2015
8 October 2015

## Slide 16: Front End Building
19 August 2015
3 September 2015
3 August 2015
8 October 2015

## Slide 17: Dog Leg
18 September 2015
8 September 2015
28 August 2015
8 October 2015

## Slide 18: Gallery
Substation 1
19 August 2015
Drilled foundations
7 July 2015
Gallery steel structure 8 October 2015

## Slide 19: G04 cryo
18 September 2015
8 October 2015

## Slide 20: Target
26 February 2015
12 March 2015
Sheet piling –
25 March 2015
22 April 2015

## Slide 21: Target
D01/D02/D03
Sheet Piles
Steel core Piles
Concrete Piles
Large diameter bored Piles (Monolith)
Progress, Target, 1st of September 2015
1101 /3958 concrete piles (28%),
84 /364 steel core piles

## Slide 22: Monolith area

## Slide 23: Target - piling
4 June 2015
19 August 2015
30 September 2015

## Slide 24: H05 aux
4 June 2015
26 February 2015
25 March 2015
21 May 2015
20 August 2015
8 October 2015

## Slide 25: H06 aux
18 September 2015
19 August 2015
7 July 2015
Roof top
8 October
2015

## Slide 26: H01 - CUB
12 June 2015
19 August 2015
8 October 2015

## Slide 27: Campus Area
Circular Road Sheet Piling
8 October 2015

## Slide 28: Aerial View

## Slide 29: Skanska ESS Construction - Building the future together