## Slide 1: Operations and Work Coordination at ESS
Marc Munoz

## Slide 2: ESS linac: overview
Parameter | Value
Ave power (design) [MW] | 5
Max energy (design) [MeV] | 2000
Peak current [mA] | 62.5
Pulse length [ms] | 2.86
Rep rate [Hz] | 14
Duty factor [%] | 4
RF freq [MHz] | 352.21/704.42
Accelerator-to-Target (A2T)
Milestones:
Ready for Beam on Target: April 25
Beam on Target: May 25
Instruments commissioning: 25/27
Users: End 2026
Upgrade to 5 MW: From 2027
Notes: physica scripta

## Slide 3: ESS Timeline
Pre-BOT
Post-BOT
2023
2024
2025
SRR5
Beam Commissioning to Target (pre-BOT)
BOT
ACC Commissioning + Test Beamline (post-BOT)
ACC, Target, NSS - Installation, Testing, Commissioning - Before BOT
Shutdown 1 (Instrument Install in Bunker)
Hot Commissioning 2
Users 1
2026
Shutdown 2 (Instrument Install in Bunker)
Hot Commissioning 3
Shutdown 3 (Instrument Install in Bunker)
Shutdown 4 (Instrument Install in Bunker + CM Install)
Recommissioning
Users 2
Buffer
2027
Hot Commissioning 1
BOT
15 May '25
EOC
31 Dec '27
Facility RBOT
14 Apr '25

## Slide 4: Tunnel Status

## Slide 5: Reorganization for Operations

## Slide 6
Responsibilities:
Operations processes and procedures, operational roles
Operational Limits and Conditions
Facilitate preparations for required technical support
Establish the required technical support
Operations Division
Control Room Operations
Work Coordination and Planning
Electrical Systems
Cooling, HVAC and sprinkler Systems
Responsibilities:
Support to safely test and commission the neutron source (accelerator, target) and related systems (24/7)
Safely and reliably operate (24/7) the neutron source
CR operations procedures
Shift planning
Training
Requirements for operational tools provided by other teams
Operational tools (development)
2nd projects
Interact with:
Beam physics
Technical systems teams
Work Coordination and Planning
Infra Operations & Maintenance
ESH, RP
Other control rooms/centers
Infrastructure Operations & Maintenance
Responsibilities*:
Support in work coordination and planning.
Shutdown coordination and planning.
Define requirements to lead development and optimization for machine fault tracking (tool)
Coordinate machine performance tracking, analyses and reporting
Interact with:
Stakeholders for planning and work coordinating
CR operations
*Current scope is G01 and G02 areas.
Responsibilities:
Own, develop, operate and maintain electrical, water cooling, fire and sprinkler, HVAC and instrument air systems ESS Electrical Operations Leader (direct delegation from DG)
Own service contracts
Maintenance planning
Provide technical support (scope TBD)
Interact with:
Work Coordination and Planning
Control Room Operations
Technical systems teams

## Slide 7: Work Coordination and Planning
Functional group inside Operations
At present:
  1 full time
  2 25%
Dealing with coordination of activities in operational areas
  At the present: Linac Tunnel and Klystron Gallery
  Coordination between installation, commissioning and maintenance
  Approval and scheduling of work orders
  Revision of permits
  Planning of maintenance periods
  Access control to the buildings
  Processes

## Slide 8: Areas covered by WC&P
G01
G02
NCL

## Slide 9: Weekly Planning
  WO created in EAM
  Work Package informs the WC&P about their plans for the following week (optional)
  WC&P will review WO and plans
    Check interferences between WOO
    Escalate issue if needed to Machine Section Coordinators
  Meeting with OHS+RP+EAM every two weeks for feedback
  Initial plan shared in the Stakeholders meeting Thursday evening
  Plan finalized on Friday Operations Morning meeting
  Shared in Confluence

## Slide 11: Work Orders
Any work in ESS needs to be under the umbrella of a Work Order
Main types
  Installation: Long standing wide WO. Review every few month to update the risk
  Maintenance: Dedicate WO
  Immediate Corrective Action: Approved by MCR
  Inspections
Rad Work Permit link to PSS

## Slide 12: Work Orders
We are having multiple type of activities going at the same time>
  Installation
  Maintenance
  Commissioning
They require different types of workflows:

## Slide 13: Basic Workflow
New
Accepted
Prepared
Planned
Released
Ongoing
Completed
Closed
ESS worker, Possibility of pause
ESS Worker
System Owner
Includes Risk Analysis, Permits, request for Scheduling
WC&P, review of the WO, Scheduling
WC&P, on the day of the start of the work
Finish of the work
Closing documentation, root cause analysis, etc

## Slide 14: Immediate Maintenance Workflow
Created
Accepted
Prepared
Ongoing
Completed
Closed
Released
By the Shift Leader or WC&P

## Slide 15: Permits
Some WO require a Work Permit to be attached
At present Electrical Work Permit and Radiation Work Permit
RadWork is also linked to access to the PSS controlled area
Permits are approved by the relevant authority at ESS
  RadWork by Radiation Protection Group
  Electrical by Electrical Operations Leader or Electrical Safety Leader

## Slide 16: Areas to improve
EAM training and information sharing with system owners and workers
  Simplification of the interface
Management of Work Orders
  To find the good balance between WO length and detail
  Too many long standing WO for installation
    WO with 2 or more years
Risk analysis
Filling the EAM database
  WO for systems being installed and not yet included in EAM
Related to WO: access control and permits

## Slide 17: Interface

## Slide 18: Discipline with WO

## Slide 19: What is needed to enter PSS
Access to FEB90
  Training -> Sabacloud
  Access -> Access Portal
Personal Dosimeter
Acquire EPD
  Card registered on Dosiserv
  Be included in a valid RPW
    User needs to be an active user in EAM
    RPW needs to be attached to an ongoing WO
Pass the Stanley system
  Training
  Access
Only the worker can access
Needs to know exactly which trainings are need
Only the worker or AR can access
Confusing to know what is rejected
Only the RP can access
Not integrate in the LDAP/IAM
Needs the help of EAM team to add a new user
You don’t know if he has the other

## Slide 20: Shutdown Planning (thanks to Olle)
  Shutdown Co-ordination
    Agree on sequence and plan for a shutdown program
      5 years look ahead, focus on the coming year
      Agree on plan/scope
    Evaluate scope of work, prioritization
      Organize and optimize the work
    Identify/Organize stakeholders
      Communication
      Ownership
    Ensure ways of working
      Engineering handbook
        Passed reviews, minimize risks
        Installation binders, etc
      Operations/WOO
        Issuing permits and WO
        Integrating shut down work into the daily planning and normal workflows
          Planning 2-4 weeks look ahead
          WOO coordination meeting
        WOO to be involved in shutdown co-ordination as detail planning takes form

## Slide 21
2023
2023
Today
3 days
Jul 31 - Aug 2
3 days
Aug 2 - Aug 4
3 days
Aug 7 - Aug 9
1 day
Jul 31
1 day
Jul 31
2 days
Aug 1 - Aug 2
2 days
Aug 3 - Aug 4
5 days
Aug 7 - Aug 11
3 days
Aug 9 - Aug 11
1 day
Jul 31
3 days
Jul 31 - Aug 2
4 days
Aug 1 - Aug 4
5 days
Aug 7 - Aug 11
5 days
Jul 31 - Aug 4
5 days
Aug 7 - Aug 11
1 day
Jul 31
1 day
Jul 31
2 days
Aug 1 - Aug 2
2 days
Aug 3 - Aug 4
5 days
Aug 7 - Aug 11
Electrical Operation and Maintenance
ICS Infrastructure
Cooling, HVAC and sprinkler systems
FM Site and Security
31/07
01/08
2023
Maintenance Switchgears H05
Maintenance Switchgears H06
Maintenance Switchgear J17 G04
Network upd.
Firewall upd.
Move Servers H01
Reinstall Servers D02 MCR
Storage upgrade
02/08
03/08
04/08
05/08
06/08
07/08
08/08
09/08
10/08
11/08
Maintenance Switchgear J16 G04
BMS update
Sectioning IAR upgrade
Motioning Valves
Motioning Valves
Maintenance Pumps
Cleaning Filters
Maintenance temporary power main station
Maintenance temporary power barracks, part 1
Maintenance temporary power baracks, part 2
Change light fixtures in G02
Change light fixtures in G02

## Slide 23: Scope for Shutdown 2023
Electrical Operation and Maintenance
Maintenance building H05, H06, incoming power, week 31
  Designed with redundancy
Switchgear supporting G04 (cryogenic plant), week 32
  Affects the cryogenic plant operation, ensure power to recovery system by generator
  Affects fire detection and suppression in G04, to be supported by generator
  Affects TS2 activities, to be co-ordinated with the shutdown
Cooling, HVAC and sprinkler systems
Building Management System update, week 31
  Affects visibility of buildings systems
Maintaining pumps, cleaning filters and motioning vales in G buildings, week 31-32
  Affects CWM and CWH cooling systems and supported ACC equipment
  Smaller work in G02 as system to be updated
  CWL unaffected
Sectioning of air system
ICS infrastructure
Network and firewall update, week 31
  Short stop, should be unnoticeable
Move servers from H01 to D02, week 31
  Redundancy
Upgrade storage, week 32

## Slide 24: Scope for Shutdown 2023
Building Maintenance, w.31
Blue area, 1 August 12.00-16.00
Pink area, 2 August 12.00-16.00
Green area, 3 August 12.00-16.00
Lack of lights, hot showers and fire detection (Skånsk Larmtjänst, will be on site to overview)
Lights G02, w.31-32
Changing the lights in the roof, warranty
Local affect
Done by Assemblin, experienced people

## Slide 25: Ongoing work
  Electrical
    Contractor identified, One Nordic to preform work, with experience from the facility
    Fully manned team from ESS
    Ensure procedure/switch-plan and LOTO is in place
    Discussions with Kraftringen as incoming provider to
    Looking at renting required generator, from Skanska Direkt to ensure compressor and fire detection/suppression functionality
    WO in EAM working on adding procedures to ensure repeatability
  Process and piping
    Inhouse personal
    EOn as contractor
    BMS update affect site wide, but no know conflicts
    Substations updates ongoing
    WO to be created
    PMS to be added to EAM
  Network
    Inhouse personal
    Redundancy
    Detailed plan in Jira and then by WO EAM, confluence page to gathered info to be created

## Slide 26: Going forward
  Looking forward, operation and commissioning activities will intensify
    Still we will have installation
    and need for maintenance, as sys. goes into operation
    and over time they need upgrades and modifications
  Typical Electrical/Process and piping for 2023 is preventive maintenance stops
    Known, scheduled, periodic,
    To be captured in EAM, adding PMS
    We avoid corrective and breakdown maintenance, costly stops
    Don’t necessarily need downtime
  Network for 2023, is updates and finalizing installation
    To existing systems/components
      To meet higher requirements
      To meet unknown requirements
    Extend life length
    Minimize corrective and breakdown maintenance
    Safety related and or regulatory

## Slide 27: Shutdown Co-ordination
  Create a program that gathers all that needs to be done to ensure high availability
    Tight schedule
  Work towards the exciting organisation
    WOO/Permits/daily planing
    Installation Coordinators
    Commissioning Coordinators
    MSC/WP/Sub projects
    Maintenance organisation
    Operations
  Gather information > Prioritize > Optimize > Plan > Communicate
    Iterate…Iterate…

## Slide 28: The Baseline
Establishing the baseline for maintenance stops, understood through EAM (PMS)
  Procedure ESS-1162328, ESS Maintenance Handbook
    Clarifying roles, responsibilities
    Ownership and ctrl of installed eq
    Supervision and inspection
    Avoid corrective and breakdown maintenance
      ESS-3185783 Rules for Equipment Criticality
        Ways to capture and describe, “things that happens”, we´re not perfect at first go
      ESS-3243953 ESS guideline for Spare Parts Management
        Waiting time when something happens
Understanding the remaining known installation work
    Impact on commissioning and operation
    Close work with MSC/WC&P/WP
Capture and prioritize unknow Updates/Changes/Ad-on
    Ensure working towards ESS procedures
      Engineering handbook > Approved Reviews > Minimize delays
    Cost time today saved time tomorrow
    Risk minimize
Availability
    Main objective to ensure and plan for controlled shutdowns under one program
    Goal 95% reliability