## Slide 2: Projects updates
High temperature and mechanical processing
PRESENTED BY Caroline curfs

## Slide 3: Agenda
1 High Temperature
2 Mechanical processing

## Slide 4
High Temperature
1

## Slide 5: High Temperature
  2nd hand furnaces from LLB
    1350 C : 1 Nb resistor with 5 Nb screens, dia. 45 mm, used on diffraction instrument
    1800 C : 1 Nb resistor with 7 Nd screens, dia 35 mm, used on spectrometer
    Planned to be ready by April 24
    Transfer on standby due to problems with CNRS
  New furnace
    Only 1 manufacturer (?) : AS Scientific
    Full vanadium for DREAM (Tmax = 1100 C) – Specifications on going
    Requested for DREAM Hot Commissioning (July 25 – March 26) / HEIMDAL Cold commissioning (October 26 – March 27)
    Planned to be ready by April 24
ILL-Type furnaces (vacuum)

## Slide 6: High-Temperature
UHT furnace
VR (Swedish Research Council) grant between Chalmers & ISIS
Started in 2017 (grant awarded)
Phase 1: design at ISIS by ISIS team based on already existing furnace
Phase 2: manufacturing by Chalmers Uni
Specifications:
Lamp furnace : max temperature 1800 C
Standalone or attached to 60 kN stress rig
Vacuum or inert gas chamber
Status:
Manufacturing moved to ESS – Budget available1.6 MSeK
Design by ISIS up to conceptual design – Mechanical design needed to enable manufacturing
Bulbs and reflectors currently at ISIS – test to be done

## Slide 7: High-Temperature
Specifications:
Quick and versatile
Min. 15 capillaries of different sizes
Suitable for DREAM and HEIMDAL
Temperature from 100 K to 800 C
Status:
HAB: on site, tested and integrated
Cryostream: 2nd hand to be tested
Mechanical part:
  Off-the-shelf equipment procured
    XY stage received
    Arinax to arrive end of May
    Z Translation + motor received
  Plate and lifting support: more design needed before manufacturing
  Gripping system tested
Control integration:
  HAB done
  Cryostream via Lakeshore done
  Motors : Arinax done by manufacturer, other to be done by MCA
Hot Air Blower/Cryostream
Project lead by Quentin Borlet (6 months Internship from UTC, France)

## Slide 8
Mechanical processing
3

## Slide 9: Mechanical processing
    Requested by BEER for cold commissioning 07.26-12.26
    Specifications :
      40kN (60kN/100 kN) uniaxial rig for tension and compression
    Joule heating (15V and 800 A) and vacuum chamber
    Can be installed horizontally or vertically
    Status :
      New control software received and installed – to be tested
      New extensometer received – to be tested
      Mechanical integration: not started
      Control integration via MQTT
    3D DVC/DIC system:
      Cameras installed - computer ready
      Software to be installed and tested: collaboration with J. Hektor from Malmö Uni.
    Use case :
    Collaboration with Alfa Laval
NPI Stress rig

## Slide 10: Mechanical processing
  Torsion/rotation rig for tomography
    Requested by ODIN for hot commissioning 07.25-03.26
    Design nearly finished
    List of off-the-shelf parts to be ordered soon
    Construction planned to be finished by Q4/24
    Control electronics planned to be Beckhoff
  Dilatometer
    Specifications still on going
    Requested by BEER for hot commissioning 01.27-09.27

## Slide 11: Thanks to Quentin Borlet, Luca Sagliano, Richard Ammer, Lauritz Saxtrup, Florence Porcher, Jonas Engqvist, Robin Woracek, Joe Kelleher and Ali Mortazavi