## Slide 1: BIFROST update – STAP 22nd of October 2024 Rasmus Toft-Petersen, Lead scientist Liam Whitelegg, Lead engineer Greg Tucker, Data scientists Tamires Gallo, Instrument operations engineer Kristine Krighaar, PhD student (KU)

## Slide 2: BIFROST: Indirect ToF with energy-multiplexing backend
Indirect neutron spectrometry: Fix the final energy via analysers, use time-of-flight to measure the incident energy

## Slide 3: BIFROST: ToF frontend – multiplexing backend
Flux @ 2 MW: 6 · 109 n/s/cm2
Elastic line resolution using full pulse: 170 μeV

## Slide 4
  PSC and FOCs installed in the bunker, monitor installed soon
  Broken disc -> PSC maximum speed is 126 Hz until new discs are procured and tested
  FOC’s are 14 Hz
  PSC commissioning will be a challenge
  Missing instrument deliverables
    Beam Monitor 1
    Vacuum snorkels for guides
      Minor rework needed
  Missing ESS deliverables
    Cable installations
    Cabinet installations
Primary Spectrometer - Bunker
No commissioning feasible
until at least Nov 24

## Slide 5
Primary Spectrometer - D03
  In D03, we have guide, beam monitor and thermal neutron shutter.
  Missing instrument deliverables
    Beam Monitor 2 and mechanics
    Shutter Q-Gate Tests
  Missing ESS deliverables
    Compressed air lines
    Pneumatics box
    Cable installations
    Trunking installations
    Network installations
    Cabinet installations
    Certain shielding blocks
No commissioning of shutter feasible until at least Dec 24

## Slide 6
Primary Spectrometer - E02
  BW chopper essentially commissioned
    Beam Monitor 3 installed
    False floor rebuilt
    Attenuator installed
  Missing ESS deliverables
    Final media connections
    Pneumatics box
    Wall box energization
    Monitor cabinet
    Certain shielding blocks
    Network

## Slide 7
Primary Spectrometer - E01
  Missing instrument deliverables
    Sample Jaws
    Beam Monitor 4
  Missing ESS deliverables
    Final media connections
    Pneumatics box
    Motion cabinet energization
    Motion cable installations
    Monitor cabinet
    Network
Picture of cave
No motion commissioning feasible
Yet!

## Slide 8
Analysers
  Fully assembled on plate
  Lots of measurement data
  Installed inside vessel last week

## Slide 9
Beryllium Filter
  FAT performed in August
  Delivered to ESS and SAT performed last week
  Vacuum performance is now robust
    2x10-9mBar.l.s maximum leak rate at cold temperature
    Secondary vacuum design now changed
  Temperature readout through ICS hardware
  Hold time of 55 hours, hopefully more soon!

## Slide 10: Component Summary

## Slide 11: Component Summary
All hardware is procured
A few SAT tests remain to be done
By the end of the year, all major installations would be complete
What remains is integrated cold commissioning, a major task

## Slide 12: Schedule
  All cabinets installed and energized by end of December 24
  All beamline components installed by the end of January 25
  Full cold commissioning to be run from February 25
  A number of bureaucratic processes to clear between then and Beam on Target We need to prepare TG5 documents and cold commission at the same time
  Handover of beamline in July 25
Estimated TG5 Dates – from P6

## Slide 13: Schedule
  CP01 and CP02 – Secondary Spectrometer
  CP03, CP04 and CP05 – Electrical Installations within D03
Critical Paths

## Slide 14: Cold commissioning – old understanding
Involved groups: Core team, ICS, MCA, Detector group, CEP, Sample environment

## Slide 15: Cold commissioning
We now have two timing networks – low precision and high precision
Sample environment and motors interface with PtP (slow)
Detectors and monitors interface with fiber (fast)
Commissioning the detectors involves detector group, ICS, CUP, CEP, ECDC, IDS, data curation. We need to test preamps, ADC, timing, backend module, event formation unit, data format and storage, slow control and EPICS.
Motors involve a different timing network than detectors, encoders, limit switches, NICOS, encoder values need timestamping, we need to work with the data-file. Involves MCA and all above.
Staff have implemented great solutions. But we don’t think that cold commissioning will be fast or straightforward. Example: We tested a goniometer and ran into problems, that needed fixing in the lab. 4 months ago, not fixed yet. Such problems will be the norm and need to be resolved ad hoc

## Slide 16: Cold commissioning summary
BW chopper is effectively commissioned (done by chopper group)
NICOS is up and running in the hutch (done by ECDC)
We have power and network in E01 (done by CEP)
Most motors have been tested during the FAT and SAT tests. However, this was a while back. We need to test the integration of the motor controllers in the rack with the timing system, NICOS and the nexus files
Critical tasks:
Getting the cables and pipes into the bunker, the racks energized in order to start the challenging commissioning of the choppers
Motion control
Detector readout chain (reference pulse timing, ADC, RMM, EFU, Kafka, NEXUS)

## Slide 17
Detector design reminder

## Slide 18
Detector test – April and September 2023 – at the LLB

## Slide 19
Detector test – April and September 2023 – at the LLB

## Slide 20
Detector test – September test, channels A and B histogrammed

## Slide 21
Detector test – Masks applied

## Slide 22
Detector test – Calibration

## Slide 23
Reminder of the spectrum and sparks
Charge distribution on A and B channels shown on the right. Sparks occur at the edges of the polygon and at the high charge end. A triplet quiets down after a few days of operation

## Slide 24
Tests at the ESS – minor noise problem
High charge noise in some tubes
NOT cables, preamps etc
Reproduced at the ILL using different power supply, ADC
1 cts/ min pr triplet
Not huge problem, but without diagnosis, we don’t know if this gets worse

## Slide 25
Tests at the ESS
After the trip to ILL, we left the noise problem for another day, and started testing all detectors
More than 1 week of cabling, 3 weeks of testing.
We now have a useful neutron source on site

## Slide 26
Tests at the ESS - results
The trivial problems:
One preamps LV circuit was broke (changed it)
Another preamps HV circuit was broke
3 RJ45 cables needed changing
Isopropanol and clean air on contacts

## Slide 27
Tests at the ESS – Big problem 1
Soldering issue, generates sparks when it rains (!)
Needs resoldering. The ‘big’ problem is that we
need a pro to do it.

## Slide 28
Tests at the ESS – Big problem 2
One triplet cannot be put to high voltage – leak current through the middle tube. Very likely broken – has to be changed before TG5

## Slide 29
Tests at the ESS – overview

## Slide 30
Tests at the ESS – overview

## Slide 31
Tests at the ESS – overview

## Slide 32
Tests at the ESS – overview
Module ID | Triplet ID | Tube ID | 
5p1 channel 0 | 5p0 meV short | Middle | 
3p2 channel 8 | 3p8 meV short | B-side | 
4p2 | 4.4 meV middle | Middle | 
1p3 – channel 2 | 2.7 meV – long | Middle | 
1p1 – channel 13 | 2p7 middle | Middle | 
We need to be able to operate with all triplets, we don’t need gaps in our dataset (or slower hot commissioning) on top of everything else.
Need-to-have: Solder the bad triplet and change the badly broken tube
Nice-to-have: Change all the leaky tubes
Ideal scenario: Go into hot commissioning with 15 spare tubes, and spares for the noisy tones (got recent approval from Pascale)

## Slide 33: BIFROST: Energy resolution simulations
Using McStas, we simulated flat modes at various energy transfers, the plots below show the modes at 0.1 ms PSC opening speed, the
energy resolution remains similar across the band

## Slide 34: BIFROST: Preliminary phonon simulations, more to come
Phonon simulations using a PSC opening time of 1 ms. Nicely defined mode with a hint of focusing/defocusing effects

## Slide 35: BIFROST: Preliminary phonon simulations, more to come
Slight asymmetry clearly present, we have a vertical tilt of the resolution function in (Q_z, E), efforts are ongoing to understand this in more detail

## Slide 36: Upgrade path
M. E. Zayed, et.al, Nature Physics, 13, 962, (2017) - SrCu2(BO3)2
Polarization analysis – incident polarization is being procured
Sample position and supermirrors are on holding pattern.
Other instruments need the money, we prefer to postpone and work on this on a prototype level (design, tests) – we need partners and funding

## Slide 37: Early science on BIFROST – focus on scientific value but also on demonstrating what BIFROST can do
M. E. Zayed, et.al, Nature Physics, 13, 962, (2017) - SrCu2(BO3)2
Hot commissioning, calibration
Round robins
Known physics, including intensity (direct ToF comparison)
Incremental physics
Demonstrating resolution
Demonstrating flux
Demonstrating mapping efficiency
Demonstrating extreme environment

## Slide 38: Early science on BIFROST – focus on scientific value but also on demonstrating what BIFROST can do
M. E. Zayed, et.al, Nature Physics, 13, 962, (2017) - SrCu2(BO3)2
Altermagnets, chiral magnons slightly split in altermagnets, This splitting is key in this new field (here, MnTe, Masuda 2024)

## Slide 39: Early science on BIFROST
  Early project @ 100 kW – flux demonstration: Finally understanding LiCoPO4, a complex magnetoelectric with 4 spin wave branches and possible hybrid modes. Only small crystals available - on the feasibility limit today, we need more signal and better resolution -> BIFROST.
LiCoPO4, Thales @ ILL
M. E. Zayed, et.al, Nature Physics, 13, 962, (2017) - SrCu2(BO3)2
  Early project @ 500 kW – Extreme environment + mapping efficiency: Shastry Sutherland compound. Well known system, the 4 spin plaquette exists at high pressure
  The nature of the plaquette is unresolved, needs a mapping experiment on small crystals under large pressure. Possible for the first time on BIFROST at 500 MW accelerator power.
M. E. Zayed, et.al, Nature Physics, 13, 962, (2017) - SrCu2(BO3)2

## Slide 40: Early science workshop on BIFROST
M. E. Zayed, et.al, Nature Physics, 13, 962, (2017) - SrCu2(BO3)2
Hold a workshop with the key partner scientists, local instrument scientists, inviting key external friendly users
Present the capabilities of the instrument
Create groups to come up with targeted demonstration experiments
Key criteria: Crystal exists, data analysis team exists, previous neutron measurements exists.
Do not promise anything
The choice of experiments is decided on the fly by local team. The right experiments depends on source power, background etc.

## Slide 41: Thank you for your attention
Scientific contributors:
Rasmus Toft-Petersen
Jonas Okkels Birk
Greg Tucker Kristine Krighaar
Marton Marko
Rodion Kolevatov
Martin Olsen
Mads Bertelsen
Sonja Holm Dahlin
Jakob Lass
Felix Groitli
Fanni Juranyi
Jacob Larsena Paul Freeman
Isabel Llamas Jansa
Technical contributors:
Liam Whitelegg
Sylvain Rodrigues
Finn Saxild
Keld Theodor
Tamires Gallo
Henrik M. Rønnow
Bjørn Hauback
Philippe Bourges
Christof Niedermayer
Kim Lefmann
Niels Bech Christensen