## Slide 2: Data Systems and Technologies (DST)
STAP presentation April 2025
PRESENTED BY Jesper Rude selknæs

## Slide 3: The DST team
Brian Lindgren Jensen
Jesper Rude Selknæs
2 vacant full time positions advertised.
1 Student worker position advertised.
Alexandre Stefanov
Kashis Verma Studentworker 10h per week
Farshid Farjad
Tilde Bonnevier Walstedt
Beatriz Cadelaiz Studentworker 10h per week
Lottie Greenwood

## Slide 4: Data systems and Technologies
Distribution of resources
Subject / Person | Jesper | Brian | Tilde | Alexandre | Farshid | Lottie
Network |  |  |  |  |  | 
Storage |  |  |  |  |  | 
HPC |  |  |  |  |  | 
OpenStack |  |  |  |  |  | 
VISA |  |  |  |  |  | 
Containers (AppTainer) |  |  |  |  |  | 
INFOSEC |  |  |  |  |  | 
Infrastructure services |  |  |  |  |  | 
Web services |  |  |  |  |  | 
Legacy systems |  |  |  |  |  | 

## Slide 5: Data pipeline
Infrastructure requirements and status
Instrument simulation
HPC cluster, VISA for frontend, Some storage capacity
All in place and being improved continuously.
Data analysis
HPC, large VMs = OpenStack, DAQ hardware, Performant storage.
All parts in place but needs to be scaled as instruments comes online.
Data archiving
Integration between DST core infrastructure and UO, Archive storage system
All parts in place but needs to be scaled as instruments comes online.
Data reduction
HPC, large VMs = OpenStack, DAQ hardware, Performant storage.
All parts in place but needs to be scaled as instruments comes online.

## Slide 6: Status report
What has been accomplished since the October 2024 STAP:
Contract signed for 1 full time position.
Got 1 resignation
Installed workstation for experimental control in the hutches for:
  LOKI
  ESTIA – network is not yet available.
  DREAM
  ODIN
  TBL
  BIFROST
Installation of additional virtualization equipment in both datacenters
Integration with SciCat and UserOffice completed.
Integration of DMSC systems with Lund based IT systems
DST continues to move from CentOS to AlmaLinux.
Engaged in the post-PaNOSC VISA ecosystem
Continues to work with VISA and software packages for reduction and analysis
Considerable effort has gone into the future hosting situation

## Slide 7: Plans for the rest of 2025
Major activities
Installation and commissioning of storage expansion
Procuring, installing and deploying a new HPC queue
Upgrading and expanding VISA
Procuring, installing and commissioning an expansion of the HPC capacity
Engaging in the effort for a new hosting facility
Handing over hutch workstations to IT
Filling the vacant positions in the group

## Slide 8: Plans for the rest of 2025
Timeline
June
July
Cold commissioning
Operations
Storage delivery
Storage commissioning
Cold Commissioning
Operations
OpenStack improvements
OpenStack improvements
Operations
Cold commissioning
Requirement gathering for HPC
May
August
September
October
November
December
Puppet upgrade
Deploy workstations in hutches for ESTIA and NMX
VISA image improvements
Vacation
Onboarding new staff
Operations
Cold Commissioning
Storage commissioning
OpenStack improvements
Deploy workstations in hutches for X
VISA improvements
Onboarding new staff
Operations
Cold commissioning
Deploy workstations in hutches for X
VISA improvements
Operations
Cold commissioning
Activities to be planned
VISA imporvements
BOT – fingers crossed.
Operations
Cold commissioning
Activities to be planned
Operations
Cold commissioning
Activities to be planned
Storage installation

## Slide 9: Plans for the rest of 2025
Server room
Significant effort will be spend in 2025 on a new server room for DMSC
We do not yet know the timeline but 2 years from start to finish is expected.
DST will need to put the effort required into this area of work without compromising commissioning of instruments nor the operational status of DMSC.
At the moment the plan is in flux but we have a very good level of details for our preferred solution.

## Slide 10: Plans for the rest of 2025
Server room – investigated solutions
Solution | Construction costs | TCO 20 years 75% load | Risk | Uncertainties
BII – building out the existing data center and extending the lease for that data center | 10.277 MEUR | 35.18 MEUR | High – lease cannot be extended beyond 2035 and termination notice is 2 years. This implies loss of investment. | Few related to landing an actual lease contract with BII
DTU modular | 9.205 MEUR | 27.1 MEUR | Low | Few – DTU delivered a very thorough concept.
Commercial data center | 3.159 MEUR | 29.19 | Low to medium since there are risks associated with depending on external providers | All prices are very uncertain since we have not gotten binding prices
ESS site modular | 8.9 to 11.7 MEUR | 25.19 to 27.87 MEUR | Medium to high when building on site. | Many costs are unknown

## Slide 11: Plans for the rest of 2025
Staff ramp up plans
DST aims to hire 2 full time positions and 1 student worker in 2025:
One position with competencies within virtualization, OpenStack and containerization.
One position with general HPC and scientific computing skills.
To mitigate lost effort from not being able to hire DST will implement the following initiatives:
  Continue to work with student workers and utilize them as much as possible.
  Seek to get acceptance for continue the existing student workers in 2025/2026.
  DST engages in masters projects and in relevant outreach activities to best leverage our new location at DTU to brand us as an attractive workplace.
  Working closely with the new Danish HR recruiter to fill the gaps.

## Slide 12: Plans for 2022 - 2027
Staff ramp up plans 2022 to 2027
Chart: Staff members 2022-2027
Actual staff members in DST | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4.25 | 4.5 | 4.5 | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.25 | 5.25 | 5.25 | 5.5 | 5.75 | 6.75 | 6.75 | 6.75 | 7.75 | 7.75 | 7.5 | 7.5 | 6.5

## Slide 13: Challenges
What keeps us awake at night
DST is facing 2 highly challenging issues:
Recruitment: DST has 2 open full-time positions and it has proven extremely difficult to attract viable candidates. While mitigated by recruiting student workers the impact is still significant. Two other full-time position has been filled since the April 2024 STAP though. However DST has not been fully staffed since 2020.
Hosting The future hosting situation for DMSC is becoming an increasingly important subject. DMSC has a lease until EOY 2026 for the COBIS server room which makes the schedule for an alternative solution pretty pressed. Also DST had a significant expansion of the COBIS server room planned, which has to be mitigated by utilizing the current site sever room for certain systems even though it is not fit for purpose.

## Slide 14: Challenges
Mitigation steps taken
DST has taken the following steps to mitigate the major challenges:
Recruitment:
  Recruited 2 student workers in 2024 to make up for lost effort.
  Engaged in talks directed towards students to promote DMSC and DST as a workplace
  Hired in a consultant for 3 months to make up for at least some of the lost effort.
  Co-supervising master thesis to promote DMSC and DST as a workplace.
  We are promoting training courses, conferences etc. to make DST attractive for current staff
  We are trying to let individuals work within their main areas of interest and promote engagement with external stakeholders and collaborators.
Hosting:
  DST is involved in the process for a new hosting solution.
  ESS Facility management is exploring possibilities for an on-site solution on the ESS site.
  DTU has produced a modular solution on the Lyngby campus.
  A temporary extension of the COBIS lease has been secured lasting until EOY 2026.

## Slide 15: Thanks for your attention