## Slide 1: Overview of Accelerator
SAR4
Ciprian Plostinar

## Slide 2: We’ve Built An Accelerator
ESS Site

## Slide 3: We’ve Built An Accelerator
G01

## Slide 4: A Long Journey
ISrc to Beam on Target
Beam: ISrc->LEBT
Beam: ISrc->LEBT->RFQ->MEBT
Beam: ISrc->LEBT->RFQ->MEBT->DTL1
Beam: ISrc->LEBT->RFQ->MEBT->DTL1->DTL4
19 Sep, 2018
26 Nov, 2021
1 Jun, 2022
20 Apr, 2023
2018
2027
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
SRR1
17 Jul, 2018
SRR2A
7 Sep, 2021
SRR2B
4 May, 2022
SRR3
22 Mar, 2023
SRR4
24 Feb, 2025
SRR TS2
29 Aug, 2019
First Beam through DTL1
1 Jun, 2022
First Beam through DTL4
20 Apr, 2023
First Beam through the RFQ
26 Nov, 2021
First Beam through the LEBT
19 Sep, 2018
SRR5
22 Sep, 2025
ACC RBOT
11 Jul, 2025
BOT
31 Oct, 2025
Facility RBOT
3 Oct, 2025
EOC
31 Dec, 2027

## Slide 5: ESS Accelerator
Overview
Parameter | Value
Ave power (design) [MW] | 5
Max energy (design) [MeV] | 2000
Peak current [mA] | 62.5
Pulse length [ms] | 2.86
Rep rate [Hz] | 14
Duty factor [%] | 4
RF freq [MHz] | 352.21/704.42
FC
Insertable stop

## Slide 6: Machine Configuration
Baseline

## Slide 7: Machine Configuration
Baseline
ACCELERATOR
All BOD/BOT technical scope
ICS
PSS, MPS, Controls, Software,
Etc.
ESH&S
SRR4, OHS, RP, REMS, Training, Security, Etc.
Eng./Infra.
Design & Engineering, Site support and services, IOM, IT, Etc.
Operations
MCR, WOO
Target
Tuning Beam Dump
Licence
SCL
Everything else
Quality, Engineering Management, Admin, Etc.

## Slide 8: ESS Accelerator Baseline Scope
ISrc
LEBT
RFQ
MEBT
HEBT
5 MW
MBL
SPK
DTL
HBL
Dump
Target
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
2000 MeV
ISrc
LEBT
RFQ
MEBT
HEBT
BOD/BOT
MBL
SPK
DTL
HBL
Dump
Target
870 MeV
BOD -> 2 MW

## Slide 9: Machine Configuration
Technical Baseline – ESS-5359878.9 – NCL

## Slide 10: Machine Configuration
Technical Baseline – ESS-5359878.9 – SCL SPK

## Slide 11: Machine Configuration
Technical Baseline – ESS-5359878.9 – SCL MBL

## Slide 12: Machine Configuration
Technical Baseline – ESS-5359878.9 – SCL HBL

## Slide 13: Machine Configuration
Technical Baseline – ESS-5359878.9 – HEBT

## Slide 14: Machine Configuration
Technical Baseline – ESS-5359878.9 – DmpL

## Slide 15: Machine Configuration
Technical Baseline – ESS-5359878.9 – A2T

## Slide 16: Machine Configuration
Technical Baseline – ESS-5359878.9 – PSS/ODH

## Slide 17: Machine Configuration
Technical Baseline – ESS-5359878.9 – BI

## Slide 18: Machine Configuration
Technical Baseline – ESS-5359878.9 – REMS

## Slide 19: Machine Configuration
Technical Baseline – ESS-5359878.9 – Infra/Site

## Slide 20: NCRs
35 In Progress

## Slide 21: SSCI2S
  OLC revision 14 applies for BOD
    ESS-0357253.14
  SCL Licence applies for BOD
    PSAR: ESS-0000002 rev 22
  For BOT the INP licence will apply.
  Between the SCL submission and the INP submission, the analysis and our general licence strategy improved and many systems listed as SSCs for BOD are not listed for BOT.
  ESS-5597859.1 clarifies beyond the OLC what these systems are.
  We need to find a way to navigate this period while maintaining safety and meeting regulatory requirements.
See ESS-0357253.14 and ESS-5597859.1

## Slide 22: SSCI2S
See ESS-0357253.14 and ESS-5597859.1

## Slide 23: Essential CCRs
See ESS-1085626 ESS Facility Change Log

## Slide 24: Energisation Status
  Many systems in ACC with temporary energisation.
  Effort ongoing to improve the documentation gap for permanent energisation.
  Not completed by SAR4, but progress has been made.
See Joakim’s talk

## Slide 25: Safety
  Since SAR3, NCL and SCL risk index files have been combined into a consolidated new risk index for the whole ACC.
  ESS-3878402.4 in review
  Probably needs a further revision before SRR4.
  The document needs to be continuously kept up to date.
ACC Risk Index - ESS-3878402

## Slide 26: Roadmap to SRR4 - Reviews
ESS-5489876

## Slide 27: Top Critical Path to ACC RBOT
Dec’24 Update
Holidays
ACC Critical Path
(October 2024)
Today
Dec
2025
Feb
Mar
Apr
May
Jun
24 Feb '25 - 10 Mar '25
SRR4
Beam Commissioning to Dump
11 Mar '25 - 19 May '25
30 Jun '25 - 11 Jul '25
ACC SAR5
2 Jan '25 - 10 Jan '25
SPK-IBS Testing
17 Apr '25 - 21 Apr '25
Easter 2025
Jul
11 Feb '25 - 24 Feb '25
SAR4
13 Jan '25
MPS_ID-SPK_IBS Interface Verification
14 Jan '25 - 10 Feb '25
MPSoS ACC SIT
SAR4 Approved
24 Feb '25
SRR4 Approved
10 Mar '25
ACC RBOT
11 Jul '25

## Slide 28: Planning 2025 – Assuming Summer CM Installation
3 MW Scope
Holidays
Commissioning Periods
Reviews
Today
Jan
Feb
Mar
Apr
May
Jun
Jul
24 Feb '25 - 10 Mar '25
SRR4
Beam Commissioning to Dump
11 Mar '25 - 19 May '25
17 Apr '25 - 21 Apr '25
Easter 2025
11 Feb '25 - 24 Feb '25
SAR4
8 Sep '25 - 19 Sep '25
Facility SAR5
22 Sep '25 - 3 Oct '25
Facility SRR5
6 Oct '25 - 10 Oct '25
System Permit
13 Oct '25 - 17 Oct '25
Beam Authorisation
31 Oct '25 - 31 Dec '25
Beam Commissioning to Target
Aug
Sep
Oct
Nov
Dec
21 Jul '25 - 8 Aug '25
Summer Maintenance 2025
3 Feb '25 - 4 Jul '25
6 CM Testing @TS2
2 Jun '25 - 6 Jun '25
Linac Cryo Warmup
2 Jun '25 - 13 Jun '25
Linac RP Cooldown Period
3 Feb '25 - 19 Sep '25
Cryo Controls
16 Jun '25 - 19 Sep '25
CM Installation/Testing
22 Sep '25 - 26 Sep '25
Linac Cooldown
3 Feb '25 - 30 May '25
CM/Infra Installation Preparation
3 Feb '25 - 26 Dec '25
RF Systems Installation and Testing in G02
SAR4 Approved
24 Feb '25
SRR4 Approved
10 Mar '25
ACC RBOT
11 Jul '25
Facility RBOT
3 Oct '25

## Slide 29: Beyond BOT
Dec’24 Update
Pre-BOT
Post-BOT
2025
2026
2027
Facility SAR5
Beam Commissioning to Dump after Facility RBOT
ACC Commissioning to Target + Test Beamline (post-BOT)
ACC, Target, NSS - Installation, Testing, Commissioning - Before BOT
Shutdown 1 (Instrument Install in Bunker)
Hot Commissioning 2
Users 1
2028
Shutdown 2 (Instrument Install in Bunker)
Hot Commissioning 3
Shutdown 3 (Instrument Install in Bunker)
Shutdown 4 (Instrument Install in Bunker + CM Install)
Recommissioning
Users 2
Hot Commissioning 1
Facility SRR5
System Permit BOT
Beam Authorisation BOT
Beam Commissioning to Dump
BOT
31 Oct '25
EOC
31 Dec '27
BOD
17 Mar '25
Facility RBOT
3 Oct '25

## Slide 30: To BOD and Beyond!