## Slide 1: Draft System Permit
SAR4
PRESENTED BY Yngve levinsen

## Slide 2: Content
  Draft scope definition of system permit for BOD
  Overall status of operational readiness, including startup checklists.

## Slide 3: What is the system permit
System permit marks start of an operational campaign (with radiological risks)
  Declaration that systems are ready for the planned campaign
    In particular SSCI2S
  Facility configuration baseline readiness
  The full review progress is completed, pre-start recommendations are addressed.
  Systems operations and monitoring is now coordinated through MCR
  Listing manuals & instructions, outstanding issues, tests, any missing systems, …
ESS-3682300 – currently rev 10 released Dec. 6th, for RF commissioning of SCL

## Slide 4: Operational Limits and Conditions
ESS-0357253 rev. 14
  Revision 14 valid for SCL License (Revision 17 current/INP submission).
  Need to carefully review revisions of references, not all are (immediately) compatible in recent revision
  Some additional documents will have two released versions while SCL license is used
  From Ops side before SRR4
    Updating old version of Handbook with “appropriate reference correction”
    Updating procedures (flow-charts) for MCR staff in emergencies (SRR-79)

## Slide 5: The Systems
  All systems with a relevant SSCI2S for SCL commissioning (as per SCL license)
  All systems included in current SCL RF commissioning permit (ESS-3682300 rev 10)
  Additionally
    Magnet systems and Power Supplies
    Machine Protection System
    Beam Diagnostics devices
    Tuning Beam Dump

## Slide 6: Template changes
  Instead of listing FBS nodes we will add a CIDL reference for each system
  A reference is needed which captures any SSCI2S for a system
  Pre-start checklist should be completed together with CR Ops before signing system permit for most systems

## Slide 7: What SSCI2S are there?
See also Joakim’s presentation..
  Explicitly in the OLC rev 14 directly, we have the table below
  Then you crawl SSC classification reports, RSFs …
  And we now have ESS-5597859 with just under 400 SSC listed (Thanks Ruji, Peter, Benjamin and others!)
  SCL license SSCI2S as baseline -> CCR -> 2-stage safety review (if needed) -> What we rely on
  CCR identified to need 2-stage review so far:
    ESS-5584795 – Masking of BLMs

## Slide 8: Pre-start checks status
Had meetings:
  Cryo
  Vacuum
  RF
  Others?
  Other BI?
  IOM (CWS, HVAC, …)?
  Timing?
  Tuning Beam Dump?
  To be scheduled:
  SRF
  Skids
  NCL cavities
  NCL ISrc/iris
  BI (BCM/BPM/FC)
  Magnets & power supplies
  Power systems & RFPS
For status&findings we refer to
system owners presentations
See OPS Confluence page for scheduling
Checklist available in ESS-5513661
~1 hour meeting with sys rep, CR Ops rep, optionally ICS rep

## Slide 9: MCR Training Program
W21
ACC HW
Modules, in progress
Completed
Completed
>BOD
< INP/SAR
TBD
Start-up
THE TRAINING
Systematic approach
Experience based
Teach to learn, learn to teach
W17
Big picture
W20
ACC HW
TBD
NSS HW
TBD
TD HW
W35
Admin
TBD/W35
Big Picture
Completed
Completed
After BoD
After BoD
Completed
Confluence page
ESS-5115994 – Training & Cert. Procedure
ESS-5505521 – Training programme details
SSM-2500 considered fully implemented for what we need for SRR4
- Should add one seminar on TBD operations
Notes: - This is the fourth week, and the last planned week before we start BoD
- Peo developed this extensive programme, we’ve come a long way since last year
- Programme is to teach how to operate, but also improve how we teach -> evaluation forms
- Some of the Big Picture content will come this week (e.g. MPS/PSS, cryo ops)
- Target, NSS will be postponed to after BoD- This week is what we call the “admin week”
- Thanks a lot to Arek and Benjamin for organising, together with great support from Kata!

## Slide 10: The operator tools - summary
  S&R functionality improvements
  SDS in testing
  RF Orchestration
  Sequencer tool in testing
  Fault Reporting Tool not in the state we would have preferred
SRR-67

## Slide 11: The end

## Slide 12: References
In no particular order..
  ESS-0357253 – Operational Limits and Conditions
  ESS-5359877 – Technical Excecution Baseline
  ESS-2070708 – ESS Procedure for System Permit
  ESS-0372700 – System permit template
  ESS-3682300 – System Permit (the actual decision/active permit)
  ESS-5597859 - SSCI2S List for SAR4 and SRR4
  ESS-5513661 – MCR pre-start checklist
  ESS-3821403 – Rules for Software Updates in Systems Supporting Accelerator
  ESS-5115994 – ESS Procedure for Training and Certifying MCR Shift Leaders and Operators
  ESS-5505521 – ESS Main Control Room Operators Training Programme
  ESS-5584795 - Global Masking of ICBLMs and nBLMs from FBIS during Beam on Dump (BOD) Commissioning

## Slide 13: Lesson’s learned summary
ESS-5590900
  Consider clarifying scope of the system
  Find a simpler way to list relevant systems
  Consider sectionizing sign-off of the system permit.
  Some systems were missed from system permit last time.
  Clearer CIDL & SSCI2S relevance. CIDL release not linked to (all) commissioning stages
  Allow time between finishing system tests and releasing CIDL
  System permit is very much focused around OLC; other safety aspects are not well captured. Administrative measures were not included. WRSF needs to be captured for INP.
  Too much focus on documentation
  Lack of verified baseline uncovered issues still to be closed.