## Slide 2: NCL Components: ISrc, RFQ, MEBT Bunchers, DTL’s, Accelerator Water Cooling
SAR-4
PRESENTED BY Domenic Nicosia TD-AD-L

## Slide 3: Agenda
1 Scope
2 System Status
3 Status of documentation (CIDL)
4 Known issues deemed OK to proceed
5 NCR’s & CCR’s
6 Does the system have any SSCI2S (rad safety) function?
7 Applicable codes and compliance (e.g required periodic inspections)
8 Describe briefly any tests needed with beam (and point to plan)
9 Have start up checklist been performed? Any issues found?
10 Have all recommendations from previous reviews (not just TRR) been addressed?

## Slide 4: 1. Scope
General Scope
NCL consist of Isrc, LEBT, RFQ, MEBT and DTL; together these systems provide proton beam generation, acceleration and transport.
Beam commissioning up to DLT4 FC completed in 2023, SRR3
Accelerator Cooling; Provided by 4 separate cooling skids;
CWS01 CWS02 CWS03 CWS04

## Slide 5: 2. System Status
System | FBS | Status
ISrc | ESS.ACC.E01 | Plasma Conditioning Ongoing Operatign with H2 Generator – ‘ATEX inactive’ HVPS – Initial Tests performed
RFQ | ESS.ACC.A01 | RF Conditioning Ongoing
MEBT Bunchers | ESS.ACC.W02.W01.C(01-03) | RF Conditioning Starting
DTL’s | ESS.ACC.A02.A(01- 05) | DTL’s 1-4 – RF Conditioning Ongoing DTL 5 – Installed, TRR completed, SAT-3 Completed, SIT-3 Ongoing, RF- Conditioning Ongoing
CWS01 – Isrc, LEBT, MEBT | ACC.E02.W01.E01 | Operational
CWS02 – CM’s, LWU’s, IBS, TBD | ACC.E02.W01.E02 | Operational
CWS03 - RFQ | ACC.E02.W01.E03 | Operational
CWS04 – DTL’s | ACC.A02.E05.E04 | Operational

## Slide 6: 2. System Status
RF - Conditioning

## Slide 7: 3. Status of Documentation (CIDLS)
Isrc - LEBT

## Slide 8: 3. Status of Documentation (CIDLS)
RFQ OS-0000008
MEBT OS-0000010
DTL OS-0000009
Accelerator Water Cooling OS-0000127

## Slide 9: 4. Known Issues
No known issues

## Slide 10: 5. NCR’s & CCR’s
No outstanding NCR’s
Addition of H2 Generator CCR ESS-4935524

## Slide 11: 6. Does the System have a SSCI2S Function
The following systems are classified as SSCI2S;
CWS01
CWS02
CWS03
CWS04
Isrc RF System and Fast Shutdown Unit
  These systems undergo periodic maintenance and MPS Testing

## Slide 12: 7. Applicable codes of compliance
‘AFS 2017:3 Användning och kontroll av trycksatta anordningar’.
Relevant to cooling skids with expansion vessels, large volume low pressure –
  No third party inspection required
  Periodic Inspection performed by IOM Process

## Slide 13: 8. Test with Beam
Yes, part of beam commissioning plan.

## Slide 14: 9. Have Start Up Checklists been performed, issues found?
Start up check lists have not yet been performed on NCL systems.
All RF cavities undergo interlock verification of RFLPS functionality prior to RF conditioning.

## Slide 15: 10. Have all recommendation from previous Reviews been addressed?
Recommendation from SAR3 to update ISrc Operations Manual – In Progress

## Slide 16: Finish presentation