## Slide 2: SAR4 Beam Instrumentation Status
PRESENTED BY Johan Norin

## Slide 3: SAR4 Beam Instrumentation Status
Scope description, Status, Open CCRs
System | Description | Status | Open CCRs
=ESS.ACC.B01.B01 | BCM - Beam Current Monitor | Ready | ESS-5536384 - Configuration Change of BCM Differential Pair Interlock
=ESS.ACC.B01.B02 | BLM – Beam Loss Monitors | Installed. Tests ongoing. | ESS-5264408 - Reducing BI scope for BOD due to late MTCA components ESS-5584795 - Global Masking of ICBLMs and nBLMs from FBIS during Beam on Dump (BOD) Commissioning
=ESS.ACC.B01.B03 | WS – Wire Scanners | DAQ: ready Motion: Debugging of found issues, tests in SCL WS ongoing | 
=ESS.ACC.B01.B04 | FC – Faraday Cups | LEBT, MEBT, DTL2: Ready DTL4 not installed | ESS-5584078 - DTL4 FC Masking from MPS during Beam on Dump (BOD) Commissioning
=ESS.ACC.B01.B05 | BPM – Beam Position Monitors | Ready | 
=ESS.ACC.B01.B06 | COLL - Collimators | Installed | ESS-5264410 - CCR - Removing some BI systems from the MPSID BOD scope
=ESS.ACC.B01.B07 | DPL - Doppler | Installed | 
=ESS.ACC.B01.B08 | EMU - Emittance measurement units | LEBT Installed MEBT ready | LEBT: ESS-5264410 - CCR - Removing some BI systems from the MPSID BOD scope
=ESS.ACC.B01.B09 | IMG - Imaging systems | Ready | 
=ESS.ACC.B01.B10 | IBS - Insertable beam stops | SPK ready | ESS-5238748 - Water cooling for SPK-010 and MBL-060 LWU insertable beam stops ESS-5584080 - MBL IBS Installation Deferral Until after BOD
=ESS.ACC.B01.B11 | LBM - Longitudinal bunch profile monitors | SPK installed MBL not installed | ESS-5264409 - Removing LBM system from BOT scope
=ESS.ACC.B01.B12 | APTM - Aperture monitors | Ready | 
=ESS.ACC.B01.B14 | PBI NPM - Non-invasive profile monitors | IPM – Ready FPM – LEBT partly ready | 
=ESS.ACC.W01.W02.R01 | LEBT Chopper | Ready | 
=ESS.ACC.W02.W01.R02 | MEBT Chopper | Ready | 

## Slide 4: SAR4 Beam Instrumentation Status
Additional questions
Status of documentation
Documentation for the systems can be found in FBS under the relevant instrument nodes. Verification results can be found one step down in FBS under the “control group” nodes. See also ACC CIDL.
Some test reports are not yet ready due to ongoing testing.
Describe briefly any tests needed with beam (provide link to plan)
For most systems, extensive tests are needed with beam. This is expected and normal for beam instrumentation systems. Test plans can be found in FBS under the respective instruments.
Know issues deemed OK to proceed
Have start up checklist been performed? Any issues found?
Start up checklists have not yet been performed. (confirm)
Have all recommendations from previous reviews (not just TRR) been adressed?
All recommendation are adressed or are in process of being adressed.

## Slide 5: SAR4 Beam Instrumentation Status
SS2I2C and Maintenance plans
Does the system have any SSCI2S (rad safety) function (if so link to maintenance plan)?
BCM: ESS-4973824 - PBI BCM maintenance plan, =ESS.ACC.B01.B01
Several systems are still listed as having SS2I2S functions, but are in the process of being removed from the list. The maintenance of the functions related to radiation safety for these systems are covered in the MPS documentation.
ESS-0213892 - MP-SoS Concept of Operations
ESS-3178302 - Beam Interlock System (BIS) Maintenance Manual

## Slide 6: Finish presentation