## Slide 2: SAR4 Beam Instrumentation Status
PRESENTED BY Johan Norin

## Slide 3: SAR4 Beam Instrumentation Status
Scope description, Status, Open CCRs
System | Description | Status | Open CCRs
=ESS.ACC.B01.B01 | BCM - Beam Current Monitor | Ready | ESS-5536384 - Configuration Change of BCM Differential Pair Interlock
=ESS.ACC.B01.B02 | BLM – Beam Loss Monitors | Installed. Tests ongoing. | ESS-5264408 - Reducing BI scope for BOD due to late MTCA components ESS-5584795 - Global Masking of ICBLMs and nBLMs from FBIS during Beam on Dump (BOD) Commissioning
=ESS.ACC.B01.B03 | WS – Wire Scanners | DAQ: ready (Tests w6-w7) Motion and scan applications in testing/debug phase. Software bugs have been found and are being addressed. Full optimization for motion controller parameters is pending. HEBT FWS: Ready (Tests w6-w7) | 
=ESS.ACC.B01.B04 | FC – Faraday Cups | LEBT, MEBT, DTL2: Ready DTL4 not installed | ESS-5584078 - DTL4 FC Masking from MPS during Beam on Dump (BOD) Commissioning
=ESS.ACC.B01.B05 | BPM – Beam Position Monitors | Ready | 
=ESS.ACC.B01.B06 | COLL - Collimators | Partly installed. | ESS-5264410 - CCR - Removing some BI systems from the MPSID BOD scope
=ESS.ACC.B01.B07 | DPL - Doppler | Installed | 
=ESS.ACC.B01.B08 | EMU - Emittance measurement units | LEBT Installed MEBT ready, (Tests w6-w7) | LEBT: ESS-5264410 - CCR - Removing some BI systems from the MPSID BOD scope
=ESS.ACC.B01.B09 | IMG - Imaging systems | HW Ready. IOC and OPI under development. | 
=ESS.ACC.B01.B10 | IBS - Insertable beam stops | SPK ready, (Tests w6-w7) MBL not installed | ESS-5238748 - Water cooling for SPK-010 and MBL-060 LWU IBS ESS-5584080 - MBL IBS Installation Deferral Until after BOD
=ESS.ACC.B01.B11 | LBM - Longitudinal bunch profile monitors | MEBT installed SPK not installed | ESS-5264409 - Removing LBM system from BOT scope
=ESS.ACC.B01.B12 | APTM - Aperture monitors | HW Ready. IOC and OPI under development. | 
=ESS.ACC.B01.B14 | PBI NPM - Non-invasive profile monitors | IPM – Ready, (Tests w6-w7) FPM – LEBT partly ready | 
=ESS.ACC.W01.W02.R01 | LEBT Chopper | Ready | 
=ESS.ACC.W02.W01.R02 | MEBT Chopper | Ready | 

## Slide 4: SAR4 Beam Instrumentation Status
Additional questions
Status of documentation
Documentation for the systems can be found in FBS under the relevant instrument nodes. Verification results can be found one step down in FBS under the control group nodes. See also ACC CIDL.
Some test reports are not yet ready due to ongoing testing.
Describe briefly any tests needed with beam (provide link to plan)
For most systems, extensive tests are needed with beam. This is expected and normal for beam instrumentation systems. Test plans can be found in FBS under the respective instruments.
Have start up checklist been performed? Any issues found?
Start up checklists have not yet been performed.
Have all recommendations from previous reviews (not just TRR) been adressed?
All recommendation are adressed or are in process of being adressed.
Are there open NCRs?
10344 – BCM Differential Pairs (Deviation from technical documentation)

## Slide 5: SAR4 Beam Instrumentation Status
SS2I2C and Maintenance plans
Does the system have any SSCI2S (rad safety) function (if so link to maintenance plan)?
  Aperture Monitor DumpLine (APTM)
  Imaging Systems DumpLine (IMG)
  Beam Current Monitors (BCMs)
  Beam Position Monitors (BPMs)
  Beam Loss Monitors (BLMs)
  Faraday Cups (FC)
  Insertable Beam Stops (IBS)
  LEBT & MEBT Chopper
Maintenance plans are covered in the PIL report ESS-3485880 - PIL report for Accelerator Beam Elements
The PIL assessment could not be done for APTM and IMG systems. This will be covered in an NCR (to be done by PSG).

## Slide 6: Finish presentation