## Slide 2: ICANS XXV
Integrated testing of the Neutron Factory - Planning, testing and Lessons Learned
PRESENTED BY ANTON LUNDMARK & Jaime arriagadA

## Slide 3: Agenda
1 Testing of the Neutron Factory
2 Lessons learned
3 Readiness for starting operation with proton beam

## Slide 4
Testing of the Neutron Factory
1

## Slide 5
  The Target station can be divided in the following functional units;
        Neutron factory -> divided in groups for commissioning purposes
        Maintenance systems; remote handling systems, casks and active cells
        HVAC & infrastructure
  The neutron factory consists of the systems required for neutron production
  Tuning beam dump (1068) is not part of NF as it is part of the accelerator operation
  LSS (1172) is not part of NS as it is part of instrument operation
5
Introduction – Neutron Factory concept
Target Group
Moderator Group
Monolith Group
NBEX Group

## Slide 6
WoW during testing w/o beam - The Target Group testing
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
TWDS
1000
From CF

## Slide 7
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
WoW during testing w/o beam - The Target Group testing

## Slide 8
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
“Option B”
“Option A”
WoW during testing w/o beam - The Target Group testing

## Slide 9
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
TMS
1063
HePu
1015
HeIn
1013
HePC
1011
HeWC
1016
HCPR
1160
For H20 PSV
“SERA compressor”
WoW during testing w/o beam - The Target Group testing

## Slide 10
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
TMS
1063
HePu
1015
HeIn
1013
HePC
1011
HeWC
1016
OBSERVATION:
Due to the turbo circulators are not available yet, an “option B” circulator has been
purchased, based on of-the-shell technology (screw compressor). This has imposed new
requirements to the group and the building, among others:
Extra water cooling (system 1016).
Extra room cooling and higher load on HVAC systems.
SERA compressor (system 1011) work continuously off-design.
Higher minimum helium flow required.
New control modules (ICS software).
Extra interlocks and control functions.
Development of extra OPI’s.
More complicated operation State Machine.
More cumbersome operation and manuals.
More maintenance needs.
Worsen work environment conditions (noise, heat).
+ Redundancy => higher availability & reliability.
HCPR
1160
For H20 PSV
WoW during testing w/o beam - The Target Group testing

## Slide 11
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
TMS
1063
HePu
1015
HeIn
1013
HePC
1011
HeWC
1016
TARGET GROUP
Option B
HCPR
1160
For H20 PSV
WoW during testing w/o beam - The Target Group testing

## Slide 12
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
TMS
1063
HePu
1015
HeIn
1013
HePC
1011
HeWC
1016
IAD
1031
DWD 1032
FM AIR
FM DW
FM N2
N2D
1033
PrHe
1030
SUPPLY SYSTEMS
A
A
A
A
W
N2
N2
He
He
He
Option B
HCPR
1160
TARGET GROUP
For H20 PSV
WoW during testing w/o beam - The Target Group testing

## Slide 13
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
FM WC
IWCT
1046
HeC
1010
TWDS
1000
From CF
TMS
1063
HePu
1015
HeIn
1013
HePC
1011
HeWC
1016
TARGET GROUP
IAD
1031
DWD 1032
FM AIR
FM DW
FM N2
N2D
1033
PrHe
1030
SUPPLY SYSTEMS
A
A
A
A
W
N2
N2
He
He
He
CDrT 1049
OffG
1140
IDrT
1047
HCPR
1160
EXHAUST SYSTEMS
Option B
TARGET GROUP
For H20 PSV
WoW during testing w/o beam - The Target Group testing

## Slide 14
WoW during testing w/o beam - The Target Group testing
IAD
1031
DWD 1032
TMS
1063
FM AIR
FM DW
FM N2
From CF
N2D
1033
CDrT 1049
OffG
1140
MPRS
1150
PrHe
1030
HePu
1015
HeIn
1013
HePC
1011
IDrT
1047
HCPR
1160
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Press. Ctrl Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
HeWC 1016 - Equipment cooling (circ & compr)
PrHe 1030 – Pristine Helium (filling St)
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
TMS 1063 – Target Monitoring System
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
FM Air: CF Instrument Air Supply
FM DW: FM Deionized Water Supply
FM WC: FM Water Cooling Supply
FM N2: FM Nitrogen Supply
A
N2
TWDS
1080
SIT2
TWDS
1080
SIT1
TWDS
1080
SIT3
HeWC
1016
HeMeas
1017
He
He
He
FM WC
IWCT
1046
HeC
1010
TWDS
1000
W
A
N2
A
SUPPLY SYSTEMS
TSS
A
For H20 PSV
For He PSV
Option B
EXHAUST SYSTEMS
TARGET GROUP
* 1150 part of
Monolith Group

## Slide 15
OPI Target System: systems 1000 and 1063

## Slide 16
OPI Target Helium cooling system: systems 1010, 1011, 1013, 1015, 1016 (and soon 1017)
System 1015
System 1010
System 1011
System 1013
System 1016
Option B
Option A
1046:W-006
1046:W-007
1046:W-008

## Slide 17
OPI Target Intermediate water-cooling system: system 1046 (3 loops)

## Slide 18: Testing status
SOT ONGOING
PREPARATION LOCAL TEST
NOT TESTED
SAT COMPLETED
SOT COMPLETED SYT ONGOING
SOT COMPLETED SYT COMPLETED
PREPARATION GROUP TEST 1
GROUP TEST 1 ONGOING
GROUP TEST 1 COMPLETED
LOCAL TESTING
INTEGRATED TESTING
SAT ONGOING
PREPARATION GROUP TEST 2
GROUP TEST 2 COMPLETED
LT DONE
GT DONE
NEUTRON FACTORY TESTING
NF ONGOING
NF COMPLETED
GROUP TEST 2
ONGOING

## Slide 19: NF test plan
The NF integrated test primarily serves to:
  Verify that all NF systems can be operated together.
  It is an opportunity to verify open issues from previous group tests.
  It is a “kind of” availability & reliability test, implying 24/7 operation during a prolonged period of time. The purpose here is:
          to identify if unplanned stops and trips occur,
          assess the NF current availability & reliability levels (without beam on target) compared to ESS global requirements.
Objectives

## Slide 20: NF test plan
Test cases and acceptance criteria
Test | Description | Acceptance criteria
Test 1: Closure of open issues from group tests | This phase of the testing serves the purpose to close open issues from previous tests, e.g. tests that may have not been finalized. Duration: 1 week. | All open issues that can have a negative impact on operation closed.
Test 2: Start-up of the NF | Test of start-up sequence from Maintenance mode to Production mode. The purpose is consolidating the proposed start-up sequence and to test operation procedures and administrative measures for start-up, together with MCR. Duration: 1 week, at least two start-ups performed. | The Neutron Factory started successfully without any trips or significant alarms.
Test 3: Shutdown of the NF | Test of shutdown sequence from Production mode to Maintenance mode. The purpose is to test operation procedures and administrative measures for shutdown, together with MCR. Duration: 1 week, at least two shutdowns performed. | The Neutron Factory successfully shut down and taken to Maintenance mode without any trips or significant alarms. Cooling down mode successfully performed.
Test 4: Long term steady state operation | Test of steady state operation. The purpose is to test that all systems are stable and reliable. Duration: 2 weeks. | The Neutron Factory successfully operated in stable steady state conditions without any significant alarms, during at least 10 consecutives shifts of uninterrupted operation.
Test 5: FAULT initiation | Simulate that one subsystem goes to FAULT an alarm in one subsystem. Verify that other subsystems react as intended. | Subsystems behave as intended according to control systems.
* Italic font = NF Operational Mode
* CAPITAL font = State Machine State

## Slide 21: NF test plan
  W45: cannot operate TW (due to electrical works) and therefore neither He cooling.
      Preparations
      Rest points from Group tests
  W46: start-up/shut-down seq. consolidation
  W47 : start-up/shut-down MCR procedures.
        MPS FIT.
        HVAC performance test
  W48: W48+49: 24/7 steady state operation.
        HVAC performance test
  W50: Fault initiation
        MPS FIT
        HVAC performance test
  W51: FIST-SIT
        HVAC Performance test
Schedule

## Slide 22
IAD
1031
DWD 1032
TMS
1063
CF AIR
CF DW
CF CWM
CF N2
From CF
N2D
1033
CDrT 1049
OffG
1140
MPRS
1150
PrHe
1030
HePu
1015
IWCT
1046
HeC
1010
TWDS
1000
HeIn
1013
HePC
1011
IDrT
1047
HCPR
1160
TWDS 1000 – Target wheel, Drive & Shaft
HeC 1010 – Target Primary Cooling
HePC 1011 – Pressure Control Primary Cooling
HeIn 1013 – Helium Injection
HePu 1015 – Helium Purification
1016 – Equip. cooling Tgt cooling circulators & compressor.
InsC 1026 – Neutron Beam Port Insert Cooling
AtOA 1028 – Neutron Beam Optic Assambly Atmosphere
PrHe 1030 – Pristine Helium
IAD 1031 – Instrument Air Distribution
DWD 1032 – Deionized Water Distribution
N2D 1033 – Nitrogen Gas Distribution
RGT 1040 – Radiolysis Gas Treatment
PWCM 1041 –Moderator Primary Water Cooling
PWCR 1042 – Reflector Primary Water Cooling
PWCS 1043 – Shielding & Plugs Primary Water Cooling
IWCL 1044 – Intermediate Water Cooling 15°C
IWCM 1045 – Intermediate Water Cooling 30°C
IWCT 1046 – Target Intermediate Water Cooling
IDrT 1047 – Intermediate Drain Tanks
PDrT 1048 – Primary Drain Tanks
CDrT 1049 – Contaminated Drain Tanks
WPuM 1050 – Water Purification Moderator
WPuR 1051 – Water Purification Reflector
WPuS 1052 – Water Purification Shielding & Plugs
Crs-CMS 1055 – Water Cooling H2 Pump
CWD 1057 – Cooling Water Distribution
Smpl 1059 – Sample Station
IrrM 1061 – Irradiation Module
PBIP 1062 – Proton Beam Instrumentation Plug
TMS 1063 – Target Monitoring System
PBW 1065 – Proton Beam Window
IS 1066 – Inner Shielding
CPMV 1067 – Covers, Penetrations & Monolith Vessel
PBWC 1070 – Proton Beam Window Cooling
PBWP 1076 – Proton Beam Window Port Block & Vessel
MPBP 1098 – Neutron Beam Port Block Package
Crs-CMS 1100 – Cryogenic Moderator System
MRP 1110 – Moderator Reflector Plug
MRRU 1112 – Moderator Reflector Roration Unit
Crs-TMCP 1120 – Target Moderator Cryo Plant
OffG 1140 – Off-gas extraction
MPRS 1150 – Monolith Pressure Relief System
HCPR 1160 – Helium Cooling Pressure Relief
CF Air: CF Instrument Air Supply
CF DW: CF Deionized Water Supply
CF WC: CF Water Cooling Supply
CF N2: CF Nitrogen Supply
N2
W
A
A
N2
He
TSS
1080
SIT2
TSS
1080
SIT1
TSS
1080
SIT3
HeWC
1016
HeMeas
1017
RGT
1040
IAD
1031
DWD 1032
CF AIR
CF DW
CF WC
CF N2
N2D
1033
IDrT
1047
CDrT 1049
IWCM
1045
PWCS
1043
CPMV
1067
MPRS
1150
Smpl
1059
OffG
1140
MPBP
1098
WPuS
1052
MRV
(1027)
InsC
1026
TMS
1063
IS
1066
PBIP
1062
PBWP
1076
PDrT 1048
from CF
ResFill
1078
SpentRes
1054
W
A
N2
W
A
A
Dry
1058
IAD
1031
DWD 1032
from CF
N2D
1033
IDrT
1047
CDrT 1049
IWCL
1044
Smpl 1059
PDrT 1048
OffG
1140
WPuM 1050
WPuR 1051
PWCR
1042
RGT
1040
PBWC 1070
MRP
1110
PBW 1065
PBIP
1062
IrrM 1061
Crs-TMCP (1120)
Crs-CMS (1055)
Crs-CMS (1100)
H2 fill St:
1107
CWD
1057
ResFill
1078
SpentRes
1054
W
A
PWCM
1041
A
W
W
A
PrHe
1030
CF AIR
CF DW
CF WC
CF N2
Dry
1058
Off-gas
1140
He
InsC 1026 – Neutron Beam Port Insert Cooling
PrHe 1030 – Pristine Helium
IAD 1031 – Instrument Air Distribution
OffG 1140 - Off-gas Extraction
NBOA T-Rex
NBOA NMX
NBOA Beer
NBOA C-Spec
NBOA Bifrost
NBOA Miracles
NBOA Heimdal
NBOA Loki
NBOA Freia
NBOA Odin
NBOA Dream
NBOA Vespa
NBOA skadi
NBOA Estia
1172
LSS
PWCS
1043
N2
W
A
A
from FM
Integration with PSS
PrHe
1030
InsC
1026
He
A
AtOA
1028
He
A
IAD
1031
CF AIR
TSS
1080
SIT4
1046
1011
1033
1046
1032
1046
1031
A
1010
1000
1031
1031
1033
1030
1011
He
He
1013
1015
1030
1030
CF CWH
D02
NEUTRON
FACTORY
TARGET GROUP
MODERATOR GROUP
NBEX GROUP
He
He
1030
1100
1041
1042
N2
1033
N2
1033
N2
1033
1040
1100
N2
1033
H2
1107
1100
1031
1031
1031
1032
1032
1041
1042
1044
1032
1041
1042
1044
MONOLITH GROUP
1027
1043
1045
1031
1031
1031
1043
1045
1032
1032
1033
N2
1033
1040
1043

## Slide 23
1068 – Tuning Beam Dump (TBD)
1069 – Tuning Beam Dump Shielding
ACC WCS02
Tuning Beam Dump testing - status
BoD
TBD & Shield
1068_1069
MPS
SAR4
SRR4
Integr.
Test
R

## Slide 24
1130 - TS HVAC - Room Environment Monitoring System
1131 - TS HVAC – Air Supply for C1, C2 and C3
1132 - TS HVAC - Air Exhaust from C1 and C2
1133 - TS HVAC - Process Control & Monitoring System
1134 - TS HVAC – Outlet of Exhaust Gases
1135 - TS HVAC – Air supply for C3
1136 - TS HVAC – Air exhaust from C3
1137 - TS HVAC – Air Exhaust from C4
1138 - TS HVAC Heating Water System
1139 - TS HVAC Cooling Water System
Off-gas extraction system
Target HVAC testing – status
HVRM
1130
(Step 1a – SOT)
HVH / HVC
1138-1139
(Step 2a - SOT)
HVH / HVC
1138-1139
(Step 2b - SyT)
HVSA / HVEA / HVEG / HVEC
1131-1132-1134-1137
(Step 3a & Step 5a - SOT)
HVSA / HVEA / HVEG
1131-1132-1134
(Step 3b - SyT)
HVSB / HVEB
1135-1136
(Step 4a - SOT)
HVSB / HVEB
1135-1136
(Step 4b - SyT)
HVEC / HVSA / HVEB
1137-1131b-1136b
(Step 5b - SyT)
OffG
1140
(Step 6 - LT)
HVRM
Final Balancing
(Step 7a)
HVRM
Stress Test
(Step 7b)
HVRM
Final Perf Test
(Step 7c)
Integr
Point
NF Test
Integr
Point
Precondition for operation with H2 in CMS
RESTPOINTS
Fire Dampers system
(OIM)
We have good evidence that the HVAC system has enough capacity for the D02 building, both flow and pressure cascade.
Issue in Active Cell, needs correction -> post BOT.
Fire protection system control logic, e.g. fire dampers, is under test now (needs to be tested for building acceptance) -> March ‘26.
Performance test and Stress test -> April ‘26.
R

## Slide 25
Lessons learned from Test and commissioning of the Neutron Factory
2

## Slide 26: Lessons learned
PBW at MUTS
System 1016:
Circulator
water cooling,
testing
Helium systems testing team,
start up circulator
HVAC balancing
Water systems
Running from
local
monitoring
room
26
The people!
Notes: RL-OK, My – ändrat document all till everything
Assess your current level of technical mastery for the system(s) you manage.
Share specific examples of how your expertise has helped you identify and resolve challenges or improve system performance.

## Slide 27: Lessons learned
Local indication
of the stem
position
Can we trust the position of the valve?

## Slide 28: Lessons learned
Everything looks good, but in reality…

## Slide 29: Lessons learned
Now we have a special color code to sign for communication lost (purple)

## Slide 30: Lessons learned
  Water system in the HVAC system.
  The system was supposed to be flushed and clean.
  We were supposed to be fill with a glycol/water mix, but for practical reasons we decided to start-up with only water.
  After 1 day of operation, inspection of filter showed that was not the case.
  Now the system is being flushed (again…). Time!
  Visual inspections, camera inspections can save time and money.
Cleanliness issues after installation

## Slide 31: Lessons learned
SERA compressor oil leakage
SERA compressor (support diaphragm compressor for keeping the helium pressure in the main helium cooling circuit to the target wheel).
Broken pipe due to high vibrations and fatigue.
Mitigated by changing process parameters and reinforcing the affected pipe support.
Vibration monitoring of this machine implemented.
More frequent inspections and maintenance than originally recommended by supplier.

## Slide 32: Lessons learned
MRP damaged
The ESS MRP is a highly integrated component, optimised for maximum brightness performance at 5 MW proton beam power.
The MRP 1 consists of two cold para hydrogen moderators that operates at a temperature of around 17K.
In addition, a thermal- and pre-moderator, a Beryllium reflector, steel frames (or outer reflectors) and steel supporting structures, which cooled with light water at around room temperature.
During commissioning without beam (25th Nov. 2025) cooling water to the MRP stopped due to external circumstances, while the cryogenic parts were at around 35 K. As a result, the water in the thermal- and pre moderator, which is in close vicinity to the cold moderator and the cryogenic supply and return pipes froze. The freezing of the water finally caused sever damages of the MRP 1 beyond the possibility of repair.
Freezing of the Moderator Reflector Plug 1
(MRP 1) at ESS, by Marc Kickulies
Wed April 15th 9:00 AM in Live 1

## Slide 33: Lessons learned
MRP damaged

## Slide 34: Engineering design of MRP-I
Freezing Risk
Pre-Moderator
Water channels/
water section
1
2
Cold Moderator (LH2 @20K)
1
2
3
3
4
Water flow
Water jacket
Thermal Moderator
4
Water-cooled reck
30
90
Ø 600
Cold moderator
Vacuum gap: 5 mm
46
Freezing of the Moderator Reflector Plug 1
(MRP 1) at ESS, by Marc Kickulies
Wed April 15th 9:00 AM in Live 1

## Slide 36: Lessons learned
MRP damaged
RCA executed that pointed out several aspects to be strengthen, both technical and procedural.
Mitigations ongoing to avoid similar incident sin the future:
  Start redundant pump
  Connect pump motors to UPS and diesel backup
  Implement additional emergency pump
  Supply water from high tank by gravity
Own lessons learned:
Prioritization of alarms to Main Control Room is of high importance
Integration of information from different systems is important.
  E.g, dedicated HMIs for monitoring health of critical components as a whole, not only at sub-system level
Automatize actions that have to be executed in a relatively short time, eliminate the human factor when required.
Spare parts of critical components (or lack of them) has big impact om availability -> mitigate through
prioritization based on availability also
Poster by Larissa Cunico
“Mitigations to the risk of water freezing in MRP”

## Slide 37
Readiness for operation with p+ beam
37
Procedures are good to have, but most important is to have competent people:
  A group of ambitious and dedicated System Owners (SO).
  A group of Target technicians is finally in place (5 target + 2 IOM).
  Training of these technicians is ongoing mainly through participation in the last stages of commissioning, actual maintenance activities and drills with typical components (e.g. exchange of helium filter, HRU testing, circulator operation, water cooling systems operation, HVAC balancing, etc.).
  We have a very experienced group of consultants that have participated in the target commissioning (most are Swedish “nuclear power plant” technicians/engineers) who are “mentoring” our technicians.
On-call preparation together
with ICS for NF test!!!
Spare slide

## Slide 38
Target commissioning – Helium circulator operation
9th of July, Target helium cooling system
In Bypass mode (w/o Target wheel
Connected).
Spare slide

## Slide 39
28th of August, Target helium cooling system
with Target wheel
connected.
Target commissioning – Helium circulator operation
Spare slide

## Slide 40
We have other important commissioning activities in parallel with the NF commissioning with beam:
  Cask commissioning- needed for maintenance and exchanges:
    Test and commissioning of all Casks configurations.
    Time demanding commissioning.
  ACF & remote handling commissioning, related to Waste handling procedures.
Tune-in and final balancing of the nuclear HVAC system in parts of D02 (ACF). Time demanding.
Reliability levels need to be established. Impact on Maintenance strategy, for instance:
  Develop a program for Condition Based Maintenance during the first operation years, based on operational data from hot commissioning.
  Take advantage of data driven tools, like AI for dynamic modelling, fault diagnostics, fault recognition and expert systems development (support to operators).
  Optimize the electricity consumption of the Target systems, etc.
Last, but not least: Finalize and update all the documentation, especially the operational documents.
40
Initial operation with p+ beam
Spare slide

## Slide 41: End