## Slide 1: Development status of the ESS cryogenic moderator system
European Spallation Source (ESS) ERIC, Lund, Sweden
Presented by Theodoros Vasilopoulos

## Slide 2: Introduction
ESS European Spallation Source
2026-04-15
2
5 MW beam (2.0 GeV proton, 62.5 mA) at 14 Hz (a pulse length of 2.86 ms.)
5 MW Proton beam
Moderator-reflector plug
Monolith vessel
- Parahydrogen fraction of more than 99.5%.
- Average temperature rise at each moderator < 3 K.
Cryogenic Moderator System (CMS)
- 18 K and 11 bar (Subcooled liquid hydrogen).
- Flow rate to each moderator >250 g/s
- Ortho/para hydrogen convertor (catalyst)
Target wheel
(Tungsten)
Proton beam
Q=6.7 kW
Q=10.5 kW
17.2 kW
Target
ESS hydrogen moderator requirements
Two hydrogen moderators
Q=4.0 kW
(3 MW)

## Slide 3: ESS Cryogenic Moderator System (CMS)
TMCP
(Target Moderator CryoPlant)
-Two compressors and three turbines.
- 30 kW at 15 K
-HP= 0.7 to 2.0 MPa
1 kg/s
CTL (300 m long)
CMS
18 K and 1.0 MPa
1 kg/s (250 g/s in each moderator)
436 liters
Bypassing the moderators during the commissioning
Target building
Accelerator building

## Slide 4: ESS Cryogenic Moderator System (CMS)
TMCP
(Target Moderator CryoPlant)
-Two compressors and three turbines.
- 30 kW at 15 K
-HP= 0.7 to 2.0 MPa
1 kg/s
CTL (300 m long)
Filling station
CMS
17 K and 1.0 MPa
1 kg/s
436 liters
Bypassing the moderators during the commissioning
2019
2019
2022
300m CTL
Nov., 2021
TMCP
valve box
CMS CBX
2023
CMS DB
Moderator
Vacuum vessel
H2 transfer lines
Jan. 2024
Feb. 2024
Bypass lines
Hydrogen filling station
Feb. 2024
May. 2024

## Slide 5: CMS commissioning
Hydrogen operation started since March 2025
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2024
2025
Phase 1 (58 days)
Phase 1 (21 days)
Phase 1
(11 days)
ESS water
system trip
2026
Phase 1 (20 days)
Phase 1 (12 days)
Phase 2 (7 days)
Phase 2 (25 days)
Phase 2 (11 days)
Phase 1 (38 days)
Moderators
connected
Heater and OPMS installed.
Helium operation
Hydrogen operation
Installation work
Vacuum pump
failure
Moderator issue
ESS water system trip due to power glitch
Phase 1
Phase 2
TMCP commissioning (without connecting the CMS) completed in December 2022.
CMS installation completed except for OPMS and the heater in January 2024.
- Due to delay of filling station and electrical cabinets.

## Slide 6: Automated CMS operation scheme
Under development

## Slide 7: Pressure fluctuation mitigation and thermal compensation
Why do the CMS consider them?
HX
Moderator
18 K
HX
Moderator
18 K
Proton beam on
Pressure rise
due to density increases
(expansion)
+2.5 K
If the heat load cannot be removed via HX,
the rise in supply temperature leads to an additional increase in pressure.
At SNS: 18 K and1.5 MPa (supercritical pressure)
HX
18 K
He refrigerator
Flow control
Heater
Bellows
(Accumulator)
At J-PARC: 18 K and1.5 MPa (supercritical pressure)
HX
18 K
Heater
Accumulator
Always 21.0 K
No impact on He refrigerator

## Slide 8: Pressure fluctuation mitigation and thermal compensation
In that case, at ESS…….
HX
TI87 18 K
Flow control by He refrigerator
CV860
CV870
CV850
Ambient He gas
TI200 21.5 K
TI300 17.0 K
+ CV870 (Return temperature:21.5 K
- Thermal compenstation
- Pressure rise mitigation
Buffer tank + CV29 + Recondenstation
CV29
Heater power was rapidly switched between 4.7 kW and 7.4 kW.
-> Simulating 2-MW proton beam operation.
TI62

## Slide 9: O/p H2 catalyst and in situ measurement by Raman spectroscopy
Parahydrogen fraction > 99.5%
Ortho/parahydrogen catalyst
In-situ ortho/parahydrogen ratio measurement system
- IONEX® Type OP
- Investigation of the adequate activation temperature
Measurement results of conversion efficiency at LN2 temperature.
Activation temperature =160
(Tatsumoto et al. 2025 Cryogenics 150 104106)
Catalyst activation and filling are planned for summer 2026.

## Slide 10: Automatic CMS shutdown triggered by failure
Vacuum pump stopped, on November 26, 2025

## Slide 11: Conclusions
Prior to hydrogen operation, preliminary CMS commissioning has been conducted using helium in 2024, and the first hydrogen cooldown was successfully completed in March 2025 without catalyst filling.
CMS is currently operated in semi-automatic mode, and ongoing performance tests aim to optimize operating conditions and establish procedures for automated control.
Dynamic heat load tests demonstrated that the buffer tank effectively suppress pressure fluctuations, and that the TMCP valve box compensated for heat load variations as designed.
During hydrogen operation at 18 K, a primary vacuum pump failure occurred, and the CMS shutdown sequence executed as designed, ensuring a safe and controlled system shutdown.
Preparations for the first beam-on-target operation are steadily progressing.

## Slide 12: Finish presentation Thank you for your attention