## Slide 1: Project Planning Update
14th Technical Board Meeting
Luisella Lari
Head planner for Accelerator & Senior Scientist
www.europeanspallationsource.se
September 23rd, 2015

## Slide 2: Outline
Budget per WPs + escalation budget.
Annual review top ten actions
   An update for ACCSYS planning.
P6 WP standardization for procurement.
Next steps/Conclusions.

## Slide 3: Budget per WP (1/4)
….Presented by M. Jakobsson/J. Brisfors

## Slide 4: Budget per WP (2/4)
~80%
~20%

## Slide 5: Budget per WP (3/4)
Planned + Possible IKC ~68%

## Slide 6: Budget per WP (4/4)
Budget escalation
Wrong actual tag for IK
Change of scope
Saved cost from AcCp
Cables/Racks
/cable
trays
Installation moved in WPs

## Slide 7: Annual Review 2015 (1/6)
1st of Top Ten actions:
Schedule: identify milestones with better visibility: i.e. Module-0, Production Readiness Review, anchor them clearer to the Installation….

## Slide 8: Annual Review 2015 (2/6)
….Presented at the TB in May
identify MS with better visibility
LEVEL 1B
PDR/CDR/TRR LEVEL 3
Added RFI for GSA and A2T

## Slide 9: Annual Review 2015 (3/6)
identify MS with better visibility & Reviews

## Slide 10: Annual Review 2015 (4/6)
identify MS with better visibility & monitoring
RFI Resulting from planning
RFI Committed/Reference dates
Reporting on LEVEL 2 MS floating
Reference dates monitored for LEVEL 3 MS (i.e. Review dates)

## Slide 11: Annual Review 2015 (5/6)
identify MS with better visibility & anchor them to installation
RFI MS is growing up from Annual Review 2015
 the goal is to have as resulting of planning all the RFI used by Eugene as input for the installation sequence.
Courtesy of Eugene
Today 70 % of RFI are in P6 with respect to Eugene list, excluding the BI

## Slide 12: Annual Review 2015 (6/6)
identify MS with better visibility & anchor them to installation
Steps to go trough in order to have
a mature installation plan
(working in close collaboration
with the Integration Team):
Match all the RFI used in Eugene installation sequence, as resulting of planning.
Move to the Project 11I in P6 to allocated resources.

## Slide 13: P6 WP standardization for procurement
ID for Procurement missing
Procurement support phase
Scope: fine-tuning of technical specifications, preparation and finalization of tender documents,
publication, evaluation, award decision, contract signature
Duration: <50K EUR = 4 weeks (min)
50K > 207K EUR = 8 weeks (min)
> 207K EUR = 20 weeks (min)
Done for WP16, work in progress for WP08, WP10, WP15

## Slide 14: Budget for 2016
First draft end of June/last version October the 4th.
Working in progress to review the TBC amount for procurement (in particular WP16 (fixed), WP07, WP12 and WP15 in progress).
2016 Budget for cash flow is saved

## Slide 15: Next steps/Conclusions
Moving into to a stable baseline resource loaded schedule for Accelerator (but still to be aligned to the new organization).
Moving into a more formal change control for AD (CHESS doc available in few days).
Moving into the first draft resource loaded installation schedule.

## Slide 16: Thanks for your attention! In particular I would like to thank L. Gunnarson

## Slide 17: In-kind in P6