## Slide 1: SKADI
Progress Update
PRESENTED BY Sebastian Jaksch, Sylvain Desert, Romuald Hanslik, Tadeusz Kozielewski, Annika Stellhorn, Tamires Gallo

## Slide 2: Progress since last STAP meeting
  Collimation shielding finalized
  Collimation tank finalized
  Chopper 2 mechanically installed
  Hutch installation being finalized
  Polarizer assembly TG3 in production
  Started compiling overall TG3 documentation (we now know what we need)
  Detector tube shipped and installed
  Out of bunker guides manufactured and shipped, installation imminent
  Detector housing large scale components manufactured
  New detector scientist started in DetGroup: Welcome Pavel
  Common projects progressed towards CR stage
Some of those are culminations of several workpackes and can amount to month of work

## Slide 3
Chopper System
FZJ
Sample Exposure System
Sample area, shielding
FZJ
Neutron detector system
Detectortube, detector vessel, shielding
LLB
Beam filtering system
Polarizer, Spin Flipper
FZJ
Beam extraction Sysystem
NBOA, BBG, Reflector
FZJ
Beam geometry conditioning
Collimation and apertures +shielding
LLB
Heavy shutter
FZJ
Installed,
In installation/storage,
In manufacturing
SKADI
Neutron Detector
FZJ
Housing ready Mid-2025
Installation of electronics into housing End-2025
Transfer to Lund until mid 2026
Hutch: nearly done
FZJ
CEP: installation ongoing
CUP: installation imminent
MCA: installation imminent

## Slide 4: Collimation
Installation done
Took a little time: A lot of coordination between MCA and AVS
Is mechanically working (now also electrically)

## Slide 5: Polarizer Assembly
Now going in stepwise installation, pending workshop availability
Shutter 2 in manufacturing, base in manufacturing, flanges in manufacturing, spin flipper in manufacturing
Hammering out details about spin-flipper power supply with Hal: Issue here is that the originally planned powersupply is not manufactured anymore

## Slide 6: Chopper
First chopper installed earlier this year
Second chopper in storage
Electronics not installed yet (no CEP)
However, Niko does not anticipate problems, since those are identical to the DREAM slow choppers

## Slide 7: Hutch
Just now under construction
Video available
CEP will start in August  permanent energetization possible?

## Slide 8: Detector Tube
Installation very impressive (video)
Vacuum excellent
Allowed for installation of hutch
Issue: Since we could not do all the MCA testing beforehand, the company handed this over, and we are now holding the risk if the inside motors do not work
  Details: Complicated LLB contract with SDMS

## Slide 9: Out of bunker guides
Installed in Collimation
Polarizer optics already in Jülich
Laminar flow tent for clean install available (to be shared with other instruments)

## Slide 10: Detector
Separate Presentation

## Slide 11: Common Projects
CEP
Installation started
CUP
CR done
Installation imminent
MCA
Installation scheduled early next year
Monitors
In-bunker installation done
Waiting for CR preparation
In general: Good communication
In particular: Sometimes prioritization can impact deliveries (see detector tube motors)
ECDC
Discussion on instrument control started

## Slide 12: Polarization setup: Polarizer + Analyzer
Pictures in courtesy of Hal Lee
3He Analyzer
Guide / Polarizer (FZJ)
Detectortube
Magnetostatic cavity
Qmax@3Å=0.11 Å -1
Uniform field coils
Qmax@3Å=0.74 Å -1
Polarizer (FZJ)
Analyzer (ESS) – current setup*
Sample
*Changes due to different magnet options shown on next page

## Slide 13: Polarization setup: Magnets
(i) Electromagnet (already purchased & available)
Specifications:
-2 to 2T
Field-ramp precision:
  0.01mT -1mT
  Depends on SE / controller
0-field precision: 0.02mT
No (half/full) PA possible
(ii) Planned to write grant proposals (such as RÅC) on:
  10T, symmetric, non-shielded magnet (no PA, STAP request)
  5-7T, asymmetric, shielded (full-PA)
    3He analyzer between magnet-detector
    Space-restrictions: remove nose + flat detector window
  >7T, asymmetric, shielded (full-PA)
    3He cell in detector vessel
    More spatial freedom at sample position
    Looking for suitable proposal partners

## Slide 14
2025
2026
TG5
No. 3 - Critical Path
(20 days TF)
No. 1 - Critical Path
(0 days TF)
No. 2 - Critical Path
(5 days TF)
Today
2025
2026
80 days
Integrated Cold Commissioning and TG5 preparations
70 days
Sep 2025 - Dec 2025
Polarizer Housing, Spin Flipper and Fast Shutter: Procurement and Manufacturing phase (FZJ)
61 days
Dec 2025 - Mar 2026
Polarizer Housing: Assembly (with optics and chopper) phase (FZJ)*
Q3
Q4
Q1
Q2
Q3
Q4
39 days
TG5 Closure of open points
17 days
Mar 2026 - Mar 2026
Polarizer, Spin Flipper, Fast Shutter and OoB Guides: Installation phase (FZJ, LLB & ESS)
Jun 2026 - Oct 2026
TG5 meeting
Oct 8
127 days
Dec 2025 - Jun 2026
MCA (including sub-systems): Installation, Energization and Commissioning phase
79 days
CEP installation
Oct 2026 - Dec 2026
93 days
Sep 2025 - Jan 2026
Detector Housing: Manufacturing and Assembly phase (FZJ)
56 days
Mar 2026 - Jun 2026
Detector: Installation and Commissioning phase (FZJ)
146 days
Sep 2025 - Mar 2026
Detector Integration (FZJ & ESS)
Sep 2025 - Dec 2025
Back into CP1 with 20 days float
Mar 31
TG5/SAR approval
Dec 2, 2026
Start of CC
Jun 17, 2026
Final TG3
Nov 28, 2025
Schedule
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
* Spin flipper and Fast shutter has 6 days float (testing in parallell to polarizer housings assembly)
Notes: 2025-09
Polarizer housing assembly delayed
2025-01
Detector housing manufacturing: moved out 2 months

## Slide 15: Breakout Detector Schedule
42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Reach out to Mundi airbox and electronics separately |  |  | TG3 | Presentation for Comparison between RMM and Switch Option |  |  | Shipping of airbox to Lund |  |  |  |  |  |  | airbox installation into tube (Sylvain with Technician, Egi) |  |  |  |  |  | End of tests before delivery/Prepare shipment |  |  |  |  | Delivery | Installation |  |  | 
 | Sebastian prep overall TG3 |  |  |  |  |  |  | SNS data article arxiv |  |  |  | Clarify availability for Pavel visit to Jülich |  |  |  |  |  |  |  | Qgate needed - for Tile |  |  | IRR Tiles |  |  |  |  |  | 
 |  |  |  |  |  | Qgate for airbox |  | SAT/FAT protocol definition |  |  |  |  |  | IRR for airbox |  |  |  |  |  |  |  |  | BOT landing zone |  |  |  |  |  | 

## Slide 16: Discussion points
Currently doing mostly installation and TG3

## Slide 17: Welcome new team member
New IOE: Tamires Gallo