## Content
FBS/LBS Tag | Name | Title | State | CI Type | Revision | Version | Released Date | Owner | Planned Completion Date | Planned to be completed by which Milestone | Project | REMARKS
| OS-0000122 | NSS Shielding and Safety System CIDL | Preliminary | Object Selection CI | 2 |  |  | Robert Connatser
=ESS.NSS.F01 | ESS-0059230 | Shielding & Safety Systems | Released | Sub-Item | 2 |  | Nov 10, 2025 | Robert Connatser | - | - | -
| ESS-0108886 | System Requirements Specification - Shielding and Safety Systems | Preliminary | Document | 1 | 7 |  | Mark Ridgley (Inactive) | 2027-01-01 |  | NSS | Not urgent to complete since all design etc are done. But they should be updated to give a clear view of the system
| ESS-1104056 | System Verification Plan - Shielding and Safety Systems | Preliminary | Document | 1 | 2 |  | Mark Ridgley (Inactive) | 2027-01-01 |  | NSS | Not urgent to complete since all design etc are done. But they should be updated to give a clear view of the system
| ESS-0108883 | Concept of Operations - Shielding and Safety Systems | Preliminary | Document | 1 | 7 |  | Mark Ridgley (Inactive) | 2027-01-01 |  | NSS | Not urgent to complete since all design etc are done. But they should be updated to give a clear view of the system
=ESS.NSS.H01.BEER.A01.F01 | ESS-2512422 | Shielding | Released | Sub-Item | 1 |  | Oct 29, 2025 | Premek Beran | - | - | -
| ESS-5866644 | SAT BEER Guide Shielding | Review | Document | 1 | 7 |  | Senad Kudumovic | 2025-12-01 | 4AN-2/2, before SAR Report | NSS
=ESS.NSS.H01.BEER.A01.W02.WH01 | ESS-3885824 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 10, 2025 | Premek Beran | - | - | -
| ESS-5765694 | Local Test Report (SAT) BEER Beam Extraction System | Preliminary | Document | 1 | 8 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.CSPEC.A01.F01 | ESS-2169373 | Neutron Guide Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Daria Noferini | - | - | -
| ESS-5866642 | SAT CSPEC Guide Shielding | Review | Document | 1 | 4 |  | Senad Kudumovic | 2025-12-01 | 4AN-2/2, before SAR Report | NSS
| ESS-0511527 | C-SPEC - Radiation Safety Analysis | Preliminary | Document | 1 | 1 |  | Fernando Yamil Moreira | 2027-09-29 | CSPEC: i-SRR | NSS
=ESS.NSS.H01.CSPEC.A01.W02.WH01 | ESS-3885945 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Daria Noferini | - | - | -
| ESS-5765743 | Local Test Report (SAT) C-SPEC Beam Extraction System | Preliminary | Document | 1 | 12 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.DREAM.A01.W02.WH01 | ESS-3887036 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Florence Porcher | - | - | -
| ESS-5765758 | Local Test Report (SAT) DREAM Beam Extraction System | Preliminary | Document | 1 | 8 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.ESTIA.A01.W01.W01.WH02 | ESS-5314270 | Bunker Wall Feedthrough | Released | Sub-Item | 1 |  | Nov 11, 2025 | Joshaniel Cooper | - | - | -
| ESS-5856532 | SAT BWI | Preliminary | Document | 1 | 1 |  | Felix Villacorta | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.ESTIA.A01.W02.WH01 | ESS-3886057 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Joshaniel Cooper | - | - | -
| ESS-5765755 | Local Test Report ESTIA Beam Extraction System | Preliminary | Document | 1 | 3 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.FREIA.A01.F01 | ESS-3886132 | Neutron Guide Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Thomas Arnold | - | - | -
| ESS-1264853 | FREIA - Radiation Safety Analysis | Preliminary | Document | 1 | 3 |  | Thomas Arnold | 2027-05-28 | FREIA: i-SRR | NSS
=ESS.NSS.H01.FREIA.A01.R03.R01 | ESS-3886137 | INSTRUMENT Safety Shutter | Released | Sub-Item | 2 |  | Nov 10, 2025 | Thomas Arnold | - | - | -
| ESS-5063387 | Freia Heavy Shutter Drawings | Preliminary | Document | 1 | 3 |  | Jon Elmer | 2025-12-01 | 4AN-2/2 | NSS
=ESS.NSS.H01.FREIA.A01.W01.W01.WH02 | ESS-5288169 | BWI - Bunker Wall Insert | Released | Sub-Item | 1 |  | Nov 11, 2025 | Thomas Arnold | - | - | -
| ESS-3864660 | Freia: Sub-System Design Desscription for 13.6.11.1.2 Beam Delivery System | Preliminary | Document | 1 | 8 |  | Clara Ines Lopez | 2027-05-28 | FREIA: i-SRR | NSS
| ESS-5572001 | SAT BWI | Preliminary | Document | 1 | 1 |  | Clara Ines Lopez | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.FREIA.A01.W02.WH01 | ESS-3886155 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Thomas Arnold | - | - | -
| ESS-3864660 | Freia: Sub-System Design Desscription for 13.6.11.1.2 Beam Delivery System | Preliminary | Document | 1 | 8 |  | Clara Ines Lopez | 2027-05-28 | FREIA: i-SRR | NSS
| ESS-5765754 | Local Test Report (SAT) FREIA Beam Extraction System | Review | Document | 1 | 6 |  | Fredrik Stjärnqvist | 2025-12-01 | 4AN-2/2, before SAR Report | NSS
=ESS.NSS.H01.HEIMD.A01.F01 | ESS-2512235 | Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Siamak Kianzad | - | - | -
| ESS-0434221 | HEIMDAL - Radiation Safety Analysis | Preliminary | Document | 1 | 1 |  | Dan Mannix | 2027-07-13 | HEIMDAL - TG5/SAR | NSS
=ESS.NSS.H01.HEIMD.A01.R03.R01.R01 | ESS-5906117 | Heavy Shutter | Released | Sub-Item | 1 |  | Nov 11, 2025 | Siamak Kianzad | - | - | -
| ESS-5299821 | HEIMDAL Heavy Shutter - Design Description | Preliminary | Document | 1 | 6 |  | Bengt Jönsson | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.HEIMD.A01.W02.WH01 | ESS-3886270 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Siamak Kianzad | - | - | -
| ESS-5765752 | Local Test Report (SAT) HEIMDAL Beam Extraction System | Preliminary | Document | 1 | 7 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.MAGIC.A01.W02.WH01 | ESS-3886376 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Denis Vasiukov | - | - | -
| ESS-5765750 | Local Test Report (SAT) MAGIC Beam Extraction System | Preliminary | Document | 1 | 7 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.MIRAC.A01.F01 | ESS-2512342 | Neutron Guide Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Pascale Deen | - | - | -
| ESS-3235269 | MIRACLES - Radiation Safety Analysis | Preliminary | Document | 1 | 1 |  | Felix Villacorta | 2027-07-08 | MIRACLES: i-SRR | NSS
=ESS.NSS.H01.MIRAC.A01.W01.W01.WH02 | ESS-5283264 | Bunker Wall Insert (feedthrough) | Released | Sub-Item | 1 |  | Nov 11, 2025 | Pascale Deen | - | - | -
| ESS-4894096 | Final Design Report MIRACLES BWI | Preliminary | Document | 1 | 1 |  | Felix Villacorta | 2025-12-15 | 4AN/2 | NSS
| ESS-5856532 | SAT BWI | Preliminary | Document | 1 | 1 |  | Felix Villacorta | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.MIRAC.A01.W02.WH01 | ESS-3886476 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Pascale Deen | - | - | -
| ESS-5765749 | Local Test Report (SAT) MIRACLES Beam Extraction System | Review | Document | 1 | 10 |  | Fredrik Stjärnqvist | 2025-12-01 | 4AN-2/2, before SAR Report | NSS
=ESS.NSS.H01.NMX.A01.F01 | ESS-0761486 | Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Justin Bergmann | - | - | -
| ESS-5866647 | SAT NMX Guide Shielding | Review | Document | 1 | 6 |  | Senad Kudumovic | 2025-12-01 | 4AN-2/2, before SAR Report | NSS
=ESS.NSS.H01.NMX.A01.W02.WH01 | ESS-1074713 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Justin Bergmann | - | - | -
| ESS-5765689 | Local Test Report NMX Beam Extraction System | Preliminary | Document | 1 | 9 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.SKADI.A01.F01 | ESS-3865552 | Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Sebastian Jaksch | - | - | -
| ESS-5878375 | Skadi - Shielding SAT | Review | Document | 1 | 2 |  | Sylvain Desert | 2025-12-01 | 4AN-2/2, before SAR Report | NSS
| ESS-5282259 | Shielding Analysis Report for the Collimator of SKADI | Preliminary | Document | 2 | 6 |  | Sebastian Jaksch | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.SKADI.A01.R03.R01 | ESS-3865557 | Instrument Shutter 1 (Heavy) | Released | Sub-Item | 2 |  | Nov 10, 2025 | Sebastian Jaksch | - | - | -
| ESS-5636423 | SKADI-Safety_shutter 1_Operation and Maintenance Manual | Preliminary | Document | 1 | 1 |  | Romuald Hanslik | 2025-12-15 | 4AN/2 | NSS | There are multiple copies of the manual.
| ESS-3731307 | SKADI Safety shutter1 (Heavy Shutter) Subsystem Design Description | Preliminary | Document | 3 | 1 |  | Romuald Hanslik | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.SKADI.A01.W01.W01.WH02 | ESS-5865612 | Bunker wall Insert | Released | Sub-Item | 1 |  | Nov 11, 2025 | Sebastian Jaksch | - | - | -
| ESS-3919918 | DM--DT-DEDD------SKADI in Bunker and Bunker wall feedthrough design report.pdf | Preliminary | Document | 1 | 1 |  | Sebastian Jaksch | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.SKADI.A01.W02.WH01 | ESS-3865563 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Sebastian Jaksch | - | - | -
| ESS-5765756 | Local Test Report (SAT) SKADI Beam Extraction System | Preliminary | Document | 1 | 6 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.T-REX.A01.F01 | ESS-2512271 | Neutron Guide Shielding | Released | Sub-Item | 2 |  | Nov 10, 2025 | Pascale Deen | - | - | -
| ESS-0457181 | T-REX - Radiation Safety Analysis | Preliminary | Document | 1 | 1 |  | Nicolo Violini | 2027-12-08 | T-REX: i-SRR | NSS
=ESS.NSS.H01.T-REX.A01.R03.R01 | ESS-3886573 | Instrument Safety Shutter | Released | Sub-Item | 2 |  | Nov 10, 2025 | Pascale Deen
| ESS-4020799 | OPERATION AND MAINTENANCE MANUAL OF THE T-REX HEAVY SHUTTER | Preliminary | Document | 1 | 1 |  | Nicolo Violini
=ESS.NSS.H01.T-REX.A01.W01.W01.WH01 | ESS-3886585 | Neutron Guide | Released | Sub-Item | 1 |  | Nov 11, 2025 | Pascale Deen | - | - | -
| ESS-0457247 | T-REX - Sub-System Design Description - Beam Transport and Conditioning | Preliminary | Document | 1 | 1 |  | Marcel Serwe | 2027-12-08 | T-REX: i-SRR | NSS
=ESS.NSS.H01.T-REX.A01.W01.W02.WH02 | ESS-5911616 | BWI - Bunker wall insert | Released | Sub-Item | 1 |  | Nov 11, 2025 | Pascale Deen | - | - | -
| ESS-5864488 | T-REX bunker wall insert SAT protocol | Preliminary | Document | 1 | 2 |  | Marcel Serwe | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.T-REX.A01.W02.WH01 | ESS-3886590 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Pascale Deen | - | - | -
| ESS-5765751 | Local Test Report (SAT) T-REX Beam Extraction System | Preliminary | Document | 1 | 6 |  | Fredrik Stjärnqvist | 2025-12-15 | 4AN/2 | NSS
| ESS-5864488 | T-REX bunker wall insert SAT protocol | Preliminary | Document | 1 | 2 |  | Marcel Serwe | 2025-12-15 | 4AN/2 | NSS
=ESS.NSS.H01.VESPA.A01.W02.WH01 | ESS-3886690 | NBOA - Neutron Beam Optics Assembly | Released | Sub-Item | 1 |  | Nov 11, 2025 | Adrien Perrichon | - | - | -
| ESS-4986595 | SN18054-SSAR42440A-1-00 VESPA NBOA Units SAT final 09-10-2022 | Preliminary | Document | 1 | 1 |  | Jim Nightingale | 2025-12-15 | 4AN/2 | NSS
| ESS-5765757 | Local Test Report (SAT) VESPA Beam Extraction System | Review | Document | 1 | 5 |  | Fredrik Stjärnqvist | 2025-12-01 | 4AN-2/2, before SAR Report | NSS