## Slide 1: The challenging step of getting a license for commissioning a proton accelerator in Sweden
Leif Spanier
Radiation safety engineer
www.europeanspallationsource.se
12th November 2015

## Slide 2: Outline
Application process
Next application
Alternative application format
Application for commissioning
Summary

## Slide 3: Time schedule and scope
Optimization of the time schedule for the SSM application
When do we need the permission
  Accelerator division first in line to install equipment that may produce ionizing radiation or radioactive material
    Planned to September 2017
When do we have to send in the application
  SSM needs one year to review the application
    SSM review should start latest in September 2016
  Need some margin for additional information requested by SSM
    Planned to submit the application in April 2016
Accelerator division needs to do step wise installation and commissioning of the accelerator
  ESS will also apply for commissioning (test operation) of the low energy part (warm part) of the accelerator
This combination will assure that the overall ESS time schedule is not compromised by the later date of the application.

## Slide 4: Graded approach SSM – Revised Schedule
General and conceptual information, enabling SSM to set the requirements
Permit and conditions for building a spallation source
Permit for installation of equipment that can generate ionising radiation and low energy test operation
Permit for test operation
Permit for permanent operation
Permit for De-commissioning
Reports and analyses showing that ESS is expected to fulfill the requirements and are fulfilling the req. for test oper.
Experience from test operation and maintenance incorporated in verifying analyses
Reports and analyses verifying that ESS fulfills the requirements
Experience from operation incorporated in the de-commissioning plan
1
3
4
5
ESS
SSM
Phase
2014
PSAR 2016-04
PSAR 2012 + amendments
SAR 2017
Ground break 2014
Installation of Equipment and Test op. 2017
Commissioning
- Acc 2018
- Target 2019
Operation
2025 - 2065
Decomm.
2065-2070
FSAR
2017
2018/2019
SAR-Decomm
2025
2065
2

## Slide 5: Structure of next Application ”Installation and limited commissioning”
Official letter
1 page
PSAR
Fulfillment of requirements
Structure according to the Permit, app 1, chapter 1
Status report
How we per topic deal with review comments given in Permit, app 4:
- Building design
- Facility design
- Components in beam line
- Physical protection
- Rad waste issues
- Releases
- etc
References
Safety review
Report describing how ESS have reviewed the content of the application.
Described by ESS-0034327
Structure of application is derived from the SSM Permit (ESS-0018828, ESS-0015358)
Structure and content of the PSAR is communicated internally and agreed at SAG, EPG and with CEO
Accepted by SSM (ESS-0039660)

## Slide 6: Content of the PSAR
Introduction
Site
Design rules
Description of facility and function
Source terms
Emissions
Radioactive waste
Radiation protection
Operation of the facility including limited commissioning of accelerator
Analysis of operating conditions
References
Drawings

## Slide 7: Alternative application format for the accelerator
ESHAC recommends to apply DOE approach for the accelerator
  Linked to the 2013/59/Euratom directive, The Basic Safety Standard
DOE Order 420.2C - Safety of accelerator facilities
Parts that may be applicable for the accelerator
  Safety Assessment Document, SAD
    Description of the facility
    Identification and analysis of hazards associated with its operation
    Use the Hazard analysis process to identify the safety systems
  Accelerator Safety Envelope, ASE
    High-level safety document defining physical and administrative bounding conditions and engineered credited controls to ensure safe operation
    Based on the safety analysis of the SAD
DOE facilities shall have approved documents before commissioning starts
SSM have noted that this approach is acceptable for the accelerator if the conditions in the permit are fulfilled
If accelerator apply the DOE approach the documents should focus on radiation safety and accelerator specific issues

## Slide 8: Possible structure of the PSAR in next Application ”Installation and commissioning”
SAD
ASE
Other Template
SEMP Template
Commissioning
PSAR
Fulfillment of requirements
Structure according to the Permit, app 1, chapter 1
Commissioning program
May be stepwise
May be a separate document (preferred by SSM)
References
SEMP Templates
Concepts of Operation
System Requirement Specification
System Architecture Description
System Design Description
Interface Description
System Maintenance manual

## Slide 9: Commissioning program
The commissioning program shall describe the commissioning of the accelerator low energy part
Examples of information that are relevant (some for each step)
  Equipment to be commissioned
  Commissioning procedure
  Programme for verification of fulfillment of design requirements
  Beam characteristics (e.g. energy, power, pulses)
  Hazards and hazard analysis for commissioning
  How to handle possible events and circumstances
  Safety functions to be in operation (e.g. PSS)
  Administrative controls to be applied (e.g. instructions and procedures)
  Physical and administrative bounding conditions
  Radiation protection
  Ionizing radiation characteristics (e.g. type, dose rate, max dose rate)
  Produced radioactive material (e.g. beam dumps)

## Slide 10: Summary
Application for installation of
  All equipment that may produce ionizing radiation
  All equipment that may be activated or contain radioactive material
  All radiation safety systems
Application for commissioning of the low energy part of the accelerator
  Ion Source to Drift Tube Linac
The DOE process may be applied for the accelerator as long as the requirements of SSM are fulfilled

## Slide 11
Thank you
Questions

## Slide 12: Applications for test stands
The application for the test stands will be made according to a simplified procedure described in ESS-0027406