## Slide 1: MAGIC ICEB
Critical paths, schedule adherence etc.

## Slide 2: Completing design for T2T3 instruments
28 meetings held Sep 25 to Feb 26
Chart: CTV/IDR/sub-TG3 Sep 2025-Feb2026
| CSPEC | ESTIA | FREIA | HEIMDAL | MAGIC | MIRACLES | SKADI | TREX | VESPA
 | 3 | 2 | 2 | 5 | 8 | 1 | 1 | 4 | 2

## Slide 3: TG5 slip chart
Note: For T2T3, tracking starts after replanning close-out. Vespa has TG5 in May 2029. Once TG5 is approved, the instrument will be removed from tracking.
,
NMX
ODIN,
DREAM ESTIA
MAGIC
BEER
SKADI
MIRACLES,
HEIMDAL
FREIA
CSPEC TREX
Data from P6 MARCH 2026 lock down
TG5/SAR approved.
(iSRR held, approval pending)
TBL
LOKI,
BIFROST

## Slide 4
2025
2027
No. 4 - Critical Path
(18 days TF)
No. 2 - Critical Path
(2 days TF)
No. 3 - Critical Path
(8 days TF)
No. 1 - Critical Path
(0 days TF)
Today
2025
2026
2027
49 days
Jul 2026 - Sep 2026
RC and Oscillation (including support): Installation phase
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
38 days
Oct 2026 - Nov 2026
MCA (including sub-systems): Energization and Commissioning phase
111 days
Sep 2025 - Feb 2026
Sample Stage: Design phase (LLB)
80 days
Feb 2026 - May 2026
Sample Stage: Procurement and Manufacturing phase (LLB)
36 days
May 2026 - Jul 2026
Sample Stage: Installation phase
78 days
Jul 2026 - Oct 2026
MCA (including sub-systems): Energization and Commissioning phase
74 days
Sep 2025 - Dec 2025
OoB VH+Supp: Design phase (LLB)
276 days
Sep 2025 - Sep 2026
OoB VH+Supp: Procurement and Manufacturing phase (LLB->ESS)
47 days
Sep 2026 - Nov 2026
OoB Guides + VH + Supp: Installation phase
98 days
Sep 2025 - Jan 2026
Oscillation of RC: Design phase (LLB)
136 days
Jan 2026 - Jul 2026
Oscillation of RC: Procurement and Manufacturing phase (LLB)
110 days
Sep 2025 - Jan 2026
Support for Analyzer and Det B: Design phase (LLB)
116 days
Feb 2026 - Jul 2026
Support for Analyzer and Det B: Procurement and Manufacturing phase (LLB)
89 days
Jul 2026 - Nov 2026
Supports (Analyzer and Det B) and Analyzer seg 1: Installation and Commisioning phase (LLB)
TG5/SAR approval
Apr 28, 2027
Start of CC
Nov 26, 2026
Final TG3
Apr 21, 2026
Magic Critical Paths
Data from P6 September 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Note: 2nd segment of Analyzer is part of the instrument scope but currently not linked to TG5 in P6
No big shift in TG5 from April to September BUT there’s a big difference in the amount of float between the different paths. Schedule has been compressed.
To note: transferring procurement from ESS to LLB for the OoB VH has been put in place as a mitigation
Notes: 2025-09
OoB VH 1 month delayed
SF 1 month delayed
Sample stage 1 month delayed
Supports RC + Det A 1 month delayed
Supports An + Det B 1 month delayed
RC 5 months delayed
Oscillation 1 month delayed
Good lift 1 month delayed
Beamstop 1 mont delayed
2025-06
OoB VH Deisgn delayed with 1 month. Manufacturing to more realistic estimates delayed with 5 months (procurement transferred to ESS, if it hadn’t been, we had seen even bigger delays)
Sample stage design delayed with 1 month.
2024-04
IB guide and VH + Support on the critical path
2025-03
Polarizer design + 2 month
Supports for RC + Det A + 1 months
2025-02
Polarizer design + 1 month
Oscillation design+ 2 months
Sample stage design+ 3 months
2024-12
LLB desinger: RF Spin flipper + OoB Vh suppoert
Mortiz + desgin pool: supports A and B
Danielle: elevated platform
LLLB 2: sample stage

## Slide 5
2026
2027
No. 1 - Critical Path
(0 days TF)
No. 2 - Critical Path
(5 days TF)
No. 3 - Critical Path
(5 days TF)
No. 4 - Critical Path
(11 days TF)
No. 5 - Critical Path
(11 days TF)
Today
2026
2027
Q1
Q2
Q3
Q4
Q1
Q2
128 days
False floor: Procurement and Installation phase
30 days
Dec 2026 - Jan 2027
Det A and Det B: Integrated testing
5 days
Jan 2027 - Jan 2027
Final Integrated testing
Mar 2026 - Aug 2026
126 days
Mar 2026 - Aug 2026
OoB VH+Supp: Manufacturing phase sections 1, 5 and 3 (LLB)
26 days
Aug 2026 - Oct 2026
MCA & CEP: Rack installation and Energization
50 days
Oct 2026 - Dec 2026
MCA: Local testing of sub-system
81 days
Jun 2026 - Sep 2026
Polarizer: Manufacturing phase (LLB)
78 days
Sep 2026 - Jan 2027
Polarizer: Installation and commissioning phase (LLB)
Back into CP1 with 5 days of float
Jan 14
0 days
101 days
Jul 2026 - Nov 2026
OoB VH+Supp: Manufacturing phase section 4 and 2 (LLB)
35 days
Nov 2026 - Jan 2027
OoB VH+Supp: Installation phase section 2 (LLB)
Back into CP2 with 5 days of float
Jan 12
0 days
48 days
Mar 2026 - May 2026
Oscillation of RC: Design phase (LLB)
93 days
May 2026 - Sep 2026
Oscillation of RC: Manufacturing phase (LLB)
48 days
Sep 2026 - Nov 2026
RC and Oscillation and Det A: Installation phase
Back into CP1 with 11 days of float
Nov 19
0 days
66 days
Aug 2026 - Nov 2026
OoB VH+Supp section 3 and chopper pit: Manufacturing and Installation phase (LLB)
16 days
Nov 2026 - Dec 2026
Local and Integrated testing of Chopper System
Back into CP2 with 11 days of float
Dec 16
0 days
TG5/SAR approval
May 26, 2027
Cold commissioning TG5 scope complete
Jan 28, 2027
Final TG3
Oct 15, 2026
0 days
0 days
+17 days
Magic Critical Paths
Data from P6 March 2026 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Note: 2nd segment of Analyzer is part of the instrument scope but currently not linked to TG5 in P6
Notes: 2026-03
MCA plan updated with links to false floor etc.
Polarizer FAT 85 days delayed
Support-RC+Det A: 26 days delayed
2026-02
OoB VH and Supports installation: 76 days delayed (some mitigations through re-prioritizing the sequence)
TG5: 18 days delayed
Sample stage: 25 days delayed
Analyzer seg 1 (128 days delayed from replanning)
2025-09
OoB VH 1 month delayed
SF 1 month delayed
Sample stage 1 month delayed
Supports RC + Det A 1 month delayed
Supports An + Det B 1 month delayed
RC 5 months delayed
Oscillation 1 month delayed
Good lift 1 month delayed
Beamstop 1 mont delayed
2025-06
OoB VH Deisgn delayed with 1 month. Manufacturing to more realistic estimates delayed with 5 months (procurement transferred to ESS, if it hadn’t been, we had seen even bigger delays)
Sample stage design delayed with 1 month.
2024-04
IB guide and VH + Support on the critical path
2025-03
Polarizer design + 2 month
Supports for RC + Det A + 1 months
2025-02
Polarizer design + 1 month
Oscillation design+ 2 months
Sample stage design+ 3 months
2024-12
LLB desinger: RF Spin flipper + OoB Vh suppoert
Mortiz + desgin pool: supports A and B
Danielle: elevated platform
LLLB 2: sample stage

## Slide 6
2026
2027
No. 3 - Critical Path
(39 days TF)
No. 1 - Critical Path
(0 days TF)
No. 2 - Critical Path
(30 days TF)
Today
2026
2027
Q2
Q3
Q4
Q1
Q2
Q3
102 days
False floor: Procurement and Installation phase
Apr 2026 - Aug 2026
26 days
Aug 2026 - Oct 2026
MCA & CEP: Rack installation and Energization
60 days
Nov 2026 - Feb 2027
MCA: Local testing of sub-system (instrument zone)
82 days
Apr 2026 - Jul 2026
Sample Stage: Design and Procurement phase (LLB)
69 days
Jul 2026 - Oct 2026
Sample Stage: Manufacturing phase (LLB)
20 days
Oct 2026 - Nov 2026
Sample Stage: Installation phase
20 days
Feb 2027 - Mar 2027
Sample Stage, Rc + Oscillation, Det A, Det B: Commissioning phase
5 days
Mar 2027 - Mar 2027
Final integrated testing
101 days
Apr 2026 - Aug 2026
Support for Analyzer and Det B: Procurement and Manufacturing phase (LLB)
40 days
Aug 2026 - Oct 2026
Det B (including supports and analyzer frame): Installation and Commissioning phase (LLB & PSI)
Back into CP1 with 30 days of float
Oct 14
0 days
Back into CP1 with 39 days of float
Oct 1
0 days
TG5/SAR approval
Aug 18, 2027
Cold commissioning TG5 scope complete
Mar 24, 2027
Final TG3
Oct 26, 2026
0 days
0 days
0 days
Magic Critical Paths
Data from P6 April 2026
Note: Analyzer optics is part of the instrument scope but currently not linked to TG5 in P6
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
TG5 approval:
39 days delay in the April period
130 days delay since rebaseline
Notes: 2026-04
Sample stage FAT: 37 days delayed
Support-Analyser+ DetB: 41 days delayed
False floor: 10 days delayed (+ previously missing link which now makes it more schedule critical)
OoB VH & Supp section 3: 20 days delayed
Support-RC+ DetA: 26 days delayed
2026-03
MCA plan updated with links to false floor etc.
Polarizer FAT 85 days delayed
Support-RC+Det A: 26 days delayed
2026-02
OoB VH and Supports installation: 76 days delayed (some mitigations through re-prioritizing the sequence)
TG5: 18 days delayed
Sample stage: 25 days delayed
Analyzer seg 1 (128 days delayed from replanning)
2025-09
OoB VH 1 month delayed
SF 1 month delayed
Sample stage 1 month delayed
Supports RC + Det A 1 month delayed
Supports An + Det B 1 month delayed
RC 5 months delayed
Oscillation 1 month delayed
Good lift 1 month delayed
Beamstop 1 mont delayed
2025-06
OoB VH Deisgn delayed with 1 month. Manufacturing to more realistic estimates delayed with 5 months (procurement transferred to ESS, if it hadn’t been, we had seen even bigger delays)
Sample stage design delayed with 1 month.
2024-04
IB guide and VH + Support on the critical path
2025-03
Polarizer design + 2 month
Supports for RC + Det A + 1 months
2025-02
Polarizer design + 1 month
Oscillation design+ 2 months
Sample stage design+ 3 months
2024-12
LLB desinger: RF Spin flipper + OoB Vh suppoert
Mortiz + desgin pool: supports A and B
Danielle: elevated platform
LLLB 2: sample stage

## Slide 7
2026
2027
No. 4 - Critical Path
(46 days TF)
No. 5 - Critical Path
(55 days TF)
No. 6 - Critical Path
(70 days TF)
No. 7 - Critical Path
(87 days TF)
Today
2026
2027
Q2
Q3
Q4
Q1
Q2
Q3
From CP4
Aug 25
0 days
101 days
Jul 2026 - Nov 2026
OoB VH+Supp: Manufacturing phase section 4 and 2 (LLB)
35 days
Nov 2026 - Jan 2027
OoB VH+Supp: Installation and commissioning phase section 2 (LLB)
Back into CP1 with 46 days of float
Jan 12
0 days
104 days
Apr 2026 - Aug 2026
OoB VH+Supp: Manufacturing phase sections 1, 5 and 3 (LLB)
66 days
Aug 2026 - Nov 2026
OoB VH+Supp section 3 and chopper pit: Installation phase (LLB)
16 days
Nov 2026 - Dec 2026
Local and Integrated testing of Chopper System
Back into CP1 with 55 days of float
Dec 16
0 days
58 days
Apr 2026 - Jun 2026
Supports for RC and Det A: Design phase (LLB->ESS)
54 days
Jun 2026 - Sep 2026
Supports for RC and Det A: Procurement and Manufacturing phase (LLB)
35 days
Sep 2026 - Oct 2026
Det A (including supports): Installation phase (LLB)
Back into CP1 with 70 days of float
Oct 22
-39 days
From CP4
Jun 8
0 days
66 days
Jun 2026 - Sep 2026
Polarizer: Manufacturing phase (LLB)
40 days
Sep 2026 - Nov 2026
Polarizer: Installation phase (LLB)
Back into CP1 with 87 days of float
Nov 2
0 days
TG5/SAR approval
Aug 18, 2027
Cold commissioning TG5 scope complete
Mar 24, 2027
Final TG3
Oct 26, 2026
0 days
0 days
0 days
Magic Critical Paths
Data from P6 April 2026
Note: Analyzer optics is part of the instrument scope but currently not linked to TG5 in P6
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Notes: 2026-04
Sample stage FAT: 37 days delayed
Support-Analyser+ DetB: 41 days delayed
False floor: 10 days delayed (+ previously missing link which now makes it more schedule critical)
OoB VH & Supp section 3: 20 days delayed
Support-RC+ DetA: 26 days delayed
2026-03
MCA plan updated with links to false floor etc.
Polarizer FAT 85 days delayed
Support-RC+Det A: 26 days delayed
2026-02
OoB VH and Supports installation: 76 days delayed (some mitigations through re-prioritizing the sequence)
TG5: 18 days delayed
Sample stage: 25 days delayed
Analyzer seg 1 (128 days delayed from replanning)
2025-09
OoB VH 1 month delayed
SF 1 month delayed
Sample stage 1 month delayed
Supports RC + Det A 1 month delayed
Supports An + Det B 1 month delayed
RC 5 months delayed
Oscillation 1 month delayed
Good lift 1 month delayed
Beamstop 1 mont delayed
2025-06
OoB VH Deisgn delayed with 1 month. Manufacturing to more realistic estimates delayed with 5 months (procurement transferred to ESS, if it hadn’t been, we had seen even bigger delays)
Sample stage design delayed with 1 month.
2024-04
IB guide and VH + Support on the critical path
2025-03
Polarizer design + 2 month
Supports for RC + Det A + 1 months
2025-02
Polarizer design + 1 month
Oscillation design+ 2 months
Sample stage design+ 3 months
2024-12
LLB desinger: RF Spin flipper + OoB Vh suppoert
Mortiz + desgin pool: supports A and B
Danielle: elevated platform
LLLB 2: sample stage

## Slide 8: Key milestones

## Slide 9: Schedule adherence
MAGIC: some good months.. And some less good
Chart: Started activities: Planned vs Achieved
| 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082
Planned start | 5 | 2 | 7 | 14 | 7 | 5 | 6 | 13
Achieved start | 4 | 2 | 6 | 9 | 3 | 4 | 3 | 2
% starts achieved | 0.8 | 1 | 0.85714 | 0.64286 | 0.42857 | 0.8 | 0.5 | 0.15385
% starts achieved NSS | 0.65 | 0.65 | 0.56 | 0.52 | 0.7 | 0.61 | 0.64 | 0.59
Chart: Finished activites: Planned vs Achieved
| 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082
Planned finish | 5 | 0 | 5 | 12 | 9 | 5 | 6 | 10
Achieved finish | 4 | 0 | 3 | 7 | 7 | 4 | 2 | 4
% finish achieved | 0.8 | 0 | 0.6 | 0.58333 | 0.77778 | 0.8 | 0.33333 | 0.4
% finish achieved NSS | 0.61 | 0.58 | 0.46 | 0.49 | 0.62 | 0.52 | 0.51 | 0.63
Notes: June and july – development code, not in the NPR report

## Slide 10: Lookout - future activities
There’s a lot in the pipeline..
Chart: Planned starts
| 45931 | 45962 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Planned start | 14 | 7 | 5 | 6 | 13 | 10 | 24 | 34 | 21 | 40 | 41 | 36
Achieved start | 9 | 3 | 4 | 3 | 2
Chart: Planned finishes
| 45931 | 45962 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Planned finish | 12 | 9 | 5 | 6 | 10 | 10 | 22 | 32 | 25 | 35 | 44 | 44
Achieved finish | 7 | 7 | 4 | 2 | 4
Notes: June and july – development code, not in the NPR report

## Slide 11
Chart: Planned starts
Planned start (in Oct-25) | 16 | 11 | 21 | 25 | 24 | 16 | 20 | 24 | 27 | 33 | 46 | 33
Achieved start | 9 | 3 | 4 | 3 | 2
Planned start (in April-26) | 14 | 7 | 5 | 6 | 13 | 10 | 24 | 34 | 21 | 40 | 41 | 36

## Slide 12: Discussion points
How can we prevent further slippage of the TG5 date, and is there any opportunity to accelerate the schedule?
Are there specific mitigations or acceleration strategies we can implement?
One of the attached slides highlights milestones that have slipped by more than four months—particularly in the design phase. What actions are we taking and what more can we do to address these delays?
Can procurements be accelerated further?

## Slide 13: Lookout - future activities
There’s a lot in the pipeline..
Chart: Planned starts
| 45809 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204
Planned start | 5 | 2 | 7 | 16 | 11 | 16 | 21 | 25 | 24 | 16 | 20 | 24 | 27
Achieved start | 4 | 2 | 6
Chart: Planned finishes
| 45809 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204
Planned finish | 5 | 0 | 5 | 12 | 14 | 25 | 27 | 20 | 26 | 17 | 16 | 18 | 32
Achieved finish | 4 | 0 | 3
Notes: June and july – development code, not in the NPR report

## Slide 14: Key milestones > 4 months delay
Comparing September 2024 with September 2025
Activity Name | Date (Sep 24) | Date (Sep 25) | Variance date (month)
MAGIC:In-B VH+Supp:Factory Acceptance Test (FAT) | 14-mar-25 | 13-Oct-25 | -7,2
MAGIC:BWF:Factory Acceptance Test (FAT) | 25-jul-25 | 24-feb-26 | -7,1
MAGIC:OoB VH & Supp: Factory Acceptance Test (FAT) | 24-Oct-25 | 08-sep-26 | -10,55
MAGIC:Polarizer: Factory Acceptance Test (FAT) | 10-jun-25 | 08-dec-25 | -6,4
MAGIC:RF SF: CDR (meeting) | 10-feb-25 | 02-dec-25 | -9,2
MAGIC: Sample St: CDR (meeting) | 14-apr-25 | 20-jan-26 | -8,2
MAGIC:Supp-RC+Det A: CDR (meeting) | 10-jun-25 | 23-jan-26 | -6,6
MAGIC: RC: Factory Acceptance Test (FAT) | 18-jun-25 | 20-apr-26 | -10,25
MAGIC: Supp- Analzr+Det B: CDR (meeting) | 01-sep-25 | 19-jan-26 | -4,5
MAGIC: Analyzer: Seg 2: Factory Acceptance Test (FAT) | 09-apr-25 ->08-jun-26 | 03-jun-26 ->04-nov-26 | -5,3

## Slide 15: Procurements
Ongoing and/or planned to start next few months
Activity Name | Activity % Complete | Start date (Sep 24) | Finish date (Sep 24) |  | Start date (Sep 25) | Finish date (Sep 25) | Variance finish date (month)
MAGIC:BWF:Procurement and tender selection | 89.06% | 04-dec-24 | 24-jul-25 |  | 15-Apr-25 A | 20-Oct-25 | -3,1
MAGIC:OoB VH & Supp : Procurement of OoB housing and supports | 20% | 26-feb-25 | 23-Oct-25 |  | 15-Sep-25 A | 05-dec-25 | -1,55
MAGIC:Polarizer: Procurement and manufacturing of the Component | 51.52% | 13-jan-25 | 09-jun-25 |  | 22-Jul-25 A | 05-dec-25 | -6,4
MAGIC:RF SF: Procurement and manufacturing of the Component | 0 % | 24-feb-25 | 08-jul-25 |  | 16-dec-25 | 07-May-26 | -10,2
MAGIC: Sample St: Procurement and manufacturing of the Component | 0 % | 30-apr-25 | 09-sep-25 |  | 03-feb-26 | 18-May-26 | -8,2
MAGIC: RC: Procurement and manufacturing of Radial Collimator | 64.11% | 16-sep-24 | 17-jun-25 |  | 16-Sep-24 A | 17-apr-26 | -9,25
MAGIC: Osc: Procurement and manufacturing of the Oscillation | 0% | 15-sep-25 | 13-mar-26 |  | 15-jan-26 | 09-jul-26 | -3,9
MAGIC: Supp- Analzr+Det B: Procurement and manufacturing of the Component | 0% | 15-sep-25 | 17-feb-26 |  | 02-feb-26 | 29-jun-26 | -4,4
MAGIC:Supp-RC+Det A: Procurement and manufacturing of the Component | 0% | 25-jun-25 | 11-nov-25 |  | 06-feb-26 | 03-jul-26 | -7,6
MAGIC: Beamstop: Procurement and manufacturing of the Component | 4% | 15-Oct-25 | 25-nov-25 |  | 29-Sep-25 A | 05-dec-25 | -0,4
MAGIC:Cave elev plat: Procurement and manufacturing | 0% | 12-nov-25 | 26-mar-26 |  | 16-dec-25 | 29-apr-26 | -1,1

## Slide 16: Bunker…

## Slide 17: NSS Replanning Evaluation
MAGIC ICEB

## Slide 18: Beer replanning finalized in June 2024
Chart: Number of activites
| Number of activities before replanning (P6) | Number of activities after replanning (P6)
ESTIA | 89 | 430
SKADI | 53 | 592
BEER | 105 | 569
FREIA | 58 | 764
HEIMDAL | 89 | 828
MIRACLES | 95 | 708
MAGIC | 97 | 833
TREX | 209 | 981
CSPEC | 165 | 1034
VESPA | 109 | 1093
COMMON PROJECTS T2T3 | 715 | 2095
More details in P6 : TA milestones + detailed plan
We have more information in P6.
How can we use this information:
to plan/coordinate (installation, commissioning etc.)
keep track of progress (updating monthly instrument dashboards with replanning dates)
make informed decisions about priorities
MAGIC has 553 open activities in P6:
43 TA activities
510 activities from detailed plan

## Slide 19: Critical paths T2T3
When a delay impacts the end date of a project
  We measure float towards the instrument’s TG5
  The first critical path has 0 float. If there’s a delay of 1 month, TG5 will shift 1 month.
  If the second critical path has 2 months float, it will push TG5 if there’s a delay of more than 2 months.
  The length of an activity reflects the start and the end of an activity, not the amount of time spent during that time period.
  The critical paths reflect the activities that are critical from a schedule perspective, not necessarily critical from a scientific or technical perspective.
  Activities on the critical paths should a priority for all of us!

## Slide 20
2025
2027
No. 2 - Critical Path
(40 days TF)
No. 1 - Critical Path
(0 days TF)
No. 3 - Critical Path
(57 days TF)
No. 4 - Critical Path
(99 days TF)
Today
2025
2026
2027
64 days
Jun 2025 - Sep 2025
Supports for RC and Det A: Detailed design (LLB)*
213 days
IB Guide+ VH+Supp: Procurement and Manufacturing phase (LLB)
46 days
Polarizer: Detailed design (LLB)
Apr 2025 - Jun 2025
145 days
Dec 2025 - Jun 2026
Oscillation of RC: Procurement and Manufacturing phase (LLB)
59 days
Jun 2026 - Sep 2026
RC and Oscillation: Installation phase (LLB)
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
38 days
Sep 2026 - Nov 2026
MCA (including sub-systems): Energization and Commissioning phase
65 days
Sep 2025 - Dec 2025
Oscillation of RC: Design phase (LLB)*
164 days
Jan 2026 - Sep 2026
IB Guide+ VH+Supp: Installation and commissioning phase (LLB)**
Apr 2025 - Jan 2026
119 days
Apr 2025 - Sep 2025
Sample Stage: Design phase (LLB)*
107 days
Sep 2025 - Feb 2026
Sample Stage: Procurement and Manufacturing phase (LLB)
52 days
Feb 2026 - Apr 2026
Sample Stage: Installation phase (LLB)
82 days
Apr 2026 - Aug 2026
MCA (including sub-systems): Installation, Energization and Commissioning phase
90 days
Apr 2025 - Aug 2025
OoB VH+Supp: Design phase (LLB)
139 days
Aug 2025 - Feb 2026
OoB VH+Supp: Procurement and Manufacturing phase (LLB)
68 days
Feb 2026 - May 2026
OoB VH+Supp: Installation phase (LLB)
TG5/SAR approval
Apr 7, 2027
Start of CC
Nov 5, 2026
Final TG3
Feb 23, 2026
Magic Critical Paths
Data from P6 April 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
*Constraints on design resources
**installation linked to first access after BOT.
Note: 2nd segment of Analyzer is part of the instrument scope but currently not linked to TG5 in P6
Notes: 2024-04
IB guide and VH + Support on the critical path
2025-03
Polarizer design + 2 month
Supports for RC + Det A + 1 months
2025-02
Polarizer design + 1 month
Oscillation design+ 2 months
Sample stage design+ 3 months
2024-12
LLB desinger: RF Spin flipper + OoB Vh suppoert
Mortiz + desgin pool: supports A and B
Danielle: elevated platform
LLLB 2: sample stage

## Slide 21: Key milestones

## Slide 22: Activities with > 3 months delay
Comparing September 2024 with April 2025
Activity Name | Activity % Complete | Start date (Sep 24) | Start date (April 25) | Variance start date (month)
MAGIC: XYZ: Factory Acceptance Test (FAT) | 0% | 26-nov-24 | 20-maj-25 | -5,6
MAGIC:Polarizer: CDR (meeting) | 0% | 09-dec-24 | 04-jun-25 | -5,55
MAGIC:OoB VH & Supp Sec 1: CDR (meeting) | 0% | 05-feb-25* | 19-jun-25 | -4,5
MAGIC:RF SF: CDR (meeting) | 0% | 10-feb-25 | 02-jul-25 | -4,75
MAGIC: Good Lift: Factory Acceptance Test (FAT) | 0% | 11-mar-25 | 20-aug-25 | -5,45
MAGIC:Guid+VH+Supp (in-bunker):Factory Acceptance Test (FAT) | 0% | 14-mar-25 | 13-jan-26 | -9,9
MAGIC: Sample St: CDR (meeting) | 0% | 14-apr-25 | 01-sep-25 | -3,65
MAGIC: Det A: Factory Acceptance Test (FAT) | 0% | 12-maj-25 | 05-dec-25 | -7,25
MAGIC:Supp-RC+Det A: CDR (meeting) | 0% | 10-jun-25 | 30-sep-25 | -2,95
MAGIC:BWF:Factory Acceptance Test (FAT) | 0% | 25-jul-25 | 20-nov-25 | -4,2

## Slide 23: Procurements
Ongoing and/or planned to start next four months
Activity Name | Activity % Complete | Start date (Sep 24) | Finish date (Sep 24) |  | Start date (April 25) | Finish date (April 25) | Variance finish date (month)
MAGIC: Analyzer: Seg 2: Procurement and manufacturing of the Component | 0% | 06-nov-24 | 15-apr-26 |  | 28-jul-25 | 16-apr-26 | -0,05
MAGIC:BWF:Procurement and manufacturing of the Component | 6.67% | 04-dec-24 | 24-jul-25 |  | 15-Apr-25 A | 19-nov-25 | -4,2
MAGIC:Polarizer: Procurement and manufacturing of the Component | 0% | 13-jan-25 | 09-jun-25 |  | 27-jun-25 | 13-nov-25 | -5,6
MAGIC:RF SF: Procurement and manufacturing of the Component | 0% | 24-feb-25 | 08-jul-25 |  | 16-jul-25 | 18-nov-25 | -4,75
MAGIC:OoB VH & Supp Sec 1: Procurement of OoB housing and supports | 0% | 26-feb-25 | 23-Oct-25 |  | 11-jul-25 | 30-Oct-25 | -0,25
MAGIC:OoB VH & Supp Sec 2: Procurement of OoB housing and supports | 0% |  |  |  | 15-jul-25 | 03-nov-25 | -0,4
MAGIC:OoB VH & Supp Sec 3: Procurement of OoB housing and supports | 0% |  |  |  | 18-aug-25 | 07-nov-25 | -0,4
MAGIC: Sample St: Procurement and manufacturing of the Component | 0% | 30-apr-25 | 09-sep-25 |  | 15-sep-25 | 03-feb-26 | -4,65
MAGIC: Supp- Analzr+Det B: Procurement and manufacturing of the Component | 0% | 15-sep-25 | 17-feb-26 |  | 25-jul-25 | 11-dec-25 | 1,8
MAGIC:Supp-RC+Det A: Procurement and manufacturing of the Component | 0% | 25-jun-25 | 11-nov-25 |  | 14-Oct-25 | 18-mar-26 | -3,95

## Slide 24: Schedule adherence
Most months – MAGIC is below average on schedule accuracy
Chart: Started activities: Planned vs Achieved
| 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748
Planned start | 21 | 9 | 7 | 1 | 9 | 12 | 13 | 14
Achieved start | 8 | 3 | 2 | 1 | 6 | 4 | 6 | 9
% starts achieved | 0.38095 | 0.33333 | 0.28571 | 1 | 0.66667 | 0.33333 | 0.46154 | 0.64286
% starts achieved NSS | 0.68 | 0.56198 | 0.7651 | 0.81928 | 0.65476 | 0.59494 | 0.57488 | 0.72
Chart: Finished activites: Planned vs Achieved
| 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748
Planned finish | 14 | 5 | 8 | 2 | 5 | 12 | 10 | 11
Achieved finish | 7 | 2 | 2 | 2 | 2 | 8 | 7 | 6
% finish achieved | 0.5 | 0.4 | 0.25 | 1 | 0.4 | 0.66667 | 0.7 | 0.54545
% finish achieved NSS | 0.56 | 0.52381 | 0.65823 | 0.80374 | 0.57396 | 0.63277 | 0.62946 | 0.68
Notes: June and july – development code, not in the NPR report

## Slide 25: Earned value
Scheduled (in the replanning September 2024) vs. performed (April 2025)

## Slide 26: Bunker next steps
  Closing roof D03 side – after summer
  West access is extended to Aug 29th,
  Roof installation starts September 1st
  Extra access before BOT currently mid Oct - mid Dec 2025. Under discussion.
  Post BOT access:
  First access after BOT: summer 2026
  Second access after BOT: xmas 2026
  Third access after BOT: summer 2027
Which MAGIC components
can be installed before BOT?

## Slide 27: Discussion points
How can we prevent further slippage of the TG5 date, and is there any opportunity to accelerate the schedule?
Are there specific mitigations or acceleration strategies we can implement?
One of the attached slides highlights milestones that have slipped by more than three months—particularly in the design phase. What actions can we take to address these delays?
Another slide outlines upcoming procurements:
  We’d like an update from partners on their procurement plans for these components—do the current timelines still appear realistic? (More details can be found in the attached Excel sheet.)
  We’re also open to discussing how ESS might support procurement efforts, if helpful.
How can we ensure focus on the components to be installed in the bunker?
How has the MAGIC team utilised ESS resources (design/engineering, technical writer etc)? How can ESS support going forward?
How has the handover and integration of new resources gone? (this topic could preferably be included in the instrument updates in the morning)

## Slide 28: Simplified view of the P6 landscape
Linking an instrument plan to common projects and technology groups
ICS – control
ICS – network
ICS – PSS
CEP
MCA
CUP
Detectors
(BM, Detector integration, Detector… )
Choppers
Vacuum
Instrument plan
Output:
Installation team
Q-gate team
Controllers
….

## Slide 29: Common projects replanning T2T3
Linked to P6 instrument plans
Information has been sent out in the NSS Progress Report
*Draft plan in place linked to the instrument plan. Further review might be needed with wp manager and instrument teams
Instrument | CEP | MCA | CUP | Choppers | Detectors | BM | ICS Network | ICS PSS
ESTIA | YES | YES | YES | YES | YES: MB | YES | YES | YES
SKADI | YES | YES* | YES | YES (Racks) | N/A | YES* | YES* | YES*
BEER | YES | YES* | YES | YES | N/A | YES* | YES* | YES*
MAGIC | YES | YES* | YES | YES | N/A |  | YES* | YES*
FREIA | YES | YES* | YES | YES (Racks) | YES: MB |  | YES* | YES*
HEIMDAL | YES | YES* | YES | YES | N/A |  | YES* | YES*
MIRACLES | YES | YES* | YES | YES (Racks) | N/A |  | YES* | YES*
CSPEC | YES | YES* | YES | N/A | YES: He3 |  | YES* | YES*
T-REX | YES | YES* | YES | YES | YES: MG |  | YES* | YES*
VESPA |  |  |  |  |  |  |  |