## Schedule adherence
| Planned start (Oct-25) | Planned starts (April-26) | Planned start | Achieved start | Planned finish (Oct-25) | Planned finish (April-26) | Planned finish | Achieved finish | % starts achieved | % finish achieved | % starts achieved NSS | % finish achieved NSS | % starts achieved ESS | % finish achieved ESS
2024-09-01 |  |  | 8 | 2 |  |  | 11 | 1 | 25% | 9.091% | 68% | 56% | 62% | 52%
2024-10-01 |  |  | 4 | 3 |  |  | 7 | 4 | 75% | 57.14% | 56.2% | 52.38% | 53% | 58%
2024-11-01 |  |  | 18 | 17 |  |  | 14 | 14 | 94.44% | 100% | 76.51% | 65.82% | 65% | 56%
2024-12-01 |  |  | 3 | 3 |  |  | 6 | 6 | 100% | 100% | 81.93% | 80.37%
2025-01-01 |  |  | 10 | 9 |  |  | 7 | 7 | 90% | 100% | 65.48% | 57.4%
2025-02-01 |  |  | 11 | 9 |  |  | 11 | 10 | 81.82% | 90.91% | 59.49% | 63.28%
2025-03-01 |  |  | 9 | 8 |  |  | 9 | 9 | 88.89% | 100% | 57.49% | 62.95%
2025-04-01 |  |  | 4 | 3 |  |  | 2 | 2 | 75% | 100% | 72% | 68%
2025-05-01 |  |  | 5 | 4 |  |  | 4 | 3 | 80% | 75% | 68% | 64%
2025-06-01 |  |  | 4 | 4 |  |  | 4 | 3 | 100% | 75% | 65% | 61%
2025-08-01 |  |  | 5 | 4 |  |  | 5 | 4 | 80% | 80% | 65% | 58%
2025-09-01 |  |  | 2 | 2 |  |  | 3 | 3 | 100% | 100% | 56% | 46%
2025-10-01 | 6 |  | 7 | 6 | 9 |  | 9 | 7 | 100% | 77.78% | 52% | 49%
2025-11-01 | 7 |  | 6 | 3 | 10 |  | 4 | 1 | 42.86% | 25% | 70% | 62%
2026-01-01 | 11 |  | 2 | 2 | 11 |  | 1 | 0 | 18.18% | 0% | 61% | 52%
2026-02-01 | 15 |  | 0 | 0 | 15 |  | 1 | 1 | 0% | 100% | 64% | 51%
2026-03-01 | 19 |  | 13 | 9 | 30 |  | 15 | 10 | 47.37% | 66.67% | 59% | 63%
2026-04-01 |  | 8 |  |  |  | 10
2026-05-01 |  | 4 |  |  |  | 5
2026-06-01 |  | 4 |  |  |  | 6
2026-07-01 |  | 11 |  |  |  | 15
2026-08-01 |  | 10 |  |  |  | 3
2026-09-01 |  | 6 |  |  |  | 13
2026-10-01 |  | 3 |  |  |  | 2

## P6 April live
Activity ID | Activity Name | Activity % Complete | Original Duration | Start | Finish | BL1 Start | BL1 Finish
13-NSS-Live Neutron Scattering Systems 2014-EOC |  |  | 500 | 03-Dec-24 A | 2027-02-26 | 2024-12-03 | 2026-12-21
13-NSS-Live.1 NSS |  |  | 500 | 03-Dec-24 A | 2027-02-26 | 2024-12-03 | 2026-12-21
13-NSS-Live.1.7 NSS Instrument Construction |  |  | 500 | 03-Dec-24 A | 2027-02-26 | 2024-12-03 | 2026-12-21
NSS-A214733800 | SKADI:Collimator: Preparation and readiness of MCA group for tests | 40% | 300 | 03-Dec-24 A | 2026-04-02 | 2024-12-03 | 2025-02-25
NSS-A214734250 | SKADI:Polrzr Housg: Manufacturing and assembly | 69.57% | 161 | 13-okt-25 A | 2026-06-15 | 2025-05-07 | 2025-09-08
NSS-A214734540 | SKADI:Polrz+SF+FS: Assembly of Polarizer with optics and Chopper by FZJ | 69.57% | 161 | 13-okt-25 A | 2026-06-15 | 2025-09-09 | 2025-11-03
NSS-A214734330 | SKADI:Spin Flipr: Manufacturing | 90% | 160 | 13-okt-25 A | 2026-06-12 | 2025-04-29 | 2025-09-29
NSS-A2147226920 | SKADI: Final TG3: Review Docs by Technical Group | 61.36% | 44 | 23-Feb-26 A | 2026-04-27
NSS-A2147428800 | SKADI: Overall maintenance manual-Prep and release | 0% | 159 | 28-Feb-26 A | 2026-11-16
NSS-A2147428810 | SKADI: Comprehensive Rad Saf report-Prep and release | 0% | 159 | 28-Feb-26 A | 2026-11-16
NSS-A214735540 | SKADI: Det Housing: Quality gate review and approval | 44% | 50 | 02-Mar-26 A | 2026-05-13 | 2026-02-10 | 2026-03-23
NSS-A2147428830 | SKADI: Overall SDD-Prep and release | 0% | 159 | 02-Mar-26 A | 2026-11-16
NSS-A2147432590 | Manufacturing of installation tool | 26.83% | 82 | 02-Mar-26 A | 2026-07-01
NSS-A2147432600 | Manufacturing of Bank 2 | 18.49% | 119 | 02-Mar-26 A | 2026-09-18
NSS-A2147414730 | SKADI: Det Elec: Internal FAT- closure of open points and approval iNSTR+ DETG+ECDC at utgård | 53.85% | 13 | 23-Mar-26 A | 2026-04-10
NSS-A214733210 | SKADI:HS: System Acceptance Test (SAT) involving all tech groups | 33.33% | 15 | 25-Mar-26 A | 2026-05-19 | 2025-11-18 | 2025-11-24
NSS-A2147414740 | SKADI: Det Elec: Submission of docs to ESS for IRR | 0% | 5 | 2026-04-02 | 2026-04-10
NSS-A214734030 | SKADI:Collimator: Local SAT | 0% | 15 | 2026-04-07 | 2026-04-27 | 2025-02-26 | 2025-03-18
NSS-A214734670 | SKADI:Samp Stage: Delivery of sample stage and Mounting test and installation | 0% | 10 | 07-Apr-26* | 2026-04-20 | 2025-09-01 | 2025-09-05
NSS-A2147414760 | SKADI: Det Elec: Submission of docs to ESS for Quality gate INSTR+DETG | 0% | 10 | 2026-04-13 | 2026-04-24
NSS-A2147414770 | SKADI: Det Elec: IRR doc review by ESS | 0% | 5 | 2026-04-13 | 2026-04-17
NSS-A214734580 | SKADI:Samp Stage: System Acceptance Test (SAT) | 0% | 5 | 2026-04-21 | 2026-04-27 | 2026-06-04 | 2026-06-10
NSS-A214734020 | SKADI:Collimator: Test readiness review (TRR) and approval | 0% | 3 | 2026-04-28 | 2026-04-30 | 2025-10-10 | 2025-10-14
NSS-A2147226900 | SKADI: Final TG3 Action closeouts | 0% | 20 | 2026-04-28 | 2026-05-28
NSS-A214735240 | SKADI: Det Housing: Submission of docs to ESS for IRR | 0% | 5 | 04-maj-26* | 2026-05-08 | 2025-12-19 | 2026-01-12
NSS-A214735750 | SKADI: Det Housing: IRR doc review by ESS | 0% | 5 | 2026-05-11 | 2026-05-19 | 2026-01-13 | 2026-01-19
NSS-A214732590 | SKADI:PSC: Submission of docs to ESS for IRR (ALAP) | 0% | 30 | 2026-05-13 | 2026-06-25 | 2025-12-05 | 2026-02-02
NSS-A214732790 | SKADI:PSC: Quality gate review and approval | 0% | 30 | 2026-05-29 | 2026-07-10 | 2025-12-19 | 2026-02-16
NSS-A214734560 | SKADI:PSC: Integration of chopper into Polarizer, Fast Shutter, Spin Flipper and dismounting | 0% | 5 | 2026-06-16 | 2026-06-22 | 2025-11-04 | 2025-11-10
NSS-A214735120 | SKADI:Polrz+SF+FS: Quality gate document submission phase | 0% | 20 | 2026-06-19 | 2026-07-17 | 2025-12-05 | 2026-01-19
NSS-A214734780 | SKADI:Polrz+SF+FS: FAT for the entire unit ( Choppers+optics+ SF+FS) | 0% | 5 | 2026-06-23 | 2026-06-30 | 2025-12-09 | 2025-12-15
NSS-A214733360 | SKADI:PSC: IRR doc review by ESS | 0% | 10 | 2026-06-29 | 2026-07-10 | 2026-02-03 | 2026-02-16
NSS-A214734850 | SKADI:Polrz+SF+FS: FAT Report and Documentation | 0% | 3 | 2026-07-01 | 2026-07-03 | 2025-12-16 | 2025-12-18
NSS-A214734980 | SKADI:Polrz+SF+FS: FAT closure of open points and approval | 0% | 8 | 2026-07-01 | 2026-07-10 | 2025-12-16 | 2026-01-12
NSS-A214734910 | SKADI:Polrz+SF+FS: IRR doc submission phase | 0% | 8 | 2026-07-01 | 2026-07-10 | 2025-12-16 | 2026-01-12
NSS-A2147430030 | Delivery and assembly of installation tool from FZJ + test of empty airbox | 0% | 12 | 2026-07-02 | 2026-07-17
NSS-A214733850 | SKADI:OoB Guides: IRR doc submission for 2nd part | 0% | 5 | 2026-07-06 | 2026-07-10 | 2026-02-10 | 2026-02-16
NSS-A214735030 | SKADI:PSC: Shipping period for the Chopper to ESS | 0% | 5 | 2026-07-13 | 2026-07-17 | 2026-01-13 | 2026-01-19
NSS-A214735040 | SKADI:Polrz+SF+FS: Shipping period for the Polarizer, Fast Shutter, Spin Flliper | 0% | 5 | 2026-07-13 | 2026-07-17 | 2026-01-13 | 2026-01-19
NSS-A214733300 | SKADI:PSC: IRR meeting prep | 0% | 5 | 2026-07-13 | 2026-07-17 | 2026-02-17 | 2026-02-23
NSS-A214735660 | SKADI:Polrz+SF+FS: IRR doc review by ESS | 0% | 5 | 2026-07-13 | 2026-07-17 | 2026-01-13 | 2026-01-19
NSS-A214733900 | SKADI:OoB Guides: IRR doc reviewed by ESS for 2nd part | 0% | 5 | 2026-07-13 | 2026-07-17 | 2026-02-17 | 2026-02-23
NSS-A214735160 | SKADI:Polrz+SF+FS: Quality gate review and approval | 0% | 10 | 2026-07-20 | 2026-07-31 | 2026-01-20 | 2026-02-16
NSS-A214735590 | SKADI: Detector: Installation of Detector Housings incl Bank 0 + Bank 1 | 0% | 7 | 2026-08-17 | 2026-08-25 | 2026-04-07 | 2026-05-05
NSS-A214735390 | SKADI:PSC: Installation of entire unit ( PSC+FS+SF) | 0% | 10 | 2026-08-17 | 2026-08-28 | 2026-03-17 | 2026-03-30
NSS-A214735270 | SKADI:Polrz+SF+FS: Installation of Polarizer, Fast Shutter, Spin Flliper | 0% | 10 | 2026-08-17 | 2026-08-28 | 2026-03-03 | 2026-03-16
NSS-A214734070 | SKADI:Collimator: Integrated System Acceptance Test (SAT) | 0% | 9 | 2026-08-21 | 2026-09-02 | 2026-06-08 | 2026-06-10
NSS-A214734110 | SKADI: Det Tube: System Acceptance Test (SAT) | 0% | 8 | 2026-08-24 | 2026-09-02 | 2026-06-08 | 2026-06-10
NSS-A214735620 | SKADI: Det Housing: System Acceptance Test (SAT) | 0% | 10 | 2026-08-26 | 2026-09-08 | 2026-05-22 | 2026-06-04
NSS-A214735430 | SKADI:PSC: Test readiness review (TRR) and checklist sign off | 0% | 2 | 2026-08-31 | 2026-09-01 | 2026-03-31 | 2026-04-01
NSS-A214735350 | SKADI:Polrz+SF+FS: Test readiness review (TRR) and checklist sign off | 0% | 3 | 2026-08-31 | 2026-09-02 | 2026-03-17 | 2026-03-19
NSS-A214734680 | SKADI: FOC: Test readiness review (TRR) and checklist sign off | 0% | 2 | 2026-08-31 | 2026-09-01 | 2025-10-10 | 2025-10-23
NSS-A214733770 | SKADI:OoB Guides: Installation and alignment of 2nd part | 0% | 5 | 2026-08-31 | 2026-09-04 | 2026-03-17 | 2026-04-15
NSS-A214735460 | SKADI:PSC: SAT (with tech group) | 0% | 15 | 2026-09-02 | 2026-09-22 | 2026-04-02 | 2026-04-17
NSS-A214733940 | SKADI:OoB Guides: SAT for 2nd part combined with PS chopper | 0% | 12 | 2026-09-07 | 2026-09-22 | 2026-04-16 | 2026-04-22
NSS-A214734750 | SKADI: FOC: System Acceptance Test (SAT) | 0% | 5 | 2026-09-14 | 2026-09-18 | 2025-10-24 | 2025-11-06
NSS-A2147428740 | SKADI: Integrated testing of Chopper system | 0% | 5 | 2026-09-14 | 2026-09-18
NSS-A2147431250 | Delivery of Bank 2 and PMT in beam | 0% | 5 | 2026-09-21 | 2026-09-25
NSS-A2147226830 | SKADI: Document compilation for SAR+SRR review | 0% | 40 | 2026-09-22 | 2026-11-16 | 2026-08-18 | 2026-10-12
NSS-A214735440 | SKADI:Polrz+SF+FS: System Acceptance Test (SAT) | 0% | 7 | 2026-10-08 | 2026-10-16 | 2026-06-09 | 2026-06-10
NSS-A2147428770 | SKADI: Integrated testing of Beam transport and conditioning system | 0% | 5 | 2026-10-19 | 2026-10-23
NSS-A2147428820 | SKADI: Overall V&V plan-Prep and release | 0% | 20 | 2026-10-20 | 2026-11-16
NSS-A2147428750 | SKADI: Integrated testing of Detector system | 0% | 5 | 2026-11-02 | 2026-11-06
NSS-A2147428760 | SKADI: Integrated testing of Beam monitor system in bunker | 0% | 5 | 2026-11-10 | 2026-11-16
NSS-A2147429880 | SKADI: Integrated testing of Beam monitor system out bunker | 0% | 5 | 2026-11-10 | 2026-11-16
NSS-A2147226810 | SKADI: Final Integrated testing | 0% | 5 | 2026-11-17 | 2026-11-23 | 2026-06-23 | 2026-08-17
NSS-A2147226930 | SKADI: Closeout actions from TG5-SAR Dry run | 0% | 15 | 2026-11-17 | 2026-12-07
NSS-A2147428790 | SKADI: Release of V&V reports (and prep for SAR dry run) | 0% | 3 | 2026-11-24 | 2026-11-26
NSS-A2147226861 | SKADI: Documentation submission for SAR+SRR committee review | 0% | 10 | 2026-12-07 | 2026-12-18
NSS-A2147226850 | SKADI: TG5/SAR closeouts and approval | 0% | 35 | 2026-12-21 | 2027-02-19 | 2026-10-13 | 2026-12-07
NSS-A2147226870 | SKADI: TG5/SAR+ SRR closeouts and approval | 0% | 40 | 2026-12-21 | 2027-02-26 | 2026-12-08 | 2026-12-21

## P6 Sep lockdown
Activity ID | Activity Name | Activity % Complete | Original Duration | Start | Finish | BL1 Start | BL1 Finish | Variance - BL1 Start Date | Budgeted Total Cost | Earned Value Cost | Activity Notes | Remaining Total Cost | user_text8 | ESS 2023 Key Milestones | Variance - BL1 Finish Date | NSS Area Code | Activity Count | Phase | ESS Activity Development Code | BL2 Finish | BL2 Start | ESS Milestone | Total Float | IK to Cash | In Kind | In Kind Country | In Kind Generate Cost | In Kind Planned Partner | In Kind TA status | Schedule Variance | Instrument
NSS-A214734530 | SKADI:PSC: Storage of Frame Overlap chopper at FZJ | 75.09% | 273 | 2024-11-25 | 2026-01-16 | 2024-11-25 | 2026-01-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
13-NSS-P09-25 Neutron Scattering Systems - P09-2025 Lockdown |  |  | 545 | 2024-11-25 | 2027-04-26 | 2024-11-25 | 2027-02-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -40 |  | 123 | [5 empty] | 429 | [6 empty] | SEK0
13-NSS-P09-25.1 NSS |  |  | 545 | 2024-11-25 | 2027-04-26 | 2024-11-25 | 2027-02-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -40 |  | 123 | [5 empty] | 429 | [6 empty] | SEK0
13-NSS-P09-25.1.7 NSS Instrument Construction |  |  | 545 | 2024-11-25 | 2027-04-26 | 2024-11-25 | 2027-02-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -40 |  | 123 | [5 empty] | 429 | [6 empty] | SEK0
NSS-A214733800 | SKADI:Collimator: Preparation and readiness of MCA group for tests | 40% | 205 | 2024-12-03 | 2025-11-06 | 2024-12-03 | 03-Oct-25 | 0 | SEK0 | SEK0 | Feb 2025: MCA group would not be able to finish do the test before April | SEK0 |  |  | -24 |  | 1 | [5 empty] | 347 | [6 empty] | SEK0 | SKADI
NSS-A214735150 | SKADI: Detector: Detector Integration and slow controls development | 59.56% | 225 | 2025-02-18 | 2026-02-18 | 2025-02-18 | 2026-02-18 | 0 | SEK0 | SEK0 | Check the noteboke for this activity\ MA | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214733780 | SKADI:Polrzr Housg: Procurement and Waiting time for workshop to be free at FZJ | 94.63% | 149 | 2025-03-07 | 2025-10-10 | 2025-03-07 | 10-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | PROC |  |  |  |  | 273 | [6 empty] | SEK0 | SKADI
NSS-A214733710 | SKADI:Spin Flipr: Procurement and Waiting time for workshop to be free at FZJ | 94.63% | 149 | 2025-03-07 | 2025-10-10 | 2025-03-07 | 10-Oct-25 | 0 | SEK0 | SEK0 | Why procurement and manuf is separately listed??-RK | SEK0 |  |  | 0 |  | 1 | PROC |  |  |  |  | 278 | [6 empty] | SEK0 | SKADI
NSS-A214733720 | SKADI:FS: Procurement and Waiting time for workshop to be free at FZJ | 94.63% | 149 | 2025-03-07 | 2025-10-10 | 2025-03-07 | 10-Oct-25 | 0 | SEK0 | SEK0 | Why procurement and manuf is separately listed??-RK | SEK0 |  |  | 0 |  | 1 | PROC |  |  |  |  | 278 | [6 empty] | SEK0 | SKADI
NSS-A214733930 | Storage for second installation | 0% | 235 | 2025-03-14 | 2026-03-31 | 2025-03-14 | 2026-03-31 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 251 | [6 empty] | SEK0 | SKADI
NSS-A214734710 | SKADI:Hutch: Installation of Hutch | 77.45% | 102 | 2025-05-09 | 2025-10-31 | 09-May-25 | 15-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -12 | D01 | 1 | INST |  |  |  |  | 353 | [6 empty] | SEK0 | SKADI
NSS-A214733700 | SKADI:Det Int into ESS-DAQ: Firmware update FEB (IDEAS) interim test- Part 2 and continues debugging | 91.26% | 103 | 2025-05-16 | 2025-10-13 | 16-May-25 | 13-Oct-25 | 0 | SEK0 | SEK0 | Feb 2025: The duration and update on this task dependent on feedback form ECDC | SEK0 |  |  | 0 |  | 1 | [5 empty] | 258 | [6 empty] | SEK0 | SKADI
NSS-A2147226750 | SKADI: Document compilation and submission for Final TG3 | 83.64% | 55 | 2025-07-01 | 2025-10-13 | 2025-07-01 | 2025-12-15 | 0 | SEK0 | SEK0 | due to busy period for Skadi team it does not seems to be happen in 30 days. at least June 2025. | SEK0 | Susanna_TG3 |  | 45 |  | 1 | [5 empty] | 747 | [6 empty] | SEK0 | SKADI
NSS-A214734260 | SKADI:Det Assembly at JCNS: Mounting the detector assemblies in frames | 50.79% | 63 | 2025-08-18 | 2025-11-12 | 2025-08-18 | 01-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -30 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214733980 | SKADI:Det Housing: Waiting for the bunker access at FZJ for leak test | 88.57% | 35 | 2025-08-19 | 2025-10-06 | 2025-08-19 | 06-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 331 | [6 empty] | SEK0
NSS-A214734480 | SKADI:Det Assembly at JCNS: Integration into the detector housings | 41.51% | 53 | 2025-09-01 | 2025-11-12 | 02-Oct-25 | 29-Oct-25 | 23 | SEK0 | SEK0 |  | SEK0 |  |  | -10 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214734510 | SKADI:Det Testing: Testing of detector assembly | 41.51% | 53 | 2025-09-01 | 2025-11-12 | 30-Oct-25 | 2025-11-12 | 43 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214734600 | SKADI:Det Testing: Evaluation of the test results | 41.51% | 53 | 2025-09-01 | 2025-11-12 | 30-Oct-25 | 2025-11-12 | 43 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214734000 | SKADI:Det Housing: Leak test of the housings | 0% | 5 | 2025-10-07 | 2025-10-13 | 07-Oct-25 | 13-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 331 | [6 empty] | SEK0
NSS-A214734250 | SKADI:Polrzr Housg: Manufacturing and assembly | 0% | 40 | 2025-10-13 | 2025-12-05 | 13-Oct-25 | 2025-12-05 | 0 | SEK0 | SEK0 | Common FAT along with FOC considered. Qgate process shall also be for the entire unit-RK | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214734330 | SKADI:Spin Flipr: Manufacturing | 0% | 40 | 2025-10-13 | 2025-12-05 | 13-Oct-25 | 2025-12-05 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 278 | [6 empty] | SEK0 | SKADI
NSS-A214734340 | SKADI:FS: Manufacturing | 0% | 40 | 2025-10-13 | 2025-12-05 | 13-Oct-25 | 2025-12-05 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 278 | [6 empty] | SEK0 | SKADI
NSS-A2147226920 | SKADI: Final TG3: Review Docs by Technical Group | 0% | 14 | 2025-10-14 | 2025-10-31 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 747 | [6 empty] | SEK0
NSS-A214734040 | SKADI:Det Int into ESS-DAQ: Debugging and improvements, firmware updates | 0% | 50 | 2025-10-14 | 2025-12-22 | 14-Oct-25 | 2025-12-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 258 | [6 empty] | SEK0 | SKADI
NSS-A214734720 | SKADI:Hutch: Local SAT | 0% | 5 | 2025-11-03 | 2025-11-07 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 353 | [6 empty] | SEK0
NSS-A2147226900 | SKADI: Final TG3 Action closeouts | 0% | 20 | 2025-11-03 | 2025-11-28 | 2025-12-16 | 2026-01-26 | 31 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | 31 |  | 1 | [5 empty] | 747 | [6 empty] | SEK0 | SKADI
NSS-A2147226880 | SKADI: Final TG3 meeting | 0% | 0 | 2025-11-03 |  | 2025-12-16 |  | 31 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | 31 |  | 1 | [5 empty] | 747 | [6 empty] | SEK0 | SKADI
NSS-A214734030 | SKADI:Collimator: Local SAT | 0% | 15 | 2025-11-07 | 2025-11-27 | 06-Oct-25 | 24-Oct-25 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 347 | [6 empty] | SEK0 | SKADI
NSS-A214734730 | SKADI:Det Testing: Applying of improvements/time contingency | 0% | 10 | 2025-11-13 | 2025-11-26 | 2025-11-13 | 2025-11-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214735110 | SKADI:Det Testing: Preparation of the (CE) documentation | 0% | 25 | 2025-11-20 | 2026-01-07 | 2025-11-20 | 2026-01-07 | 0 | SEK0 | SEK0 | This is Oct 2025 in SS March-RK | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214735020 | SKADI:Det Testing: Update and modification of the project documentation for the FAT / Report | 0% | 15 | 2025-12-04 | 2026-01-07 | 2025-12-04 | 2026-01-07 | 0 | SEK0 | SEK0 | Matched with Smartsheet | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214734660 | SKADI:Samp Stage: Integration of sample stage | 0% | 5 | 2025-12-08 | 2025-12-12 | 08-Oct-25 | 14-Oct-25 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 338 | [6 empty] | SEK0 | SKADI
NSS-A214734470 | SKADI:Spin Flipr: Testing | 0% | 15 | 2025-12-08 | 2026-01-09 | 2025-12-08 | 2026-01-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 278 | [6 empty] | SEK0 | SKADI
NSS-A214734500 | SKADI:FS: Testing | 0% | 15 | 2025-12-08 | 2026-01-09 | 2025-12-08 | 2026-01-09 | 0 | SEK0 | SEK0 | CP-SKADI | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 278 | [6 empty] | SEK0 | SKADI
NSS-A214734540 | SKADI:Polrz+SF+FS: Assembly of Polarizer with optics and Chopper by FZJ | 0% | 20 | 2025-12-08 | 2026-01-16 | 2025-12-08 | 2026-01-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214734020 | SKADI:Collimator: Test readiness review (TRR) and approval | 0% | 3 | 2025-12-12 | 2025-12-16 | 2025-12-12 | 2025-12-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.TRR | 337 | [6 empty] | SEK0 | SKADI
NSS-A214734680 | SKADI: FOC: Test readiness review (TRR) and checklist sign off | 0% | 10 | 2025-12-12 | 2026-01-08 | 2025-12-12 | 2026-01-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.TRR | 319 | [6 empty] | SEK0 | SKADI
NSS-A214734490 | SKADI:Det Int into ESS-DAQ: Release of the software and documentation of Firmware and Software implementation | 0% | 55 | 2025-12-23 | 2026-03-23 | 2025-12-23 | 2026-03-23 | 0 | SEK0 | SEK0 | This is Oct 2025 in SS March-RK | SEK0 |  |  | 0 |  | 1 | [5 empty] | 258 | [6 empty] | SEK0 | SKADI
NSS-A214735200 | SKADI: Detector: FAT Report and Documentation | 0% | 10 | 2026-01-08 | 2026-01-21 | 2026-01-08 | 2026-01-21 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214735140 | SKADI: Detector: Factory Acceptance Test (FAT) | 0% | 0 | 2026-01-08 |  | 2026-01-08 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 259 | [6 empty] | SEK0 | SKADI
NSS-A214734750 | SKADI: FOC: System Acceptance Test (SAT) | 0% | 10 | 2026-01-09 | 2026-01-22 | 2026-01-09 | 2026-01-22 | 0 | SEK0 | SEK0 | If racks provided by chopper group, link to this activity will come from the chopper plan-RK | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 319 | [6 empty] | SEK0 | SKADI
NSS-A214734560 | SKADI:PSC: Integration of chopper into Polarizer, Fast Shutter, Spin Flipper and dismounting | 0% | 5 | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-01-23 | 0 | SEK0 | SEK0 | (Unit arriving at ESS as integrated?-RK) (Clarification has been conidered in the sequences of installation at ESS/ MA) | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214732590 | SKADI:PSC: Submission of docs to ESS for IRR (ALAP) | 0% | 30 | 2026-01-20 | 2026-03-02 | 2026-01-20 | 2026-03-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 277 | [6 empty] | SEK0 | SKADI
NSS-A214735240 | SKADI: Detector: Submission of docs to ESS for IRR | 0% | 5 | 2026-01-22 | 2026-01-28 | 2026-01-22 | 2026-01-28 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 282 | [6 empty] | SEK0 | SKADI
NSS-A214735420 | SKADI: Detector: FAT- closure of open points and approval | 0% | 10 | 2026-01-22 | 2026-02-04 | 2026-01-22 | 2026-02-04 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214734860 | SKADI: FOC: SAT approval | 0% | 10 | 2026-01-23 | 2026-02-05 | 2026-01-23 | 2026-02-05 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 319 | [6 empty] | SEK0 | SKADI
NSS-A214734760 | SKADI:Polrz+SF+FS: Testing of the assembled unit | 0% | 13 | 2026-01-26 | 2026-02-11 | 2026-01-26 | 2026-02-11 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214735750 | SKADI: Detector: IRR doc review by ESS | 0% | 5 | 2026-01-29 | 2026-02-04 | 2026-01-29 | 2026-02-04 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 262 | [6 empty] | SEK0 | SKADI
NSS-A214735360 | SKADI: Detector: Submission of docs to ESS for Quality gate | 0% | 10 | 2026-01-29 | 2026-02-11 | 2026-01-29 | 2026-02-11 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214732790 | SKADI:PSC: Quality gate review and approval | 0% | 30 | 2026-02-03 | 2026-03-16 | 2026-02-03 | 2026-03-16 | 0 | SEK0 | SEK0 | (CE marked. duration to be reviewed?-RK) (Agree to be reduced/ MA) | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 277 | [6 empty] | SEK0 | SKADI
NSS-A214735480 | SKADI: Detector: Shipping period for the Detector | 0% | 7 | 2026-02-05 | 2026-02-13 | 2026-02-05 | 2026-02-13 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 279 | [6 empty] | SEK0 | SKADI
NSS-A214735120 | SKADI:Polrz+SF+FS: Quality gate document submission phase | 0% | 20 | 2026-02-10 | 2026-03-09 | 2026-02-10 | 2026-03-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214734780 | SKADI:Polrz+SF+FS: FAT for the entire unit ( Choppers+optics+ SF+FS) | 0% | 5 | 2026-02-12 | 2026-02-18 | 2026-02-12 | 2026-02-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 273 | [6 empty] | SEK0 | SKADI
NSS-A214735540 | SKADI: Detector: Quality gate review and approval | 0% | 20 | 2026-02-12 | 2026-03-11 | 2026-02-12 | 2026-03-11 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 259 | [6 empty] | SEK0 | SKADI
NSS-A214733150 | SKADI:HS: Test readiness review (TRR) and approval | 0% | 3 | 2026-02-17 | 2026-02-19 | 2025-11-28 | 2025-12-02 | -47 | SEK0 | SEK0 |  | SEK0 |  |  | -47 |  | 1 |  |  |  |  | COMM.TRR | 294 | [6 empty] | SEK0 | SKADI
NSS-A214735510 | SKADI: Detector: Arrival and inspection of of Detector | 0% | 4 | 2026-02-17 | 2026-02-20 | 2026-02-17 | 2026-02-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 279 | [6 empty] | SEK0 | SKADI
NSS-A214734740 | SKADI:Hutch: Test readiness review (TRR) and approval | 0% | 5 | 2026-02-17 | 2026-02-23 | 2025-12-05 | 2025-12-11 | -42 | SEK0 | SEK0 |  | SEK0 |  |  | -42 |  | 1 |  |  |  |  | COMM.TRR | 292 | [6 empty] | SEK0 | SKADI
NSS-A214734850 | SKADI:Polrz+SF+FS: FAT Report and Documentation | 0% | 3 | 2026-02-19 | 2026-02-23 | 2026-02-19 | 2026-02-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214734980 | SKADI:Polrz+SF+FS: FAT closure of open points and approval | 0% | 8 | 2026-02-19 | 2026-03-02 | 2026-02-19 | 2026-03-02 | 0 | SEK0 | SEK0 | (SS with predec-RK) (Yes, SS with longer duration like new template/ MA) | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A214734910 | SKADI:Polrz+SF+FS: IRR doc submission phase | 0% | 8 | 2026-02-19 | 2026-03-02 | 2026-02-19 | 2026-03-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 283 | [6 empty] | SEK0 | SKADI
NSS-A214733210 | SKADI:HS: System Acceptance Test (SAT) involving all tech groups | 0% | 5 | 2026-02-20 | 2026-02-26 | 2025-12-03 | 2025-12-09 | -47 | SEK0 | SEK0 |  | SEK0 |  |  | -47 | BUN D01 | 1 | COMM |  |  |  |  | 294 | [6 empty] | SEK0 | SKADI
NSS-A214735600 | SKADI: Detector Backend and Integration | 0% | 20 | 2026-02-23 | 2026-03-20 | 2026-02-23 | 2026-03-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 267 | [6 empty] | SEK0 | SKADI
NSS-A214734770 | SKADI:Hutch: System Acceptance Test (SAT) | 0% | 5 | 2026-02-24 | 2026-03-02 | 2025-12-12 | 2025-12-18 | -42 | SEK0 | SEK0 |  | SEK0 |  |  | -42 |  | 1 | COMM |  |  |  |  | 292 | [6 empty] | SEK0 | SKADI
NSS-A214733320 | SKADI:HS: SAT approval | 0% | 10 | 2026-02-27 | 2026-03-12 | 2025-12-10 | 2025-12-23 | -47 | SEK0 | SEK0 |  | SEK0 |  |  | -47 |  | 1 | COMM |  |  |  | COMM.SAT | 294 | [6 empty] | SEK0 | SKADI
NSS-A214735030 | SKADI:PSC: Shipping period for the Chopper to ESS | 0% | 5 | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-03-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 293 | [6 empty] | SEK0 | SKADI
NSS-A214735040 | SKADI:Polrz+SF+FS: Shipping period for the Polarizer, Fast Shutter, Spin Flliper | 0% | 5 | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-03-09 | 0 | SEK0 | SEK0 | (including chopper integrated?-RK) (refer to shippment of Chopper/ MA) | SEK0 |  |  | 0 |  | 1 | [5 empty] | 283 | [6 empty] | SEK0 | SKADI
NSS-A214735660 | SKADI:Polrz+SF+FS: IRR doc review by ESS | 0% | 5 | 2026-03-03 | 2026-03-09 | 2026-03-03 | 2026-03-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 261 | [6 empty] | SEK0 | SKADI
NSS-A214734940 | SKADI:Hutch: SAT approval | 0% | 10 | 2026-03-03 | 2026-03-16 | 2025-12-19 | 2026-01-15 | -42 | SEK0 | SEK0 |  | SEK0 |  |  | -42 |  | 1 |  |  |  |  | COMM.SAT | 292 | [6 empty] | SEK0 | SKADI
NSS-A214733360 | SKADI:PSC: IRR doc review by ESS | 0% | 10 | 2026-03-03 | 2026-03-16 | 2026-03-03 | 2026-03-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 255 | [6 empty] | SEK0 | SKADI
NSS-A214733850 | SKADI:OoB Guides: IRR doc submission for 2nd part | 0% | 5 | 2026-03-10 | 2026-03-16 | 2026-03-10 | 2026-03-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 252 | [6 empty] | SEK0 | SKADI
NSS-A214735160 | SKADI:Polrz+SF+FS: Quality gate review and approval | 0% | 10 | 2026-03-10 | 2026-03-23 | 2026-03-10 | 2026-03-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 273 | [6 empty] | SEK0 | SKADI
NSS-A214735760 | SKADI: Detector: IRR meeting prep | 0% | 3 | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 237 | [6 empty] | SEK0 | SKADI
NSS-A214735450 | SKADI: Detector: Prep for Installation | 0% | 4 | 2026-03-17 | 2026-03-20 | 2026-03-17 | 2026-03-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | SKADI
NSS-A214733300 | SKADI:PSC: IRR meeting prep | 0% | 5 | 2026-03-17 | 2026-03-23 | 2026-03-17 | 2026-03-23 | 0 | SEK0 | SEK0 | Feb 2025: Including the electrical documents for installation of electrical parts | SEK0 |  |  | 0 |  | 1 | [5 empty] | 255 | [6 empty] | SEK0 | SKADI
NSS-A214733900 | SKADI:OoB Guides: IRR doc reviewed by ESS for 2nd part | 0% | 5 | 2026-03-17 | 2026-03-23 | 2026-03-17 | 2026-03-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 252 | [6 empty] | SEK0 | SKADI
NSS-A214735290 | SKADI: Detector: Installation readiness review (IRR) | 0% | 0 | 2026-03-17 |  | 2026-03-17 |  | 0 | SEK0 | SEK0 | Jan 2025: anticipated the installation Jan-Feb 2026 which should be earier than the current installation date for the detector | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 259 | [6 empty] | SEK0 | SKADI
NSS-A214735070 | SKADI:PSC: Prep for Installation | 0% | 5 | 2026-03-24 | 2026-03-30 | 2026-03-24 | 2026-03-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 279 | [6 empty] | SEK0 | SKADI
NSS-A214735270 | SKADI:Polrz+SF+FS: Installation of Polarizer, Fast Shutter, Spin Flliper | 0% | 6 | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-03-31 | 0 | SEK0 | SEK0 | (Standalone installation without chopper?-RK) (Sequence of installation has been considered at ESS/ MA ) | SEK0 |  |  | 0 | D01 | 1 | INST |  |  |  |  | 251 | [6 empty] | SEK0 | SKADI
NSS-A214735590 | SKADI: Detector: Installation of detectors | 0% | 20 | 2026-03-24 | 2026-04-22 | 2026-03-24 | 2026-04-22 | 0 | SEK0 | SEK0 | (Aren't these detectors inside the detector vessel? Link from vessel?-RK) | SEK0 |  |  | 0 | D01 | 1 | INST |  |  |  |  | 236 | [6 empty] | SEK0 | SKADI
NSS-A214734920 | SKADI:PSC: Instrument readiness review (IRR)-( PSC+FS+SF) | 0% | 0 | 2026-03-24 |  | 2026-03-24 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 279 | [6 empty] | SEK0 | SKADI
NSS-A214734930 | SKADI:Polrz+SF+FS: Instrument Readiness Review (IRR)-( PSC+FS+SF) | 0% | 0 | 2026-03-24 |  | 2026-03-24 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 273 | [6 empty] | SEK0 | SKADI
NSS-A214733620 | SKADI:OoB Guides: IRR meeting for 2nd batch | 0% | 0 | 2026-03-24 |  | 2026-03-24 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 252 | [6 empty] | SEK0 | SKADI
NSS-A214733640 | SKADI:OoB Guides: Installation Prep for 2nd part | 0% | 5 | 2026-03-25 | 2026-03-31 | 2026-03-25 | 2026-03-31 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 251 | [6 empty] | SEK0 | SKADI
NSS-A214735350 | SKADI:Polrz+SF+FS: Test readiness review (TRR) and checklist sign off | 0% | 3 | 2026-04-01 | 2026-04-07 | 2026-04-01 | 2026-04-07 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.TRR | 271 | [6 empty] | SEK0 | SKADI
NSS-A214735390 | SKADI:PSC: Installation of entire unit ( PSC+FS+SF) | 0% | 10 | 2026-04-01 | 2026-04-16 | 2026-04-01 | 2026-04-16 | 0 | SEK0 | SEK0 | Feb 2025: Including electrical installation for both choppers | SEK0 |  |  | 0 | D01 | 1 | INST |  |  |  |  | 254 | [6 empty] | SEK0 | SKADI
NSS-A214733770 | SKADI:OoB Guides: Installation of 2nd part | 0% | 20 | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 251 | [6 empty] | SEK0 | SKADI
NSS-A214735430 | SKADI:PSC: Test readiness review (TRR) and checklist sign off | 0% | 2 | 2026-04-17 | 2026-04-20 | 2026-04-17 | 2026-04-20 | 0 | SEK0 | SEK0 | Cooling water not considered-RK | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.TRR | 254 | [6 empty] | SEK0 | SKADI
NSS-A214735460 | SKADI:PSC: Integrated SAT (with tech group) | 0% | 10 | 2026-04-21 | 2026-05-05 | 2026-04-21 | 05-May-26 | 0 | SEK0 | SEK0 | This is assumed to be the Local sub-system commissioning-RK | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 254 | [6 empty] | SEK0 | SKADI
NSS-A214735610 | SKADI: Detector: Test readiness review (TRR) and approval | 0% | 10 | 2026-04-23 | 2026-05-07 | 2026-04-23 | 07-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.TRR | 236 | [6 empty] | SEK0 | SKADI
NSS-A214733940 | SKADI:OoB Guides: SAT for 2nd part | 0% | 5 | 2026-05-04 | 2026-05-08 | 04-May-26 | 08-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 251 | [6 empty] | SEK0 | SKADI
NSS-A214735500 | SKADI:PSC: SAT approval | 0% | 5 | 2026-05-06 | 2026-05-12 | 06-May-26 | 12-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 254 | [6 empty] | SEK0 | SKADI
NSS-A214735620 | SKADI: Detector: System Acceptance Test (SAT) | 0% | 10 | 2026-05-08 | 2026-05-25 | 08-May-26 | 25-May-26 | 0 | SEK0 | SEK0 | (wouldn't be a combined SAT with vessel?-RK) | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 236 | [6 empty] | SEK0 | SKADI
NSS-A214733790 | SKADI:OoB Guides: SAT approval for 2nd part | 0% | 5 | 2026-05-11 | 2026-05-19 | 11-May-26 | 19-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 251 | [6 empty] | SEK0 | SKADI
NSS-A214735630 | SKADI: Detector: SAT approval | 0% | 11 | 2026-05-26 | 2026-06-09 | 26-May-26 | 2026-06-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 236 | [6 empty] | SEK0 | SKADI
NSS-A214734580 | SKADI:Samp Stage: System Acceptance Test (SAT) | 0% | 5 | 2026-06-02 | 2026-06-08 | 2026-06-02 | 2026-06-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 232 | [6 empty] | SEK0 | SKADI
NSS-A214734070 | SKADI:Collimator: Integrated System Acceptance Test (SAT) | 0% | 3 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-06-08 | 0 | SEK0 | SEK0 | (Integ SAT with chopper?-RK) | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 231 | [6 empty] | SEK0 | SKADI
NSS-A214734110 | SKADI: Det Tube: System Acceptance Test (SAT) | 0% | 3 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-06-08 | 0 | SEK0 | SEK0 | CUP interface not envisaged here-RK | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 232 | [6 empty] | SEK0 | SKADI
NSS-A214735440 | SKADI:Polrz+SF+FS: System Acceptance Test (SAT) | 0% | 2 | 2026-06-05 | 2026-06-08 | 2026-06-05 | 2026-06-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 232 | [6 empty] | SEK0 | SKADI
NSS-A214734590 | SKADI:Samp Stage: SAT approval | 0% | 5 | 2026-06-09 | 2026-06-15 | 2026-06-09 | 2026-06-15 | 0 | SEK0 | SEK0 | Reduced to 5 from 10 to accomodate MCA-RK | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 232 | [6 empty] | SEK0 | SKADI
NSS-A214734180 | SKADI: Det Tube: SAT approval | 0% | 5 | 2026-06-09 | 2026-06-15 | 2026-06-09 | 2026-06-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 232 | [6 empty] | SEK0 | SKADI
NSS-A214735490 | SKADI:Polrz+SF+FS: SAT approval | 0% | 5 | 2026-06-09 | 2026-06-15 | 2026-06-09 | 2026-06-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 232 | [6 empty] | SEK0 | SKADI
NSS-A214734140 | SKADI:Collimator: Integrated SAT approval | 0% | 6 | 2026-06-09 | 2026-06-16 | 2026-06-09 | 2026-06-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226810 | SKADI: Integrated cold commissioning | 0% | 20 | 2026-06-17 | 2026-07-15 | 2026-06-17 | 2026-07-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226770 | SKADI: Ready for cold Commissioning | 0% | 0 | 2026-06-17 |  | 2026-06-17 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 620 | [6 empty] | SEK0 | SKADI
NSS-A2147226830 | SKADI: Preparation for TG5 review meeting (Float 2 months) | 0% | 40 | 2026-07-16 | 2026-10-07 | 2026-07-16 | 07-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226820 | SKADI: Instrument complete (TG5/SAR start) | 0% | 0 | 2026-07-16 |  | 2026-07-16 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226850 | SKADI: TG5/SAR action closeouts and approval | 0% | 40 | 2026-10-08 | 2026-12-02 | 08-Oct-26 | 2026-12-02 | 0 | SEK0 | SEK0 | Priorities with In-kind partner to handle their activities. | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAR.A | 256 | [6 empty] | SEK0 | SKADI
NSS-A2147226840 | SKADI: TG5/SAR meeting | 0% | 0 | 2026-10-08 |  | 08-Oct-26 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAR.M | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226870 | SKADI: Prep for i-SRR | 0% | 10 | 2026-12-03 | 2026-12-16 | 2026-12-03 | 2026-12-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226890 | SKADI: All construction scope for the Instrument complete | 0% | 5 | 2027-04-20 | 2027-04-26 | 2027-02-19 | 2027-02-25 | -40 | SEK0 | SEK0 |  | SEK0 |  |  | -40 |  | 1 | [5 empty] | 150 | [6 empty] | SEK0 | SKADI
NSS-A214734670 | SKADI:Samp Stage: Delivery of sample stage | 0% | 5 | 01-Dec-25* | 2025-12-05 | 01-Oct-25 | 07-Oct-25 | -43 | SEK0 | SEK0 | Nov: The component will be delivered from FZJ not earlier regarding the storage and safty issue | SEK0 |  |  | -43 |  | 1 | PROC.DELIV |  |  |  |  | 338 | [6 empty] | SEK0 | SKADI
NSS-A2147226910 | SKADI: Final TG3 Approval | 0% | 0 |  | 2025-11-28 |  | 2026-01-26 | 31 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | 31 |  | 1 | [5 empty] | 747 | [6 empty] | SEK0 | SKADI
NSS-A214734450 | SKADI:Hutch: CEP energization complete | 0% | 0 |  | 2025-12-04 |  | 2025-12-04 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | ENERG |  |  |  |  | 334 | [6 empty] | SEK0 | SKADI
NSS-A214734050 | SKADI:Det Int into ESS-DAQ: ECDC/DMSC integration acceptance | 0% | 0 |  | 2025-12-22 |  | 2025-12-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 238 | [6 empty] | SEK0 | SKADI
NSS-A214734790 | SKADI:Spin Flipr: FAT for spin flipper complete | 0% | 0 |  | 2026-02-18 |  | 2026-02-18 | 0 | SEK0 | SEK0 | Common FAT along with FOC considered. Qgate process shall also be for the entire unit-RK | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 273 | [6 empty] | SEK0 | SKADI
NSS-A214734800 | SKADI:FS: FAT for fast shutter complete | 0% | 0 |  | 2026-02-18 |  | 2026-02-18 | 0 | SEK0 | SEK0 | Common FAT along with FOC considered. Qgate process shall also be for the entire unit-RK | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 273 | [6 empty] | SEK0 | SKADI
NSS-A214735050 | SKADI:Polrz+SF+FS: Delivery of Polarizer, Fast Shutter, Spin Flliper | 0% | 0 |  | 2026-03-09 |  | 2026-03-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | PROC.DELIV |  |  |  |  | 283 | [6 empty] | SEK0 | SKADI
NSS-A214735060 | SKADI:PSC: Delivery to ESS | 0% | 0 |  | 2026-03-10 |  | 2026-03-10 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | PROC.DELIV |  |  |  |  | 293 | [6 empty] | SEK0 | SKADI
NSS-A214735550 | SKADI: Detector: TG4 completed for detectors | 0% | 0 |  | 2026-03-20 |  | 2026-03-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 771 | [6 empty] | SEK0 | SKADI
NSS-A214735080 | SKADI:PSC: TG4 completed | 0% | 0 |  | 2026-03-24 |  | 2026-03-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 284 | [6 empty] | SEK0 | SKADI
NSS-A214735170 | SKADI:Polrz+SF+FS: TG4 completed for the component | 0% | 0 |  | 2026-03-24 |  | 2026-03-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 273 | [6 empty] | SEK0 | SKADI
NSS-A2147226760 | SKADI: TG4 | 0% | 0 |  | 2026-03-24 |  | 2026-03-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 676 | [6 empty] | SEK0 | SKADI
NSS-A2147226780 | All In-Bunker SAT Approval | 0% | 0 |  | 2026-04-28 |  | 2026-04-28 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 263 | [6 empty] | SEK0 | SKADI
NSS-A2147226790 | All Out-Bunker SAT Approval | 0% | 0 |  | 2026-06-16 |  | 2026-06-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | COMM.SAT | 231 | [6 empty] | SEK0 | SKADI
NSS-A2147226800 | SKADI: TG5 | 0% | 0 |  | 2026-12-02 |  | 2026-12-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 520 | [6 empty] | SEK0 | SKADI
NSS-A2147226860 | SKADI TG5/SAR approval | 0% | 0 |  | 2026-12-02 |  | 2026-12-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | Instruments.TG5 | 231 | [6 empty] | SEK0 | SKADI

## CDR IRR sep-25 vs replanning
Activity ID | Activity Name | Activity % Complete | Original Duration | Budgeted Total Cost | Activity Count | Start | Finish | BL1 Start | BL1 Finish | Variance - BL1 Finish Date | Budgeted Nonlabor Cost | Budgeted Labor Cost | Earned Value Cost | Remaining Total Cost | Activity Notes | user_text8 | ESS 2023 Key Milestones | Variance - BL1 Start Date | NSS Area Code | Phase | ESS Activity Development Code | BL2 Finish | BL2 Start | ESS Milestone | Total Float | IK to Cash | In Kind | In Kind Country | In Kind Generate Cost | In Kind Planned Partner | In Kind TA status | Schedule Variance | Instrument
13-NSS-P09-25 Neutron Scattering Systems - P09-2025 Lockdown |  |  | 462 | SEK0 | 18 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-03-27 | 3 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1 NSS |  |  | 462 | SEK0 | 18 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-03-27 | 3 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1.7 NSS Instrument Construction |  |  | 462 | SEK0 | 18 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-03-27 | 3 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7 Instrument SKADI |  |  | 462 | SEK0 | 18 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-03-27 | 3 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7.1 SKADI replan |  |  | 462 | SEK0 | 18 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-03-27 | 3 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7.1.3 Out-Bunker |  |  | 462 | SEK0 | 18 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-03-27 | 3 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7.1.3.1 Beam Transport and Conditioning |  |  | 462 | SEK0 | 12 | 01-Mar-24 A | 2026-03-24 | 2024-03-01 | 2026-02-24 | -20 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 257 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7.1.3.1.1 Pulse Shaping Chopper |  |  | 0 | SEK0 | 1 | 2026-03-24 | 2026-03-24 | 2026-02-24 | 2026-02-24 | -20 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -20 | [6 empty] | 279 | [6 empty] | SEK0
NSS-A214734920 | SKADI:PSC: Instrument readiness review (IRR)-( PSC+FS+SF) | 0% | 0 | SEK0 | 1 | 2026-03-24 |  | 2026-02-24 |  | -20 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -20 | [5 empty] | INST.IRR | 279 | [6 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.2 Polarizer, Fast Shutter, Spin Flipper |  |  | 452 | SEK0 | 5 | 17-May-24 A | 2026-03-24 | 17-May-24 | 2026-02-24 | -20 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 273 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7.1.3.1.2.1 Polarizer |  |  | 132 | SEK0 | 2 | 17-May-24 A | 22-Nov-24 A | 17-May-24 | 2024-11-22 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
13-NSS-P09-25.1.7.7.1.3.1.2.1.2 Polarizer housing |  |  | 0 | SEK0 | 1 | 22-Nov-24 A | 22-Nov-24 A | 2024-11-22 | 2024-11-22 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214732660 | SKADI:Polrzr Housg: CDR | 100% | 0 | SEK0 | 1 | 22-Nov-24 A |  | 2024-11-22 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.2.1.3 Polarizer optics |  |  | 0 | SEK0 | 1 | 17-May-24 A | 17-May-24 A | 17-May-24 | 17-May-24 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214730970 | SKADI:Polrzr Opt: CDR | 100% | 0 | SEK0 | 1 | 17-May-24 A |  | 17-May-24 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.2.3 Spin Flipper |  |  | 0 | SEK0 | 1 | 22-Nov-24 A | 22-Nov-24 A | 2024-11-22 | 2024-11-22 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214732700 | SKADI:Spin Flipr: CDR | 100% | 0 | SEK0 | 1 | 22-Nov-24 A |  | 2024-11-22 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.2.4 Fast Shutter |  |  | 0 | SEK0 | 1 | 22-Nov-24 A | 22-Nov-24 A | 2024-11-22 | 2024-11-22 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214732710 | SKADI:FS: CDR | 100% | 0 | SEK0 | 1 | 22-Nov-24 A |  | 2024-11-22 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.2.5 Common activities-Polarizer-SF-FS |  |  | 0 | SEK0 | 1 | 2026-03-24 | 2026-03-24 | 2026-02-24 | 2026-02-24 | -20 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -20 | [6 empty] | 273 | [6 empty] | SEK0
NSS-A214734930 | SKADI:Polrz+SF+FS: Instrument Readiness Review (IRR)-( PSC+FS+SF) | 0% | 0 | SEK0 | 1 | 2026-03-24 |  | 2026-02-24 |  | -20 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -20 | [5 empty] | INST.IRR | 273 | [6 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.3 Frame Overlap Chopper |  |  | 0 | SEK0 | 1 | 04-Mar-25 A | 04-Mar-25 A | 2025-03-11 | 2025-03-11 | 5 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 5 | [13 empty] | SEK0
NSS-A214734220 | SKADI: FOC: Instrument readiness review (IRR) | 100% | 0 | SEK0 | 1 | 04-Mar-25 A |  | 2025-03-11 |  | 5 | SEK0 | SEK0 | SEK0 | SEK0 | (Calendar-RK) (Changed/ MA) |  |  | 5 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.4 Guides |  |  | 192 | SEK0 | 2 | 12-Aug-24 A | 27-May-25 A | 2024-08-12 | 21-May-25 | -4 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214731310 | SKADI:OoB Guides: CDR | 100% | 0 | SEK0 | 1 | 12-Aug-24 A |  | 2024-08-12 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
NSS-A214732770 | SKADI:OoB Guides: Installation readiness review (IRR) | 100% | 0 | SEK0 | 1 | 27-May-25 A |  | 21-May-25 |  | -4 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -4 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.5 Collimator |  |  | 0 | SEK0 | 1 | 30-Oct-24 A | 30-Oct-24 A | 30-Oct-24 | 30-Oct-24 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214733480 | SKADI:Collimator: Installation readiness review (IRR) | 100% | 0 | SEK0 | 1 | 30-Oct-24 A |  | 30-Oct-24 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.6 Collimator Shielding |  |  | 69 | SEK0 | 2 | 01-Mar-24 A | 17-Jun-24 A | 2024-03-01 | 2024-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214730200 | SKADI:Collim Shield: CDR | 100% | 0 | SEK0 | 1 | 01-Mar-24 A |  | 2024-03-01 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.1.6.1.5.1.6.6 Walls |  |  | 0 | SEK0 | 1 | 17-Jun-24 A | 17-Jun-24 A | 2024-06-17 | 2024-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214731440 | SKADI:Collim Shield: Installation readiness review (IRR) - Walls | 100% | 0 | SEK0 | 1 | 17-Jun-24 A |  | 2024-06-17 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.3 Detector, Detector Shielding/ Cave |  |  | 456 | SEK0 | 4 | 02-May-24 A | 2026-03-17 | 02-May-24 | 2026-03-27 | 8 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 259 | [6 empty] | SEK0
13-NSS-P09-25.1.7.7.1.3.3.1 Detector |  |  | 0 | SEK0 | 1 | 2026-03-17 | 2026-03-17 | 2026-03-27 | 2026-03-27 | 8 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 8 | [6 empty] | 259 | [6 empty] | SEK0
NSS-A214735290 | SKADI: Detector: Installation readiness review (IRR) | 0% | 0 | SEK0 | 1 | 2026-03-17 |  | 2026-03-27 |  | 8 | SEK0 | SEK0 | SEK0 | SEK0 | Jan 2025: anticipated the installation Jan-Feb 2026 which should be earier than the current installation date for the detector |  |  | 8 | [5 empty] | INST.IRR | 259 | [6 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.3.2 Detector Tube |  |  | 0 | SEK0 | 1 | 24-Feb-25 A | 24-Feb-25 A | 2025-02-24 | 2025-02-24 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214732090 | SKADI: Det Tube: Installation readiness review (IRR) | 100% | 0 | SEK0 | 1 | 24-Feb-25 A |  | 2025-02-24 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.3.3 Detector Shielding |  |  | 32 | SEK0 | 2 | 02-May-24 A | 20-Jun-24 A | 02-May-24 | 2024-06-20 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214730210 | SKADI: Det shield: CDR/sub-TG3 review | 100% | 0 | SEK0 | 1 |  | 02-May-24 A |  | 02-May-24 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.3.3.1 Walls |  |  | 0 | SEK0 | 1 | 20-Jun-24 A | 20-Jun-24 A | 2024-06-20 | 2024-06-20 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214731350 | SKADI: Det shield: Installation readiness review (IRR) - Walls | 100% | 0 | SEK0 | 1 |  | 20-Jun-24 A |  | 2024-06-20 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI
13-NSS-P09-25.1.7.7.1.3.4 Hutch |  |  | 162 | SEK0 | 2 | 06-Sep-24 A | 09-May-25 A | 2024-09-06 | 2025-03-31 | -26 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214733100 | SKADI:Hutch: CDR | 100% | 0 | SEK0 | 1 | 06-Sep-24 A |  | 2024-09-06 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | SKADI
NSS-A214733890 | SKADI:Hutch: Installation readiness review (IRR) | 100% | 0 | SEK0 | 1 | 09-May-25 A |  | 2025-03-31 |  | -26 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -26 | [5 empty] | INST.IRR | [7 empty] | SEK0 | SKADI

## Milestones (hidden)
Activity ID | Activity Name | Activity % Complete | Start date (Sep 24) | Start date (April 25) | Variance - BL1 Start Date | Variance start date (month)
NSS-A2147510270 | MAGIC: XYZ: Factory Acceptance Test (FAT) | 0% | 2024-11-26 | 2025-05-20 | -112 | -5.6
NSS-A214757070 | MAGIC:Polarizer: CDR (meeting) | 0% | 2024-12-09 | 2025-06-04 | -111 | -5.55
NSS-A214756690 | MAGIC:OoB VH & Supp Sec 1: CDR (meeting) | 0% | 2025-02-05 | 2025-06-19 | -90 | -4.5
NSS-A214757350 | MAGIC:RF SF: CDR (meeting) | 0% | 2025-02-10 | 2025-07-02 | -95 | -4.75
NSS-A2147510050 | MAGIC: Good Lift: Factory Acceptance Test (FAT) | 0% | 2025-03-11 | 2025-08-20 | -109 | -5.45
NSS-A214756020 | MAGIC:Guid+VH+Supp (in-bunker):Factory Acceptance Test (FAT) | 0% | 2025-03-14 | 2026-01-13 | -198 | -9.9
NSS-A214757790 | MAGIC: Sample St: CDR (meeting) | 0% | 2025-04-14 | 2025-09-01 | -73 | -3.65
NSS-A214758640 | MAGIC: Det A: Factory Acceptance Test (FAT) | 0% | 2025-05-12 | 2025-12-05 | -145 | -7.25
NSS-A214758050 | MAGIC:Supp-RC+Det A: CDR (meeting) | 0% | 2025-06-10 | 2025-09-30 | -59 | -2.95
NSS-A214756290 | MAGIC:BWF:Factory Acceptance Test (FAT) | 0% | 2025-07-25 | 2025-11-20 | -84 | -4.2

## Procurement (hidden)
Activity Name | Activity % Complete | Start date (Sep 24) | Finish date (Sep 24) | Start date (April 25) | Finish date (April 25) | Variance - BL1 Start Date | Variance - BL1 Finish Date | Variance finish date (month)
MAGIC: Analyzer Seg 1: Procurement and manufacturing of the Component | 82.24% | 2024-04-02 | 2025-07-25 | 02-Apr-24 A | 2025-07-25 | 0 | 0 | 0 | In manufacturing? Contract in place?
MAGIC: XYZ: Procurement and manufacturing of the Component | 75% | 2024-04-02 | 2024-11-25 | 02-Apr-24 A | 19-May-25 | 0 | -112 | -5.6
MAGIC:Guid+VH+Supp: Procurement of the Component | 70% | 2024-06-03 | 2025-03-13 | 03-Jun-24 A | 17-Apr-25 A | 0 | -25 | -1.25
MAGIC: RC: Procurement and manufacturing of Radial Collimator | 68.81% | 2024-09-16 | 2025-06-17 | 16-Sep-24 A | 2025-09-08 | 0 | -38 | -1.9
MAGIC: Analyzer: Seg 2: Procurement and manufacturing of the Component | 0% | 2024-11-06 | 2026-04-15 | 2025-07-28 | 2026-04-16 | -171 | -1 | -0.05
MAGIC:BWF:Procurement and manufacturing of the Component | 6.67% | 2024-12-04 | 2025-07-24 | 15-Apr-25 A | 2025-11-19 | -84 | -84 | -4.2
MAGIC:Polarizer: Procurement and manufacturing of the Component | 0% | 2025-01-13 | 2025-06-09 | 2025-06-27 | 2025-11-13 | -112 | -112 | -5.6
MAGIC:RF SF: Procurement and manufacturing of the Component | 0% | 2025-02-24 | 2025-07-08 | 2025-07-16 | 2025-11-18 | -95 | -95 | -4.75
MAGIC:OoB VH & Supp Sec 1: Procurement of OoB housing and supports | 0% | 2025-02-26 | 23-Oct-25 | 2025-07-11 | 30-Oct-25 | -90 | -5 | -0.25 | In manufacturing? Contract in place?
MAGIC:OoB VH & Supp Sec 2: Procurement of OoB housing and supports | 0% |  |  | 2025-07-15 | 2025-11-03 |  |  | 0
MAGIC:OoB VH & Supp Sec 3: Procurement of OoB housing and supports | 0% |  |  | 2025-08-18 | 2025-11-07 |  |  | 0
MAGIC: Sample St: Procurement and manufacturing of the Component | 0% | 2025-04-30 | 2025-09-09 | 2025-09-15 | 2026-02-03 | -93 | -93 | -4.65
MAGIC: Supp- Analzr+Det B: Procurement and manufacturing of the Component | 0% | 2025-09-15 | 2026-02-17 | 2025-07-25 | 2025-12-11 | 36 | 36 | 1.8 | In manufacturing? Contract in place?
MAGIC:Supp-RC+Det A: Procurement and manufacturing of the Component | 0% | 2025-06-25 | 2025-11-11 | 14-Oct-25 | 2026-03-18 | -79 | -79 | -3.95 | -79 | -79

## Sheet4 (hidden)
Activity ID | Activity Name | Activity % Complete | Original Duration | Start (juni lockdown) | Finish (juni lockdown) | Start (juni lockdown) | Finish (juni lockdown) | Start (december lockdown) | Finish (december lockdown) | Variance start date | Variance finish date
13-NSS-P06-24.1.7.16.16.11 Technology groups/Common Projects |  |  | 318 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.1 Common Electrical Project |  |  | 188 | [6 empty] | 0 | 0
NSS-A2147186560 | Common electrical project offer accepted | 0% | 0 |  | 2024-08-21 |  | 2024-08-21 |  | 2025-01-30 | 0 | -117
13-NSS-P06-24.1.7.16.16.11.1.1 CEP milestones to be met by Instrument for start of Detail design |  |  | 18 | [6 empty] | 0 | 0
NSS-A2147186570 | MIRACLES: CEP: Updated PID released in CHESS | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186580 | MIRACLES: CEP: Updated EPL model available | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186590 | MIRACLES: CEP: FBS/LBS is incorporated within the EPL model | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186600 | MIRACLES: CEP: Cave prelim design complete | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186610 | MIRACLES: CEP: CEP feedthroughs into cave agreed. | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186620 | MIRACLES: CEP: nstrument components/systems incorporated into the EPL model | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186630 | MIRACLES: CEP: All Rack/box positions incorporated within the EPL model. (with FBS in model) | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186690 | MIRACLES: CEP: All CEP requirement milestones completed | 0% | 0 |  | 2024-08-21 |  | 2024-08-21 |  | 2025-01-30 | 0 | -117
13-NSS-P06-24.1.7.16.16.11.1.2 CEP milestones to be met by Instrument for start of Installation |  |  | 0 | [6 empty] | 0 | 0
NSS-A2147186640 | MIRACLES: CEP:Cave installed and complete | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186650 | MIRACLES: CEP:Guide installations complete | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186660 | MIRACLES: CEP:Shield wall complete | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186670 | MIRACLES: CEP:Instrument ready for CEP installations | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186680 | MIRACLES: CEP: Approximate delivery of cabinets/racks provided | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186740 | MIRACLES: CEP:All CEP Installation reqmt milestones completed | 0% | 0 |  | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 | 0 | -137
13-NSS-P06-24.1.7.16.16.11.1.3 CEP Detailed Design |  |  | 100 | [6 empty] | 0 | 0
NSS-A2147186700 | MIRACLES: CEP: Detailed design (Inst zone) | 0% | 100 | 2024-08-22 | 2025-01-23 | 2024-08-22 | 2025-01-23 | 2025-01-31 | 2025-06-30 | -117 | -113
NSS-A2147186710 | MIRACLES: CEP: Detailed design (Bunker zone) | 0% | 60 | 2024-08-22 | 2024-11-13 | 2024-08-22 | 2024-11-13 | 2025-01-31 | 2025-04-28 | -117 | -119
13-NSS-P06-24.1.7.16.16.11.1.4 CEP Installation |  |  | 186 | [6 empty] | 0 | 0
NSS-A2147186750 | MIRACLES: CEP: Installation (Inst zone)- Infrastructure (cave) | 0% | 25 | 03-Jul-24* | 2024-09-03 | 2024-07-03 | 2024-09-03 | 2025-01-07 | 2025-02-10 | -135 | -115
NSS-A2147186760 | MIRACLES: CEP: Installation (Inst zone)- Cabling (cave) | 0% | 20 | 2024-09-04 | 2024-10-01 | 2024-09-04 | 2024-10-01 | 2025-02-11 | 2025-03-10 | -115 | -115
NSS-A2147186770 | MIRACLES: Inst Installation (Inst zone)- Level 3 cable termination (cave) complete (Incom link from Inst) | 0% | 0 | 2024-10-02 |  | 2024-10-02 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186800 | MIRACLES: Inst Installation (Inst zone)- Component (inside cave) ready for SAT (outgoing link to Inst) | 0% | 0 | 2024-10-02 |  | 2024-10-02 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186730 | MIRACLES: CEP: Installation (Bunker zone) | 0% | 50 | 2024-11-14 | 2025-02-06 | 2024-11-14 | 2025-02-06 | 2025-04-29 | 2025-07-14 | -119 | -113
NSS-A2147186720 | MIRACLES: CEP: Installation (Inst zone)- Infrastructure (excluding cave) | 0% | 30 | 2025-01-24 | 2025-03-06 | 2025-01-24 | 2025-03-06 | 2025-07-01 | 2025-09-08 | -113 | -133
NSS-A2147187280 | MIRACLES: CEP: Installation (Inst zone)- Cabling (excluding cave) | 0% | 25 | 2025-03-07 | 2025-04-10 | 2025-03-07 | 2025-04-10 | 2025-09-09 | 2025-10-13 | -133 | -133
NSS-A2147187290 | MIRACLES: Inst Installation (Inst zone)- false floors | 0% | 5 | 2025-04-11 | 2025-04-17 | 2025-04-11 | 2025-04-17 | 2025-10-14 | 2025-10-20 | -133 | -133
NSS-A2147187330 | MIRACLES:Inst Installation (Inst zone)- Level 3 cable termination (excluding cave) complete | 0% | 0 | 2025-04-11 |  | 2025-04-11 |  | 2025-10-14 |  | -133 | 0
NSS-A2147187300 | MIRACLES: Inst Installation (Inst zone)- Racks and cabinets installation complete | 0% | 0 | 2025-04-22 |  | 2025-04-22 |  | 2025-10-21 |  | -131 | 0
NSS-A2147187310 | MIRACLES: CEP: Level 2 termination | 0% | 5 | 2025-04-22 | 2025-04-28 | 2025-04-22 | 2025-04-28 | 2025-10-21 | 2025-10-27 | -131 | -131
NSS-A2147187320 | MIRACLES: CEP: Energization of racks | 0% | 5 | 2025-04-29 | 2025-05-06 | 2025-04-29 | 2025-05-06 | 2025-10-28 | 2025-11-03 | -131 | -130
NSS-A2147187340 | Component ready for testing at site | 0% | 0 | 2025-05-07 |  | 2025-05-07 |  | 2025-11-04 |  | -130 | 0
13-NSS-P06-24.1.7.16.16.11.7 Common Shielding Project |  |  | 225 | [6 empty] | 0 | 0
NSS-A2147187120 | Detailed Design | 0% | 225 | 2024-07-01 | 2025-07-02 | 2024-07-01 | 2025-07-02 | 2025-01-07 | 2026-01-07 | -137 | -136
NSS-A2147187130 | Manufacturing and Procurment | 0% | 225 | 2024-07-01 | 2025-07-02 | 2024-07-01 | 2025-07-02 | 2025-01-07 | 2026-01-07 | -137 | -136
NSS-A2147187140 | Installation | 0% | 175 | 2024-07-01 | 2025-04-14 | 2024-07-01 | 2025-04-14 | 2025-01-07 | 2025-10-15 | -137 | -133
13-NSS-P06-24.1.7.16.16.11.2 Common Utilities Project |  |  | 200 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.2.1 CUP milestones to be met by Instrument for start of Detail design |  |  | 0 | [6 empty] | 0 | 0
NSS-A2147187040 | Updated PID released in CHESS | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187050 | Updated EPL model available | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187060 | FBS/LBS is incorporated within the EPL model | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187070 | Cave prelim design complete | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187080 | CUP feedthroughs into cave agreed. | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187090 | Instrument components/systems incorporated into the EPL model | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187100 | All components requiring utility interface incorporated within the EPL model. (with FBS in model) | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187110 | All CUP requirement milestones completed | 0% | 0 |  | 2024-07-01 |  | 2024-07-01 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.6 Design |  |  | 65 | [6 empty] | 0 | 0
NSS-A2147349840 | MIRACLES CUP: Preliminary design phase | 0% | 15 | 2024-07-01 | 2024-08-16 | 2024-07-01 | 2024-08-16 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349790 | MIRACLES CUP: Detailed design phase (Piping) | 0% | 50 | 2024-08-19 | 2024-10-25 | 2024-08-19 | 2024-10-25 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349830 | MIRACLES CUP: PDR (Piping) | 0% | 0 | 2024-08-19 |  | 2024-08-19 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147349850 | MIRACLES CUP: Detail design phase for skids | 0% | 35 | 2024-08-19 | 2024-10-04 | 2024-08-19 | 2024-10-04 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349860 | MIRACLES CUP: CDR for skids and approval | 0% | 10 | 2024-10-07 | 2024-10-18 | 2024-10-07 | 2024-10-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349820 | MIRACLES CUP: CDR (Piping) | 0% | 0 | 2024-10-28 |  | 2024-10-28 |  | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.7 Manufacturing and Delivery |  |  | 45 | [6 empty] | 0 | 0
NSS-A2147349870 | MIRACLES CUP: Procurement and Order placement for skids | 0% | 30 | 2024-10-21 | 2024-11-29 | 2024-10-21 | 2024-11-29 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349900 | MIRACLES CUP: Procurement and Order placement (Piping) | 0% | 40 | 2024-10-28 | 2024-12-20 | 2024-10-28 | 2024-12-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349880 | MIRACLES CUP: Delivery of skids to ESS | 0% | 5 | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-06 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.8 Installation Preparation and Reviews |  |  | 120 | [6 empty] | 0 | 0
NSS-A2147349750 | MIRACLES CUP: Procurement and Installation (Piping & Skids)-CUP ESTIA | 0% | 120 | 2024-10-21 | 2025-04-23 | 2024-10-21 | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349920 | MIRACLES CUP: IRR preparation (skids) | 0% | 15 | 2024-12-02 | 2024-12-20 | 2024-12-02 | 2024-12-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349810 | MIRACLES CUP: IRR preparation (piping) | 0% | 20 | 2025-01-07 | 2025-02-03 | 2025-01-07 | 2025-02-03 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349740 | MIRACLES CUP: IRR (skids and piping) | 0% | 0 | 2025-02-04 |  | 2025-02-04 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147349760 | MIRACLES CUP: IPL work | 0% | 55 | 2025-02-04 | 2025-04-23 | 2025-02-04 | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349950 | MIRACLES CUP: Installation preparation | 0% | 10 | 2025-02-04 | 2025-02-17 | 2025-02-04 | 2025-02-17 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.4 Installation phase |  |  | 45 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.2.4.1 Bunker zone |  |  | 15 | [6 empty] | 0 | 0
NSS-A2147349930 | MIRACLES CUP: Installation of supports for vacuum manifold | 0% | 15 | 2025-02-18 | 2025-03-10 | 2025-02-18 | 2025-03-10 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349940 | MIRACLES CUP: Installation of piping for In bunker components | 0% | 15 | 2025-02-18 | 2025-03-10 | 2025-02-18 | 2025-03-10 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.4.5 Instrument zone |  |  | 45 | [6 empty] | 0 | 0
NSS-A2147349890 | MIRACLES CUP: Installation phase for skids | 0% | 10 | 2025-02-18 | 2025-03-03 | 2025-02-18 | 2025-03-03 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349960 | MIRACLES CUP: Installation phase-Cave exterior | 0% | 30 | 2025-02-18 | 2025-03-31 | 2025-02-18 | 2025-03-31 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349980 | MIRACLES CUP: Installation phase-Galleries Level 90 | 0% | 20 | 2025-02-18 | 2025-03-17 | 2025-02-18 | 2025-03-17 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349970 | MIRACLES CUP: Installation phase-Cave interior | 0% | 15 | 2025-04-01 | 2025-04-23 | 2025-04-01 | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.5 Final inspections and commissioning |  |  | 20 | [6 empty] | 0 | 0
NSS-A2147349910 | MIRACLES CUP: All installations complete | 0% | 0 |  | 2025-04-23 |  | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349990 | MIRACLES CUP: Mechanical inspection of installations | 0% | 5 | 2025-04-24 | 2025-04-30 | 2025-04-24 | 2025-04-30 | #N/A | #N/A | #N/A | #N/A
NSS-A2147350000 | MIRACLES CUP: Pressure testing and Quality control | 0% | 5 | 2025-05-02 | 2025-05-08 | 2025-05-02 | 2025-05-08 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349780 | MIRACLES CUP: Commissioning & final documentation | 0% | 10 | 2025-05-09 | 2025-05-22 | 2025-05-09 | 2025-05-22 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349770 | MIRACLES CUP: Documentation released (scope complete - feed into SRR) | 0% | 0 | 2025-05-23 |  | 2025-05-23 |  | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.3 Motion Control and Automation |  |  | 253 | [6 empty] | 0 | 0
NSS-A2147186780 | MCA MIRACLES: offer accepted and project kicked off | 0% | 5 | 16-Sep-24* | 2024-09-20 | 2024-09-16 | 2024-09-20 | 2025-01-07 | 2025-01-13 | -82 | -82
NSS-A2147186790 | MCA MIRACLES: Sheet 4 of Table of Motion fully filled | 0% | 0 | 16-Sep-24* |  | 2024-09-16 |  | 2025-01-07 |  | -82 | 0
13-NSS-P06-24.1.7.16.16.11.3.1 D03 Hall (Bunker Zone) |  |  | 130 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.3.1.4 Junction boxes |  |  | 48 | [6 empty] | 0 | 0
NSS-A2147350250 | MCA MIRACLES: Design, Eplan of junction box (for switches)) | 0% | 15 | 2024-09-23 | 2024-10-11 | 2024-09-23 | 2024-10-11 | 2025-01-14 | 2025-02-03 | -82 | -82
NSS-A2147350260 | MCA MIRACLES: Procurement of junction box (for switches) | 0% | 30 | 2024-10-14 | 2024-11-22 | 2024-10-14 | 2024-11-22 | 2025-02-04 | 2025-03-17 | -82 | -82
NSS-A2147350270 | MCA MIRACLES: Installation of junction box (for switches)) | 0% | 3 | 2024-11-25 | 2024-11-27 | 2024-11-25 | 2024-11-27 | 2025-03-18 | 2025-03-20 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.1.3 Wall boxes |  |  | 56 | [6 empty] | 0 | 0
NSS-A2147350130 | MCA MIRACLES: Design , Eplan of wall boxes (pneumatic box ) | 0% | 15 | 2024-09-30 | 2024-10-18 | 2024-09-30 | 2024-10-18 | 2025-01-21 | 2025-02-10 | -82 | -82
NSS-A2147350140 | MCA MIRACLES: Procurement and adaptation of wall boxes (pneumatic box ) | 0% | 36 | 2024-10-21 | 2024-12-09 | 2024-10-21 | 2024-12-09 | 2025-02-11 | 2025-04-01 | -82 | -82
NSS-A2147350150 | MCA MIRACLES: Installation of wall boxes (pneumatic box ) | 0% | 5 | 2024-12-10 | 2024-12-16 | 2024-12-10 | 2024-12-16 | 2025-04-02 | 2025-04-08 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.1.5 Cabinets |  |  | 56 | [6 empty] | 0 | 0
NSS-A2147350100 | MCA MIRACLES: Design, Eplan of cabinet 1 (shutter cabinet) | 0% | 15 | 2024-10-07 | 2024-10-25 | 2024-10-07 | 2024-10-25 | 2025-01-28 | 2025-02-17 | -82 | -82
NSS-A2147350110 | MCA MIRACLES: Procurement of cabinet 1 (shutter cabinet) | 0% | 36 | 2024-10-28 | 2024-12-16 | 2024-10-28 | 2024-12-16 | 2025-02-18 | 2025-04-08 | -82 | -82
NSS-A2147350120 | MCA MIRACLES: Installation of cabinet 1 (shutter cabinet) link pred install false floor | 0% | 5 | 2024-12-17 | 2025-01-07 | 2024-12-17 | 2025-01-07 | 2025-04-09 | 2025-04-15 | -82 | -71
13-NSS-P06-24.1.7.16.16.11.3.1.6 MCA L3 and energization |  |  | 60 | [6 empty] | 0 | 0
NSS-A2147350160 | MCA MIRACLES: Design of all MCA cables, cable data base (CDB), label list | 0% | 15 | 2024-10-28 | 2024-11-15 | 2024-10-28 | 2024-11-15 | 2025-02-18 | 2025-03-10 | -82 | -82
NSS-A2147350170 | MCA MIRACLES: Procurement and labelling of all MCA cables | 0% | 30 | 2024-11-18 | 2025-01-13 | 2024-11-18 | 2025-01-13 | 2025-03-11 | 2025-04-23 | -82 | -73
NSS-A2147350180 | MCA MIRACLES: Termination and testing of all installed cables | 0% | 10 | 2025-01-14 | 2025-01-27 | 2025-01-14 | 2025-01-27 | 2025-04-24 | 2025-05-08 | -73 | -74
NSS-A2147350430 | MCA MIRACLES: Final energization of cabinets Bunker Zone | 0% | 5 | 2025-01-28 | 2025-02-03 | 2025-01-28 | 2025-02-03 | 2025-05-09 | 2025-05-15 | -74 | -74
13-NSS-P06-24.1.7.16.16.11.3.1.1 MCA control system setup Bunker Zone |  |  | 45 | [6 empty] | 0 | 0
NSS-A2147350370 | MCA MIRACLES: Setting up of control systems (not related to ICS) | 0% | 10 | 2025-02-04 | 2025-02-17 | 2025-02-04 | 2025-02-17 | 2025-05-16 | 2025-06-02 | -74 | -76
NSS-A2147350380 | MCA MIRACLES: Commissioning of subsystem related to respective cabinets | 0% | 15 | 2025-02-18 | 2025-03-10 | 2025-02-18 | 2025-03-10 | 2025-06-03 | 2025-06-25 | -76 | -78
NSS-A2147350390 | MCA MIRACLES: Configuration of interfaces to EPICS/NICOS in bunker | 0% | 10 | 2025-03-11 | 2025-03-24 | 2025-03-11 | 2025-03-24 | 2025-06-26 | 2025-07-09 | -78 | -78
NSS-A2147350540 | MCA MIRACLES: Local SAT D03 with ECDC/ICS for motion control testing with EPICS/NICOS | 0% | 10 | 2025-03-25 | 2025-04-07 | 2025-03-25 | 2025-04-07 | 2025-07-10 | 2025-08-20 | -78 | -98
13-NSS-P06-24.1.7.16.16.11.3.3 E02 Hall (Instrument Zone)-if applicable for MCA |  |  | 88 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.3.3.4 Junction boxes |  |  | 9 | [6 empty] | 0 | 0
NSS-A2147350190 | MCA MIRACLES: Design, Eplan of junction box (for switches) | 0% | 2 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2025-01-07 | 2025-01-08 | -137 | -137
NSS-A2147350200 | MCA MIRACLES: Procurement of junction box(for switches) | 0% | 5 | 2024-07-03 | 2024-07-09 | 2024-07-03 | 2024-07-09 | 2025-01-09 | 2025-01-15 | -137 | -137
NSS-A2147350210 | MCA MIRACLES: Installation of junction box(for switches) | 0% | 2 | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-11 | 2025-01-16 | 2025-01-17 | -137 | -137
13-NSS-P06-24.1.7.16.16.11.3.3.3 Wall boxes |  |  | 48 | [6 empty] | 0 | 0
NSS-A2147350220 | MCA MIRACLES: Design , Eplan of wall boxes (pneumatic box ) | 0% | 12 | 2024-07-01 | 2024-08-13 | 2024-07-01 | 2024-08-13 | 2025-01-07 | 2025-01-22 | -137 | -117
NSS-A2147350230 | MCA MIRACLES: Procurement of wall boxes (pneumatic box ) | 0% | 34 | 2024-08-14 | 2024-09-30 | 2024-08-14 | 2024-09-30 | 2025-01-23 | 2025-03-11 | -117 | -117
NSS-A2147350240 | MCA MIRACLES: Installation of wall boxes (pneumatic box ) | 0% | 2 | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-02 | 2025-03-12 | 2025-03-13 | -117 | -117
13-NSS-P06-24.1.7.16.16.11.3.3.2 Cabinets |  |  | 22 | [6 empty] | 0 | 0
NSS-A2147350310 | MCA MIRACLES: Design, Eplan of cabinet 2.1 (EC node wall box) | 0% | 15 | 2024-07-01 | 2024-08-16 | 2024-07-01 | 2024-08-16 | 2025-01-07 | 2025-01-27 | -137 | -117
NSS-A2147350320 | MCA MIRACLES: Procurement of cabinet 2.1 (EC node wall box) | 0% | 6 | 2024-08-19 | 2024-08-26 | 2024-08-19 | 2024-08-26 | 2025-01-28 | 2025-02-04 | -117 | -117
NSS-A2147350330 | MCA MIRACLES: Installation of cabinet 2.1 (EC node wall box) | 0% | 1 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2025-02-05 | 2025-02-05 | -117 | -117
13-NSS-P06-24.1.7.16.16.11.3.3.1 MCA L3 and energization |  |  | 63 | [6 empty] | 0 | 0
NSS-A2147350280 | MCA MIRACLES: Design of all MCA cables, cable data base (CDB), label list | 0% | 5 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-05 | 2025-01-07 | 2025-01-13 | -137 | -137
NSS-A2147350290 | MCA MIRACLES: Procurement and labelling of all MCA cables | 0% | 30 | 2024-07-08 | 2024-09-13 | 2024-07-08 | 2024-09-13 | 2025-01-14 | 2025-02-24 | -137 | -117
NSS-A2147350300 | MCA MIRACLES: Termination of all installed cables E02 | 0% | 10 | 2024-10-03 | 2024-10-16 | 2024-10-03 | 2024-10-16 | 2025-03-14 | 2025-03-27 | -117 | -117
NSS-A2147350500 | MCA MIRACLES: Final energization of cabinets E02 Hall instrument Zone | 0% | 5 | 2024-10-17 | 2024-10-23 | 2024-10-17 | 2024-10-23 | 2025-03-28 | 2025-04-03 | -117 | -117
13-NSS-P06-24.1.7.16.16.11.3.3.5 MCA control system setup E02 Instrument Zone |  |  | 88 | [6 empty] | 0 | 0
NSS-A2147350480 | MCA MIRACLES: Temporary energization of MCA cabinets E02 | 0% | 5 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-05 | 2025-01-07 | 2025-01-13 | -137 | -137
NSS-A2147350450 | MCA MIRACLES: Setting up of control systems | 0% | 5 | 2024-07-08 | 2024-07-12 | 2024-07-08 | 2024-07-12 | 2025-01-14 | 2025-01-20 | -137 | -137
NSS-A2147350460 | MCA MIRACLES: Commissioning of subsystem related to respective cabinets | 0% | 10 | 2024-10-24 | 2024-11-06 | 2024-10-24 | 2024-11-06 | 2025-04-04 | 2025-04-17 | -117 | -117
NSS-A2147350470 | MCA MIRACLES: Configuration of interfaces to EPICS/NICOS E02 | 0% | 5 | 2024-11-07 | 2024-11-13 | 2024-11-07 | 2024-11-13 | 2025-04-22 | 2025-04-28 | -119 | -119
NSS-A2147350530 | MCA MIRACLES: Local SAT EO2 with ECDC/ICS for motion control testing with EPICS/NICOS | 0% | 10 | 2024-11-14 | 2024-11-27 | 2024-11-14 | 2024-11-27 | 2025-04-29 | 2025-05-13 | -119 | -120
13-NSS-P06-24.1.7.16.16.11.3.2 E01 Hall (Instrument Zone) |  |  | 198 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.3.2.4 Junction boxes |  |  | 55 | [6 empty] | 0 | 0
NSS-A2147350010 | MCA MIRACLES: Design, Eplan of junction boxes (connection plates, switch boxes) | 0% | 22 | 2024-10-14 | 2024-11-12 | 2024-10-14 | 2024-11-12 | 2025-02-04 | 2025-03-05 | -82 | -82
NSS-A2147350020 | MCA MIRACLES: Procurement of junction boxes (connection plates, switch boxes) | 0% | 15 | 2024-11-13 | 2024-12-03 | 2024-11-13 | 2024-12-03 | 2025-03-06 | 2025-03-26 | -82 | -82
NSS-A2147350030 | MCA MIRACLES: Installation of junction boxes (connection plates, switch boxes) | 0% | 3 | 2025-01-09 | 2025-01-13 | 2025-01-09 | 2025-01-13 | 2025-04-17 | 2025-04-23 | -71 | -73
13-NSS-P06-24.1.7.16.16.11.3.2.3 Wall boxes |  |  | 50 | [6 empty] | 0 | 0
NSS-A2147350070 | MCA MIRACLES: Design, Eplan of wall boxes (pneumatic box, shutter operator panel ) | 0% | 15 | 2024-10-21 | 2024-11-08 | 2024-10-21 | 2024-11-08 | 2025-02-11 | 2025-03-03 | -82 | -82
NSS-A2147350080 | MCA MIRACLES: Procurement of wall boxes (pneumatic box , shutter operator panel ) | 0% | 30 | 2024-11-11 | 2024-12-20 | 2024-11-11 | 2024-12-20 | 2025-03-04 | 2025-04-14 | -82 | -82
NSS-A2147350090 | MCA MIRACLES: Installation of wall boxes (pneumatic box, shutter operator panel ) | 0% | 5 | 2025-01-07 | 2025-01-13 | 2025-01-07 | 2025-01-13 | 2025-04-15 | 2025-04-23 | -71 | -73
13-NSS-P06-24.1.7.16.16.11.3.2.5 Cabinet 3 |  |  | 35 | [6 empty] | 0 | 0
NSS-A2147350040 | MCA MIRACLES: Design, Eplan of cabinet 3 | 0% | 15 | 2024-10-28 | 2024-11-15 | 2024-10-28 | 2024-11-15 | 2025-02-18 | 2025-03-10 | -82 | -82
NSS-A2147350050 | MCA MIRACLES: Procurement of cabinet 3 | 0% | 15 | 2024-11-18 | 2024-12-06 | 2024-11-18 | 2024-12-06 | 2025-03-11 | 2025-03-31 | -82 | -82
NSS-A2147350060 | MCA MIRACLES: Installation of cabinet 3 | 0% | 5 | 2024-12-09 | 2024-12-13 | 2024-12-09 | 2024-12-13 | 2025-04-01 | 2025-04-07 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.2.2 Cabinet 2 |  |  | 35 | [6 empty] | 0 | 0
NSS-A2147350550 | MCA MIRACLES: Design, Eplan of cabinet 2 | 0% | 15 | 2024-11-04 | 2024-11-22 | 2024-11-04 | 2024-11-22 | 2025-02-25 | 2025-03-17 | -82 | -82
NSS-A2147350560 | MCA MIRACLES: Procurement of cabinet 2 | 0% | 15 | 2024-11-25 | 2024-12-13 | 2024-11-25 | 2024-12-13 | 2025-03-18 | 2025-04-07 | -82 | -82
NSS-A2147350570 | MCA MIRACLES: Installation of cabinet 2 | 0% | 5 | 2024-12-16 | 2024-12-20 | 2024-12-16 | 2024-12-20 | 2025-04-08 | 2025-04-14 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.2.6 MCA L3 and energization |  |  | 108 | [6 empty] | 0 | 0
NSS-A2147350400 | MCA MIRACLES: Design of all MCA cables, cable data base (CDB), label list | 0% | 5 | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-29 | 2025-03-18 | 2025-03-24 | -82 | -82
NSS-A2147350410 | MCA MIRACLES: Procurement and labelling of all MCA cables | 0% | 30 | 2024-12-02 | 2025-01-27 | 2024-12-02 | 2025-01-27 | 2025-03-25 | 2025-05-08 | -82 | -74
NSS-A2147350420 | MCA MIRACLES: Termination of all installed cables E01 | 0% | 10 | 2025-01-14 | 2025-01-27 | 2025-01-14 | 2025-01-27 | 2025-04-24 | 2025-05-08 | -73 | -74
NSS-A2147350510 | MCA MIRACLES: Final energization of cabinets E01 Hall instrument zone | 0% | 5 | 2025-05-07 | 2025-05-13 | 2025-05-07 | 2025-05-13 | 2025-11-04 | 2025-11-10 | -130 | -130
13-NSS-P06-24.1.7.16.16.11.3.2.1 MCA control system setup E01 Instrument Zone |  |  | 60 | [6 empty] | 0 | 0
NSS-A2147350340 | MCA MIRACLES: Setting up of control systems | 0% | 10 | 2025-05-14 | 2025-05-27 | 2025-05-14 | 2025-05-27 | 2025-11-11 | 2025-11-24 | -130 | -130
NSS-A2147350350 | MCA MIRACLES: Commissioning of subsystem related to respective cabinets | 0% | 30 | 2025-05-28 | 2025-07-14 | 2025-05-28 | 2025-07-14 | 2025-11-25 | 2026-01-19 | -130 | -136
NSS-A2147350360 | MCA MIRACLES: Configuration of interfaces to EPICS/NICOS E01 succ local sat with duration (how g with pred from ics, ecd | 0% | 10 | 2025-07-15 | 2025-08-25 | 2025-07-15 | 2025-08-25 | 2026-01-20 | 2026-02-02 | -136 | -116
NSS-A2147350520 | MCA MIRACLES: Local SAT E01 with ECDC/ICS for motion control testing with EPICS/NICOS | 0% | 10 | 2025-08-26 | 2025-09-08 | 2025-08-26 | 2025-09-08 | 2026-02-03 | 2026-02-16 | -116 | -116
13-NSS-P06-24.1.7.16.16.11.4 Detector project |  |  | 261 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.4.7 Detector Racks |  |  | 261 | [6 empty] | 0 | 0
NSS-A2147186370 | Preliminary design review (PDR) and approval | 0% | 15 | 2024-10-16 | 2024-11-05 | 2024-10-16 | 2024-11-05 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187350 | Scope transfer agreed and project kicked off with Det Group | 0% | 0 | 16-okt-24* |  | 2024-10-16 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186320 | Tender/offer issuance | 0% | 5 | 2024-11-06 | 2024-11-12 | 2024-11-06 | 2024-11-12 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186330 | Tender review,selection and award of contract completed | 0% | 40 | 2024-11-13 | 2025-01-22 | 2024-11-13 | 2025-01-22 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186380 | Detailed design phase for the Racks | 0% | 30 | 2025-01-23 | 2025-03-05 | 2025-01-23 | 2025-03-05 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186340 | Submission of docs to ESS for CDR/TG3 | 0% | 20 | 2025-02-20 | 2025-03-19 | 2025-02-20 | 2025-03-19 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186350 | CDR/sub-TG3 review | 0% | 0 |  | 2025-03-19 |  | 2025-03-19 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186360 | CDR/sub-TG3 approval | 0% | 20 | 2025-03-20 | 2025-04-16 | 2025-03-20 | 2025-04-16 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186410 | Procurement and manufacturing | 0% | 60 | 17-Apr-25* | 2025-07-18 | 2025-04-17 | 2025-07-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186420 | Factory Acceptance Test (FAT) | 0% | 5 | 18-Aug-25* | 2025-08-22 | 2025-08-18 | 2025-08-22 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186430 | FAT approval and documentation | 0% | 10 | 25-Aug-25* | 2025-09-05 | 2025-08-25 | 2025-09-05 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186530 | Shipping period for the components | 0% | 10 | 2025-09-08 | 2025-09-19 | 2025-09-08 | 2025-09-19 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186460 | IRR document submission phase | 0% | 15 | 2025-09-08 | 2025-09-26 | 2025-09-08 | 2025-09-26 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186390 | Pre-installation testing of detectors with ECDC and ICS | 0% | 30 | 2025-09-22 | 2025-10-31 | 2025-09-22 | 2025-10-31 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186400 | Handing over of Level 3 cables to CEP | 0% | 2 | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186450 | Delivery of Racks and cables | 0% | 0 | 2025-09-22 |  | 2025-09-22 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186470 | Instrument readiness review (IRR) | 0% | 0 |  | 2025-09-26 |  | 2025-09-26 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186550 | Detector racks TG4 approved | 0% | 0 |  | 2025-09-26 |  | 2025-09-26 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186490 | Installation of Racks | 0% | 3 | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-05 | 2026-09-18 | 2026-09-24 | -230 | -232
NSS-A2147186500 | Level 3 cable termination | 0% | 3 | 2025-11-06 | 2025-11-10 | 2025-11-06 | 2025-11-10 | 2026-10-09 | 2026-10-15 | -242 | -244
NSS-A2147186540 | Test readiness review (TRR) and approval | 0% | 2 | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-12 | 2026-10-16 | 2026-10-29 | -244 | -252
NSS-A2147186510 | System Acceptance Test (SAT)- along with detectors | 0% | 15 | 2025-11-13 | 2025-12-03 | 2025-11-13 | 2025-12-03 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186520 | SAT approval | 0% | 3 | 2025-12-04 | 2025-12-08 | 2025-12-04 | 2025-12-08 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.5 Chopper project |  |  | 201 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.5.7 Chopper Rack 1-3 |  |  | 201 | [6 empty] | 0 | 0
NSS-A2147187160 | Delivery of Chopper Rack | 100% | 5 | 14-Aug-23 A | 18-Aug-23 A | 2023-08-14 | 2023-08-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187150 | Quality gate review and approval | 0% | 20 | 2024-07-01 | 2024-08-23 | 2024-07-01 | 2024-08-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187170 | Submission of docs to ESS for Quality gate and IRR/sub-TG4 | 0% | 20 | 2024-07-01 | 2024-08-23 | 2024-07-01 | 2024-08-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187180 | Installation Readiness Review (IRR) | 0% | 0 |  | 2024-08-23 |  | 2024-08-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187190 | IRR Approval | 0% | 20 | 2024-08-26 | 2024-09-20 | 2024-08-26 | 2024-09-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187270 | TG4 | 0% | 0 |  | 2024-09-20 |  | 2024-09-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187200 | Installation of Chopper Rack | 0% | 20 | 2024-09-23 | 2024-10-18 | 2024-09-23 | 2024-10-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187210 | CEP interface ( earthing and bonding connections) | 0% | 10 | 2024-09-23 | 2024-10-04 | 2024-09-23 | 2024-10-04 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187250 | CUP interface | 0% | 10 | 2024-09-23 | 2024-10-04 | 2024-09-23 | 2024-10-04 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187260 | Pre-installation testing at site with ECDC and ICS | 0% | 5 | 2024-09-23 | 2024-09-27 | 2024-09-23 | 2024-09-27 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187240 | Test readiness review (TRR) and approval | 0% | 5 | 2024-10-21 | 2024-10-25 | 2024-10-21 | 2024-10-25 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187220 | System Acceptance Test (SAT) | 0% | 5 | 2024-10-28 | 2024-11-01 | 2024-10-28 | 2024-11-01 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187230 | SAT approval | 0% | 10 | 2024-11-04 | 2024-11-15 | 2024-11-04 | 2024-11-15 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.6 Beam Monitor project |  |  | 211 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.6.1 Beam monitors |  |  | 211 | [6 empty] | 0 | 0
NSS-A2147186990 | Contract signed and order placed | 0% | 5 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-05 | 2025-01-07 | 2025-01-13 | -137 | -137
NSS-A2147187000 | Detailed design phase for the Beam monitor including electronics | 0% | 30 | 2024-07-08 | 2024-09-13 | 2024-07-08 | 2024-09-13 | 2025-01-14 | 2025-02-24 | -137 | -117
NSS-A2147187010 | Design documents submitted for review | 0% | 10 | 2024-08-26 | 2024-09-06 | 2024-08-26 | 2024-09-06 | 2025-02-04 | 2025-02-17 | -117 | -117
NSS-A2147187020 | CDR and approval | 0% | 10 | 2024-09-09 | 2024-09-20 | 2024-09-09 | 2024-09-20 | 2025-02-18 | 2025-03-03 | -117 | -117
NSS-A2147187030 | Manufacturing and Procurement | 0% | 50 | 2024-09-23 | 2024-11-29 | 2024-09-23 | 2024-11-29 | 2025-03-04 | 2025-05-15 | -117 | -120
NSS-A2147186810 | Factory Acceptance Test (FAT) | 0% | 5 | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-06 | 2025-05-16 | 2025-05-22 | -120 | -120
NSS-A2147186850 | Submission of docs to ESS for Quality gate and IRR | 0% | 56 | 2024-12-09 | 2025-03-11 | 2024-12-09 | 2025-03-11 | 2025-05-23 | 2025-09-11 | -120 | -133
NSS-A2147186940 | FAT Report and Documentation | 0% | 15 | 2024-12-09 | 2025-01-13 | 2024-12-09 | 2025-01-13 | 2025-05-23 | 2025-06-17 | -120 | -112
NSS-A2147186820 | FAT- closure of open points and approval | 0% | 20 | 2024-12-16 | 2025-01-27 | 2024-12-16 | 2025-01-27 | 2025-06-03 | 2025-07-02 | -122 | -113
NSS-A2147186830 | Quality gate review and approval | 0% | 32 | 2025-01-17 | 2025-03-03 | 2025-01-17 | 2025-03-03 | 2025-06-24 | 2025-09-03 | -113 | -133
NSS-A2147186980 | Testing of beam monitors prior to shipment and related documentation | 0% | 20 | 2025-01-28 | 2025-02-24 | 2025-01-28 | 2025-02-24 | 2025-07-03 | 2025-08-27 | -113 | -133
NSS-A2147186920 | Shipping period for the Beam monitors | 0% | 10 | 2025-02-25 | 2025-03-10 | 2025-02-25 | 2025-03-10 | 2025-08-28 | 2025-09-10 | -133 | -133
NSS-A2147186840 | Delivery of Beam monitor, electronics and racks | 0% | 0 |  | 2025-03-11 |  | 2025-03-11 |  | 2025-09-11 | 0 | -133
NSS-A2147186860 | Instrument readiness review (IRR) | 0% | 0 |  | 2025-03-11 |  | 2025-03-11 |  | 2025-09-11 | 0 | -133
NSS-A2147186870 | IRR approval | 0% | 20 | 2025-03-12 | 2025-04-08 | 2025-03-12 | 2025-04-08 | 2025-09-12 | 2025-10-09 | -133 | -133
NSS-A2147186970 | TG4 completed for Beam monitors and racks | 0% | 0 |  | 2025-04-08 |  | 2025-04-08 |  | 2025-10-09 | 0 | -133
NSS-A2147186880 | Installation of Beam monitors and racks | 0% | 10 | 2025-04-09 | 2025-04-24 | 2025-04-09 | 2025-04-24 | 2025-10-10 | 2025-10-23 | -133 | -131
NSS-A2147186890 | CEP interface | 0% | 15 | 2025-04-09 | 2025-05-02 | 2025-04-09 | 2025-05-02 | 2025-10-10 | 2025-10-30 | -133 | -130
NSS-A2147186950 | CUP interface | 0% | 10 | 2025-04-09 | 2025-04-24 | 2025-04-09 | 2025-04-24 | 2025-10-10 | 2025-10-23 | -133 | -131
NSS-A2147186960 | ECDC-ICS integration (EPICS/NICOS) and Pre installation testing | 0% | 10 | 2025-04-09 | 2025-04-24 | 2025-04-09 | 2025-04-24 | 2025-10-10 | 2025-10-23 | -133 | -131
NSS-A2147186930 | Test readiness review (TRR) and approval | 0% | 10 | 2025-05-05 | 2025-05-16 | 2025-05-05 | 2025-05-16 | 2025-10-31 | 2025-11-13 | -130 | -130
NSS-A2147186900 | System Acceptance Test (SAT) | 0% | 5 | 2025-05-19 | 2025-05-23 | 2025-05-19 | 2025-05-23 | 2025-11-14 | 2025-11-20 | -130 | -130
NSS-A2147186910 | SAT approval | 0% | 10 | 2025-05-26 | 2025-06-11 | 2025-05-26 | 2025-06-11 | 2025-11-21 | 2025-12-04 | -130 | -127
Formulas:
Variance start date = IF([Start (juni lockdown)]<>0&[Finish (juni lockdown)]<>0,+NETWORKDAYS([Start (december lockdown)],[Start (juni lockdown)]),"")
Variance finish date = IF([Finish (juni lockdown)]<>0&[Finish (december lockdown)]<>0,+NETWORKDAYS([Finish (december lockdown)],[Finish (juni lockdown)]),"")