## Slide 1: SKADI ICEB
Critical paths, schedule adherence etc.

## Slide 2: TG5 slip chart
Note: For T2T3, tracking starts after replanning close-out. Vespa has TG5 in May 2029. Once TG5 is approved, the instrument will be removed from tracking.
,
NMX
ODIN,
DREAM ESTIA
MAGIC
BEER
SKADI
MIRACLES,
HEIMDAL
FREIA
CSPEC TREX
Data from P6 MARCH 2026 lock down
TG5/SAR approved.
(iSRR held, approval pending)
TBL
LOKI,
BIFROST

## Slide 3
2025
2026
TG5
No. 3 - Critical Path
(20 days TF)
No. 1 - Critical Path
(0 days TF)
No. 2 - Critical Path
(5 days TF)
Today
2025
2026
80 days
Integrated Cold Commissioning and TG5 preparations
70 days
Sep 2025 - Dec 2025
Polarizer Housing, Spin Flipper and Fast Shutter: Procurement and Manufacturing phase (FZJ)
61 days
Dec 2025 - Mar 2026
Polarizer Housing: Assembly (with optics and chopper) phase (FZJ)*
Q3
Q4
Q1
Q2
Q3
Q4
39 days
TG5 Closure of open points
17 days
Mar 2026 - Mar 2026
Polarizer, Spin Flipper, Fast Shutter and OoB Guides: Installation phase (FZJ, LLB & ESS)
Jun 2026 - Oct 2026
TG5 meeting
Oct 8
127 days
Dec 2025 - Jun 2026
MCA (including sub-systems): Installation, Energization and Commissioning phase
79 days
CEP installation
Oct 2026 - Dec 2026
93 days
Sep 2025 - Jan 2026
Detector Housing: Manufacturing and Assembly phase (FZJ)
56 days
Mar 2026 - Jun 2026
Detector: Installation and Commissioning phase (FZJ)
146 days
Sep 2025 - Mar 2026
Detector Integration (FZJ & ESS)
Sep 2025 - Dec 2025
Back into CP1 with 20 days float
Mar 31
TG5/SAR approval
Dec 2, 2026
Start of CC
Jun 17, 2026
Final TG3
Nov 28, 2025
Skadi Critical Paths
Data from P6 September 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
* Spin flipper and Fast shutter has 6 days float (testing in parallell to polarizer housings assembly)
Since last ICEB…
No shift on TG5, well done!
CEP and MCA new as CP1
Some delays on deliveries on the other critical paths.
LAST ICEB
Notes: 2025-09
Polarizer housing assembly delayed
2025-01
Detector housing manufacturing: moved out 2 months

## Slide 4
2026
2027
No. 1 - Critical Path
(0 days TF)
No. 4 - Critical Path
(9 days TF)
No. 2 - Critical Path
(5 days TF)
No. 3 - Critical Path
(8 days TF)
TG5
Today
2026
Q1
Q2
Q3
Q4
145 days
Mar 2026 - Sep 2026
Detector: Manufacturing phase bank 2 (FZJ)
58 days
Mar 2026 - May 2026
BMs: Design phase
108 days
May 2026 - Oct 2026
BM: Installation and Commissioning phase
76 days
Mar 2026 - Jun 2026
Polarizer Housing: Manufacturing phase (FZJ)
19 days
Jun 2026 - Jul 2026
Polarizer, SF and FS: Assembly (with optics and chopper) phase and FAT (FZJ)*
35 days
Jul 2026 - Aug 2026
Polarizer, SF, FS and chopper: Installation phase
40 days
Aug 2026 - Oct 2026
Commissioning phase
2027
Q1
35 days
Sep 2026 - Nov 2026
Detector: Installation and Commissioning phase (FZJ)
Back into CP01 with 5 days float
Oct 23
0 days
88 days
Mar 2026 - Jul 2026
Detector tool: Manufacturing phase (FZJ)
39 days
Jul 2026 - Aug 2026
Detector housing (including bank 0 and bank 1): Installation phase (FZJ)
Back into CP01 with 8 days float
Aug 25
0 days
Back into CP01 with 9 days float
Oct 19
0 days
29 days
Nov 2026 - Dec 2026
TG5 preparations
TG5/SAR+ iSRR meeting
Dec 21
0 days
44 days
Dec 2026 - Feb 2027
TG5 Closure of open points
TG5/SAR approval
Feb 19, 2027
Cold Commissioning of TG5 scope complete
Nov 9, 2026
Final TG3 approval
May 29, 2026
0 days
-6 days
0 days
Skadi Critical Paths (TG5 scope)
Data from P6 March 2026 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
iSRR scope:
PSS Skadi Complete – 18th of December
Motion Safety testing and validation complete – 10th of November
iSRR approval – 1st of March
Notes: 2026-03
Spin flipper manufacturing: 59 days delayed
Detector installation (due to detector installation tool): 65 days delayed
2026-01
Polarizer housing: 48 days delayed
Skadi Det: 20 days delayed
2025-10
Polarizer housing: one month delayed
CEP accelerated their schedule
2025-09
Polarizer housing assembly delayed
2025-01
Detector housing manufacturing: moved out 2 months

## Slide 5: Key milestones
MARCH lockdown

## Slide 6: Schedule adherence
Chart: Started activities: Planned vs Achieved
| 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082
Planned start | 4 | 5 | 2 | 7 | 6 | 2 | 0 | 13
Achieved start | 4 | 4 | 2 | 6 | 3 | 2 | 0 | 9
% starts achieved | 1 | 0.8 | 1 | 1 | 0.42857 | 0.18182 | 0 | 0.47368
% starts achieved NSS | 0.65 | 0.65 | 0.56 | 0.52 | 0.7 | 0.61 | 0.64 | 0.59
Chart: Finished activites: Planned vs Achieved
| 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082
Planned finish | 4 | 5 | 3 | 9 | 4 | 1 | 1 | 15
Achieved finish | 3 | 4 | 3 | 7 | 1 | 0 | 1 | 10
% finish achieved | 0.75 | 0.8 | 1 | 0.77778 | 0.25 | 0 | 1 | 0.66667
% finish achieved NSS | 0.61 | 0.58 | 0.46 | 0.49 | 0.62 | 0.52 | 0.51 | 0.63

## Slide 7: Lookout - future activities
There’s a lot in the pipeline.. But maybe not enough?
Component deliveries and dependencies are missing from the plan, creating a false impression that completion can be achieved earlier than is realistically feasible (e.g. M3 beam positioner still in design)
Chart: Planned starts
| 45931 | 45962 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Planned start | 7 | 6 | 2 | 0 | 13
Achieved start | 6 | 3 | 2 | 0 | 9
Planned start (Oct-25) | 6 | 7 | 11 | 15 | 19
Planned starts (April-26) | 8 | 4 | 4 | 11 | 10 | 6 | 3
Chart: Planned finishes
| 45931 | 45962 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Planned finish | 9 | 4 | 1 | 1 | 15
Achieved finish | 7 | 1 | 0 | 1 | 10
Planned finish (Oct-25) | 9 | 10 | 11 | 15 | 30
Planned finish (April-26) | 10 | 5 | 6 | 15 | 3 | 13 | 2

## Slide 9: Key milestones
TG3 has been delayed, no other big shifts on other key milestones

## Slide 10: Schedule adherence
Most months – SKADI is above average on schedule accuracy
Chart: Started activities: Planned vs Achieved
| 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45870 | 45901
Planned start | 10 | 11 | 9 | 4 | 5 | 4 | 5 | 2
Achieved start | 9 | 9 | 8 | 3 | 4 | 4 | 4 | 2
% starts achieved | 0.9 | 0.81818 | 0.88889 | 0.75 | 0.8 | 1 | 0.8 | 1
% starts achieved NSS | 0.65476 | 0.59494 | 0.57488 | 0.72 | 0.68 | 0.65 | 0.65 | 0.56
Chart: Finished activites: Planned vs Achieved
| 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45870 | 45901
Planned finish | 7 | 11 | 9 | 2 | 4 | 4 | 5 | 3
Achieved finish | 7 | 10 | 9 | 2 | 3 | 3 | 4 | 3
% finish achieved | 1 | 0.90909 | 1 | 1 | 0.75 | 0.75 | 0.8 | 1
% finish achieved NSS | 0.57396 | 0.63277 | 0.62946 | 0.68 | 0.64 | 0.61 | 0.58 | 0.47

## Slide 11: Lookout - future activities
There’s a lot in the pipeline..
Chart: Planned starts
| 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082
Planned start | 5 | 2 | 6 | 7 | 8 | 11 | 15 | 19
Achieved start | 4 | 2
Chart: Planned finishes
| 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082
Planned finish | 5 | 3 | 9 | 10 | 9 | 11 | 15 | 30
Achieved finish | 4 | 3