## Slide 1: TREX ICEB
Critical paths, schedule adherence etc.

## Slide 2: Completing design for T2T3 instruments
28 meetings held Sep 25 to Feb 26
Chart: CTV/IDR/sub-TG3 Sep 2025-Feb2026
| CSPEC | ESTIA | FREIA | HEIMDAL | MAGIC | MIRACLES | SKADI | TREX | VESPA
 | 3 | 2 | 2 | 5 | 8 | 1 | 1 | 4 | 2
As shown at ICB

## Slide 3: TG5 slip chart
Note: For T2T3, tracking starts after replanning close-out. Vespa has TG5 in May 2029. Once TG5 is approved, the instrument will be removed from tracking.
,
NMX
ODIN,
DREAM ESTIA
MAGIC
BEER
SKADI
MIRACLES,
HEIMDAL
FREIA
CSPEC TREX
Data from P6 MARCH 2026 lock down
TG5/SAR approved.
(iSRR held, approval pending)
TBL
LOKI,
BIFROST

## Slide 4
2026
2027
No. 1 - Critical Path M Chopper
(0 days TF)
No. 4 - Critical Path Primary Coll & Slits
(9 days TF)
No. 2 - Critical Path
(0 days TF)
No. 3 - Trans Table & Cold Polariz
(4 days TF)
Today
2026
2027
252 days
M Chopper: Manufacturing phase (FZJ)
89 days
Feb 2027 - Jun 2027
M Chopper : Installation and Commissioning phase (FZJ)
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Mar 2026 - Feb 2027
44 days
Mar 2026 - Apr 2026
Primary Coll & Slits Design phase (CNR)
198 days
May 2026 - Feb 2027
Primary Coll & Slits: Procurement and Manufacturing phase (CNR)
40 days
Jun 2027 - Aug 2027
Integrated Cold Commissioning
52 days
Feb 2027 - Apr 2027
Primary Coll & Slits: Installation phase (CNR)
37 days
Apr 2027 - Jun 2027
MCA, Translation Table, Secondary RC, Primary Coll & Slits Commissioning phase
167 days
Mar 2026 - Oct 2026
CEP: Requirement and Desigh phase (ESS)
107 days
Oct 2026 - Mar 2027
CEP and ICS: Installation and Energization (ESS)
67 days
Mar 2027 - Jun 2027
Detector and Vessel: Commissioning phase (FZJ & ESS)
Back into CP01 with 0 days float
Jun 21
0 days
78 days
Mar 2026 - Jun 2026
Transl Table: Design phase (FZJ)
125 days
Jun 2026 - Dec 2026
Transl Table: Manufacturing phase (FZJ)
134 days
Dec 2026 - Jun 2027
Transl Table & Therm Polariz: Installation and Commissioning phase (FZJ)
Back into CP01 with 4 days float
Jun 15
0 days
Back into CP01 with 9 days float
Jun 8
0 days
TG5/SAR approval
Dec 7, 2027
Cold Commissioning TG5 scope complete
Aug 17, 2027
Final TG3
Nov 2, 2026
0 days
0 days
0 days
TREX Critical Paths
Data from P6 March 2026 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Note: MG detector boxes 2-4 (including 18 modules) is part of the instrument scope but currently not linked to TG5 in P6. Tentatively planned to be completed in Q2-2028
Notes: 2026-03
Translation table design: 17 days delayed
Primary coll & slits design: 31 days delayed
Polarization alanyser design: 16 days delayed
Secondary RC FAT: 37 days delaed
2026-01
Primary Coll & slits 30 days delayed
Polarization Analyser: 29 days delayed
Translation table: 14 days delayed (sixth CP)
2025-09
OoB Guides 43 days delayed
M-chopper FAT delayd 139 days
P-chopper Fat delayed 45 dyas
Fan chopper 33 days delayed
OoB Guides 33 days delayed
2025-09
Delay to M chopper
2025-05
P-chopper manufacturing delayed 8 months
OoB Guides (design, procurement and manufacturing) is 1 month delayed
2025-04
CP3 new: Translation table delayed 1 month
OoB Guide delayed 1 month

## Slide 5
2026
2027
No. 1 - Critical Path M Chopper
(0 days TF)
No. 5 - Critical Path Pol. Analyser
(11 days TF)
No. 6 - Critical Path P Chopper
(13 days TF)
No. 7 - Critical Path OoB guides
(30 days TF)
No. 8 - Critical Path Vessel and cave
(30 days TF)
Today
2026
2027
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
91 days
Mar 2026 - Jul 2026
Polarization Analyser: Design phase (FZJ)
120 days
Jul 2026 - Dec 2026
Polarization Analyser: Manufacturing phase (FZJ)
119 days
Dec 2026 - Jun 2027
Polarization Analyser: Installation and Commissioning phase (FZJ)
40 days
Jun 2027 - Aug 2027
Integrated Cold Commissioning
235 days
Mar 2026 - Jan 2027
P Chopper: Manufacturing phase (FZJ)
93 days
Jan 2027 - Jun 2027
P Chopper : Installation and Commissioning phase (FZJ)
125 days
Mar 2026 - Aug 2026
OoB guides: Design phase (FZJ)
87 days
Aug 2026 - Dec 2026
OoB guides: Manufacturing phase (FZJ)
65 days
Dec 2026 - Mar 2027
OoB guides : Installation preparation phase (FZJ)
Back into CP1 with 30 days of float
0 days
Mar 23
Back into CP01 with 11 days float
Jun 4
0 days
Back into CP01 with 13 days float
Jun 4
0 days
77 days
Mar 2026 - Jun 2026
Secondary RC: Manufacturing and Integration phase (FZJ)
77 days
Jun 2026 - Oct 2026
Detector Vessel: Rework, testing and shipping phase (FZJ)
10 days
Oct 2026 - Oct 2026
Detector Vessel: Installation phase (FZJ)
Back into CP02 with 30 days float
Nov 12
0 days
20 days
Oct 2026 - Nov 2026
Cave: Installation (last wall) phase (CNR)
TG5/SAR approval
Dec 7, 2027
Cold Commissioning TG5 scope complete
Aug 17, 2027
Final TG3
Nov 2, 2026
0 days
0 days
0 days
TREX Critical Paths
Data from P6 March 2026 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Notes: 2026-03
Translation table design: 17 days delayed
Primary coll & slits design: 31 days delayed
Polarization alanyser design: 16 days delayed
Secondary RC FAT: 37 days delayed
2026-01
Primary Coll & slits 30 days delayed
Polarization Analyser: 29 days delayed
Translation table: 14 days delayed (sixth CP)
2025-09
OoB Guides 43 days delayed
M-chopper FAT delayd 139 days
P-chopper Fat delayed 45 dyas
Fan chopper 33 days delayed
OoB Guides 33 days delayed
2025-09
Delay to M chopper
2025-05
P-chopper manufacturing delayed 8 months
OoB Guides (design, procurement and manufacturing) is 1 month delayed
2025-04
CP3 new: Translation table delayed 1 month
OoB Guide delayed 1 month

## Slide 6
2025
2027
No. 1 - Critical Path M Chopper
(0 days TF)
No. 5 - Out of bunker optics
(45 days TF)
No. 2 - Critical Path P Chopper
(8 days TF)
No. 3 - Critical Path Fan Chopper
(20 days TF)
No. 4 - Primary Coll & Slit
(41 days TF)
Today
2025
2026
2027
367 days
M Chopper: Manufacturing phase (FZJ)
94 days
Jan 2027 - Jun 2027
M Chopper : Installation and Commissioning phase (FZJ)
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
218 days
OoB Optics: Design phase (FZJ)
307 days
OoB Optics: Procurement and Manufacturing (FZJ)
Sep 2025 - Jan 2027
Sep 2025 - Jul 2026
Sep 2025 - Nov 2026
354 days
Sep 2025 - Jan 2027
P Chopper: Manufacturing phase (FZJ)
99 days
Jan 2027 - May 2027
P Chopper : Installation and Commissioning phase (FZJ)
101 days
Sep 2025 - Jan 2026
Fan Chopper: Design phase (FZJ)
195 days
Jan 2026 - Oct 2026
Fan Chopper: Procurement and Manufacturing phase (FZJ)
138 days
Oct 2026 - Apr 2027
Fan Chopper : Installation and Commissioning phase (FZJ)
70 days
Nov 2026 - Feb 2027
OoB Optics: Installation preparations (FZJ)
Go back to CP 1 (45 days of float)
103 days
Sep 2025 - Jan 2026
Primary Coll & Slits: Design phase (CNR/INFN)
167 days
Jan 2026 - Sep 2026
Primary Coll & Slits: Procurement and Manufacturing phase (CNR/INFN)
148 days
Sep 2026 - Apr 2027
Primary Coll & Slits and MCA: Installation and Commissioning phase (CNR/INFN)
Feb 9
TG5/SAR approval
Nov 23, 2027
Start of CC
Jun 8, 2027
Final TG3
Oct 7, 2026
Cave has 6 months of float and is no longer top 5 CP
Note: MG detector boxes 2-4 (including 18 modules) is part of the instrument scope but currently not linked to TG5 in P6
TREX Critical Paths
Data from P6 September 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Since last ICEB…
Shift on TG5
Cave no longer on top critical path
3 new deliverables on top critical paths (M chopper, P chopper and primary collimator & slits
As shown at last ICEB
Notes: 2025-09
OoB Guides 43 days delayed
M-chopper FAT delayd 139 days
P-chopper Fat delayed 45 dyas
Fan chopper 33 days delayed
OoB Guides 33 days delayed
2025-09
Delay to M chopper
2025-05
P-chopper manufacturing delayed 8 months
OoB Guides (design, procurement and manufacturing) is 1 month delayed
2025-04
CP3 new: Translation table delayed 1 month
OoB Guide delayed 1 month

## Slide 7: Key milestones (as shown in dashboard)
Delays on all key milestones since the replanning

## Slide 8: Schedule adherence
Most months – T-REX is above average on schedule accuracy
Chart: Started activities: Planned vs Achieved
| 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082
Planned start | 4 | 1 | 8 | 6 | 9 | 14 | 9 | 15
Achieved start | 4 | 1 | 6 | 6 | 8 | 8 | 6 | 10
% starts achieved | 1 | 1 | 0.75 | 1 | 0.88889 | 0.57143 | 0.66667 | 0.66667
% starts achieved NSS | 0.65 | 0.65 | 0.56 | 0.52 | 0.7 | 0.61 | 0.64 | 0.59
Chart: Finished activites: Planned vs Achieved
| 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082
Planned finish | 4 | 2 | 10 | 6 | 9 | 16 | 6 | 15
Achieved finish | 4 | 0 | 8 | 6 | 7 | 8 | 3 | 9
% finish achieved | 1 | 0 | 0.8 | 1 | 0.77778 | 0.5 | 0.5 | 0.6
% finish achieved NSS | 0.61 | 0.58 | 0.46 | 0.49 | 0.62 | 0.52 | 0.51 | 0.63

## Slide 9: Lookout - future activities
There’s a lot in the pipeline..
Chart: Planned starts
| 45931 | 45962 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Planned start | 6 | 9 | 14 | 9 | 15
Achieved start | 6 | 8 | 8 | 6 | 10
Planned start (Oct-25) | 6 | 29 | 21 | 12 | 21
Planned starts (April-26) | 13 | 17 | 20 | 15 | 15 | 25 | 41
Chart: Planned finishes
| 45931 | 45962 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296
Planned finish | 6 | 9 | 16 | 6 | 15
Achieved finish | 6 | 7 | 8 | 3 | 9
Planned finish (Oct-25) | 6 | 23 | 17 | 11 | 19
Planned finish (April-26) | 18 | 22 | 18 | 11 | 10 | 24 | 43

## Slide 11: NSS Replanning Evaluation
TREX ICEB

## Slide 12
2025
2027
No. 1 - Critical Path M Chopper
(0 days TF)
No. 5 - Out of bunker optics
(45 days TF)
No. 2 - Critical Path P Chopper
(8 days TF)
No. 3 - Critical Path Fan Chopper
(20 days TF)
No. 4 - Primary Coll & Slit
(41 days TF)
Today
2025
2026
2027
367 days
M Chopper: Manufacturing phase (FZJ)
94 days
Jan 2027 - Jun 2027
M Chopper : Installation and Commissioning phase (FZJ)
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
218 days
OoB Optics: Design phase (FZJ)
307 days
OoB Optics: Procurement and Manufacturing (FZJ)
Sep 2025 - Jan 2027
Sep 2025 - Jul 2026
Sep 2025 - Nov 2026
354 days
Sep 2025 - Jan 2027
P Chopper: Manufacturing phase (FZJ)
99 days
Jan 2027 - May 2027
P Chopper : Installation and Commissioning phase (FZJ)
101 days
Sep 2025 - Jan 2026
Fan Chopper: Design phase (FZJ)
195 days
Jan 2026 - Oct 2026
Fan Chopper: Procurement and Manufacturing phase (FZJ)
138 days
Oct 2026 - Apr 2027
Fan Chopper : Installation and Commissioning phase (FZJ)
70 days
Nov 2026 - Feb 2027
OoB Optics: Installation preparations (FZJ)
Go back to CP 1 (45 days of float)
103 days
Sep 2025 - Jan 2026
Primary Coll & Slits: Design phase (CNR/INFN)
167 days
Jan 2026 - Sep 2026
Primary Coll & Slits: Procurement and Manufacturing phase (CNR/INFN)
148 days
Sep 2026 - Apr 2027
Primary Coll & Slits and MCA: Installation and Commissioning phase (CNR/INFN)
Feb 9
TG5/SAR approval
Nov 23, 2027
Start of CC
Jun 8, 2027
Final TG3
Oct 7, 2026
Cave has 6 months of float and is no longer top 5 CP
Note: MG detector boxes 2-4 (including 18 modules) is part of the instrument scope but currently not linked to TG5 in P6
TREX Critical Paths
Data from P6 September 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Since last ICEB…
Shift on TG5
Cave no longer on top critical path
3 new deliverables on top critical paths (M chopper, P chopper and primary collimator & slits
Notes: 2025-09
OoB Guides 43 days delayed
M-chopper FAT delayd 139 days
P-chopper Fat delayed 45 dyas
Fan chopper 33 days delayed
OoB Guides 33 days delayed
2025-09
Delay to M chopper
2025-05
P-chopper manufacturing delayed 8 months
OoB Guides (design, procurement and manufacturing) is 1 month delayed
2025-04
CP3 new: Translation table delayed 1 month
OoB Guide delayed 1 month

## Slide 13
2025
2027
No. 2 - Critical Path Fan Chopper
(5 days TF)
No. 1 - Critical Path Cave
(0 days TF)
No. 3 - Out of bunker optics
(11 days TF)
No. 4 - Out of bunker optics
(25 days TF)
Today
2025
2026
2027
121 days
Fan Chopper: Design phase (FZJ)
208 days
Cave: Procurement and Manufacturing phase (CNR)
181 days
Jan 2026 - Sep 2026
Cave and Vessel: Installation phase (CNR & FZJ)
145 days
Jul 2026 - Feb 2027
Fan, P and M Chopper : Installation and Commissioning phase (FZJ)
Q2
Q3
Q4
Q1
Q2
Q3
Q4
54 days
Sep 2026 - Dec 2026
CEP and ICS: Installation and Energization (ESS)
Energization instrument zone complete
Dec 11
45 days
Dec 2026 - Feb 2027
MCA: Commissioning phase for sub-system
188 days
Thermal Polarization and Translation Table: Design phase (FZJ)
140 days
Translation Table: Procurement and Manufacturing phase (FZJ)
Q1
Q2
Q3
218 days
Sep 2025 - Jul 2026
Fan Chopper: Procurement and Manufacturing phase (FZJ)
Dec 2025 - Jul 2026
150 days
Jul 2026 - Jan 2027
Translation Table and Cold Polarization: Installation phase (FZJ)
229 days
OoB Optics: Design phase (FZJ)
324 days
OoB Optics: Procurement and Manufacturing (FZJ)
140 days
Jun 2026 - Jan 2027
OoB Optics and Polarization Flipper: Installation and Commissioning phase (FZJ)
Apr 2025 - Jan 2026
Apr 2025 - Sep 2025
Apr 2025 - Dec 2025
Apr 2025 - Feb 2026
Apr 2025 - Jun 2026
TG5/SAR approval
Jul 8, 2027
Start of CC
Feb 15, 2027
Final TG3
Apr 29, 2026
Note: MG detector boxes 2-4 (including 18 modules) is part of the instrument scope but currently not linked to TG5 in P6. MG Detector box 1 (including 6 modules) has 91 days of float
TREX Critical Paths
Data from P6 April 2025 Lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
Notes: 2025-04
CP3 new: Translation table delayed 1 month
OoB Guide delayed 1 month

## Slide 14: Key milestones (as shown in dashboard)
Delays on all key milestones since the replanning

## Slide 15: Key milestones > 4 months delay
Comparing January 2025 with September 2025
Activity Name | Date (Jan 25) | Date (Sep 25) | Variance date (month)
T-REX:OoB Guide (96-151.5): CDR/subTG3 (meeting) | 02-jun-25 | 11-dec-25 | -5,8
T-REX:OoB Guide (151.5-163.1): IRR/subTG4 (meeting) | 15-sep-26 | 03-feb-27 | -4,55
T-REX: P- Fast Chopper: Factory Acceptance Test (FAT) | 23-sep-25 | 23-nov-26 | -13,4
T-REX: M- Fast Chopper: Factory Acceptance Test (FAT) | 19-dec-25 | 06-nov-26 | -9,7
T-REX: Fan Chopper:CDR/subTG3 (meeting) | 14-apr-25 | 16-dec-25 | -7,45
T-REX: BG Chopper (Disk & Housing): CDR/subTG3 (meeting) | 01-apr-25 | 25-nov-25 | -7,15
T-REX: Thermal Polarization: CDR/subTG3 (meeting) | 30-apr-25 | 24-nov-25 | -6,15
T-REX: Polarization Analyser: CDR/subTG3 (meeting) | 06-May-25 | 19-dec-25 | -6,95
T-REX: Polarization Flipper: CDR/subTG3 (meeting) | 07-May-25 | 15-dec-25 | -6,7
T-REX: Cd Shielding: Factory Acceptance Test (FAT) | 01-dec-25 | 29-apr-26 | -4,75
T-REX: Primary Coll & Slits: CDR/subTG3 (meeting) | 26-jun-25 | 08-jan-26 | -5,5
T-REX: Beamstop: CDR/subTG3 (meeting) | 27-May-25 | 14-jan-26 | -6,6
T-REX: Det boxes 2-4: Factory Acceptance Test (FAT) | 31-aug-26 | 10-feb-27 | -5,35

## Slide 16: Completing design for T2T3 instruments
30 meetings held this year from Jan 25 to mid-Sep 25
Chart: CTV/IDR/sub-TG3 held
| BEER | CSPEC | ESTIA | FREIA | HEIMDAL | MAGIC | MIRACLES | T-REX
CTV/IDR/sub-TG3 held in 2025 (from jan to mid-sep) | 2 | 2 | 3 | 3 | 6 | 6 | 2 | 6
As shown at ICB

## Slide 17: The path to TG3
Planned CDR meetings
Activity Name | Date (Sep 25)
T-REX: Control Hutch: CDR/subTG3 (meeting) | 17-okt-25
T-REX: Thermal Polarization: CDR/subTG3 (meeting) | 24-nov-25
T-REX: BG Chopper (Disk & Housing): CDR/subTG3 (meeting) | 25-nov-25
T-REX:OoB Guide (96-151.5): CDR/subTG3 (meeting) | 11-dec-25
T-REX: Translation Table: CDR/subTG3 (meeting) | 15-dec-25
T-REX: Polarization Flipper: CDR/subTG3 (meeting) | 15-dec-25
T-REX: Fan Chopper:CDR/subTG3 (meeting) | 16-dec-25
T-REX: Polarization Analyser: CDR/subTG3 (meeting) | 19-dec-25
T-REX: Primary Coll & Slits: CDR/subTG3 (meeting) | 08-jan-26
T-REX: Beamstop: CDR/subTG3 (meeting) | 14-jan-26
T-REX: Sample Environment: CDR/subTG3 (meeting) | 14-jan-26
T-REX:OoB Guide (151.5-163.1): CDR/subTG3 (meeting) | 11-jun-26

## Slide 18: Schedule adherence
Most months – T-REX is above average on schedule accuracy - improvement form last period!
Chart: Started activities: Planned vs Achieved
| 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45870 | 45901
Planned start | 4 | 5 | 9 | 7 | 6 | 4 | 1 | 8
Achieved start | 2 | 3 | 5 | 7 | 6 | 4 | 1 | 6
% starts achieved | 0.5 | 0.6 | 0.55556 | 1 | 1 | 1 | 1 | 0.75
% starts achieved NSS | 0.65476 | 0.59494 | 0.57488 | 0.72 | 0.68 | 0.65 | 0.65 | 0.55
Chart: Finished activites: Planned vs Achieved
| 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45870 | 45901
Planned finish | 7 | 10 | 6 | 5 | 5 | 4 | 2 | 10
Achieved finish | 5 | 6 | 4 | 4 | 4 | 4 | 0 | 8
% finish achieved | 0.71429 | 0.6 | 0.66667 | 0.8 | 0.8 | 1 | 0 | 0.8
% finish achieved NSS | 0.57396 | 0.63277 | 0.62946 | 0.68 | 0.64 | 0.61 | 0.58 | 0.45

## Slide 19: Lookout - future activities
There’s a lot in the pipeline..
Chart: Planned starts
| 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082
Planned start | 1 | 8 | 6 | 29 | 29 | 21 | 12 | 21
Achieved start | 1 | 6
Chart: Planned finishes
| 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082
Planned finish | 2 | 10 | 6 | 23 | 24 | 17 | 11 | 19
Achieved finish | 0 | 8