## Schedule adherence
| Planned start (Oct-25) | Planned starts (April-26) | Planned start | Achieved start | Planned finish (Oct-25) | Planned finish (April-26) | Planned finish | Achieved finish | % starts achieved | % finish achieved | % starts achieved NSS | % finish achieved NSS | % starts achieved ESS | % finish achieved ESS
2024-09-01 |  |  | 16 | 10 |  |  | 15 | 10 | 62.5% | 66.67% | 68% | 56% | 62% | 52%
2024-10-01 |  |  | 8 | 5 |  |  | 13 | 8 | 62.5% | 61.54% | 56.2% | 52.38% | 53% | 58%
2024-11-01 |  |  | 4 | 2 |  |  | 2 | 0 | 50% | 0% | 76.51% | 65.82% | 65% | 56%
2024-12-01 |  |  | 1 | 1 |  |  | 0 | 0 | 100% |  | 81.93% | 80.37%
2025-01-01 |  |  | 4 | 2 |  |  | 7 | 5 | 50% | 71.43% | 65.48% | 57.4%
2025-02-01 |  |  | 5 | 3 |  |  | 10 | 6 | 60% | 60% | 59.49% | 63.28%
2025-03-01 |  |  | 9 | 5 |  |  | 6 | 4 | 55.56% | 66.67% | 57.49% | 62.95%
2025-04-01 |  |  | 7 | 7 |  |  | 5 | 4 | 100% | 80% | 72% | 68%
2025-05-01 |  |  | 6 | 6 |  |  | 5 | 4 | 100% | 80% | 68% | 64%
2025-06-01 |  |  | 4 | 4 |  |  | 4 | 4 | 100% | 100% | 65% | 61%
2025-08-01 |  |  | 1 | 1 |  |  | 2 | 0 | 100% | 0% | 65% | 58%
2025-09-01 |  |  | 8 | 6 |  |  | 10 | 8 | 75% | 80% | 56% | 46%
2025-10-01 | 6 |  | 6 | 6 | 6 |  | 6 | 6 | 100% | 100% | 52% | 49%
2025-11-01 | 29 |  | 9 | 8 | 23 |  | 9 | 7 | 88.89% | 77.78% | 70% | 62%
2026-01-01 | 21 |  | 14 | 8 | 17 |  | 16 | 8 | 57.14% | 50% | 61% | 52%
2026-02-01 | 12 |  | 9 | 6 | 11 |  | 6 | 3 | 66.67% | 50% | 64% | 51%
2026-03-01 | 21 |  | 15 | 10 | 19 |  | 15 | 9 | 66.67% | 60% | 59% | 63%
2026-04-01 |  | 13 |  |  |  | 18
2026-05-01 |  | 17 |  |  |  | 22
2026-06-01 |  | 20 |  |  |  | 18
2026-07-01 |  | 15 |  |  |  | 11
2026-08-01 |  | 15 |  |  |  | 10
2026-09-01 |  | 25 |  |  |  | 24
2026-10-01 |  | 41 |  |  |  | 43

## P6 APRIL
REPLANNING
Activity ID | Activity Name | Activity % Complete | Original Duration | Start | Finish | BL1 Start | BL1 Finish
NSS-A214781310 | T-REX: Polarization Analyser: Detailed design | 91% | 521 | 01-Jan-24 A | 2026-05-13 | 2024-01-01 | 2025-03-21
NSS-A214787920 | T-REX: Polarization Flipper: Detailed design | 81% | 480 | 01-Mar-24 A | 2026-05-13 | 2024-03-01 | 2025-03-24
NSS-A214784910 | T-REX: Det prototype box: Storage at FZJ until detector group is ready for the test of Grids | 89.82% | 226 | 05-maj-25 A | 2026-05-06 | 2026-04-29 | 2026-04-29
NSS-A214786830 | T-REX: Translation Table: Submission of docs to ESS for CDR/TG3 | 84.91% | 159 | 18-Aug-25 A | 2026-05-07 | 2025-06-24 | 2025-09-05
NSS-A214784750 | T-REX: P- Fast Chopper: Manufacturing of housing and spindles | 76.76% | 185 | 01-Sep-25 A | 2026-06-05 | 2025-09-25 | 2026-02-09
NSS-A214785100 | T-REX: M- Fast Chopper: Manufacturing of housing and spindles | 92.16% | 153 | 02-Sep-25 A | 2026-04-20 | 2027-02-02 | 2027-03-01
NSS-A214786120 | T-REX: Cave: Qgate document submission phase (CE) | 78.23% | 124 | 03-Nov-25 A | 2026-05-12 | 2025-11-03 | 2025-11-20
NSS-A214788430 | T-REX: Primary Coll & Slits: CDR: Closure of open points and approval | 81.31% | 107 | 17-Nov-25 A | 2026-04-30 | 2025-06-26 | 2025-07-09
NSS-A2147382610 | T-REX: Det boxes 2-4: Tendering process | 75% | 112 | 20-Nov-25 A | 2026-05-13 | 2025-05-21 | 2025-10-23
NSS-A214785170 | T-REX: M- Fast Chopper: Manufacturing of New Disks | 47.59% | 166 | 27-Nov-25 A | 2026-09-04
NSS-A214784780 | T-REX: P- Fast Chopper: Manufacturing of New Disks | 49.66% | 145 | 08-Dec-25 A | 2026-08-17 | 2026-03-26 | 2026-03-31
NSS-A214783450 | T-REX:OoB Guide (28-40): Qgate document submission phase (CE n/a) | 96.88% | 64 | 22-Dec-25 A | 2026-04-02 | 2025-11-20 | 2025-12-17
NSS-A214783460 | T-REX:OoB Guide (28-40): Preparation of installation binder | 96.88% | 64 | 22-Dec-25 A | 2026-04-02 | 2025-11-20 | 2025-12-17
NSS-A214787680 | T-REX: Cave: Quality gate review and approval (CE) | 49.52% | 105 | 19-Jan-26 A | 2026-06-22 | 2025-11-21 | 2025-12-10
NSS-A214783930 | T-REX:OoB Guide (151.5-163.1): Detailed design | 67.14% | 70 | 26-Jan-26 A | 2026-05-06 | 2025-06-17 | 2025-10-21
NSS-A214786210 | T-REX: Cave: Installation of Wall + celling | 62.67% | 75 | 26-Jan-26 A | 2026-05-13 | 2026-02-03 | 2026-03-02
NSS-A214783200 | T-REX: Cd Shielding: Manufacturing | 34.55% | 110 | 06-Feb-26 A | 2026-07-17 | 2025-06-24 | 2025-11-24
NSS-A214784000 | T-REX: Secondary RC: FAT-closure of open points and approval | 61.54% | 52 | 16-Feb-26 A | 2026-04-30 | 2025-12-16 | 2026-01-14
NSS-A214786470 | T-REX: Control Hutch: Preparation of installation binder | 82.05% | 39 | 16-Feb-26 A | 2026-04-13 | 2026-04-02 | 2026-05-04
NSS-A214783470 | T-REX:OoB Guide (28-40): IRR documents review by ESS | 83.78% | 37 | 17-Feb-26 A | 2026-04-10 | 2025-12-18 | 2026-01-14
NSS-A214787150 | T-REX:OoB Guide (28-40): Quality gate review and approval | 45.95% | 37 | 17-Feb-26 A | 2026-04-30 | 2025-12-18 | 2026-01-28
NSS-A214785570 | T-REX: BG Chopper (Disk & Housing): Shipping | 89.66% | 29 | 24-Feb-26 A | 2026-04-07 | 2026-01-26 | 2026-02-06
NSS-A214784070 | T-REX:OoB Guide (96-151.5): Manufacturing Part 2 | 30% | 80 | 26-Feb-26 A | 2026-06-25 | 2026-05-20 | 2026-05-20
NSS-A214786700 | T-REX: Thermal Polarization: Manufacturing | 18.33% | 120 | 02-Mar-26 A | 2026-09-21 | 2025-06-24 | 2026-01-19
NSS-A214786100 | T-REX: Cave: Manufacturing of crane | 35.29% | 51 | 06-Mar-26 A | 2026-05-22 | 2025-12-01 | 2025-12-05
NSS-A214787200 | T-REX:OoB Guide (96-151.5): FAT Report and Documentation Part 1 | 0% | 10 | 20-Mar-26 A | 2026-04-24 | 2025-09-26 | 2025-10-13
NSS-A214785620 | T-REX: BG Chopper (Disk & Housing): FAT Approval | 0% | 10 | 26-Mar-26 A | 2026-04-30
NSS-A214784570 | T-REX: Beamstop: Preparation for CTV | 0% | 20 | 2026-04-01 | 2026-04-30 | 2025-09-11 | 2025-09-11
NSS-A214781670 | T-REX: IBG (HS): Installation (ESS/common projects) | 0% | 10 | 07-Apr-26* | 2026-04-20 | 2025-02-21 | 2025-03-06
NSS-A214781850 | T-REX: IBG (fixed and remote): Installation (ESS/common projects) | 0% | 10 | 07-Apr-26* | 2026-04-20 | 2025-04-22 | 2025-05-06
NSS-A214782210 | T-REX: BBG:Installation (ESS/common projects) | 0% | 10 | 07-Apr-26* | 2026-04-20 | 2025-06-02 | 2025-06-16
NSS-A214784200 | T-REX:OoB Guide (151.5-163.1): IDR | 0% | 5 | 2026-04-08 | 2026-04-14 | 2025-09-24 | 2025-09-30
NSS-A214785580 | T-REX: BG Chopper (Disk & Housing): Arrival Inspection | 0% | 5 | 2026-04-08 | 2026-04-14 | 2026-02-09 | 2026-02-13
NSS-A214788720 | T-REX: Sample Environment: CDR: Closure of open points and approval | 0% | 18 | 08-Apr-26* | 2026-05-04 | 2025-10-23 | 2025-11-12
NSS-A214786490 | T-REX: Control Hutch: IRR documents review by ESS | 0% | 10 | 2026-04-14 | 2026-04-27 | 2026-05-05 | 2026-05-20
NSS-A214786530 | T-REX: Control Hutch: Installation (partner/supplier) | 0% | 40 | 2026-04-14 | 2026-06-11 | 2026-06-22 | 2026-07-15
NSS-A214781680 | T-REX: IBG (HS): Integrated SAT | 0% | 20 | 2026-04-21 | 2026-05-21 | 2025-03-07 | 2025-04-03
NSS-A214781860 | T-REX: IBG (fixed and remote): Integrated: SAT | 0% | 20 | 2026-04-21 | 2026-05-21 | 2025-05-07 | 2025-06-05
NSS-A214782220 | T-REX: BBG:Integrated SAT | 0% | 20 | 2026-04-21 | 2026-05-21 | 2025-06-17 | 2025-07-15
NSS-A214787210 | T-REX:OoB Guide (96-151.5): FAT-closure of open points and approval Part 1 | 0% | 6 | 2026-04-27 | 2026-05-05 | 2025-10-14 | 2025-10-29
NSS-A214783580 | T-REX: Primary Coll & Slits: Tendering process | 0% | 30 | 2026-05-04 | 2026-06-16 | 2025-07-10 | 2025-08-20
NSS-A214784030 | T-REX: Secondary RC: Integration with the drive system & testing | 0% | 30 | 2026-05-04 | 2026-06-16 | 2026-01-29 | 2026-03-11
NSS-A214784410 | T-REX: Beamstop: Submission of docs to ESS for CDR/TG3 | 0% | 14 | 2026-05-04 | 2026-05-25 | 2025-04-14 | 2025-05-06
NSS-A214785820 | T-REX: Com Chop: Coating of disks | 0% | 20 | 2026-05-04 | 2026-06-02 | 2026-02-16 | 2026-03-13
NSS-A2147409960 | T-REX: OoB Guide 1 B: Installation (partner/supplier) | 0% | 5 | 2026-05-04 | 2026-05-08
NSS-A214781070 | T-REX: Sample Environment: Manufacturing | 0% | 78 | 2026-05-05 | 2026-09-22 | 2025-11-13 | 2026-03-16
NSS-A214784210 | T-REX:OoB Guide (151.5-163.1): Submission of docs to ESS for CDR/TG3 | 0% | 20 | 2026-05-07 | 2026-06-05 | 2025-10-22 | 2025-11-18
NSS-A214784880 | T-REX: Det prototype box: Shipping to Utgård | 0% | 5 | 2026-05-07 | 2026-05-13 | 2025-12-10 | 2025-12-16
NSS-A214787740 | T-REX: Translation Table: Review of CDR documents by ESS | 0% | 15 | 2026-05-08 | 2026-06-01 | 2025-09-08 | 2025-09-30
NSS-A2147409970 | T-REX: OoB Guide 1 B: Local SAT | 0% | 5 | 2026-05-11 | 2026-05-19
NSS-A214781470 | T-REX: Polarization Analyser: Submission of docs to ESS for CDR/TG3 | 0% | 10 | 2026-05-18 | 2026-05-29 | 2025-03-24 | 2025-04-10
NSS-A214787940 | T-REX: Polarization Flipper: Submission of docs to ESS for CDR/TG3 | 0% | 10 | 2026-05-18 | 2026-05-29 | 2025-03-25 | 2025-04-11
NSS-A2147354840 | T-REX: Det boxes 2: Manufacturing | 0% | 150 | 2026-05-18 | 2027-01-25 | 2025-10-24 | 2026-08-28
NSS-A214786240 | T-REX: Cave: Carpentry | 0% | 10 | 2026-05-18 | 2026-05-29 | 2026-04-01 | 2026-04-27
NSS-A214783110 | T-REX: OoB Guide 1 B: Installation (ESS/common projects) | 0% | 10 | 2026-05-20 | 2026-06-02 | 2026-01-28 | 2026-02-10
NSS-A214786280 | T-REX: Cave: Delivery of crane | 0% | 5 | 2026-05-25 | 2026-05-29 | 2026-06-29 | 2026-09-04
NSS-A214788570 | T-REX: Beamstop: Review of CDR documents by ESS | 0% | 14 | 2026-05-26 | 2026-06-12 | 2025-05-07 | 2025-05-26
NSS-A1201050 | PSS - WP15.2 - Installed | 0% | 1 | 01-Jun-26* | 2026-06-01
NSS-A214786220 | T-REX: Cave: Installation of Crane | 0% | 10 | 2026-06-01 | 2026-06-12 | 2026-03-03 | 2026-03-31
NSS-A214787850 | T-REX: Polarization Analyser: Review of CDR documents by ESS | 0% | 15 | 2026-06-01 | 2026-06-22 | 2025-04-11 | 2025-05-05
NSS-A214788090 | T-REX: Polarization Flipper: Review of CDR documents by ESS | 0% | 15 | 2026-06-01 | 2026-06-22 | 2025-04-14 | 2025-05-06
NSS-A214787730 | T-REX: Translation Table: CDR: Closure of open points and approval | 0% | 12 | 2026-06-02 | 2026-06-17 | 2025-10-01 | 2025-10-16
NSS-A214783120 | T-REX: OoB Guide 1 B: Integrated SAT | 0% | 20 | 2026-06-03 | 2026-07-01 | 2026-02-11 | 2026-03-10
NSS-A214785830 | T-REX: Com Chop: Integration CNR+ESS | 0% | 20 | 2026-06-03 | 2026-07-01 | 2026-03-16 | 2026-04-14
NSS-A214787250 | T-REX:OoB Guide (151.5-163.1): Review of CDR documents by ESS | 0% | 20 | 2026-06-08 | 2026-07-06 | 2025-11-19 | 2025-12-16
NSS-A214786550 | T-REX: Control Hutch: Local SAT | 0% | 5 | 2026-06-12 | 2026-06-18 | 2026-07-16 | 2026-08-19
NSS-A214786230 | T-REX: Cave: First crane certification | 0% | 5 | 2026-06-15 | 2026-06-22 | 2026-04-01 | 2026-04-09
NSS-A214788580 | T-REX: Beamstop: CDR: Closure of open points and approval | 0% | 15 | 2026-06-15 | 2026-07-06 | 2025-05-27 | 2025-07-09
NSS-A214783590 | T-REX: Primary Coll & Slits: Manufacturing | 0% | 135 | 2026-06-17 | 2026-12-23 | 2025-08-21 | 2026-03-06
NSS-A214788840 | T-REX: Secondary RC: FAT report and documentation (Drive and Blades) | 0% | 10 | 2026-06-17 | 2026-07-01 | 2026-03-12 | 2026-03-25
NSS-A214782040 | T-REX: Detector Vessel: Rework and testing at FZJ (Cad integration) | 0% | 46 | 2026-06-17 | 2026-09-17 | 2026-11-11 | 2026-11-24
NSS-A214786850 | T-REX: Translation Table: Manufacturing | 0% | 80 | 2026-06-18 | 2026-11-05 | 2025-10-17 | 2026-03-19
NSS-A214787860 | T-REX: Polarization Analyser: CDR: Closure of open points and approval | 0% | 10 | 2026-06-23 | 2026-07-06 | 2025-05-06 | 2025-06-17
NSS-A214788100 | T-REX: Polarization Flipper: CDR: Closure of open points and approval | 0% | 10 | 2026-06-23 | 2026-07-06 | 2025-05-07 | 2025-06-18
NSS-A214783850 | T-REX:OoB Guide (96-151.5): Qgate document submission phase | 0% | 15 | 2026-06-26 | 2026-07-16 | 2025-10-30 | 2025-11-26
NSS-A214784140 | T-REX:OoB Guide (96-151.5): FAT-closure of open points and approval Part 2 | 0% | 25 | 2026-06-26 | 2026-08-27
NSS-A214783490 | T-REX:OoB Guide (28-40): Installation (partner/supplier) | 0% | 10 | 2026-06-30 | 2026-07-13 | 2026-02-12 | 2026-03-13
NSS-A214785850 | T-REX: Com Chop: Factory Acceptance Test (FAT) | 0% | 22 | 2026-07-02 | 2026-08-28 | 2026-04-15 | 2026-05-19
NSS-A214788850 | T-REX: Secondary RC: FAT- Closure of open point and approval (Drive and Blades) | 0% | 10 | 2026-07-02 | 2026-07-15 | 2026-03-26 | 2026-04-10
NSS-A214781970 | T-REX: Detector Vessel: Qgate document submission phase | 0% | 20 | 2026-07-03 | 2026-08-27 | 2026-02-13 | 2026-03-12
NSS-A214781490 | T-REX: Polarization Analyser: Manufacturing | 0% | 80 | 2026-07-07 | 2026-11-23 | 2025-06-18 | 2025-12-10
NSS-A214784430 | T-REX: Beamstop: Manufacturing | 0% | 60 | 2026-07-07 | 2026-10-26 | 2025-07-10 | 2025-11-26
NSS-A214787260 | T-REX:OoB Guide (151.5-163.1): CDR: Closure of open points and approval | 0% | 14 | 2026-07-07 | 2026-08-21 | 2025-12-17 | 2026-01-19
NSS-A214787960 | T-REX: Polarization Flipper: Manufacturing | 0% | 90 | 2026-07-07 | 2026-12-07 | 2025-06-19 | 2025-12-04
NSS-A214782280 | T-REX: False floor and Det supp: Qgate document submission phase (partial CE) | 0% | 20 | 2026-07-10 | 2026-09-03 | 2026-03-06 | 2026-04-02
NSS-A214783500 | T-REX:OoB Guide (28-40): Local SAT | 0% | 5 | 2026-07-14 | 2026-08-17 | 2026-03-16 | 2026-03-20
NSS-A2146961230 | Neutron Detector - WP09.14 - Delivered (ESS) - Package 2 | 0% | 57 | 15-Jul-26* | 2026-10-29
NSS-A214784050 | T-REX: Secondary RC: Shipping to ESS | 0% | 19 | 2026-07-16 | 2026-09-09 | 2026-04-13 | 2026-05-11
NSS-A214784080 | T-REX: Secondary RC: Qgate document submission phase | 0% | 20 | 2026-07-16 | 2026-09-09 | 2026-04-13 | 2026-05-11
NSS-A214784090 | T-REX: Secondary RC: Preparation of installation binder | 0% | 14 | 2026-07-16 | 2026-09-01 | 2026-04-13 | 2026-04-30
NSS-A214781980 | T-REX: Detector Vessel: Preparation of installation binder | 0% | 20 | 2026-07-17 | 2026-09-10 | 2026-02-27 | 2026-03-26
NSS-A214787240 | T-REX:OoB Guide (96-151.5): Quality gate review and approval | 0% | 15 | 2026-07-17 | 2026-09-03 | 2025-11-27 | 2026-01-21
NSS-A214788370 | T-REX: Cd Shielding: Factory Acceptance Test (FAT) | 0% | 5 | 2026-08-17 | 2026-08-21 | 2025-11-25 | 2025-12-01
NSS-A214783510 | T-REX:OoB Guide (28-40): Installation (ESS/common projects) | 0% | 10 | 2026-08-18 | 2026-08-31 | 2026-03-23 | 2026-04-07
NSS-A214784770 | T-REX: P- Fast Chopper: Lab test at FZJ | 0% | 80 | 2026-08-18 | 2026-12-07 | 2026-02-17 | 2026-03-26
NSS-A214784890 | T-REX: Det prototype box: Arrival Inspection at Utgård | 0% | 5 | 2026-08-20 | 2026-08-26 | 2025-12-17 | 2025-12-23
NSS-A214782290 | T-REX: False floor and Det supp: Preparation of installation binder | 0% | 20 | 2026-08-21 | 2026-09-17 | 2026-03-20 | 2026-04-20
NSS-A214782600 | T-REX: RC Drive: Qgate document submission phase (partial CE) | 0% | 20 | 2026-08-21 | 2026-09-17 | 2026-03-02 | 2026-03-27
NSS-A214784230 | T-REX:OoB Guide (151.5-163.1): Manufacturing | 0% | 65 | 2026-08-24 | 2026-11-20 | 2026-01-20 | 2026-04-22
NSS-A214785110 | T-REX: Document compilation and submission for Final TG3 | 0% | 30 | 2026-08-24 | 2026-10-02 | 2026-01-20 | 2026-03-02
NSS-A214788380 | T-REX: Cd Shielding: FAT Report and Documentation | 0% | 5 | 2026-08-24 | 2026-08-28 | 2025-12-02 | 2025-12-08
NSS-A214782890 | T-REX: Sample ex-container: Qgate document submission phase (partial CE) | 0% | 20 | 2026-08-28 | 2026-09-24 | 2025-09-22 | 2025-10-17
NSS-A214783820 | T-REX:OoB Guide (96-151.5): Shipping | 0% | 5 | 2026-08-28 | 2026-09-03 | 2025-10-30 | 2025-11-05
NSS-A214783860 | T-REX:OoB Guide (96-151.5): Preparation of installation binder | 0% | 15 | 2026-08-28 | 2026-09-17 | 2025-10-30 | 2025-11-26
NSS-A214788160 | T-REX: Detector Vessel: Quality gate review and approval | 0% | 20 | 2026-08-28 | 2026-09-24 | 2026-03-13 | 2026-04-13
NSS-A214783210 | T-REX: Cd Shielding: FAT-closure of open points and approval | 0% | 20 | 2026-08-31 | 2026-09-25 | 2025-12-09 | 2026-01-19
NSS-A214787590 | T-REX: Com Chop: FAT Report and Documentation | 0% | 10 | 2026-08-31 | 2026-09-11 | 2026-05-20 | 2026-06-02
NSS-A214783520 | T-REX:OoB Guide (28-40): Integrated SAT | 0% | 20 | 2026-09-01 | 2026-09-28 | 2026-04-08 | 2026-05-06
NSS-A214782610 | T-REX: RC Drive: Preparation of installation binder | 0% | 20 | 2026-09-04 | 2026-10-01 | 2026-03-02 | 2026-03-27
NSS-A214783830 | T-REX:OoB Guide (96-151.5): Arrival Inspection | 0% | 5 | 2026-09-04 | 2026-09-10 | 2025-11-06 | 2025-11-12
NSS-A214788220 | T-REX: False floor and Det supp: Quality gate review and approval | 0% | 20 | 2026-09-04 | 2026-10-01 | 2026-04-07 | 2026-05-05
NSS-A214785160 | T-REX: M- Fast Chopper: Lab test at FZJ | 0% | 70 | 2026-09-07 | 2026-12-11
NSS-A214784060 | T-REX: Secondary RC: Arrival Inspection (ESS) | 0% | 5 | 2026-09-09 | 2026-09-16 | 2026-05-11 | 2026-05-20
NSS-A214781990 | T-REX: Detector Vessel: IRR documents review by ESS | 0% | 10 | 2026-09-11 | 2026-09-24 | 2026-03-27 | 2026-04-13
NSS-A214782900 | T-REX: Sample ex-container: Preparation of installation binder | 0% | 20 | 2026-09-11 | 2026-10-08 | 2025-09-22 | 2025-10-17
NSS-A214787600 | T-REX: Com Chop: FAT-closure of open points and approval | 0% | 12 | 2026-09-14 | 2026-09-29 | 2026-06-03 | 2026-06-18
NSS-A214781960 | T-REX: Detector Vessel: Shipping | 0% | 10 | 2026-09-18 | 2026-10-01 | 2025-12-10 | 2026-02-17
NSS-A214782300 | T-REX: False floor and Det supp: IRR documents review by ESS | 0% | 10 | 2026-09-18 | 2026-10-01 | 2026-04-21 | 2026-05-05
NSS-A214782570 | T-REX: RC Drive: Shipping | 0% | 5 | 2026-09-18 | 2026-09-24 | 2026-03-02 | 2026-03-06
NSS-A214783870 | T-REX:OoB Guide (96-151.5): IRR documents review by ESS | 0% | 10 | 2026-09-18 | 2026-10-01 | 2025-11-27 | 2025-12-10
NSS-A214788270 | T-REX: RC Drive: Quality gate review and approval | 0% | 20 | 2026-09-18 | 2026-10-15 | 2026-04-21 | 2026-05-21
NSS-A214787760 | T-REX: Thermal Polarization: FAT Report and Documentation | 0% | 12 | 2026-09-22 | 2026-10-07 | 2026-01-20 | 2026-02-04
NSS-A214788740 | T-REX: Sample Environment: FAT Report and Documentation | 0% | 12 | 2026-09-23 | 2026-10-08 | 2026-03-17 | 2026-04-01
NSS-A214782580 | T-REX: RC Drive: Arrival Inspection | 0% | 5 | 2026-09-25 | 2026-10-01 | 2026-03-09 | 2026-03-13
NSS-A214788170 | T-REX: Detector Vessel: IRR meeting preparation | 0% | 5 | 2026-09-25 | 2026-10-01 | 2026-04-14 | 2026-04-20
NSS-A214788320 | T-REX: Sample ex-container: Quality gate review and approval | 0% | 20 | 2026-09-25 | 2026-10-22 | 2026-04-28 | 2026-05-28
NSS-A214788540 | T-REX: Secondary RC: Quality gate review and approval | 0% | 20 | 2026-09-25 | 2026-10-22 | 2026-05-12 | 2026-06-10
NSS-A214783220 | T-REX: Cd Shielding: Shipping | 0% | 5 | 2026-09-28 | 2026-10-02 | 2026-01-20 | 2026-01-26
NSS-A214783250 | T-REX: Cd Shielding: Qgate document submission phase | 0% | 20 | 2026-09-28 | 2026-10-23 | 2026-01-20 | 2026-02-16
NSS-A214783260 | T-REX: Cd Shielding: Preparation of installation binder | 0% | 20 | 2026-09-28 | 2026-10-23 | 2026-01-20 | 2026-02-16
NSS-A214785890 | T-REX: Com Chop: Qgate document submission phase (ESS chopper group) | 0% | 20 | 2026-09-30 | 2026-10-27 | 2026-06-22 | 2026-07-17
NSS-A214785900 | T-REX: Com Chop: Preparation of installation binder | 0% | 20 | 2026-09-30 | 2026-10-27 | 2026-06-22 | 2026-07-17
NSS-A1201020 | Neutron Detector - WP09.15 - Installation - Package 2 | 0% | 86 | 01-okt-26* | 2027-02-11
NSS-A1201060 | Neutron Detector - WP09.16 - Installed | 0% | 86 | 01-okt-26* | 2027-02-11
NSS-A214782250 | T-REX: False floor and Det supp: Shipping | 0% | 5 | 2026-10-01 | 2026-10-07 | 2026-05-05 | 2026-05-11
NSS-A214782000 | T-REX: Detector Vessel: Installation (partner/supplier) | 0% | 10 | 2026-10-02 | 2026-10-15 | 2026-04-28 | 2026-05-21
NSS-A214782620 | T-REX: RC Drive: IRR documents review by ESS | 0% | 10 | 2026-10-02 | 2026-10-15 | 2026-05-06 | 2026-05-21
NSS-A214787220 | T-REX:OoB Guide (96-151.5): IRR meeting preparation | 0% | 5 | 2026-10-02 | 2026-10-08 | 2026-01-22 | 2026-01-28
NSS-A214788230 | T-REX: False floor and Det supp: IRR meeting preparation | 0% | 5 | 2026-10-02 | 2026-10-08 | 2026-05-06 | 2026-05-12
NSS-A214783230 | T-REX: Cd Shielding: Arrival Inspection | 0% | 5 | 2026-10-05 | 2026-10-09 | 2026-01-27 | 2026-02-02
NSS-A214785140 | T-REX: Final TG3 action closeouts | 0% | 20 | 2026-10-05 | 2026-10-30
NSS-A214782260 | T-REX: False floor and Det supp: Arrival Inspection | 0% | 6 | 2026-10-08 | 2026-10-15 | 2026-05-12 | 2026-05-21
NSS-A214786710 | T-REX: Thermal Polarization: FAT-closure of open points and approval | 0% | 12 | 2026-10-08 | 2026-10-23 | 2026-02-05 | 2026-02-20
NSS-A214781080 | T-REX: Sample Environment: FAT-closure of open points and approval | 0% | 12 | 2026-10-09 | 2026-10-26 | 2026-04-02 | 2026-04-21
NSS-A214782910 | T-REX: Sample ex-container: IRR documents review by ESS | 0% | 10 | 2026-10-09 | 2026-10-22 | 2026-05-13 | 2026-05-28
NSS-A214784100 | T-REX: Secondary RC: IRR documents review by ESS | 0% | 10 | 2026-10-09 | 2026-10-22 | 2026-05-04 | 2026-05-19
NSS-A214787230 | T-REX:OoB Guide (96-151.5): Installation preparation | 0% | 5 | 2026-10-09 | 2026-10-15 | 2026-01-29 | 2026-02-04
NSS-A214788240 | T-REX: False floor and Det supp: Installation preparation | 0% | 5 | 2026-10-09 | 2026-10-15 | 2026-05-13 | 2026-05-21
NSS-A214782010 | T-REX: Detector Vessel: Local SAT | 0% | 5 | 2026-10-16 | 2026-10-22 | 2026-05-22 | 2026-05-28
NSS-A214782320 | T-REX: False floor and Det supp: Installation (partner/supplier) | 0% | 10 | 2026-10-16 | 2026-10-29 | 2026-05-22 | 2026-06-04
NSS-A214783890 | T-REX:OoB Guide (96-151.5): Installation (partner/supplier) | 0% | 25 | 2026-10-16 | 2026-11-19 | 2026-02-05 | 2026-03-04
NSS-A214786250 | T-REX: Cave: Installation of Last wall | 0% | 15 | 2026-10-16 | 2026-11-05 | 2026-05-22 | 2026-06-18
NSS-A214788280 | T-REX: RC Drive: IRR meeting preparation | 0% | 5 | 2026-10-16 | 2026-10-22 | 2026-05-22 | 2026-05-28
NSS-A214782020 | T-REX: Detector Vessel + MG.TREX.1 : Installation of box 1 with columns into vessel (ESS/common projects) | 0% | 10 | 2026-10-23 | 2026-11-05 | 2026-05-29 | 2026-06-11
NSS-A214782860 | T-REX: Sample ex-container: Shipping | 0% | 5 | 2026-10-23 | 2026-10-29 | 2026-05-29 | 2026-06-04
NSS-A214788290 | T-REX: RC Drive: Installation preparation | 0% | 5 | 2026-10-23 | 2026-10-29 | 2026-05-29 | 2026-06-04
NSS-A214788330 | T-REX: Sample ex-container: IRR meeting preparation | 0% | 5 | 2026-10-23 | 2026-10-29 | 2026-05-29 | 2026-06-04
NSS-A214788550 | T-REX: Secondary RC: IRR meeting preparation | 0% | 5 | 2026-10-23 | 2026-10-29 | 2026-06-11 | 2026-06-17
NSS-A214786720 | T-REX: Thermal Polarization: Shipping | 0% | 5 | 2026-10-26 | 2026-10-30 | 2026-02-23 | 2026-02-27
NSS-A214786750 | T-REX: Thermal Polarization: Qgate document submission phase (complicated) | 0% | 34 | 2026-10-26 | 2026-12-10 | 2026-02-23 | 2026-04-13
NSS-A214786760 | T-REX: Thermal Polarization: Preparation of installation binder | 0% | 20 | 2026-10-26 | 2026-11-20 | 2026-02-23 | 2026-03-20
NSS-A214788390 | T-REX: Cd Shielding: Quality gate review and approval | 0% | 20 | 2026-10-26 | 2026-11-20 | 2026-05-06 | 2026-06-04
NSS-A214781090 | T-REX: Sample Environment: Shipping | 0% | 5 | 2026-10-27 | 2026-11-02 | 2026-04-22 | 2026-04-28
NSS-A214781120 | T-REX: Sample Environment: Qgate document submission phase (probably CE) | 0% | 20 | 2026-10-27 | 2026-11-23 | 2026-04-22 | 2026-05-22
NSS-A214781130 | T-REX: Sample Environment: Preparation of installation binder | 0% | 20 | 2026-10-27 | 2026-11-23 | 2026-04-22 | 2026-05-22
NSS-A214788600 | T-REX: Beamstop: FAT Report and Documentation | 0% | 12 | 2026-10-27 | 2026-11-11 | 2025-11-27 | 2025-12-12
NSS-A214785910 | T-REX: Com Chop: IRR documents review by ESS | 0% | 10 | 2026-10-28 | 2026-11-10 | 2026-08-17 | 2026-08-28
NSS-A214787610 | T-REX: Com Chop: Quality gate review and approval | 0% | 20 | 2026-10-28 | 2026-11-24 | 2026-08-17 | 2026-09-11
NSS-A214782330 | T-REX: False floor and Det supp: Local SAT | 0% | 5 | 2026-10-30 | 2026-11-05 | 2026-06-05 | 2026-06-11
NSS-A214782640 | T-REX: RC Drive: Installation (partner/supplier) | 0% | 5 | 2026-10-30 | 2026-11-05 | 2026-06-05 | 2026-06-11
NSS-A214782870 | T-REX: Sample ex-container: Arrival Inspection | 0% | 5 | 2026-10-30 | 2026-11-05 | 2026-06-05 | 2026-06-11
NSS-A214784120 | T-REX: Secondary RC: Installation | 0% | 10 | 2026-10-30 | 2026-11-12 | 2026-06-18 | 2026-07-02
NSS-A214788340 | T-REX: Sample ex-container: installation preparation | 0% | 5 | 2026-10-30 | 2026-11-05 | 2026-06-05 | 2026-06-11
NSS-A214786730 | T-REX: Thermal Polarization: Arrival Inspection | 0% | 5 | 2026-11-02 | 2026-11-06 | 2026-03-02 | 2026-03-06
NSS-A214781100 | T-REX: Sample Environment: Arrival Inspection | 0% | 5 | 2026-11-03 | 2026-11-09 | 2026-04-29 | 2026-05-06
NSS-A214782340 | T-REX: False floor and Det supp: Installation (ESS/common projects) | 0% | 10 | 2026-11-06 | 2026-11-19 | 2026-06-12 | 2026-06-26
NSS-A214782650 | T-REX: RC Drive: Local SAT | 0% | 5 | 2026-11-06 | 2026-11-12 | 2026-06-12 | 2026-06-18
NSS-A214782930 | T-REX: Sample ex-container: Installation (partner/supplier) | 0% | 5 | 2026-11-06 | 2026-11-12 | 2026-06-12 | 2026-06-18
NSS-A214786270 | T-REX: Cave: Local SAT | 0% | 5 | 2026-11-06 | 2026-11-12 | 2026-06-22 | 2026-06-26
NSS-A214787780 | T-REX: Translation Table: FAT Report and Documentation | 0% | 12 | 2026-11-06 | 2026-11-23 | 2026-03-20 | 2026-04-08
NSS-A214783270 | T-REX: Cd Shielding: IRR documents review by ESS | 0% | 10 | 2026-11-09 | 2026-11-20 | 2026-05-22 | 2026-06-04
NSS-A214784440 | T-REX: Beamstop: FAT-closure of open points and approval | 0% | 12 | 2026-11-12 | 2026-11-27 | 2025-12-15 | 2026-01-13
NSS-A214782660 | T-REX: RC Drive: Installation (ESS/common projects) | 0% | 10 | 2026-11-13 | 2026-11-26 | 2026-06-22 | 2026-07-03
NSS-A214782940 | T-REX: Sample ex-container: Local SAT | 0% | 5 | 2026-11-13 | 2026-11-19 | 2026-06-22 | 2026-06-26
NSS-A214784130 | T-REX: Secondary RC: Local SAT | 0% | 5 | 2026-11-13 | 2026-11-19 | 2026-07-03 | 2026-07-09
NSS-A214782350 | T-REX: False floor and Det supp: Integrated SAT | 0% | 10 | 2026-11-20 | 2026-12-03 | 2026-06-29 | 2026-07-10
NSS-A214783910 | T-REX:OoB Guide (96-151.5): Installation (ESS/common projects) | 0% | 10 | 2026-11-20 | 2026-12-03 | 2026-03-05 | 2026-03-18
NSS-A214786770 | T-REX: Thermal Polarization: IRR documents review by ESS | 0% | 10 | 2026-11-23 | 2026-12-04 | 2026-03-23 | 2026-04-07
NSS-A214787270 | T-REX:OoB Guide (151.5-163.1): FAT Report and Documentation | 0% | 10 | 2026-11-23 | 2026-12-04 | 2026-04-23 | 2026-05-11
NSS-A214788400 | T-REX: Cd Shielding: IRR meeting preparation | 0% | 5 | 2026-11-23 | 2026-11-27 | 2026-06-05 | 2026-06-11
NSS-A214781140 | T-REX: Sample Environment: IRR documents review by ESS | 0% | 10 | 2026-11-24 | 2026-12-07 | 2026-05-25 | 2026-06-05
NSS-A214786860 | T-REX: Translation Table: FAT-closure of open points and approval | 0% | 12 | 2026-11-24 | 2026-12-09 | 2026-04-09 | 2026-04-24
NSS-A214787880 | T-REX: Polarization Analyser: FAT Report and Documentation | 0% | 10 | 2026-11-24 | 2026-12-07 | 2025-12-11 | 2026-01-07
NSS-A214788750 | T-REX: Sample Environment: Quality gate review and approval | 0% | 20 | 2026-11-24 | 2026-12-21 | 2026-05-25 | 2026-06-22
NSS-A214787620 | T-REX: Com Chop: IRR meeting preparation | 0% | 5 | 2026-11-25 | 2026-12-01 | 2026-09-14 | 2026-09-18
NSS-A214787630 | T-REX: Com Chop: Installation preparation | 0% | 5 | 2026-11-25 | 2026-12-01 | 2026-09-21 | 2026-09-25
NSS-A214782670 | T-REX: RC Drive: Integrated SAT | 0% | 20 | 2026-11-27 | 2027-01-07 | 2026-07-06 | 2026-08-28
NSS-A214784450 | T-REX: Beamstop: Shipping | 0% | 5 | 2026-11-30 | 2026-12-04 | 2026-01-14 | 2026-01-20
NSS-A214784480 | T-REX: Beamstop: Qgate document submission phase | 0% | 15 | 2026-11-30 | 2026-12-18 | 2026-01-14 | 2026-02-10
NSS-A214784490 | T-REX: Beamstop: Preparation of installation binder | 0% | 15 | 2026-11-30 | 2026-12-18 | 2026-01-14 | 2026-02-10
NSS-A214788410 | T-REX: Cd Shielding: Installation preparation | 0% | 5 | 2026-11-30 | 2026-12-04 | 2026-06-12 | 2026-06-18
NSS-A214785930 | T-REX: Com Chop: Installation (partner and ESS) | 0% | 17 | 2026-12-02 | 2027-01-07 | 2026-09-28 | 2026-10-20
NSS-A214783920 | T-REX:OoB Guide (96-151.5): Integrated SAT | 0% | 20 | 2026-12-04 | 2027-01-14 | 2026-03-19 | 2026-04-17
NSS-A214783290 | T-REX: Cd Shielding: nstallation (partner/supplier) | 0% | 20 | 2026-12-07 | 2027-01-15 | 2026-06-22 | 2026-07-17
NSS-A214784460 | T-REX: Beamstop: Arrival Inspection | 0% | 5 | 2026-12-07 | 2026-12-11 | 2026-01-21 | 2026-01-27
NSS-A214787280 | T-REX:OoB Guide (151.5-163.1): FAT-closure of open points and approval | 0% | 12 | 2026-12-07 | 2026-12-22 | 2026-05-12 | 2026-05-29
NSS-A214781500 | T-REX: Polarization Analyser: FAT-closure of open points and approval | 0% | 10 | 2026-12-08 | 2026-12-21 | 2026-01-08 | 2026-01-21
NSS-A214787340 | T-REX: P- Fast Chopper: FAT Report and Documentation | 0% | 12 | 2026-12-08 | 2026-12-23 | 2025-09-23 | 2025-10-27
NSS-A214788120 | T-REX: Polarization Flipper: FAT Report and Documentation | 0% | 10 | 2026-12-08 | 2026-12-21 | 2025-12-05 | 2025-12-18
NSS-A214781010 | T-REX: Translation Table: Shipping | 0% | 5 | 2026-12-10 | 2026-12-16 | 2026-04-27 | 2026-05-04
NSS-A214781230 | T-REX: Translation Table: Qgate document submission phase (CE) | 0% | 20 | 2026-12-10 | 2027-01-20 | 2026-04-27 | 2026-05-27
NSS-A214781240 | T-REX: Translation Table: Preparation of installation binder | 0% | 20 | 2026-12-10 | 2027-01-20 | 2026-04-27 | 2026-05-27
NSS-A214787790 | T-REX: Thermal Polarization: Quality gate review and approval | 0% | 34 | 2026-12-11 | 2027-02-10 | 2026-04-14 | 2026-06-03
NSS-A214787410 | T-REX: M- Fast Chopper: FAT Report and Documentation | 0% | 20 | 2026-12-14 | 2027-01-22 | 2025-12-19 | 2026-01-29
NSS-A2147433480 | T-REX: Det boxes 3:: Manufacturing | 0% | 120 | 2026-12-15 | 2027-06-18
NSS-A214781210 | T-REX: Translation Table: Arrival Inspection | 0% | 5 | 2026-12-17 | 2026-12-23 | 2026-05-05 | 2026-05-11
NSS-A214782480 | T-REX:HS:Final SAT with MCA and PSS | 0% | 15 | 2026-12-17 | 2027-01-20 | 2026-09-21 | 2026-10-16
NSS-A214788610 | T-REX: Beamstop: Quality gate review and approval | 0% | 15 | 2026-12-21 | 2027-01-22 | 2026-02-11 | 2026-03-10
NSS-A214781510 | T-REX: Polarization Analyser: Shipping | 0% | 5 | 2026-12-22 | 2027-01-11 | 2026-01-22 | 2026-01-28
NSS-A214781540 | T-REX: Polarization Analyser: Qgate document submission phase (complicated) | 0% | 30 | 2026-12-22 | 2027-02-15 | 2026-01-22 | 2026-03-04
NSS-A214781550 | T-REX: Polarization Analyser: Preparation of installation binder | 0% | 20 | 2026-12-22 | 2027-02-01 | 2026-01-22 | 2026-02-18
NSS-A214787970 | T-REX: Polarization Flipper: FAT-closure of open points and approval | 0% | 10 | 2026-12-22 | 2027-01-18 | 2025-12-19 | 2026-01-15
NSS-A214788760 | T-REX: Sample Environment: IRR meeting preparation | 0% | 5 | 2026-12-22 | 2027-01-11 | 2026-06-23 | 2026-06-29
NSS-A214784250 | T-REX:OoB Guide (151.5-163.1): Shipping | 0% | 5 | 2026-12-23 | 2027-01-12 | 2026-06-01 | 2026-06-05
NSS-A214784280 | T-REX:OoB Guide (151.5-163.1): Qgate document submission phase | 0% | 20 | 2026-12-23 | 2027-02-02 | 2026-06-01 | 2026-06-29
NSS-A214784290 | T-REX:OoB Guide (151.5-163.1): Preparation of installation binder | 0% | 20 | 2026-12-23 | 2027-02-02 | 2026-06-01 | 2026-06-29
NSS-A214787350 | T-REX: P- Fast Chopper: FAT-closure of open points and approval | 0% | 12 | 2027-01-07 | 2027-01-22 | 2025-10-28 | 2025-11-24
NSS-A214788440 | T-REX: Primary Coll & Slits: Factory Acceptance Test (FAT) | 0% | 5 | 2027-01-07 | 2027-01-13 | 2026-03-09 | 2026-03-13
NSS-A214785940 | T-REX: Com Chop: Local SAT | 0% | 15 | 2027-01-08 | 2027-01-28 | 2026-10-21 | 2026-11-10
NSS-A214784500 | T-REX: Beamstop: IRR documents review by ESS | 0% | 10 | 2027-01-11 | 2027-01-22 | 2026-02-11 | 2026-02-24
NSS-A214788770 | T-REX: Sample Environment: Installation preparation | 0% | 3 | 2027-01-12 | 2027-01-14 | 2026-06-30 | 2026-07-02
NSS-A214784260 | T-REX:OoB Guide (151.5-163.1): Arrival Inspection | 0% | 5 | 2027-01-13 | 2027-01-19 | 2026-06-08 | 2026-06-12
NSS-A214788450 | T-REX: Primary Coll & Slits: FAT Report and Documentation | 0% | 5 | 2027-01-14 | 2027-01-20 | 2026-03-16 | 2026-03-20
NSS-A214781160 | T-REX: Sample Environment: Installation (partner/supplier) | 0% | 17 | 2027-01-15 | 2027-02-08 | 2026-07-03 | 2026-08-24
NSS-A214783300 | T-REX: Cd Shielding: Local SAT | 0% | 5 | 2027-01-18 | 2027-01-22 | 2026-08-17 | 2026-08-21
NSS-A214787980 | T-REX: Polarization Flipper: Shipping | 0% | 5 | 2027-01-19 | 2027-01-25 | 2026-01-16 | 2026-01-22
NSS-A214788010 | T-REX: Polarization Flipper: Qgate document submission phase (complicated) | 0% | 30 | 2027-01-19 | 2027-03-01 | 2026-01-16 | 2026-02-26
NSS-A214788020 | T-REX: Polarization Flipper: Preparation of installation binder | 0% | 20 | 2027-01-19 | 2027-02-15 | 2026-01-16 | 2026-02-12
NSS-A214781250 | T-REX: Translation Table: IRR documents review by ESS | 0% | 10 | 2027-01-21 | 2027-02-03 | 2026-05-28 | 2026-06-10
NSS-A214783600 | T-REX: Primary Coll & Slits: FAT-closure of open points and approval | 0% | 10 | 2027-01-21 | 2027-02-03 | 2026-03-23 | 2026-04-07
NSS-A214787840 | T-REX: Translation Table: Quality gate review and approval | 0% | 20 | 2027-01-21 | 2027-02-17 | 2026-05-28 | 2026-06-25
NSS-A214783310 | T-REX: Cd Shielding: Installation (ESS/common projects) | 0% | 10 | 2027-01-25 | 2027-02-05 | 2026-08-24 | 2026-09-04
NSS-A214784620 | T-REX: P- Fast Chopper: Shipping | 0% | 5 | 2027-01-25 | 2027-01-29 | 2025-11-25 | 2025-12-01
NSS-A214784650 | T-REX: P- Fast Chopper: Qgate document submission phase | 0% | 10 | 2027-01-25 | 2027-02-05 | 2025-11-25 | 2025-12-22
NSS-A214784660 | T-REX: P- Fast Chopper: Preparation of installation binder | 0% | 14 | 2027-01-25 | 2027-02-11 | 2025-11-25 | 2025-12-22
NSS-A214787420 | T-REX: M- Fast Chopper: FAT-closure of open points and approval | 0% | 17 | 2027-01-25 | 2027-02-16 | 2026-01-30 | 2026-02-26
NSS-A214788620 | T-REX: Beamstop: IRR meeting preparation | 0% | 5 | 2027-01-25 | 2027-01-29 | 2026-03-11 | 2026-03-17
NSS-A2147382590 | T-REX: Det boxes 2: FAT Report and Documentation | 0% | 5 | 2027-01-26 | 2027-02-01 | 2026-08-31 | 2026-09-04
NSS-A214786500 | T-REX: Cold Polarization: Qgate document submission phase (CE n/a) | 0% | 20 | 2027-01-28 | 2027-02-24 | 2025-11-03 | 2025-11-28
NSS-A214784630 | T-REX: P- Fast Chopper: Arrival Inspection | 0% | 5 | 2027-02-01 | 2027-02-05 | 2025-12-02 | 2025-12-08
NSS-A214788630 | T-REX: Beamstop: Installation preparation | 0% | 5 | 2027-02-01 | 2027-02-05 | 2026-03-18 | 2026-03-24
NSS-A214781560 | T-REX: Polarization Analyser: IRR documents review by ESS | 0% | 10 | 2027-02-02 | 2027-02-15 | 2026-02-19 | 2026-03-04
NSS-A2147382600 | T-REX: Det boxes 2: FAT-closure of open points and approval | 0% | 5 | 2027-02-02 | 2027-02-08 | 2026-09-07 | 2026-09-11
NSS-A214787290 | T-REX:OoB Guide (151.5-163.1): Quality gate review and approval | 0% | 25 | 2027-02-03 | 2027-03-09 | 2026-06-30 | 2026-08-31
NSS-A214783610 | T-REX: Primary Coll & Slits: Shipping | 0% | 5 | 2027-02-04 | 2027-02-10 | 2026-04-08 | 2026-04-14
NSS-A214783640 | T-REX: Primary Coll & Slits: Qgate document submission phase | 0% | 15 | 2027-02-04 | 2027-02-24 | 2026-04-08 | 2026-05-08
NSS-A214783650 | T-REX: Primary Coll & Slits: Preparation of installation binder | 0% | 15 | 2027-02-04 | 2027-02-24 | 2026-04-08 | 2026-05-06
NSS-A214783320 | T-REX: Cd Shielding: Integrated SAT | 0% | 20 | 2027-02-08 | 2027-03-05 | 2026-09-07 | 2026-10-02
NSS-A214784520 | T-REX: Beamstop: Installation (partner/supplier) | 0% | 5 | 2027-02-08 | 2027-02-12 | 2026-05-29 | 2026-06-23
NSS-A214785960 | T-REX: Com Chop: Integrated SAT | 0% | 20 | 2027-02-08 | 2027-03-05 | 2026-11-11 | 2026-12-08
NSS-A214786600 | T-REX: Control Hutch: Integrated SAT | 0% | 20 | 2027-02-08 | 2027-03-05 | 2026-10-13 | 2026-11-09
NSS-A214787360 | T-REX: P- Fast Chopper: Quality gate review and approval | 0% | 14 | 2027-02-08 | 2027-02-25 | 2025-12-23 | 2026-02-02
NSS-A214781170 | T-REX: Sample Environment: Local SAT | 0% | 5 | 2027-02-09 | 2027-02-15 | 2026-08-25 | 2026-08-31
NSS-A2147354680 | T-REX: Det boxes 2: Shipping to Utgård | 0% | 5 | 2027-02-09 | 2027-02-15 | 2026-09-14 | 2026-09-18
NSS-A214783620 | T-REX: Primary Coll & Slits: Arrival Inspection | 0% | 5 | 2027-02-11 | 2027-02-17 | 2026-04-15 | 2026-04-21
NSS-A214786520 | T-REX: Cold Polarization: Preparation of installation binder | 0% | 20 | 2027-02-11 | 2027-03-10 | 2025-11-03 | 2025-11-28
NSS-A214787800 | T-REX: Thermal Polarization: IRR meeting preparation | 0% | 5 | 2027-02-11 | 2027-02-17 | 2026-06-04 | 2026-06-10
NSS-A214784530 | T-REX: Beamstop: Local SAT | 0% | 5 | 2027-02-15 | 2027-02-19 | 2026-06-24 | 2026-06-30
NSS-A214781190 | T-REX: Sample Environment: Integrated SAT | 0% | 20 | 2027-02-16 | 2027-03-15 | 2026-10-13 | 2026-11-09
NSS-A214787890 | T-REX: Polarization Analyser: Quality gate review and approval | 0% | 30 | 2027-02-16 | 2027-03-31 | 2026-03-05 | 2026-04-17
NSS-A214788030 | T-REX: Polarization Flipper: IRR documents review by ESS | 0% | 10 | 2027-02-16 | 2027-03-01 | 2026-02-13 | 2026-02-26
NSS-A2147354690 | T-REX: Det boxes 2: Arrival Inspection at Utgård | 0% | 5 | 2027-02-16 | 2027-02-22 | 2026-09-21 | 2026-09-25
NSS-A214784970 | T-REX: M- Fast Chopper: Shipping | 0% | 5 | 2027-02-17 | 2027-02-23 | 2026-02-27 | 2026-03-05
NSS-A214785000 | T-REX: M- Fast Chopper: Qgate document submission phase | 0% | 20 | 2027-02-17 | 2027-03-16 | 2026-02-27 | 2026-03-26
NSS-A214785010 | T-REX: M- Fast Chopper: Preparation of installation binder | 0% | 20 | 2027-02-17 | 2027-03-16 | 2026-02-27 | 2026-03-26
NSS-A214787810 | T-REX: Thermal Polarization: Installation preparation | 0% | 5 | 2027-02-18 | 2027-02-24 | 2026-06-11 | 2026-06-17
NSS-A214787820 | T-REX: Translation Table: IRR meeting preparation | 0% | 5 | 2027-02-18 | 2027-02-24 | 2026-06-26 | 2026-07-02
NSS-A214784980 | T-REX: M- Fast Chopper: Arrival Inspection | 0% | 5 | 2027-02-24 | 2027-03-02 | 2026-03-06 | 2026-03-12
NSS-A214783660 | T-REX: Primary Coll & Slits: IRR documents review by ESS | 0% | 10 | 2027-02-25 | 2027-03-10 | 2026-06-16 | 2026-06-30
NSS-A214787830 | T-REX: Translation Table: Installation preparation | 0% | 5 | 2027-02-25 | 2027-03-03 | 2026-07-03 | 2026-07-09
NSS-A214788460 | T-REX: Primary Coll & Slits: Quality gate review and approval | 0% | 15 | 2027-02-25 | 2027-03-17 | 2026-05-11 | 2026-06-30
NSS-A214788780 | T-REX: Cold Polarization: Quality gate review and approval | 0% | 20 | 2027-02-25 | 2027-03-24 | 2026-07-03 | 2026-08-27
NSS-A214784670 | T-REX: P- Fast Chopper: IRR documents review by ESS | 0% | 10 | 2027-02-26 | 2027-03-11 | 2026-02-03 | 2026-02-16
NSS-A214788130 | T-REX: Polarization Flipper: Quality gate review and approval | 0% | 30 | 2027-03-02 | 2027-04-14 | 2026-02-27 | 2026-04-13
NSS-A214786290 | T-REX: Cave: Integrated SAT | 0% | 20 | 2027-03-03 | 2027-04-01 | 2026-10-13 | 2026-11-09
NSS-A214781270 | T-REX: Translation Table: Installation (partner/supplier) | 0% | 20 | 2027-03-04 | 2027-04-02 | 2026-07-10 | 2026-09-03
NSS-A214782950 | T-REX: Sample ex-container: Preparation for Testing / TRR (prep period+ sign off) | 0% | 10 | 2027-03-05 | 2027-03-18 | 2026-09-29 | 2026-10-12
NSS-A214784300 | T-REX:OoB Guide (151.5-163.1): IRR documents review by ESS | 0% | 10 | 2027-03-10 | 2027-03-23 | 2026-09-01 | 2026-09-14
NSS-A214786540 | T-REX: Cold Polarization: IRR documents review by ESS | 0% | 10 | 2027-03-11 | 2027-03-24 | 2026-07-17 | 2026-08-27
NSS-A214784690 | T-REX: P- Fast Chopper: Installation (partner/supplier) | 0% | 20 | 2027-03-12 | 2027-04-12 | 2026-03-23 | 2026-04-21
NSS-A214787430 | T-REX: M- Fast Chopper: Quality gate review and approval | 0% | 20 | 2027-03-17 | 2027-04-15 | 2026-03-27 | 2026-04-27
NSS-A214783670 | T-REX: Primary Coll & Slits: Installation (partner/supplier) | 0% | 20 | 2027-03-18 | 2027-04-16 | 2026-07-15 | 2026-09-08
NSS-A214782960 | T-REX: Sample ex-container: Final SAT with MCA | 0% | 20 | 2027-03-19 | 2027-04-19 | 2026-10-13 | 2026-11-09
NSS-A214784150 | T-REX: Secondary RC: Final SAT with MCA | 0% | 20 | 2027-03-19 | 2027-04-19 | 2026-11-17 | 2026-12-14
NSS-A214787310 | T-REX:OoB Guide (151.5-163.1): Installation preparation | 0% | 5 | 2027-03-24 | 2027-04-01 | 2026-09-15 | 2026-09-21
NSS-A214786460 | T-REX: Cold Polarization: Shipping to ESS | 0% | 5 | 2027-03-25 | 2027-04-02 | 2026-08-28 | 2026-09-03
NSS-A214788790 | T-REX: Cold Polarization: IRR meeting preparation | 0% | 5 | 2027-03-25 | 2027-04-02 | 2026-08-28 | 2026-09-03
NSS-A214787900 | T-REX: Polarization Analyser: IRR meeting preparation | 0% | 5 | 2027-04-01 | 2027-04-07 | 2026-04-20 | 2026-04-24
NSS-A214785020 | T-REX: M- Fast Chopper: IRR documents review by ESS | 0% | 10 | 2027-04-02 | 2027-04-15 | 2026-03-27 | 2026-04-13
NSS-A214781280 | T-REX: Translation Table: Local SAT | 0% | 5 | 2027-04-05 | 2027-04-09 | 2026-09-04 | 2026-09-10
NSS-A214786480 | T-REX: Cold Polarization: Arrival Inspection | 0% | 5 | 2027-04-05 | 2027-04-09 | 2026-09-04 | 2026-09-10
NSS-A214788800 | T-REX: Cold Polarization: Installation preparation | 0% | 5 | 2027-04-05 | 2027-04-09 | 2026-09-04 | 2026-09-10
NSS-A214787910 | T-REX: Polarization Analyser: Installation preparation | 0% | 5 | 2027-04-08 | 2027-04-14 | 2026-04-27 | 2026-05-04
NSS-A214786580 | T-REX: Cold Polarization: Installation (partner/supplier) | 0% | 20 | 2027-04-12 | 2027-05-11 | 2026-09-11 | 2026-10-08
NSS-A214786790 | T-REX: Thermal Polarization: Installation (partner/supplier) | 0% | 18 | 2027-04-12 | 2027-05-05 | 2026-09-11 | 2026-10-06
NSS-A214784700 | T-REX: P- Fast Chopper: Local SAT | 0% | 5 | 2027-04-13 | 2027-04-19 | 2026-04-22 | 2026-04-28
NSS-A214781580 | T-REX: Polarization Analyser: Installation (partner/supplier) | 0% | 20 | 2027-04-15 | 2027-05-14 | 2026-05-05 | 2026-06-03
NSS-A214788140 | T-REX: Polarization Flipper: IRR meeting preparation | 0% | 5 | 2027-04-15 | 2027-04-21 | 2026-08-25 | 2026-08-31
NSS-A214787450 | T-REX: M- Fast Chopper: Installation preparation | 0% | 5 | 2027-04-16 | 2027-04-22 | 2026-05-06 | 2026-05-12
NSS-A214783680 | T-REX: Primary Coll & Slits: Local SAT | 0% | 5 | 2027-04-19 | 2027-04-23 | 2026-09-09 | 2026-09-15
NSS-A214784710 | T-REX: P- Fast Chopper: TRR and integrated SAT | 0% | 10 | 2027-04-20 | 2027-05-03 | 2026-12-08 | 2026-12-21
NSS-A214788150 | T-REX: Polarization Flipper: Installation preparation | 0% | 5 | 2027-04-22 | 2027-04-28 | 2026-09-01 | 2026-09-07
NSS-A214784320 | T-REX:OoB Guide (151.5-163.1): Installation (partner/supplier) | 0% | 10 | 2027-04-23 | 2027-05-10 | 2026-09-22 | 2026-10-05
NSS-A214785040 | T-REX: M- Fast Chopper: Installation (partner/supplier) | 0% | 10 | 2027-04-23 | 2027-05-10 | 2026-09-09 | 2026-09-22
NSS-A214788050 | T-REX: Polarization Flipper: Installation (partner/supplier) | 0% | 20 | 2027-04-29 | 2027-05-28 | 2026-09-08 | 2026-10-05
NSS-A214781300 | T-REX: Translation Table: Final SAT with MCA | 0% | 20 | 2027-04-30 | 2027-05-31 | 2026-11-17 | 2026-12-14
NSS-A214783700 | T-REX: Primary Coll & Slits: Final SAT with MCA | 0% | 20 | 2027-04-30 | 2027-05-31 | 2026-11-17 | 2026-12-14
NSS-A214784720 | T-REX: P- Fast Chopper: Integrated SAT Approval | 0% | 20 | 2027-05-04 | 2027-06-02 | 2026-12-22 | 2027-02-01
NSS-A214786800 | T-REX: Thermal Polarization: Local SAT | 0% | 5 | 2027-05-10 | 2027-05-14 | 2026-10-07 | 2026-10-13
NSS-A214784330 | T-REX:OoB Guide (151.5-163.1): Local SAT | 0% | 5 | 2027-05-11 | 2027-05-17 | 2026-10-06 | 2026-10-12
NSS-A214785060 | T-REX: M- Fast Chopper: TRR and integrated SAT | 0% | 10 | 2027-05-11 | 2027-05-24 | 2026-12-08 | 2026-12-21
NSS-A214786590 | T-REX: Cold Polarization: Local SAT | 0% | 5 | 2027-05-12 | 2027-05-18 | 2026-10-09 | 2026-10-15
NSS-A214781590 | T-REX: Polarization Analyser: Local SAT | 0% | 5 | 2027-05-17 | 2027-05-21 | 2026-06-04 | 2026-06-10
NSS-A214786820 | T-REX: Thermal Polarization: Integrated SAT | 0% | 20 | 2027-05-17 | 2027-06-11 | 2026-10-14 | 2026-11-10
NSS-A214784350 | T-REX:OoB Guide (151.5-163.1): Integrated SAT | 0% | 10 | 2027-05-18 | 2027-05-31 | 2026-10-27 | 2026-11-23
NSS-A214786630 | T-REX: Cold Polarization: Integrated SAT | 0% | 20 | 2027-05-19 | 2027-06-15 | 2026-10-16 | 2026-11-12
NSS-A214781610 | T-REX: Polarization Analyser: Integrated SAT | 0% | 10 | 2027-05-24 | 2027-06-04 | 2026-10-13 | 2026-11-09
NSS-A2147433540 | T-REX: Det boxes 4:: Manufacturing | 0% | 120 | 2027-05-24 | 2027-12-06
NSS-A214782030 | T-REX: Detector Vessel + MG.TREX.1: Integrated SAT | 0% | 10 | 2027-05-25 | 2027-06-07 | 2026-06-12 | 2026-07-10
NSS-A214785070 | T-REX: M- Fast Chopper: Integrated SAT approval | 0% | 20 | 2027-05-25 | 2027-06-21 | 2026-12-22 | 2027-02-01
NSS-A214788060 | T-REX: Polarization Flipper: Integrated SAT | 0% | 5 | 2027-05-31 | 2027-06-04 | 2026-10-06 | 2026-10-12
NSS-A214788080 | T-REX: Polarization Flipper: Integrated SAT Approval | 0% | 10 | 2027-06-07 | 2027-06-18 | 2026-10-27 | 2026-11-23
NSS-A214785790 | T-REX: MG Detector: Integrated SAT Approval | 0% | 10 | 2027-06-08 | 2027-06-21
NSS-A2147433500 | T-REX: Det boxes 3:: FAT Report and Documentation | 0% | 5 | 2027-06-21 | 2027-06-28
NSS-A214786870 | T-REX: Integrated cold commissioning | 0% | 20 | 2027-06-22 | 2027-08-17 | 2027-02-02 | 2027-03-01
NSS-A2147433510 | T-REX: Det boxes 3:: FAT-closure of open points and approval | 0% | 5 | 2027-06-29 | 2027-07-05
NSS-A2147433520 | T-REX: Det boxes 3:: Shipping to Utgård | 0% | 5 | 2027-07-06 | 2027-07-12
NSS-A2147433530 | T-REX: Det boxes 3:: Arrival Inspection at Utgård | 0% | 5 | 2027-07-13 | 2027-08-16
NSS-A214786890 | T-REX: Preparation for TG5 review meeting (Float 2 months) | 0% | 40 | 2027-08-18 | 2027-10-12 | 2027-03-02 | 2027-04-28
NSS-A214786910 | T-REX: TG5/SAR action closeouts and approval | 0% | 40 | 2027-10-13 | 2027-12-07 | 2027-04-29 | 2027-06-23
NSS-A2147433560 | T-REX: Det boxes 4:: FAT Report and Documentation | 0% | 5 | 2027-12-07 | 2027-12-13
NSS-A214786930 | T-REX: i-SRR (approval) | 0% | 10 | 2027-12-08 | 2027-12-21 | 2027-06-24 | 2027-07-08
NSS-A2147433570 | T-REX: Det boxes 4:: FAT-closure of open points and approval | 0% | 5 | 2027-12-14 | 2027-12-20
NSS-A2147433580 | T-REX: Det boxes 4:: Shipping to Utgård | 0% | 5 | 2027-12-21 | 2028-01-11
NSS-A2147433590 | T-REX: Det boxes 4:: Arrival Inspection at Utgård | 0% | 5 | 2028-01-12 | 2028-01-18
NSS-A2147354760 | T-REX: MG Det 2-4: Preparation of installation binder | 0% | 20 | 2028-01-19 | 2028-02-15 | 2027-04-30 | 2027-05-31
NSS-A2147354770 | T-REX: MG Detector: IRR documents review by ESS | 0% | 10 | 2028-02-16 | 2028-02-29 | 2027-06-01 | 2027-06-14
NSS-A2147354790 | T-REX: MG Det 2-4: Installation preparation | 0% | 5 | 2028-03-03 | 2028-03-09 | 2027-06-17 | 2027-06-23
NSS-A2147354800 | T-REX: MG Det 2-4: Installation | 0% | 15 | 2028-03-10 | 2028-03-30 | 2027-06-24 | 2027-07-15
NSS-A2147354810 | T-REX: MG Detector: Local SAT | 0% | 5 | 2028-03-31 | 2028-04-06 | 2027-07-16 | 2027-08-19
NSS-A2147354820 | T-REX: MG Det 2-4: Installation (ESS/common projects) | 0% | 10 | 2028-04-07 | 2028-04-24 | 2027-08-20 | 2027-09-02
NSS-A2147354830 | T-REX: MG Detector: Integrated SAT | 0% | 20 | 2028-04-25 | 2028-05-23 | 2027-09-03 | 2027-09-30
NSS-A214788870 | T-REX: All construction scope for the Instrument complete | 0% | 5 | 2028-05-24 | 2028-06-01 | 2027-10-01 | 2027-10-07

## P6 Sep lockdown
Activity ID | Activity Name | Activity % Complete | Original Duration | Start | Finish | BL1 Start | BL1 Finish | Variance - BL1 Start Date | Budgeted Total Cost | Earned Value Cost | Activity Notes | Remaining Total Cost | user_text8 | ESS 2023 Key Milestones | Variance - BL1 Finish Date | NSS Area Code | Activity Count | Phase | ESS Activity Development Code | BL2 Finish | BL2 Start | ESS Milestone | Total Float | IK to Cash | In Kind | In Kind Country | In Kind Generate Cost | In Kind Planned Partner | In Kind TA status | Schedule Variance | Instrument
NSS-A214781310 | T-REX: Polarization Analyser: Detailed design | 90% | 398 | 2024-01-01 | 2025-11-13 | 2024-01-01 | 13-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | Design |  |  |  |  | 94 | [6 empty] | SEK0 | TREX
NSS-A214783330 | T-REX: Primary Coll & Slits: Detailed design | 85% | 410 | 2024-01-01 | 2025-11-28 | 2024-01-01 | 29-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 | Design |  |  |  |  | 59 | [6 empty] | SEK0 | TREX
13-NSS-P09-25 Neutron Scattering Systems - P09-2025 Lockdown |  |  | 888 | 2024-01-01 | 2027-12-07 | 2024-01-01 | 07-Oct-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 530 | [5 empty] | 412 | [6 empty] | SEK0
13-NSS-P09-25.1 NSS |  |  | 888 | 2024-01-01 | 2027-12-07 | 2024-01-01 | 07-Oct-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 530 | [5 empty] | 412 | [6 empty] | SEK0
13-NSS-P09-25.1.7 NSS Instrument Construction |  |  | 888 | 2024-01-01 | 2027-12-07 | 2024-01-01 | 07-Oct-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 530 | [5 empty] | 412 | [6 empty] | SEK0
NSS-A214787920 | T-REX: Polarization Flipper: Detailed design | 80% | 352 | 2024-03-01 | 2025-11-07 | 2024-03-01 | 06-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | Design |  |  |  |  | 113 | [6 empty] | SEK0 | TREX
NSS-A214785220 | T-REX: Fan Chopper:Early procurement & pre-tests | 80% | 345 | 2024-03-25 | 2025-11-17 | 2024-03-25 | 01-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | PROC |  |  |  |  | 73 | [6 empty] | SEK0 | TREX
NSS-A214786440 | T-REX: Cold Polarization: Storage time | 54% | 563 | 2024-05-03 | 2026-11-17 | 03-May-24 | 2026-11-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214785520 | T-REX: BG Chopper (Disk & Housing): Submission of docs to ESS for CDR/TG3 | 80% | 255 | 2024-09-16 | 2025-11-10 | 2024-09-16 | 29-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | Design |  |  |  |  | 65 | [6 empty] | SEK0 | TREX
NSS-A214781950 | T-REX: Detector Vessel: Pre-installation in Juelich (vacuum ESS) | 80.77% | 260 | 2024-11-18 | 2025-12-09 | 2024-11-18 | 2025-12-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 181 | [6 empty] | SEK0 | TREX
NSS-A214784390 | T-REX: Beamstop: Detailed design | 60% | 212 | 2024-12-06 | 2025-11-20 | 2024-12-06 | 20-Oct-25 | 0 | SEK0 | SEK0 | Sep 25: Jira ticket is regisered for Eng pool. No response yet | SEK0 |  |  | -23 |  | 1 | Design |  |  |  |  | 107 | [6 empty] | SEK0 | TREX
NSS-A214783400 | T-REX:OoB Guide (28-40): Manufacturing | 80% | 130 | 2025-04-01 | 2025-11-05 | 2025-04-01 | 2025-11-05 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214788860 | T-REX: Sample ex-container: Manugacturing (replacement) | 96.94% | 98 | 2025-04-14 | 2025-10-03 | 2025-04-14 | 2025-09-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | [5 empty] | 264 | [6 empty] | SEK0 | TREX
NSS-A214784910 | T-REX: Det prototype box: Storage at FZJ until detector group is ready for the test of Grids | 0% | 100 | 2025-05-05 | 2026-06-10 | 05-May-25 | 23-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -149 |  | 1 | [5 empty] | 183 | [6 empty] | SEK0 | TREX
NSS-A214783990 | T-REX: Secondary RC: Manufacturing | 74.29% | 105 | 2025-05-12 | 2025-11-06 | 12-May-25 | 2025-11-06 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214783340 | T-REX: Cd Shielding: Procurement | 52% | 97 | 2025-05-19 | 2025-11-03 | 19-May-25 | 13-Oct-25 | 0 | SEK0 | SEK0 | Sep 25: on Hold. Failed tender process. Eng is on sick leave | SEK0 |  |  | -15 |  | 1 | PROC |  |  |  |  | 132 | [6 empty] | SEK0 | TREX
NSS-A214786070 | T-REX: Cave: Manufacturing | 50.67% | 150 | 2025-06-16 | 2026-01-26 | 2025-06-16 | 2026-01-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214787710 | T-REX: Thermal Polarization: Submission of docs to ESS for CDR/TG3 | 44% | 50 | 2025-07-01 | 2025-11-07 | 2025-07-01 | 06-Oct-25 | 0 | SEK0 | SEK0 | No progress. Why?!! | SEK0 |  |  | -24 |  | 1 | Design |  |  |  |  | 88 | [6 empty] | SEK0 | TREX
NSS-A214786830 | T-REX: Translation Table: Submission of docs to ESS for CDR/TG3 | 47.06% | 68 | 2025-08-18 | 2025-11-19 | 2025-08-18 | 2025-11-19 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | Design |  |  |  |  | 92 | [6 empty] | SEK0 | TREX
NSS-A2147409820 | T-REX: OoB Guide 1 B: Manufacturing | 45.07% | 71 | 2025-08-18 | 2025-11-24 | 2025-08-18 | 2025-11-21 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 280 | [6 empty] | SEK0 | TREX
NSS-A214781020 | T-REX: Sample Environment: Detailed design | 42.67% | 75 | 2025-08-18 | 2025-11-28 | 2025-08-18 | 2025-11-28 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | Design |  |  |  |  | 129 | [6 empty] | SEK0 | TREX
NSS-A214784750 | T-REX: P- Fast Chopper: Manufacturing of housing and spindles | 0% | 185 | 2025-09-01 | 2026-06-05 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 39 | [6 empty] | SEK0
NSS-A214785100 | T-REX: M- Fast Chopper: Manufacturing of housing and spindles | 0% | 140 | 2025-09-02 | 2026-03-30 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 74 | [6 empty] | SEK0
NSS-A214786350 | T-REX: Control Hutch: Submission of docs to ESS for CDR/TG3 | 80% | 20 | 2025-09-09 | 2025-10-06 | 2025-09-09 | 2025-09-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -6 |  | 1 | Design |  |  |  |  | 167 | [6 empty] | SEK0 | TREX
NSS-A214785090 | T-REX: M- Fast Chopper: Sample program | 0% | 50 | 2025-09-11 | 2025-11-19 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 12 | [6 empty] | SEK0
NSS-A214784760 | T-REX: P- Fast Chopper: Sample program | 0% | 55 | 2025-09-12 | 2025-11-27 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 20 | [6 empty] | SEK0
NSS-A214783780 | T-REX:OoB Guide (96-151.5): Submission of docs to ESS for CDR/TG3 | 0% | 20 | 2025-09-15 | 2025-12-03 | 2025-09-15 | 03-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | Design |  |  |  |  | 47 | [6 empty] | SEK0 | TREX
NSS-A214783090 | T-REX: OoB Guide 1 A: Installation (partner/supplier) | 56.25% | 16 | 2025-09-26 | 2025-10-09 | 2025-09-26 | 09-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | D03 | 1 | INST |  |  |  |  | 359 | [6 empty] | SEK0 | TREX
NSS-A214788300 | T-REX: Sample ex-container: Factory Acceptance Test (FAT) | 0% | 0 | 2025-10-06 |  | 2025-09-17 |  | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 |  |  |  |  | PROC.FAT | 264 | [6 empty] | SEK0 | TREX
NSS-A214788640 | T-REX: Control Hutch: Review of CDR documents by ESS | 0% | 8 | 2025-10-07 | 2025-10-16 | 2025-09-29 | 16-Oct-25 | -6 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214783100 | T-REX: OoB Guide 1 A: Local SAT | 0% | 5 | 2025-10-10 | 2025-10-16 | 10-Oct-25 | 16-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 359 | [6 empty] | SEK0 | TREX
NSS-A214788650 | T-REX: Control Hutch: CDR: Closure of open points and approval | 0% | 28 | 2025-10-17 | 2025-11-25 | 17-Oct-25 | 2025-11-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214786360 | T-REX: Control Hutch: CDR/subTG3 (meeting) | 0% | 0 | 2025-10-17 |  | 17-Oct-25 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | ENG.CDR | 167 | [6 empty] | SEK0 | TREX
NSS-A214782850 | T-REX: Sample ex-container: FAT-closure of open points and approval | 0% | 12 | 2025-10-22 | 2025-11-06 | 03-Oct-25 | 20-Oct-25 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | [5 empty] | 264 | [6 empty] | SEK0 | TREX
NSS-A214783200 | T-REX: Cd Shielding: Manufacturing | 0% | 110 | 2025-11-04 | 2026-04-22 | 14-Oct-25 | 2026-03-30 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 | [5 empty] | 132 | [6 empty] | SEK0 | TREX
NSS-A214787130 | T-REX:OoB Guide (28-40): FAT Report and Documentation | 0% | 12 | 2025-11-06 | 2025-11-21 | 2025-11-06 | 2025-11-21 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214783410 | T-REX:OoB Guide (28-40): Factory Acceptance Test (FAT) | 0% | 0 | 2025-11-06 |  | 2025-11-06 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 219 | [6 empty] | SEK0 | TREX
NSS-A214788530 | T-REX: Secondary RC: FAT Report and Documentation | 0% | 12 | 2025-11-07 | 2025-11-24 | 2025-11-07 | 2025-11-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214782890 | T-REX: Sample ex-container: Qgate document submission phase (partial CE) | 0% | 20 | 2025-11-07 | 2025-12-04 | 21-Oct-25 | 2025-11-17 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | [5 empty] | 264 | [6 empty] | SEK0 | TREX
NSS-A214782900 | T-REX: Sample ex-container: Preparation of installation binder | 0% | 20 | 2025-11-07 | 2025-12-04 | 21-Oct-25 | 2025-11-17 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | [5 empty] | 274 | [6 empty] | SEK0 | TREX
NSS-A214788520 | T-REX: Secondary RC: Factory Acceptance Test (FAT) | 0% | 0 | 2025-11-07 |  | 2025-11-07 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 190 | [6 empty] | SEK0 | TREX
NSS-A214787720 | T-REX: Thermal Polarization: Review of CDR documents by ESS | 0% | 10 | 2025-11-10 | 2025-11-21 | 07-Oct-25 | 20-Oct-25 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214787940 | T-REX: Polarization Flipper: Submission of docs to ESS for CDR/TG3 | 0% | 10 | 2025-11-10 | 2025-11-21 | 07-Oct-25 | 20-Oct-25 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | Design |  |  |  |  | 113 | [6 empty] | SEK0 | TREX
NSS-A214787530 | T-REX: BG Chopper (Disk & Housing): Review of CDR documents by ESS | 0% | 10 | 2025-11-11 | 2025-11-24 | 30-Oct-25 | 2025-11-12 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214781470 | T-REX: Polarization Analyser: Submission of docs to ESS for CDR/TG3 | 0% | 10 | 2025-11-14 | 2025-11-27 | 14-Oct-25 | 27-Oct-25 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | Design |  |  |  |  | 94 | [6 empty] | SEK0 | TREX
NSS-A214785230 | T-REX: Fan Chopper:Submission of docs to ESS for CDR/TG3 | 0% | 10 | 2025-11-18 | 2025-12-01 | 02-Oct-25 | 15-Oct-25 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | Design |  |  |  |  | 73 | [6 empty] | SEK0 | TREX
NSS-A214787740 | T-REX: Translation Table: Review of CDR documents by ESS | 0% | 17 | 2025-11-20 | 2025-12-12 | 2025-11-20 | 2025-12-12 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214785170 | T-REX: M- Fast Chopper: Manufacturing of New Disks | 0% | 145 | 2025-11-20 | 2026-07-02 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 12 | [6 empty] | SEK0
NSS-A214784410 | T-REX: Beamstop: Submission of docs to ESS for CDR/TG3 | 0% | 14 | 2025-11-21 | 2025-12-10 | 21-Oct-25 | 2025-11-07 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | Design |  |  |  |  | 107 | [6 empty] | SEK0 | TREX
NSS-A214786680 | T-REX: Thermal Polarization: CDR: Closure of open points and approval | 0% | 10 | 2025-11-24 | 2025-12-05 | 21-Oct-25 | 2025-11-03 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214787140 | T-REX:OoB Guide (28-40): FAT-closure of open points and approval | 0% | 12 | 2025-11-24 | 2025-12-09 | 2025-11-24 | 2025-12-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214788090 | T-REX: Polarization Flipper: Review of CDR documents by ESS | 0% | 15 | 2025-11-24 | 2025-12-12 | 21-Oct-25 | 2025-11-10 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 113 | [6 empty] | SEK0 | TREX
NSS-A214786690 | T-REX: Thermal Polarization: CDR/subTG3 (meeting) | 0% | 0 | 2025-11-24 |  | 21-Oct-25 |  | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 |  |  |  |  | ENG.CDR | 88 | [6 empty] | SEK0 | TREX
NSS-A214787540 | T-REX: BG Chopper (Disk & Housing):CDR: Closure of open points and approval | 0% | 10 | 2025-11-25 | 2025-12-08 | 2025-11-13 | 2025-11-26 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214784000 | T-REX: Secondary RC: FAT-closure of open points and approval | 0% | 12 | 2025-11-25 | 2025-12-10 | 2025-11-25 | 2025-12-10 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A2147409840 | T-REX: OoB Guide 1 B: FAT Report and Documentation | 0% | 12 | 2025-11-25 | 2025-12-10 | 2025-11-24 | 2025-12-09 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 280 | [6 empty] | SEK0 | TREX
NSS-A2147409900 | T-REX: OoB Guide 1 B: Qgate document submission phase | 0% | 15 | 2025-11-25 | 2025-12-15 | 2025-11-24 | 2025-12-12 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 287 | [6 empty] | SEK0 | TREX
NSS-A2147409850 | T-REX: OoB Guide 1 B: Preparation of installation binder | 0% | 15 | 2025-11-25 | 2025-12-15 | 2025-11-24 | 2025-12-12 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 292 | [6 empty] | SEK0 | TREX
NSS-A214785530 | T-REX: BG Chopper (Disk & Housing): CDR/subTG3 (meeting) | 0% | 0 | 2025-11-25 |  | 2025-11-13 |  | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 |  |  |  |  | ENG.CDR | 65 | [6 empty] | SEK0 | TREX
NSS-A2147409830 | T-REX: OoB Guide 1 B: FAT | 0% | 0 | 2025-11-25 |  | 2025-11-24 |  | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 |  |  |  |  | PROC.FAT | 280 | [6 empty] | SEK0 | TREX
NSS-A214786370 | T-REX: Control Hutch: Manufacturing | 0% | 80 | 2025-11-26 | 2026-03-31 | 2025-11-26 | 2026-03-31 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214787850 | T-REX: Polarization Analyser: Review of CDR documents by ESS | 0% | 15 | 2025-11-28 | 2025-12-18 | 28-Oct-25 | 2025-11-17 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214784780 | T-REX: P- Fast Chopper: Manufacturing of New Disks | 0% | 140 | 2025-11-28 | 2026-07-03 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 20 | [6 empty] | SEK0
NSS-A214783560 | T-REX: Primary Coll & Slits: Submission of docs to ESS for CDR/TG3 | 0% | 8 | 2025-12-01 | 2025-12-10 | 30-Oct-25 | 2025-11-10 | -22 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 | Design |  |  |  |  | 59 | [6 empty] | SEK0 | TREX
NSS-A214781050 | T-REX: Sample Environment: Submission of docs to ESS for CDR/TG3 | 0% | 14 | 2025-12-01 | 2025-12-18 | 2025-12-01 | 2025-12-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | Design |  |  |  |  | 129 | [6 empty] | SEK0 | TREX
NSS-A214787460 | T-REX: Fan Chopper:Review of CDR documents by ESS | 0% | 10 | 2025-12-02 | 2025-12-15 | 16-Oct-25 | 29-Oct-25 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214787180 | T-REX:OoB Guide (96-151.5): Review of CDR documents by ESS | 0% | 5 | 2025-12-04 | 2025-12-10 | 06-Oct-25 | 10-Oct-25 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 47 | [6 empty] | SEK0 | TREX
NSS-A214786700 | T-REX: Thermal Polarization: Manufacturing | 0% | 120 | 2025-12-08 | 2026-06-12 | 2025-11-04 | 07-May-26 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214785550 | T-REX: BG Chopper (Disk & Housing): Manufacturing | 0% | 60 | 2025-12-09 | 2026-03-16 | 2025-11-27 | 2026-03-04 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214783420 | T-REX:OoB Guide (28-40): Shipping | 0% | 5 | 2025-12-10 | 2025-12-16 | 2025-12-10 | 2025-12-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 259 | [6 empty] | SEK0 | TREX
NSS-A214783450 | T-REX:OoB Guide (28-40): Qgate document submission phase (CE n/a) | 0% | 20 | 2025-12-10 | 2026-01-20 | 2025-12-10 | 2026-01-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214783460 | T-REX:OoB Guide (28-40): Preparation of installation binder | 0% | 20 | 2025-12-10 | 2026-01-20 | 2025-12-10 | 2026-01-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214784010 | T-REX: Secondary RC: Shipping to FZJ | 0% | 5 | 2025-12-11 | 2025-12-17 | 2025-12-11 | 2025-12-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214787190 | T-REX:OoB Guide (96-151.5): CDR: Closure of open points and approval | 0% | 5 | 2025-12-11 | 2025-12-17 | 13-Oct-25 | 17-Oct-25 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 47 | [6 empty] | SEK0 | TREX
NSS-A214788420 | T-REX: Primary Coll & Slits: Review of CDR documents by ESS | 0% | 10 | 2025-12-11 | 2026-01-07 | 2025-11-11 | 2025-11-24 | -22 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 | [5 empty] | 59 | [6 empty] | SEK0 | TREX
NSS-A2147409860 | T-REX: OoB Guide 1 B: FAT-closure of open points and approval | 0% | 10 | 2025-12-11 | 2026-01-07 | 2025-12-10 | 2025-12-23 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 280 | [6 empty] | SEK0 | TREX
NSS-A214788570 | T-REX: Beamstop: Review of CDR documents by ESS | 0% | 14 | 2025-12-11 | 2026-01-13 | 2025-11-10 | 2025-11-27 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214783790 | T-REX:OoB Guide (96-151.5): CDR/subTG3 (meeting) | 0% | 0 | 2025-12-11 |  | 13-Oct-25 |  | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 |  |  |  |  | ENG.CDR | 47 | [6 empty] | SEK0 | TREX
NSS-A214788100 | T-REX: Polarization Flipper: CDR: Closure of open points and approval | 0% | 10 | 2025-12-15 | 2026-01-09 | 2025-11-11 | 2025-11-24 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 113 | [6 empty] | SEK0 | TREX
NSS-A214787730 | T-REX: Translation Table: CDR: Closure of open points and approval | 0% | 12 | 2025-12-15 | 2026-01-13 | 2025-12-15 | 2026-01-13 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214786840 | T-REX: Translation Table: CDR/subTG3 (meeting) | 0% | 0 | 2025-12-15 |  | 2025-12-15 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | ENG.CDR | 92 | [6 empty] | SEK0 | TREX
NSS-A214787950 | T-REX: Polarization Flipper: CDR/subTG3 (meeting) | 0% | 0 | 2025-12-15 |  | 2025-11-11 |  | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 |  |  |  |  | ENG.CDR | 113 | [6 empty] | SEK0 | TREX
NSS-A2147409870 | T-REX: OoB Guide 1 B: IRR documents review by ESS | 0% | 10 | 2025-12-16 | 2026-01-12 | 2025-12-15 | 2026-01-09 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 292 | [6 empty] | SEK0 | TREX
NSS-A214787470 | T-REX: Fan Chopper:CDR: Closure of open points and approval | 0% | 15 | 2025-12-16 | 2026-01-19 | 30-Oct-25 | 2025-11-19 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A2147409910 | T-REX: OoB Guide 1 B: Quality gate review and approval | 0% | 15 | 2025-12-16 | 2026-01-19 | 2025-12-15 | 2026-01-16 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 |  |  |  |  | PROC.QGATE | 287 | [6 empty] | SEK0 | TREX
NSS-A214785240 | T-REX: Fan Chopper:CDR/subTG3 (meeting) | 0% | 0 | 2025-12-16 |  | 30-Oct-25 |  | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | ENG.CDR | 73 | [6 empty] | SEK0 | TREX
NSS-A214783430 | T-REX:OoB Guide (28-40): Arrival Inspection | 0% | 5 | 2025-12-17 | 2025-12-23 | 2025-12-17 | 2025-12-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | D03 | 1 | PROC.DELIV |  |  |  |  | 259 | [6 empty] | SEK0 | TREX
NSS-A214784020 | T-REX: Secondary RC: Arrival Inspection (FZJ) | 0% | 5 | 2025-12-18 | 2026-01-07 | 2025-12-18 | 2026-01-07 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214783800 | T-REX:OoB Guide (96-151.5): Manufacturing Part 1 | 0% | 52 | 2025-12-18 | 2026-03-13 | 20-Oct-25 | 2026-01-13 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 149 | [6 empty] | SEK0 | TREX
NSS-A214788710 | T-REX: Sample Environment: Review of CDR documents by ESS | 0% | 8 | 2025-12-19 | 2026-01-13 | 2025-12-19 | 2026-01-13 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214787860 | T-REX: Polarization Analyser: CDR: Closure of open points and approval | 0% | 10 | 2025-12-19 | 2026-01-15 | 2025-11-18 | 2025-12-01 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214781480 | T-REX: Polarization Analyser: CDR/subTG3 (meeting) | 0% | 0 | 2025-12-19 |  | 2025-11-18 |  | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | ENG.CDR | 94 | [6 empty] | SEK0 | TREX
NSS-A214783440 | T-REX:OoB Guide (28-40): Storage time | 0% | 40 | 2026-01-07 | 2026-03-03 | 2026-01-07 | 2026-03-03 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214788430 | T-REX: Primary Coll & Slits: CDR: Closure of open points and approval | 0% | 10 | 2026-01-08 | 2026-01-21 | 2025-11-25 | 2025-12-08 | -22 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 | [5 empty] | 59 | [6 empty] | SEK0 | TREX
NSS-A2147409880 | T-REX: OoB Guide 1 B: Shipping | 0% | 10 | 2026-01-08 | 2026-01-21 | 2026-01-07 | 2026-01-20 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | [5 empty] | 280 | [6 empty] | SEK0 | TREX
NSS-A214784030 | T-REX: Secondary RC: Integration with the drive system & testing | 0% | 30 | 2026-01-08 | 2026-02-18 | 2026-01-08 | 2026-02-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214783570 | T-REX: Primary Coll & Slits: CDR/subTG3 (meeting) | 0% | 0 | 2026-01-08 |  | 2025-11-25 |  | -22 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 |  |  |  |  | ENG.CDR | 59 | [6 empty] | SEK0 | TREX
NSS-A214787960 | T-REX: Polarization Flipper: Manufacturing | 0% | 100 | 2026-01-12 | 2026-06-05 | 2025-11-25 | 2026-04-29 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 113 | [6 empty] | SEK0 | TREX
NSS-A214788720 | T-REX: Sample Environment: CDR: Closure of open points and approval | 0% | 15 | 2026-01-14 | 2026-02-03 | 2026-01-14 | 2026-02-03 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214788580 | T-REX: Beamstop: CDR: Closure of open points and approval | 0% | 28 | 2026-01-14 | 2026-02-20 | 2025-11-28 | 2026-01-20 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214786850 | T-REX: Translation Table: Manufacturing | 0% | 100 | 2026-01-14 | 2026-06-09 | 2026-01-14 | 2026-06-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214781060 | T-REX: Sample Environment: CDR/subTG3 (meeting) | 0% | 0 | 2026-01-14 |  | 2026-01-14 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | ENG.CDR | 129 | [6 empty] | SEK0 | TREX
NSS-A214784420 | T-REX: Beamstop: CDR/subTG3 (meeting) | 0% | 0 | 2026-01-14 |  | 2025-11-28 |  | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | ENG.CDR | 107 | [6 empty] | SEK0 | TREX
NSS-A214781490 | T-REX: Polarization Analyser: Manufacturing | 0% | 105 | 2026-01-16 | 2026-06-18 | 2025-12-02 | 18-May-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214785250 | T-REX: Fan Chopper: Procurement, Manufacturing, Assembly | 0% | 100 | 2026-01-20 | 2026-06-15 | 2025-11-20 | 2026-04-24 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | PROC |  |  |  |  | 73 | [6 empty] | SEK0 | TREX
NSS-A2147409930 | T-REX: OoB Guide 1 B: IRR/subTG4 (meeting) | 0% | 0 | 2026-01-20 |  | 2026-01-19 |  | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 |  |  |  |  | INST.IRR | 287 | [6 empty] | SEK0 | TREX
NSS-A214783470 | T-REX:OoB Guide (28-40): IRR documents review by ESS | 0% | 10 | 2026-01-21 | 2026-02-03 | 2026-01-21 | 2026-02-03 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214787150 | T-REX:OoB Guide (28-40): Quality gate review and approval | 0% | 20 | 2026-01-21 | 2026-02-17 | 2026-01-21 | 2026-02-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 219 | [6 empty] | SEK0 | TREX
NSS-A2147409890 | T-REX: OoB Guide 1 B: Arrival Inspection | 0% | 5 | 2026-01-22 | 2026-01-28 | 2026-01-21 | 2026-01-27 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | PROC.DELIV |  |  |  |  | 280 | [6 empty] | SEK0 | TREX
NSS-A214783580 | T-REX: Primary Coll & Slits: Tendering process | 0% | 10 | 2026-01-22 | 2026-02-04 | 2025-12-09 | 2025-12-22 | -22 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 | PROC |  |  |  |  | 59 | [6 empty] | SEK0 | TREX
NSS-A214787670 | T-REX: Cave: FAT Report and Documentation | 0% | 12 | 2026-01-27 | 2026-02-11 | 2026-01-27 | 2026-02-11 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214787660 | T-REX: Cave: Factory Acceptance Test (FAT) | 0% | 0 | 2026-01-27 |  | 2026-01-27 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 62 | [6 empty] | SEK0 | TREX
NSS-A2147409960 | T-REX: OoB Guide 1 B: Installation (partner/supplier) | 0% | 10 | 2026-01-29 | 2026-02-11 | 2026-01-28 | 2026-02-10 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 | D03 | 1 | INST |  |  |  |  | 280 | [6 empty] | SEK0 | TREX
NSS-A214787160 | T-REX:OoB Guide (28-40): Preparation for IRR meeting | 0% | 10 | 2026-02-04 | 2026-02-17 | 2026-02-04 | 2026-02-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214781070 | T-REX: Sample Environment: Manufacturing | 0% | 78 | 2026-02-04 | 2026-05-29 | 2026-02-04 | 29-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214783590 | T-REX: Primary Coll & Slits: Manufacturing | 0% | 130 | 2026-02-05 | 2026-08-13 | 2025-12-23 | 2026-07-14 | -22 | SEK0 | SEK0 |  | SEK0 |  |  | -22 |  | 1 | [5 empty] | 59 | [6 empty] | SEK0 | TREX
NSS-A214784070 | T-REX:OoB Guide (96-151.5): Manufacturing Part 2 | 0% | 80 | 2026-02-06 | 2026-06-04 | 2025-11-25 | 2026-03-30 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 149 | [6 empty] | SEK0 | TREX
NSS-A2147409970 | T-REX: OoB Guide 1 B: Local SAT | 0% | 5 | 2026-02-12 | 2026-02-18 | 2026-02-11 | 2026-02-17 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 |  | 1 | COMM |  |  |  |  | 280 | [6 empty] | SEK0 | TREX
NSS-A214786080 | T-REX: Cave: FAT-closure of open points and approval | 0% | 12 | 2026-02-12 | 2026-02-27 | 2026-02-12 | 2026-02-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214787170 | T-REX:OoB Guide (28-40): Installation preparation | 0% | 10 | 2026-02-18 | 2026-03-03 | 2026-02-18 | 2026-03-03 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 219 | [6 empty] | SEK0 | TREX
NSS-A214783480 | T-REX:OoB Guide (28-40): IRR/subTG4 (meeting) | 0% | 0 | 2026-02-18 |  | 2026-02-18 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 219 | [6 empty] | SEK0 | TREX
NSS-A214783110 | T-REX: OoB Guide 1 A: Installation (ESS/common projects) | 0% | 10 | 2026-02-19 | 2026-03-04 | 2026-02-18 | 2026-03-03 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 | D03 | 1 | INST |  |  |  |  | 280 | [6 empty] | SEK0 | TREX
NSS-A214788840 | T-REX: Secondary RC: FAT report and documentation (Drive and Blades) | 0% | 10 | 2026-02-19 | 2026-03-04 | 2026-02-19 | 2026-03-04 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214784040 | T-REX: Secondary RC: Integrated FAT (Drive and Blades) | 0% | 0 | 2026-02-19 |  | 2026-02-19 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214784430 | T-REX: Beamstop: Manufacturing | 0% | 80 | 2026-02-23 | 2026-06-22 | 2026-01-21 | 19-May-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214786090 | T-REX: Cave: Shipping | 0% | 10 | 2026-03-02 | 2026-03-13 | 2026-03-02 | 2026-03-13 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 68 | [6 empty] | SEK0 | TREX
NSS-A214786130 | T-REX: Cave: Preparation of installation binder | 0% | 10 | 2026-03-02 | 2026-03-13 | 2026-03-02 | 2026-03-13 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 63 | [6 empty] | SEK0 | TREX
NSS-A214786120 | T-REX: Cave: Qgate document submission phase (CE) | 0% | 14 | 2026-03-02 | 2026-03-19 | 2026-03-02 | 2026-03-19 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214782740 | T-REX:BS:Installation E01 | 0% | 20 | 2026-03-03 | 2026-03-31 | 2026-03-03 | 2026-03-31 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | INST |  |  |  |  | 782 | [6 empty] | SEK0 | TREX
NSS-A214783490 | T-REX:OoB Guide (28-40): Installation (partner/supplier) | 0% | 22 | 2026-03-04 | 2026-04-02 | 2026-03-04 | 2026-04-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | D03 | 1 | INST |  |  |  |  | 219 | [6 empty] | SEK0 | TREX
NSS-A214788850 | T-REX: Secondary RC: FAT- Closure of open point and approval (Drive and Blades) | 0% | 10 | 2026-03-05 | 2026-03-18 | 2026-03-05 | 2026-03-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214783120 | T-REX: OoB Guide 1 A: Integrated SAT | 0% | 20 | 2026-03-05 | 2026-04-01 | 2026-03-04 | 2026-03-31 | -1 | SEK0 | SEK0 |  | SEK0 |  |  | -1 | D03 | 1 | COMM |  |  |  |  | 280 | [6 empty] | SEK0 | TREX
NSS-A214787680 | T-REX: Cave: Quality gate review and approval (CE) | 0% | 14 | 2026-03-11 | 2026-03-30 | 2026-03-11 | 2026-03-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 62 | [6 empty] | SEK0 | TREX
NSS-A214784200 | T-REX:OoB Guide (151.5-163.1): IDR | 0% | 5 | 2026-03-12 | 2026-03-18 | 2026-01-12 | 2026-01-16 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214786100 | T-REX: Cave: Arrival Inspection | 0% | 5 | 2026-03-16 | 2026-03-20 | 2026-03-16 | 2026-03-20 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 68 | [6 empty] | SEK0 | TREX
NSS-A214787200 | T-REX:OoB Guide (96-151.5): FAT Report and Documentation Part 1 | 0% | 6 | 2026-03-16 | 2026-03-23 | 2026-01-14 | 2026-01-21 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 186 | [6 empty] | SEK0 | TREX
NSS-A214786140 | T-REX: Cave: IRR documents review by ESS | 0% | 10 | 2026-03-16 | 2026-03-27 | 2026-03-16 | 2026-03-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 63 | [6 empty] | SEK0 | TREX
NSS-A214783810 | T-REX:OoB Guide (96-151.5): Factory Acceptance Test (FAT) Part 1 | 0% | 0 | 2026-03-16 |  | 2026-01-14 |  | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 |  |  |  |  | PROC.FAT | 186 | [6 empty] | SEK0 | TREX
NSS-A214787550 | T-REX: BG Chopper (Disk & Housing): FAT Report and Documentation | 0% | 12 | 2026-03-17 | 2026-04-01 | 2026-03-05 | 2026-03-20 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214785560 | T-REX: BG Chopper (Disk & Housing): Factory Acceptance Test (FAT) | 0% | 0 | 2026-03-17 |  | 2026-03-05 |  | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 |  |  |  |  | PROC.FAT | 65 | [6 empty] | SEK0 | TREX
NSS-A214784090 | T-REX: Secondary RC: Preparation of installation binder | 0% | 14 | 2026-03-19 | 2026-04-09 | 2026-03-19 | 2026-04-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 206 | [6 empty] | SEK0 | TREX
NSS-A214784050 | T-REX: Secondary RC: Shipping to ESS | 0% | 19 | 2026-03-19 | 2026-04-17 | 2026-03-19 | 2026-04-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 211 | [6 empty] | SEK0 | TREX
NSS-A214784080 | T-REX: Secondary RC: Qgate document submission phase | 0% | 20 | 2026-03-19 | 2026-04-17 | 2026-03-19 | 2026-04-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214787210 | T-REX:OoB Guide (96-151.5): FAT-closure of open points and approval Part 1 | 0% | 6 | 2026-03-24 | 2026-03-31 | 2026-01-22 | 2026-01-29 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 166 | [6 empty] | SEK0 | TREX
NSS-A214786160 | T-REX: Cave: Installation of Elevated floor / slab | 0% | 20 | 2026-03-31 | 2026-04-29 | 2026-03-31 | 2026-04-29 | 0 | SEK0 | SEK0 | Will the installation starts at early January? | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214786150 | T-REX: Cave: IRR/subTG4 (meeting) | 0% | 0 | 2026-03-31 |  | 2026-03-31 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 62 | [6 empty] | SEK0 | TREX
NSS-A214788670 | T-REX: Control Hutch: FAT Report and Documentation | 0% | 10 | 2026-04-01 | 2026-04-16 | 2026-04-01 | 2026-04-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214783850 | T-REX:OoB Guide (96-151.5): Qgate document submission phase | 0% | 20 | 2026-04-01 | 2026-04-30 | 2026-01-30 | 2026-02-26 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 166 | [6 empty] | SEK0 | TREX
NSS-A214783860 | T-REX:OoB Guide (96-151.5): Preparation of installation binder | 0% | 20 | 2026-04-01 | 2026-04-30 | 2026-01-30 | 2026-02-26 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 186 | [6 empty] | SEK0 | TREX
NSS-A214788660 | T-REX: Control Hutch: Factory Acceptance Test (FAT) | 0% | 0 | 2026-04-01 |  | 2026-04-01 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 167 | [6 empty] | SEK0 | TREX
NSS-A214787560 | T-REX: BG Chopper (Disk & Housing): FAT-closure of open points and approval | 0% | 14 | 2026-04-02 | 2026-04-23 | 2026-03-23 | 2026-04-13 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214783500 | T-REX:OoB Guide (28-40): Local SAT | 0% | 5 | 2026-04-07 | 2026-04-13 | 2026-04-07 | 2026-04-13 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 219 | [6 empty] | SEK0 | TREX
NSS-A2147354840 | T-REX: Det boxes 2-4: Manufacturing | 0% | 185 | 2026-04-09 | 2027-02-09 | 2026-04-09 | 2027-02-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 90 | [6 empty] | SEK0 | TREX
NSS-A214784210 | T-REX:OoB Guide (151.5-163.1): Submission of docs to ESS for CDR/TG3 | 0% | 20 | 2026-04-13 | 2026-05-11 | 2026-02-09 | 2026-03-06 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | Design |  |  |  |  | 47 | [6 empty] | SEK0 | TREX
NSS-A214783510 | T-REX:OoB Guide (28-40): Installation (ESS/common projects) | 0% | 10 | 2026-04-14 | 2026-04-27 | 2026-04-14 | 2026-04-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | D03 | 1 | INST |  |  |  |  | 244 | [6 empty] | SEK0 | TREX
NSS-A214784060 | T-REX: Secondary RC: Arrival Inspection (ESS) | 0% | 5 | 2026-04-17 | 2026-04-24 | 2026-04-17 | 2026-04-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 211 | [6 empty] | SEK0 | TREX
NSS-A214786380 | T-REX: Control Hutch: FAT-closure of open points and approval | 0% | 10 | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-04-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214788540 | T-REX: Secondary RC: Quality gate review and approval | 0% | 20 | 2026-04-20 | 2026-05-20 | 2026-04-20 | 20-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 190 | [6 empty] | SEK0 | TREX
NSS-A214788370 | T-REX: Cd Shielding: Factory Acceptance Test (FAT) | 0% | 5 | 2026-04-23 | 2026-04-29 | 2026-03-31 | 2026-04-08 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 |  |  |  |  | PROC.FAT | 132 | [6 empty] | SEK0 | TREX
NSS-A214785570 | T-REX: BG Chopper (Disk & Housing): Shipping | 0% | 10 | 2026-04-24 | 2026-05-08 | 2026-04-14 | 2026-04-27 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214783520 | T-REX:OoB Guide (28-40): Integrated SAT | 0% | 20 | 2026-04-28 | 2026-05-28 | 2026-04-28 | 28-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | D03 | 1 | COMM |  |  |  |  | 244 | [6 empty] | SEK0 | TREX
NSS-A214788380 | T-REX: Cd Shielding: FAT Report and Documentation | 0% | 5 | 2026-04-30 | 2026-05-07 | 2026-04-09 | 2026-04-15 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 | [5 empty] | 132 | [6 empty] | SEK0 | TREX
NSS-A214786210 | T-REX: Cave: Installation of Wall + celling | 0% | 15 | 2026-04-30 | 2026-05-25 | 2026-04-30 | 25-May-26 | 0 | SEK0 | SEK0 |  | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214781970 | T-REX: Detector Vessel: Qgate document submission phase | 0% | 20 | 2026-04-30 | 2026-06-01 | 2026-04-30 | 2026-06-01 | 0 | SEK0 | SEK0 | Check with Lockdown | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214786390 | T-REX: Control Hutch: Shipping | 0% | 5 | 2026-05-04 | 2026-05-08 | 04-May-26 | 08-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 208 | [6 empty] | SEK0 | TREX
NSS-A214783870 | T-REX:OoB Guide (96-151.5): IRR documents review by ESS | 0% | 10 | 2026-05-04 | 2026-05-19 | 2026-02-27 | 2026-03-12 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 186 | [6 empty] | SEK0 | TREX
NSS-A214786450 | T-REX: Control Hutch: Qgate document submission phase | 0% | 20 | 2026-05-04 | 2026-06-02 | 04-May-26 | 2026-06-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214786470 | T-REX: Control Hutch: Preparation of installation binder | 0% | 20 | 2026-05-04 | 2026-06-02 | 04-May-26 | 2026-06-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 177 | [6 empty] | SEK0 | TREX
NSS-A214787240 | T-REX:OoB Guide (96-151.5): Quality gate review and approval | 0% | 30 | 2026-05-04 | 2026-06-16 | 2026-02-27 | 2026-04-13 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 |  |  |  |  | PROC.QGATE | 166 | [6 empty] | SEK0 | TREX
NSS-A214784100 | T-REX: Secondary RC: IRR documents review by ESS | 0% | 10 | 2026-05-05 | 2026-05-20 | 05-May-26 | 20-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214783210 | T-REX: Cd Shielding: FAT-closure of open points and approval | 0% | 20 | 2026-05-08 | 2026-06-08 | 2026-04-16 | 18-May-26 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 | [5 empty] | 132 | [6 empty] | SEK0 | TREX
NSS-A214785580 | T-REX: BG Chopper (Disk & Housing): Arrival Inspection | 0% | 5 | 2026-05-11 | 2026-05-19 | 2026-04-28 | 05-May-26 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | D03 | 1 | PROC.DELIV |  |  |  |  | 65 | [6 empty] | SEK0 | TREX
NSS-A214786410 | T-REX: Control Hutch: Arrival Inspection | 0% | 5 | 2026-05-11 | 2026-05-19 | 11-May-26 | 19-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 208 | [6 empty] | SEK0 | TREX
NSS-A214787250 | T-REX:OoB Guide (151.5-163.1): Review of CDR documents by ESS | 0% | 20 | 2026-05-12 | 2026-06-10 | 2026-03-09 | 2026-04-07 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 47 | [6 empty] | SEK0 | TREX
NSS-A214782570 | T-REX: RC Drive: Shipping | 0% | 5 | 2026-05-19 | 2026-05-25 | 2025-12-10 | 2025-12-16 | -99 | SEK0 | SEK0 |  | SEK0 |  |  | -99 |  | 1 | [5 empty] | 172 | [6 empty] | SEK0 | TREX
NSS-A214781980 | T-REX: Detector Vessel: Preparation of installation binder | 0% | 20 | 2026-05-19 | 2026-06-15 | 19-May-26 | 2026-06-15 | 0 | SEK0 | SEK0 | Check with Lockdown | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214781960 | T-REX: Detector Vessel: Shipping | 0% | 40 | 2026-05-19 | 2026-07-14 | 2025-12-10 | 2026-02-17 | -99 | SEK0 | SEK0 | Should be May 2026 | SEK0 |  |  | -99 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214785820 | T-REX: Com Chop: Coating of disks | 0% | 20 | 2026-05-20 | 2026-06-16 | 06-May-26 | 2026-06-04 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214786430 | T-REX: Control Hutch: Storage time | 0% | 41 | 2026-05-20 | 2026-07-16 | 20-May-26 | 2026-07-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214788550 | T-REX: Secondary RC: IRR meeting preparation | 0% | 5 | 2026-05-21 | 2026-05-27 | 21-May-26 | 27-May-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 190 | [6 empty] | SEK0 | TREX
NSS-A214782580 | T-REX: RC Drive: Arrival Inspection | 0% | 5 | 2026-05-26 | 2026-06-01 | 2025-12-17 | 2025-12-23 | -99 | SEK0 | SEK0 |  | SEK0 |  |  | -99 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 172 | [6 empty] | SEK0 | TREX
NSS-A214786220 | T-REX: Cave: Installation of Crane | 0% | 18 | 2026-05-26 | 2026-06-18 | 26-May-26 | 2026-06-18 | 0 | SEK0 | SEK0 |  | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214782280 | T-REX: False floor and Det supp: Qgate document submission phase (partial CE) | 0% | 20 | 2026-05-26 | 2026-06-23 | 26-May-26 | 2026-06-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214784110 | T-REX: Secondary RC: IRR/subTG4 (meeting) | 0% | 0 | 2026-05-28 |  | 28-May-26 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 190 | [6 empty] | SEK0 | TREX
NSS-A214788740 | T-REX: Sample Environment: FAT Report and Documentation | 0% | 12 | 2026-06-01 | 2026-06-16 | 2026-06-01 | 2026-06-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214788730 | T-REX: Sample Environment: Factory Acceptance Test (FAT) | 0% | 0 | 2026-06-01 |  | 2026-06-01 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 129 | [6 empty] | SEK0 | TREX
NSS-A214788160 | T-REX: Detector Vessel: Quality gate review and approval | 0% | 20 | 2026-06-02 | 2026-06-30 | 2026-06-02 | 2026-06-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 62 | [6 empty] | SEK0 | TREX
NSS-A214782590 | T-REX: RC Drive: Storage time | 0% | 55 | 2026-06-02 | 2026-09-15 | 2026-01-07 | 2026-09-15 | -99 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214786490 | T-REX: Control Hutch: IRR documents review by ESS | 0% | 10 | 2026-06-03 | 2026-06-16 | 2026-06-03 | 2026-06-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 177 | [6 empty] | SEK0 | TREX
NSS-A214788680 | T-REX: Control Hutch: Quality gate review and approval | 0% | 20 | 2026-06-03 | 2026-07-01 | 2026-06-03 | 2026-07-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 167 | [6 empty] | SEK0 | TREX
NSS-A214784140 | T-REX:OoB Guide (96-151.5): FAT-closure of open points and approval Part 2 | 0% | 25 | 2026-06-05 | 2026-07-10 | 2026-03-31 | 07-May-26 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 149 | [6 empty] | SEK0 | TREX
NSS-A214788120 | T-REX: Polarization Flipper: FAT Report and Documentation | 0% | 10 | 2026-06-08 | 2026-06-22 | 2026-04-30 | 18-May-26 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 113 | [6 empty] | SEK0 | TREX
NSS-A214788110 | T-REX: Polarization Flipper: Factory Acceptance Test (FAT) | 0% | 0 | 2026-06-08 |  | 2026-04-30 |  | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 |  |  |  |  | PROC.FAT | 113 | [6 empty] | SEK0 | TREX
NSS-A214783220 | T-REX: Cd Shielding: Shipping | 0% | 5 | 2026-06-09 | 2026-06-15 | 19-May-26 | 25-May-26 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 | [5 empty] | 172 | [6 empty] | SEK0 | TREX
NSS-A214782290 | T-REX: False floor and Det supp: Preparation of installation binder | 0% | 20 | 2026-06-09 | 2026-07-07 | 2026-06-09 | 2026-07-07 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214782600 | T-REX: RC Drive: Qgate document submission phase (partial CE) | 0% | 20 | 2026-06-09 | 2026-07-07 | 2026-06-09 | 2026-07-07 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214783250 | T-REX: Cd Shielding: Qgate document submission phase | 0% | 20 | 2026-06-09 | 2026-07-07 | 19-May-26 | 2026-06-15 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 | [5 empty] | 132 | [6 empty] | SEK0 | TREX
NSS-A214783260 | T-REX: Cd Shielding: Preparation of installation binder | 0% | 20 | 2026-06-09 | 2026-07-07 | 19-May-26 | 2026-06-15 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 |  | 1 | [5 empty] | 142 | [6 empty] | SEK0 | TREX
NSS-A214787780 | T-REX: Translation Table: FAT Report and Documentation | 0% | 12 | 2026-06-10 | 2026-06-26 | 2026-06-10 | 2026-06-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214787770 | T-REX: Translation Table: Factory Acceptance Test (FAT) | 0% | 0 | 2026-06-10 |  | 2026-06-10 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 92 | [6 empty] | SEK0 | TREX
NSS-A214787260 | T-REX:OoB Guide (151.5-163.1): CDR: Closure of open points and approval | 0% | 14 | 2026-06-11 | 2026-07-01 | 2026-04-08 | 2026-04-27 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 47 | [6 empty] | SEK0 | TREX
NSS-A214784220 | T-REX:OoB Guide (151.5-163.1): CDR/subTG3 (meeting) | 0% | 0 | 2026-06-11 |  | 2026-04-08 |  | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 |  |  |  |  | ENG.CDR | 47 | [6 empty] | SEK0 | TREX
NSS-A214787760 | T-REX: Thermal Polarization: FAT Report and Documentation | 0% | 12 | 2026-06-15 | 2026-07-01 | 08-May-26 | 27-May-26 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214787750 | T-REX: Thermal Polarization: Factory Acceptance Test (FAT) | 0% | 0 | 2026-06-15 |  | 08-May-26 |  | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 |  |  |  |  | PROC.FAT | 88 | [6 empty] | SEK0 | TREX
NSS-A214783230 | T-REX: Cd Shielding: Arrival Inspection | 0% | 5 | 2026-06-16 | 2026-06-23 | 26-May-26 | 2026-06-01 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | -15 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 172 | [6 empty] | SEK0 | TREX
NSS-A214781990 | T-REX: Detector Vessel: IRR documents review by ESS | 0% | 10 | 2026-06-16 | 2026-06-30 | 2026-06-16 | 2026-06-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214785260 | T-REX: Fan Chopper: Testing period | 0% | 34 | 2026-06-16 | 2026-08-31 | 2026-04-27 | 2026-06-16 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214784880 | T-REX: Det prototype box: Shipping to Utgård | 0% | 5 | 2026-06-17 | 2026-06-24 | 2026-06-17 | 2026-06-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 179 | [6 empty] | SEK0 | TREX
NSS-A214787220 | T-REX:OoB Guide (96-151.5): IRR meeting preparation | 0% | 5 | 2026-06-17 | 2026-06-24 | 2026-04-14 | 2026-04-20 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 166 | [6 empty] | SEK0 | TREX
NSS-A214781080 | T-REX: Sample Environment: FAT-closure of open points and approval | 0% | 12 | 2026-06-17 | 2026-07-03 | 2026-06-17 | 2026-07-03 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214785830 | T-REX: Com Chop: Integration CNR+ESS | 0% | 20 | 2026-06-17 | 2026-07-15 | 2026-06-05 | 2026-07-03 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214786230 | T-REX: Cave: First crane certification | 0% | 5 | 2026-06-22 | 2026-06-26 | 2026-06-22 | 2026-06-26 | 0 | SEK0 | SEK0 |  | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 74 | [6 empty] | SEK0 | TREX
NSS-A214787880 | T-REX: Polarization Analyser: FAT Report and Documentation | 0% | 10 | 2026-06-22 | 2026-07-03 | 19-May-26 | 2026-06-01 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214786240 | T-REX: Cave: Installation of Platform | 0% | 17 | 2026-06-22 | 2026-07-14 | 2026-06-22 | 2026-07-14 | 0 | SEK0 | SEK0 |  | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214787870 | T-REX: Polarization Analyser: Factory Acceptance Test (FAT) | 0% | 0 | 2026-06-22 |  | 19-May-26 |  | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | PROC.FAT | 94 | [6 empty] | SEK0 | TREX
NSS-A214787970 | T-REX: Polarization Flipper: FAT-closure of open points and approval | 0% | 10 | 2026-06-23 | 2026-07-06 | 19-May-26 | 2026-06-01 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 113 | [6 empty] | SEK0 | TREX
NSS-A214788600 | T-REX: Beamstop: FAT Report and Documentation | 0% | 12 | 2026-06-23 | 2026-07-08 | 20-May-26 | 2026-06-04 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214788590 | T-REX: Beamstop: Factory Acceptance Test (FAT) | 0% | 0 | 2026-06-23 |  | 20-May-26 |  | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | PROC.FAT | 107 | [6 empty] | SEK0 | TREX
NSS-A214782610 | T-REX: RC Drive: Preparation of installation binder | 0% | 20 | 2026-06-24 | 2026-08-18 | 2026-06-24 | 2026-08-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214788220 | T-REX: False floor and Det supp: Quality gate review and approval | 0% | 20 | 2026-06-24 | 2026-08-18 | 2026-06-24 | 2026-08-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 117 | [6 empty] | SEK0 | TREX
NSS-A214783240 | T-REX: Cd Shielding: Storage time | 0% | 50 | 2026-06-24 | 2026-09-29 | 2026-06-02 | 2026-09-29 | -15 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214784890 | T-REX: Det prototype box: Arrival Inspection at Utgård | 0% | 5 | 2026-06-25 | 2026-07-01 | 2026-06-25 | 2026-07-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 179 | [6 empty] | SEK0 | TREX
NSS-A214787230 | T-REX:OoB Guide (96-151.5): Installation preparation | 0% | 5 | 2026-06-25 | 2026-07-01 | 2026-04-21 | 2026-04-27 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 166 | [6 empty] | SEK0 | TREX
NSS-A214783880 | T-REX:OoB Guide (96-151.5): IRR/subTG4 (meeting) | 0% | 0 | 2026-06-25 |  | 2026-04-21 |  | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 |  |  |  |  | INST.IRR | 166 | [6 empty] | SEK0 | TREX
NSS-A214786860 | T-REX: Translation Table: FAT-closure of open points and approval | 0% | 12 | 2026-06-29 | 2026-07-14 | 2026-06-29 | 2026-07-14 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214788170 | T-REX: Detector Vessel: IRR meeting preparation | 0% | 5 | 2026-07-01 | 2026-07-07 | 2026-07-01 | 2026-07-07 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214784900 | T-REX: Det prototype box: Storage time | 0% | 0 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 2026-07-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 731 | [6 empty] | SEK0 | TREX
NSS-A214788690 | T-REX: Control Hutch: IRR meeting preparation | 0% | 6 | 2026-07-02 | 2026-07-09 | 2026-07-02 | 2026-07-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214786710 | T-REX: Thermal Polarization: FAT-closure of open points and approval | 0% | 12 | 2026-07-02 | 2026-07-17 | 28-May-26 | 2026-06-12 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214785110 | T-REX: Document compilation and submission for Final TG3 | 0% | 30 | 2026-07-02 | 2026-09-09 | 2026-04-28 | 2026-06-11 | -43 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | -43 |  | 1 | [5 empty] | 281 | [6 empty] | SEK0 | TREX
NSS-A214784230 | T-REX:OoB Guide (151.5-163.1): Manufacturing | 0% | 65 | 2026-07-02 | 2026-09-30 | 2026-04-28 | 2026-07-31 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214785160 | T-REX: M- Fast Chopper: Lab test at FZJ | 0% | 70 | 2026-07-03 | 2026-11-05 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 12 | [6 empty] | SEK0
NSS-A214781090 | T-REX: Sample Environment: Shipping | 0% | 5 | 2026-07-06 | 2026-07-10 | 2026-07-06 | 2026-07-10 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214781500 | T-REX: Polarization Analyser: FAT-closure of open points and approval | 0% | 10 | 2026-07-06 | 2026-07-17 | 2026-06-02 | 2026-06-15 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214781120 | T-REX: Sample Environment: Qgate document submission phase (probably CE) | 0% | 20 | 2026-07-06 | 2026-08-28 | 2026-07-06 | 2026-08-28 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214781130 | T-REX: Sample Environment: Preparation of installation binder | 0% | 20 | 2026-07-06 | 2026-08-28 | 2026-07-06 | 2026-08-28 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 139 | [6 empty] | SEK0 | TREX
NSS-A214784770 | T-REX: P- Fast Chopper: Lab test at FZJ | 0% | 80 | 2026-07-06 | 2026-11-20 |  |  |  | SEK0 | SEK0 |  | SEK0 |  |  |  |  | 1 | [5 empty] | 20 | [6 empty] | SEK0
NSS-A214787980 | T-REX: Polarization Flipper: Shipping | 0% | 5 | 2026-07-07 | 2026-07-13 | 2026-06-02 | 2026-06-08 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 178 | [6 empty] | SEK0 | TREX
NSS-A214788020 | T-REX: Polarization Flipper: Preparation of installation binder | 0% | 20 | 2026-07-07 | 2026-08-31 | 2026-06-02 | 2026-06-30 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 143 | [6 empty] | SEK0 | TREX
NSS-A214788010 | T-REX: Polarization Flipper: Qgate document submission phase (complicated) | 0% | 30 | 2026-07-07 | 2026-09-14 | 2026-06-02 | 2026-07-14 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 113 | [6 empty] | SEK0 | TREX
NSS-A214788180 | T-REX: Detector Vessel: Installation preparation | 0% | 5 | 2026-07-08 | 2026-07-14 | 2026-07-08 | 2026-07-14 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 62 | [6 empty] | SEK0 | TREX
NSS-A214782300 | T-REX: False floor and Det supp: IRR documents review by ESS | 0% | 10 | 2026-07-08 | 2026-08-18 | 2026-07-08 | 2026-08-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214788270 | T-REX: RC Drive: Quality gate review and approval | 0% | 20 | 2026-07-08 | 2026-09-01 | 2026-07-08 | 2026-09-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 117 | [6 empty] | SEK0 | TREX
NSS-A214788190 | T-REX: Detector Vessel: IRR/subTG4 (meeting) | 0% | 0 | 2026-07-08 |  | 2026-07-08 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 62 | [6 empty] | SEK0 | TREX
NSS-A214784440 | T-REX: Beamstop: FAT-closure of open points and approval | 0% | 12 | 2026-07-09 | 2026-08-21 | 2026-06-05 | 2026-06-23 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214788700 | T-REX: Control Hutch: Installation preparation | 0% | 5 | 2026-07-10 | 2026-07-16 | 2026-07-10 | 2026-07-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214786510 | T-REX: Control Hutch: IRR/subTG4 (meeting) | 0% | 0 | 2026-07-10 |  | 2026-07-10 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 167 | [6 empty] | SEK0 | TREX
NSS-A214781100 | T-REX: Sample Environment: Arrival Inspection | 0% | 5 | 2026-07-13 | 2026-07-17 | 2026-07-13 | 2026-07-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 167 | [6 empty] | SEK0 | TREX
NSS-A214783820 | T-REX:OoB Guide (96-151.5): Shipping | 0% | 5 | 2026-07-13 | 2026-07-17 | 08-May-26 | 18-May-26 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 149 | [6 empty] | SEK0 | TREX
NSS-A214788000 | T-REX: Polarization Flipper: Storage time | 0% | 0 | 2026-07-14 | 2026-07-14 | 2026-06-09 | 2026-06-09 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 723 | [6 empty] | SEK0 | TREX
NSS-A214781010 | T-REX: Translation Table: Shipping | 0% | 5 | 2026-07-15 | 2026-08-18 | 2026-07-15 | 2026-08-18 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 132 | [6 empty] | SEK0 | TREX
NSS-A214782000 | T-REX: Detector Vessel: Installation (partner/supplier) | 0% | 15 | 2026-07-15 | 2026-09-01 | 2026-07-15 | 2026-09-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214781230 | T-REX: Translation Table: Qgate document submission phase (CE) | 0% | 20 | 2026-07-15 | 2026-09-08 | 2026-07-15 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214781240 | T-REX: Translation Table: Preparation of installation binder | 0% | 20 | 2026-07-15 | 2026-09-08 | 2026-07-15 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 102 | [6 empty] | SEK0 | TREX
NSS-A214788320 | T-REX: Sample ex-container: Quality gate review and approval | 0% | 20 | 2026-07-15 | 2026-09-08 | 2026-07-15 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 122 | [6 empty] | SEK0 | TREX
NSS-A214785850 | T-REX: Com Chop: Factory Acceptance Test (FAT) | 0% | 22 | 2026-07-16 | 2026-09-11 | 2026-07-06 | 2026-09-01 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 |  |  |  |  | PROC.FAT | 65 | [6 empty] | SEK0 | TREX
NSS-A214786530 | T-REX: Control Hutch: Installation (partner/supplier) | 0% | 18 | 2026-07-17 | 2026-09-08 | 2026-07-17 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 167 | [6 empty] | SEK0 | TREX
NSS-A214781680 | T-REX: IBG (HS): Integrated SAT | 0% | 20 | 2026-08-14 | 2026-09-10 | 2025-11-03 | 2025-11-28 | -10 | SEK0 | SEK0 |  | SEK0 |  |  | -30 | BUN D03 | 1 | COMM |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214781860 | T-REX: IBG (fixed and remote): Integrated: SAT | 0% | 20 | 2026-08-14 | 2026-09-10 | 2025-11-03 | 2025-11-28 | -10 | SEK0 | SEK0 |  | SEK0 |  |  | -30 | BUN D03 | 1 | COMM |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214782220 | T-REX: BBG:Integrated SAT | 0% | 20 | 2026-08-14 | 2026-09-10 | 2025-11-03 | 2025-11-28 | -10 | SEK0 | SEK0 |  | SEK0 |  |  | -30 | BUN D03 | 1 | COMM |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214781510 | T-REX: Polarization Analyser: Shipping | 0% | 5 | 2026-08-17 | 2026-08-21 | 2026-06-16 | 2026-06-23 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 159 | [6 empty] | SEK0 | TREX
NSS-A214783830 | T-REX:OoB Guide (96-151.5): Arrival Inspection | 0% | 5 | 2026-08-17 | 2026-08-21 | 19-May-26 | 25-May-26 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 149 | [6 empty] | SEK0 | TREX
NSS-A214786720 | T-REX: Thermal Polarization: Shipping | 0% | 5 | 2026-08-17 | 2026-08-21 | 2026-06-15 | 2026-06-22 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 156 | [6 empty] | SEK0 | TREX
NSS-A214788440 | T-REX: Primary Coll & Slits: Factory Acceptance Test (FAT) | 0% | 5 | 2026-08-17 | 2026-08-21 | 2026-07-15 | 2026-08-18 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 |  |  |  |  | PROC.FAT | 58 | [6 empty] | SEK0 | TREX
NSS-A214781550 | T-REX: Polarization Analyser: Preparation of installation binder | 0% | 20 | 2026-08-17 | 2026-09-11 | 2026-06-16 | 2026-07-14 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 124 | [6 empty] | SEK0 | TREX
NSS-A214786760 | T-REX: Thermal Polarization: Preparation of installation binder | 0% | 20 | 2026-08-17 | 2026-09-11 | 2026-06-15 | 2026-07-13 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 126 | [6 empty] | SEK0 | TREX
NSS-A214781540 | T-REX: Polarization Analyser: Qgate document submission phase (complicated) | 0% | 30 | 2026-08-17 | 2026-09-25 | 2026-06-16 | 2026-08-25 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214786750 | T-REX: Thermal Polarization: Qgate document submission phase (complicated) | 0% | 34 | 2026-08-17 | 2026-10-01 | 2026-06-15 | 2026-08-28 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214782250 | T-REX: False floor and Det supp: Shipping | 0% | 5 | 2026-08-18 | 2026-08-24 | 2026-08-18 | 2026-08-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214781210 | T-REX: Translation Table: Arrival Inspection | 0% | 5 | 2026-08-19 | 2026-08-25 | 2026-08-19 | 2026-08-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 132 | [6 empty] | SEK0 | TREX
NSS-A214788230 | T-REX: False floor and Det supp: IRR meeting preparation | 0% | 5 | 2026-08-19 | 2026-08-25 | 2026-08-19 | 2026-08-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214782620 | T-REX: RC Drive: IRR documents review by ESS | 0% | 10 | 2026-08-19 | 2026-09-01 | 2026-08-19 | 2026-09-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214788390 | T-REX: Cd Shielding: Quality gate review and approval | 0% | 20 | 2026-08-19 | 2026-09-15 | 2026-08-19 | 2026-09-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 122 | [6 empty] | SEK0 | TREX
NSS-A214781530 | T-REX: Polarization Analyser: Storage time | 0% | 0 | 2026-08-24 | 2026-08-24 | 2026-06-24 | 2026-06-24 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 714 | [6 empty] | SEK0 | TREX
NSS-A214783840 | T-REX:OoB Guide (96-151.5): Storage time | 0% | 0 | 2026-08-24 | 2026-08-24 | 26-May-26 | 26-May-26 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | [5 empty] | 149 | [6 empty] | SEK0 | TREX
NSS-A214784450 | T-REX: Beamstop: Shipping | 0% | 5 | 2026-08-24 | 2026-08-28 | 2026-06-24 | 2026-06-30 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 147 | [6 empty] | SEK0 | TREX
NSS-A214786730 | T-REX: Thermal Polarization: Arrival Inspection | 0% | 5 | 2026-08-24 | 2026-08-28 | 2026-06-23 | 2026-06-29 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 156 | [6 empty] | SEK0 | TREX
NSS-A214788450 | T-REX: Primary Coll & Slits: FAT Report and Documentation | 0% | 5 | 2026-08-24 | 2026-08-28 | 2026-08-19 | 2026-08-25 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214784480 | T-REX: Beamstop: Qgate document submission phase | 0% | 20 | 2026-08-24 | 2026-09-18 | 2026-06-24 | 2026-08-18 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214784490 | T-REX: Beamstop: Preparation of installation binder | 0% | 20 | 2026-08-24 | 2026-09-18 | 2026-06-24 | 2026-08-18 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214783890 | T-REX:OoB Guide (96-151.5): Installation (partner/supplier) | 0% | 25 | 2026-08-24 | 2026-09-25 | 26-May-26 | 2026-06-30 | -43 | SEK0 | SEK0 | june 2025: installation starts in january for the first batch | SEK0 |  |  | -43 | E01-02 | 1 | INST |  |  |  |  | 149 | [6 empty] | SEK0 | TREX
NSS-A214782260 | T-REX: False floor and Det supp: Arrival Inspection | 0% | 6 | 2026-08-25 | 2026-09-01 | 2026-08-25 | 2026-09-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 117 | [6 empty] | SEK0 | TREX
NSS-A214781220 | T-REX: Translation Table: Storage time | 0% | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 712 | [6 empty] | SEK0 | TREX
NSS-A214788240 | T-REX: False floor and Det supp: Installation preparation | 0% | 5 | 2026-08-26 | 2026-09-01 | 2026-08-26 | 2026-09-01 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214782910 | T-REX: Sample ex-container: IRR documents review by ESS | 0% | 10 | 2026-08-26 | 2026-09-08 | 2026-08-26 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214782310 | T-REX: False floor and Det supp: IRR/subTG4 (meeting) | 0% | 0 | 2026-08-26 |  | 2026-08-26 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 117 | [6 empty] | SEK0 | TREX
NSS-A214784460 | T-REX: Beamstop: Arrival Inspection | 0% | 5 | 2026-08-31 | 2026-09-04 | 2026-07-01 | 2026-07-07 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 147 | [6 empty] | SEK0 | TREX
NSS-A214781140 | T-REX: Sample Environment: IRR documents review by ESS | 0% | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 139 | [6 empty] | SEK0 | TREX
NSS-A214782490 | T-REX:BS: Installation lower part D03 | 0% | 10 | 2026-08-31 | 2026-09-11 | 2026-06-02 | 2026-06-15 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | INST |  |  |  |  | 624 | [6 empty] | SEK0 | TREX
NSS-A214783600 | T-REX: Primary Coll & Slits: FAT-closure of open points and approval | 0% | 10 | 2026-08-31 | 2026-09-11 | 2026-08-26 | 2026-09-08 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214788750 | T-REX: Sample Environment: Quality gate review and approval | 0% | 20 | 2026-08-31 | 2026-09-25 | 2026-08-31 | 2026-09-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 129 | [6 empty] | SEK0 | TREX
NSS-A214787480 | T-REX: Fan Chopper: FAT Report and Documentation | 0% | 15 | 2026-09-01 | 2026-09-21 | 2026-06-17 | 2026-07-08 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214785270 | T-REX: Fan Chopper: Factory Acceptance Test (FAT) | 0% | 0 | 2026-09-01 |  | 2026-06-17 |  | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | PROC.FAT | 73 | [6 empty] | SEK0 | TREX
NSS-A214782010 | T-REX: Detector Vessel: Local SAT | 0% | 5 | 2026-09-02 | 2026-09-08 | 2026-09-02 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 145 | [6 empty] | SEK0 | TREX
NSS-A214788280 | T-REX: RC Drive: IRR meeting preparation | 0% | 5 | 2026-09-02 | 2026-09-08 | 2026-09-02 | 2026-09-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214782320 | T-REX: False floor and Det supp: Installation (partner/supplier) | 0% | 10 | 2026-09-02 | 2026-09-15 | 2026-09-02 | 2026-09-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 117 | [6 empty] | SEK0 | TREX
NSS-A214783270 | T-REX: Cd Shielding: IRR documents review by ESS | 0% | 10 | 2026-09-02 | 2026-09-15 | 2026-09-02 | 2026-09-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214786250 | T-REX: Cave: Installation of Last wall | 0% | 20 | 2026-09-02 | 2026-09-29 | 2026-09-02 | 2026-09-29 | 0 | SEK0 | SEK0 |  | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214782860 | T-REX: Sample ex-container: Shipping | 0% | 5 | 2026-09-09 | 2026-09-15 | 2026-09-09 | 2026-09-15 | 0 | SEK0 | SEK0 | in may 2026. review Smartseet | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214786550 | T-REX: Control Hutch: Local SAT | 0% | 5 | 2026-09-09 | 2026-09-15 | 2026-09-09 | 2026-09-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 167 | [6 empty] | SEK0 | TREX
NSS-A214788290 | T-REX: RC Drive: Installation preparation | 0% | 5 | 2026-09-09 | 2026-09-15 | 2026-09-09 | 2026-09-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214788330 | T-REX: Sample ex-container: IRR meeting preparation | 0% | 5 | 2026-09-09 | 2026-09-15 | 2026-09-09 | 2026-09-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214781250 | T-REX: Translation Table: IRR documents review by ESS | 0% | 10 | 2026-09-09 | 2026-09-22 | 2026-09-09 | 2026-09-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 102 | [6 empty] | SEK0 | TREX
NSS-A214782020 | T-REX: Detector Vessel + MG.TREX.1 : Installation of box 1 with columns into vessel (ESS/common projects) | 0% | 10 | 2026-09-09 | 2026-09-22 | 2026-09-09 | 2026-09-22 | 0 | SEK0 | SEK0 | We should add a TRR and remove detector WBS below. | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 162 | [6 empty] | SEK0 | TREX
NSS-A214787840 | T-REX: Translation Table: Quality gate review and approval | 0% | 20 | 2026-09-09 | 2026-10-06 | 2026-09-09 | 06-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 92 | [6 empty] | SEK0 | TREX
NSS-A214782630 | T-REX: RC Drive: IRR/subTG4 (meeting) | 0% | 0 | 2026-09-09 |  | 2026-09-09 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 117 | [6 empty] | SEK0 | TREX
NSS-A214785710 | T-REX: MG Detector: Installation | 0% | 0 | 2026-09-09 |  | 2026-09-09 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | INST |  |  |  |  | 182 | [6 empty] | SEK0 | TREX
NSS-A214785140 | T-REX: Final TG3 action closeouts | 0% | 20 | 2026-09-10 | 2026-10-07 | 2026-06-12 | 2026-07-10 | -43 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | -43 |  | 1 | [5 empty] | 281 | [6 empty] | SEK0 | TREX
NSS-A214788810 | T-REX: Final TG3 meeting | 0% | 0 | 2026-09-10 |  | 2026-06-12 |  | -43 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | -43 |  | 1 | [5 empty] | 281 | [6 empty] | SEK0 | TREX
NSS-A214783610 | T-REX: Primary Coll & Slits: Shipping | 0% | 5 | 2026-09-14 | 2026-09-18 | 2026-09-09 | 2026-09-15 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 114 | [6 empty] | SEK0 | TREX
NSS-A214781560 | T-REX: Polarization Analyser: IRR documents review by ESS | 0% | 10 | 2026-09-14 | 2026-09-25 | 2026-07-15 | 2026-08-25 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 124 | [6 empty] | SEK0 | TREX
NSS-A214786770 | T-REX: Thermal Polarization: IRR documents review by ESS | 0% | 10 | 2026-09-14 | 2026-09-25 | 2026-07-14 | 2026-08-24 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 126 | [6 empty] | SEK0 | TREX
NSS-A214787590 | T-REX: Com Chop: FAT Report and Documentation | 0% | 10 | 2026-09-14 | 2026-09-25 | 2026-09-02 | 2026-09-15 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214783650 | T-REX: Primary Coll & Slits: Preparation of installation binder | 0% | 20 | 2026-09-14 | 2026-10-09 | 2026-09-09 | 06-Oct-26 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 84 | [6 empty] | SEK0 | TREX
NSS-A214783640 | T-REX: Primary Coll & Slits: Qgate document submission phase | 0% | 22 | 2026-09-14 | 2026-10-13 | 2026-09-09 | 08-Oct-26 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214782330 | T-REX: False floor and Det supp: Local SAT | 0% | 5 | 2026-09-16 | 2026-09-22 | 2026-09-16 | 2026-09-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 162 | [6 empty] | SEK0 | TREX
NSS-A214782640 | T-REX: RC Drive: Installation (partner/supplier) | 0% | 5 | 2026-09-16 | 2026-09-22 | 2026-09-16 | 2026-09-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 117 | [6 empty] | SEK0 | TREX
NSS-A214782870 | T-REX: Sample ex-container: Arrival Inspection | 0% | 5 | 2026-09-16 | 2026-09-22 | 2026-09-16 | 2026-09-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 122 | [6 empty] | SEK0 | TREX
NSS-A214788340 | T-REX: Sample ex-container: installation preparation | 0% | 5 | 2026-09-16 | 2026-09-22 | 2026-09-16 | 2026-09-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214788400 | T-REX: Cd Shielding: IRR meeting preparation | 0% | 5 | 2026-09-16 | 2026-09-22 | 2026-09-16 | 2026-09-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214784120 | T-REX: Secondary RC: Installation | 0% | 10 | 2026-09-16 | 2026-09-29 | 2026-09-16 | 2026-09-29 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 132 | [6 empty] | SEK0 | TREX
NSS-A214786500 | T-REX: Cold Polarization: Qgate document submission phase (CE n/a) | 0% | 20 | 2026-09-16 | 2026-10-13 | 2025-11-03 | 2025-11-28 | -191 | SEK0 | SEK0 |  | SEK0 |  |  | -191 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214782920 | T-REX: Sample ex-container: RR/subTG4 (meeting) | 0% | 0 | 2026-09-16 |  | 2026-09-16 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214783620 | T-REX: Primary Coll & Slits: Arrival Inspection | 0% | 5 | 2026-09-21 | 2026-09-25 | 2026-09-16 | 2026-09-22 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 114 | [6 empty] | SEK0 | TREX
NSS-A214788610 | T-REX: Beamstop: Quality gate review and approval | 0% | 20 | 2026-09-21 | 2026-10-16 | 2026-08-19 | 2026-09-15 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | PROC.QGATE | 107 | [6 empty] | SEK0 | TREX
NSS-A214787490 | T-REX: Fan Chopper: FAT-closure of open points and approval | 0% | 20 | 2026-09-22 | 2026-10-19 | 2026-07-09 | 2026-09-02 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214782880 | T-REX: Sample ex-container: Storage time | 0% | 0 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214782650 | T-REX: RC Drive: Local SAT | 0% | 5 | 2026-09-23 | 2026-09-29 | 2026-09-23 | 2026-09-29 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 147 | [6 empty] | SEK0 | TREX
NSS-A214782930 | T-REX: Sample ex-container: Installation (partner/supplier) | 0% | 5 | 2026-09-23 | 2026-09-29 | 2026-09-23 | 2026-09-29 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 122 | [6 empty] | SEK0 | TREX
NSS-A214788410 | T-REX: Cd Shielding: Installation preparation | 0% | 5 | 2026-09-23 | 2026-09-29 | 2026-09-23 | 2026-09-29 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214782340 | T-REX: False floor and Det supp: Installation (ESS/common projects) | 0% | 10 | 2026-09-23 | 2026-10-06 | 2026-09-23 | 06-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 162 | [6 empty] | SEK0 | TREX
NSS-A214783280 | T-REX: Cd Shielding: IRR/subTG4 (meeting) | 0% | 0 | 2026-09-23 |  | 2026-09-23 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 122 | [6 empty] | SEK0 | TREX
NSS-A214788760 | T-REX: Sample Environment: IRR meeting preparation | 0% | 5 | 2026-09-28 | 2026-10-02 | 2026-09-28 | 02-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214783910 | T-REX:OoB Guide (96-151.5): Installation (ESS/common projects) | 0% | 10 | 2026-09-28 | 2026-10-09 | 2026-07-01 | 2026-07-14 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 | E01-02 | 1 | INST |  |  |  |  | 149 | [6 empty] | SEK0 | TREX
NSS-A214787600 | T-REX: Com Chop: FAT-closure of open points and approval | 0% | 12 | 2026-09-28 | 2026-10-13 | 2026-09-16 | 01-Oct-26 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214782690 | T-REX:BS:Installation side part D03 | 0% | 20 | 2026-09-28 | 2026-10-23 | 2026-07-01 | 2026-08-25 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | INST |  |  |  |  | 614 | [6 empty] | SEK0 | TREX
NSS-A214787890 | T-REX: Polarization Analyser: Quality gate review and approval | 0% | 30 | 2026-09-28 | 2026-11-06 | 2026-08-26 | 06-Oct-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | PROC.QGATE | 94 | [6 empty] | SEK0 | TREX
NSS-A214783630 | T-REX: Primary Coll & Slits: Storage time | 0% | 56 | 2026-09-28 | 2026-12-14 | 2026-09-23 | 2026-12-09 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214782940 | T-REX: Sample ex-container: Local SAT | 0% | 5 | 2026-09-30 | 2026-10-06 | 2026-09-30 | 06-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 142 | [6 empty] | SEK0 | TREX
NSS-A214784130 | T-REX: Secondary RC: Local SAT | 0% | 5 | 2026-09-30 | 2026-10-06 | 2026-09-30 | 06-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 152 | [6 empty] | SEK0 | TREX
NSS-A214786260 | T-REX: Cave: Second crane certification | 0% | 5 | 2026-09-30 | 2026-10-06 | 2026-09-30 | 06-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 | 3 cave installations |  | 0 | E01-02 | 1 | INST |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214786270 | T-REX: Cave: Local SAT | 0% | 5 | 2026-09-30 | 2026-10-06 | 2026-09-30 | 06-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214782660 | T-REX: RC Drive: Installation (ESS/common projects) | 0% | 10 | 2026-09-30 | 2026-10-13 | 2026-09-30 | 13-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 147 | [6 empty] | SEK0 | TREX
NSS-A214783290 | T-REX: Cd Shielding: nstallation (partner/supplier) | 0% | 20 | 2026-09-30 | 2026-10-27 | 2026-09-30 | 27-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A214786520 | T-REX: Cold Polarization: Preparation of installation binder | 0% | 20 | 2026-09-30 | 2026-10-27 | 2026-09-30 | 27-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214787270 | T-REX:OoB Guide (151.5-163.1): FAT Report and Documentation | 0% | 12 | 2026-10-01 | 2026-10-16 | 2026-08-17 | 2026-09-01 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214784240 | T-REX:OoB Guide (151.5-163.1): Factory Acceptance Test (FAT) | 0% | 0 | 2026-10-01 |  | 2026-08-17 |  | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | PROC.FAT | 67 | [6 empty] | SEK0 | TREX
NSS-A214787790 | T-REX: Thermal Polarization: Quality gate review and approval | 0% | 34 | 2026-10-02 | 2026-11-18 | 2026-08-31 | 15-Oct-26 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 |  |  |  |  | PROC.QGATE | 88 | [6 empty] | SEK0 | TREX
NSS-A214788770 | T-REX: Sample Environment: Installation preparation | 0% | 3 | 2026-10-05 | 2026-10-07 | 05-Oct-26 | 07-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 129 | [6 empty] | SEK0 | TREX
NSS-A214784500 | T-REX: Beamstop: IRR documents review by ESS | 0% | 10 | 2026-10-05 | 2026-10-16 | 2026-09-02 | 2026-09-15 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214781150 | T-REX: Sample Environment: IRR/subTG4 (meeting) | 0% | 0 | 2026-10-05 |  | 05-Oct-26 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 129 | [6 empty] | SEK0 | TREX
NSS-A214787820 | T-REX: Translation Table: IRR meeting preparation | 0% | 5 | 2026-10-07 | 2026-10-13 | 07-Oct-26 | 13-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214782350 | T-REX: False floor and Det supp: Integrated SAT | 0% | 10 | 2026-10-07 | 2026-10-20 | 07-Oct-26 | 20-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 162 | [6 empty] | SEK0 | TREX
NSS-A214781160 | T-REX: Sample Environment: Installation (partner/supplier) | 0% | 17 | 2026-10-08 | 2026-10-30 | 08-Oct-26 | 30-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 129 | [6 empty] | SEK0 | TREX
NSS-A214783920 | T-REX:OoB Guide (96-151.5): Integrated SAT | 0% | 20 | 2026-10-12 | 2026-11-06 | 2026-07-15 | 2026-09-08 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 | E01-02 | 1 | COMM |  |  |  |  | 149 | [6 empty] | SEK0 | TREX
NSS-A214787830 | T-REX: Translation Table: Installation preparation | 0% | 5 | 2026-10-14 | 2026-10-20 | 14-Oct-26 | 20-Oct-26 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214782670 | T-REX: RC Drive: Integrated SAT | 0% | 20 | 2026-10-14 | 2026-11-10 | 14-Oct-26 | 2026-11-10 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 147 | [6 empty] | SEK0 | TREX
NSS-A214785890 | T-REX: Com Chop: Qgate document submission phase (ESS chopper group) | 0% | 20 | 2026-10-14 | 2026-11-10 | 02-Oct-26 | 29-Oct-26 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214785900 | T-REX: Com Chop: Preparation of installation binder | 0% | 20 | 2026-10-14 | 2026-11-10 | 02-Oct-26 | 29-Oct-26 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 75 | [6 empty] | SEK0 | TREX
NSS-A214788780 | T-REX: Cold Polarization: Quality gate review and approval | 0% | 20 | 2026-10-14 | 2026-11-10 | 14-Oct-26 | 2026-11-10 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.QGATE | 92 | [6 empty] | SEK0 | TREX
NSS-A214788460 | T-REX: Primary Coll & Slits: Quality gate review and approval | 0% | 34 | 2026-10-14 | 2026-11-30 | 09-Oct-26 | 2026-11-25 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 |  |  |  |  | PROC.QGATE | 58 | [6 empty] | SEK0 | TREX
NSS-A214781260 | T-REX: Translation Table: IRR/subTG4 (meeting) | 0% | 0 | 2026-10-14 |  | 14-Oct-26 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 92 | [6 empty] | SEK0 | TREX
NSS-A214788620 | T-REX: Beamstop: IRR meeting preparation | 0% | 5 | 2026-10-19 | 2026-10-23 | 2026-09-16 | 2026-09-22 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214787280 | T-REX:OoB Guide (151.5-163.1): FAT-closure of open points and approval | 0% | 12 | 2026-10-19 | 2026-11-03 | 2026-09-02 | 2026-09-17 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214785280 | T-REX: Fan Chopper: Shipping | 0% | 5 | 2026-10-20 | 2026-10-26 | 2026-09-03 | 2026-09-09 | -33 | SEK0 | SEK0 | Adjusted to Smartsheet. | SEK0 |  |  | -33 |  | 1 | [5 empty] | 98 | [6 empty] | SEK0 | TREX
NSS-A214785310 | T-REX: Fan Chopper: Qgate document submission phase (inhouse CE) | 0% | 15 | 2026-10-20 | 2026-11-09 | 2026-09-03 | 2026-09-23 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214785320 | T-REX: Fan Chopper: Preparation of installation binder | 0% | 15 | 2026-10-20 | 2026-11-09 | 2026-09-03 | 2026-09-23 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 78 | [6 empty] | SEK0 | TREX
NSS-A214781270 | T-REX: Translation Table: Installation (partner/supplier) | 0% | 20 | 2026-10-21 | 2026-11-17 | 21-Oct-26 | 2026-11-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 92 | [6 empty] | SEK0 | TREX
NSS-A214788630 | T-REX: Beamstop: Installation preparation | 0% | 5 | 2026-10-26 | 2026-10-30 | 2026-09-23 | 2026-09-29 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 107 | [6 empty] | SEK0 | TREX
NSS-A214784510 | T-REX: Beamstop: IRR/subTG4 (meeting) | 0% | 0 | 2026-10-26 |  | 2026-09-23 |  | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | INST.IRR | 107 | [6 empty] | SEK0 | TREX
NSS-A214785290 | T-REX: Fan Chopper: Arrival Inspection | 0% | 5 | 2026-10-27 | 2026-11-02 | 2026-09-10 | 2026-09-16 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 98 | [6 empty] | SEK0 | TREX
NSS-A214783300 | T-REX: Cd Shielding: Local SAT | 0% | 5 | 2026-10-28 | 2026-11-03 | 28-Oct-26 | 2026-11-03 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 122 | [6 empty] | SEK0 | TREX
NSS-A214786540 | T-REX: Cold Polarization: IRR documents review by ESS | 0% | 10 | 2026-10-28 | 2026-11-10 | 28-Oct-26 | 2026-11-10 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214781170 | T-REX: Sample Environment: Local SAT | 0% | 5 | 2026-11-02 | 2026-11-06 | 2026-11-02 | 2026-11-06 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 129 | [6 empty] | SEK0 | TREX
NSS-A214784520 | T-REX: Beamstop: Installation (partner/supplier) | 0% | 17 | 2026-11-02 | 2026-11-24 | 2026-09-30 | 22-Oct-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | INST |  |  |  |  | 107 | [6 empty] | SEK0 | TREX
NSS-A214785300 | T-REX: Fan Chopper: Storage time | 0% | 35 | 2026-11-03 | 2026-12-21 | 2026-09-17 | 2026-11-04 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214784250 | T-REX:OoB Guide (151.5-163.1): Shipping | 0% | 5 | 2026-11-04 | 2026-11-10 | 2026-09-18 | 2026-09-24 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 117 | [6 empty] | SEK0 | TREX
NSS-A214783310 | T-REX: Cd Shielding: Installation (ESS/common projects) | 0% | 10 | 2026-11-04 | 2026-11-17 | 2026-11-04 | 2026-11-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 122 | [6 empty] | SEK0 | TREX
NSS-A214784280 | T-REX:OoB Guide (151.5-163.1): Qgate document submission phase | 0% | 20 | 2026-11-04 | 2026-12-01 | 2026-09-18 | 15-Oct-26 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214784290 | T-REX:OoB Guide (151.5-163.1): Preparation of installation binder | 0% | 20 | 2026-11-04 | 2026-12-01 | 2026-09-18 | 15-Oct-26 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214787410 | T-REX: M- Fast Chopper: FAT Report and Documentation | 0% | 24 | 2026-11-06 | 2026-12-09 | 2026-04-01 | 2026-04-30 | -131 | SEK0 | SEK0 |  | SEK0 |  |  | -135 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214784960 | T-REX: M- Fast Chopper: Factory Acceptance Test (FAT) | 0% | 0 | 2026-11-06 |  | 2026-04-01 |  | -131 | SEK0 | SEK0 |  | SEK0 |  |  | -131 |  | 1 |  |  |  |  | PROC.FAT | 12 | [6 empty] | SEK0 | TREX
NSS-A214787900 | T-REX: Polarization Analyser: IRR meeting preparation | 0% | 5 | 2026-11-09 | 2026-11-13 | 07-Oct-26 | 13-Oct-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214785330 | T-REX: Fan Chopper: IRR documents review by ESS | 0% | 20 | 2026-11-10 | 2026-12-07 | 2026-09-24 | 21-Oct-26 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 78 | [6 empty] | SEK0 | TREX
NSS-A214787500 | T-REX: Fan Chopper: Quality gate review and approval (inhouse CE) | 0% | 25 | 2026-11-10 | 2026-12-14 | 2026-09-24 | 28-Oct-26 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | PROC.QGATE | 73 | [6 empty] | SEK0 | TREX
NSS-A214784260 | T-REX:OoB Guide (151.5-163.1): Arrival Inspection | 0% | 5 | 2026-11-11 | 2026-11-17 | 2026-09-25 | 01-Oct-26 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 117 | [6 empty] | SEK0 | TREX
NSS-A214786460 | T-REX: Cold Polarization: Shipping to ESS | 0% | 5 | 2026-11-11 | 2026-11-17 | 2026-11-11 | 2026-11-17 | 0 | SEK0 | SEK0 | is it going to be delivered at ESS in a short time before installation? | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214788790 | T-REX: Cold Polarization: IRR meeting preparation | 0% | 5 | 2026-11-11 | 2026-11-17 | 2026-11-11 | 2026-11-17 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214785910 | T-REX: Com Chop: IRR documents review by ESS | 0% | 10 | 2026-11-11 | 2026-11-24 | 30-Oct-26 | 2026-11-12 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 75 | [6 empty] | SEK0 | TREX
NSS-A214787610 | T-REX: Com Chop: Quality gate review and approval | 0% | 20 | 2026-11-11 | 2026-12-08 | 30-Oct-26 | 2026-11-26 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 |  |  |  |  | PROC.QGATE | 65 | [6 empty] | SEK0 | TREX
NSS-A214787910 | T-REX: Polarization Analyser: Installation preparation | 0% | 5 | 2026-11-16 | 2026-11-20 | 14-Oct-26 | 20-Oct-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | [5 empty] | 94 | [6 empty] | SEK0 | TREX
NSS-A214781570 | T-REX: Polarization Analyser: IRR/subTG4 (meeting) | 0% | 0 | 2026-11-16 |  | 14-Oct-26 |  | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 |  |  |  |  | INST.IRR | 94 | [6 empty] | SEK0 | TREX
NSS-A214783660 | T-REX: Primary Coll & Slits: IRR documents review by ESS | 0% | 10 | 2026-11-17 | 2026-11-30 | 2026-11-12 | 2026-11-25 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214781280 | T-REX: Translation Table: Local SAT | 0% | 5 | 2026-11-18 | 2026-11-24 | 2026-11-18 | 2026-11-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 92 | [6 empty] | SEK0 | TREX
NSS-A214786480 | T-REX: Cold Polarization: Arrival Inspection | 0% | 5 | 2026-11-18 | 2026-11-24 | 2026-11-18 | 2026-11-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 92 | [6 empty] | SEK0 | TREX
NSS-A214788800 | T-REX: Cold Polarization: Installation preparation | 0% | 5 | 2026-11-18 | 2026-11-24 | 2026-11-18 | 2026-11-24 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 92 | [6 empty] | SEK0 | TREX
NSS-A214783320 | T-REX: Cd Shielding: Integrated SAT | 0% | 20 | 2026-11-18 | 2026-12-15 | 2026-11-18 | 2026-12-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 122 | [6 empty] | SEK0 | TREX
NSS-A214784270 | T-REX:OoB Guide (151.5-163.1): Storage time | 0% | 50 | 2026-11-18 | 2027-02-09 | 02-Oct-26 | 2026-12-10 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214786560 | T-REX: Cold Polarization: IRR/subTG4 (meeting) | 0% | 0 | 2026-11-18 |  | 2026-11-18 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 92 | [6 empty] | SEK0 | TREX
NSS-A214787800 | T-REX: Thermal Polarization: IRR meeting preparation | 0% | 5 | 2026-11-19 | 2026-11-25 | 16-Oct-26 | 22-Oct-26 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214787340 | T-REX: P- Fast Chopper: FAT Report and Documentation | 0% | 12 | 2026-11-23 | 2026-12-08 | 2026-09-21 | 06-Oct-26 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 20 | [6 empty] | SEK0 | TREX
NSS-A214781580 | T-REX: Polarization Analyser: Installation (partner/supplier) | 0% | 20 | 2026-11-23 | 2026-12-18 | 21-Oct-26 | 2026-11-17 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | INST |  |  |  |  | 94 | [6 empty] | SEK0 | TREX
NSS-A214784610 | T-REX: P- Fast Chopper: Factory Acceptance Test (FAT) | 0% | 0 | 2026-11-23 |  | 2026-09-21 |  | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 |  |  |  |  | PROC.FAT | 20 | [6 empty] | SEK0 | TREX
NSS-A214784530 | T-REX: Beamstop: Local SAT | 0% | 5 | 2026-11-25 | 2026-12-01 | 23-Oct-26 | 29-Oct-26 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 |  | 1 | COMM |  |  |  |  | 107 | [6 empty] | SEK0 | TREX
NSS-A214786580 | T-REX: Cold Polarization: Installation (partner/supplier) | 0% | 20 | 2026-11-25 | 2026-12-22 | 2026-11-25 | 2026-12-22 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 92 | [6 empty] | SEK0 | TREX
NSS-A214787810 | T-REX: Thermal Polarization: Installation preparation | 0% | 5 | 2026-11-26 | 2026-12-02 | 23-Oct-26 | 29-Oct-26 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 | [5 empty] | 88 | [6 empty] | SEK0 | TREX
NSS-A214786780 | T-REX: Thermal Polarization: IRR/subTG4 (meeting) | 0% | 0 | 2026-11-26 |  | 23-Oct-26 |  | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 |  | 1 |  |  |  |  | INST.IRR | 88 | [6 empty] | SEK0 | TREX
NSS-A214788470 | T-REX: Primary Coll & Slits: IRR meeting preparation | 0% | 5 | 2026-12-01 | 2026-12-07 | 2026-11-26 | 2026-12-02 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214784540 | T-REX: Beamstop: Installation (ESS/common projects) | 0% | 10 | 2026-12-02 | 2026-12-15 | 30-Oct-26 | 2026-11-12 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | INST |  |  |  |  | 107 | [6 empty] | SEK0 | TREX
NSS-A214787290 | T-REX:OoB Guide (151.5-163.1): Quality gate review and approval | 0% | 25 | 2026-12-02 | 2027-01-19 | 16-Oct-26 | 2026-11-19 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | PROC.QGATE | 67 | [6 empty] | SEK0 | TREX
NSS-A214786790 | T-REX: Thermal Polarization: Installation (partner/supplier) | 0% | 18 | 2026-12-03 | 2027-01-11 | 2026-11-25 | 2026-12-18 | -6 | SEK0 | SEK0 |  | SEK0 |  |  | -6 | E01-02 | 1 | INST |  |  |  |  | 88 | [6 empty] | SEK0 | TREX
NSS-A214788480 | T-REX: Primary Coll & Slits: Installation preparation | 0% | 5 | 2026-12-08 | 2026-12-14 | 2026-12-03 | 2026-12-09 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | [5 empty] | 58 | [6 empty] | SEK0 | TREX
NSS-A214788490 | T-REX: Primary Coll & Slits: IRR/subTG4 (meeting) | 0% | 0 | 2026-12-08 |  | 2026-12-03 |  | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 |  |  |  |  | INST.IRR | 58 | [6 empty] | SEK0 | TREX
NSS-A214787620 | T-REX: Com Chop: IRR meeting preparation | 0% | 5 | 2026-12-09 | 2026-12-15 | 2026-11-27 | 2026-12-03 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214787350 | T-REX: P- Fast Chopper: FAT-closure of open points and approval | 0% | 12 | 2026-12-09 | 2027-01-07 | 07-Oct-26 | 22-Oct-26 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 20 | [6 empty] | SEK0 | TREX
NSS-A214787420 | T-REX: M- Fast Chopper: FAT-closure of open points and approval | 0% | 24 | 2026-12-10 | 2027-01-26 | 04-May-26 | 2026-06-02 | -135 | SEK0 | SEK0 |  | SEK0 |  |  | -139 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214787520 | T-REX: Fan Chopper: Installation preparation | 0% | 5 | 2026-12-15 | 2026-12-21 | 29-Oct-26 | 2026-11-04 | -33 | SEK0 | SEK0 | (Installation prep to be closer to installation. Predec for installation to be predec here-RK) | SEK0 |  |  | -33 |  | 1 | [5 empty] | 73 | [6 empty] | SEK0 | TREX
NSS-A214783670 | T-REX: Primary Coll & Slits: Installation (partner/supplier) | 0% | 20 | 2026-12-15 | 2027-01-25 | 2026-12-10 | 2027-01-20 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 | E01-02 | 1 | INST |  |  |  |  | 58 | [6 empty] | SEK0 | TREX
NSS-A214785340 | T-REX: Fan Chopper: IRR/subTG4 (meeting) | 0% | 0 | 2026-12-15 |  | 29-Oct-26 |  | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | INST.IRR | 73 | [6 empty] | SEK0 | TREX
NSS-A214787630 | T-REX: Com Chop: Installation preparation | 0% | 5 | 2026-12-16 | 2026-12-22 | 2026-12-04 | 2026-12-10 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | [5 empty] | 65 | [6 empty] | SEK0 | TREX
NSS-A214784550 | T-REX: Beamstop: Integrated SAT | 0% | 15 | 2026-12-16 | 2027-01-19 | 2026-11-13 | 2026-12-03 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | COMM |  |  |  |  | 107 | [6 empty] | SEK0 | TREX
NSS-A214785920 | T-REX: Com Chop: IRR/subTG4 (meeting) | 0% | 0 | 2026-12-16 |  | 2026-12-04 |  | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 |  |  |  |  | INST.IRR | 65 | [6 empty] | SEK0 | TREX
NSS-A214781590 | T-REX: Polarization Analyser: Local SAT | 0% | 5 | 2026-12-21 | 2027-01-08 | 2026-11-18 | 2026-11-24 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | COMM |  |  |  |  | 94 | [6 empty] | SEK0 | TREX
NSS-A214785350 | T-REX: Fan Chopper: Installation (FZJ/ESS) | 0% | 10 | 2026-12-22 | 2027-01-18 | 2026-11-05 | 2026-11-18 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 | E01-02 | 1 | INST |  |  |  |  | 73 | [6 empty] | SEK0 | TREX
NSS-A214786590 | T-REX: Cold Polarization: Local SAT | 0% | 5 | 2026-12-23 | 2027-01-12 | 2026-12-23 | 2027-01-12 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | COMM |  |  |  |  | 92 | [6 empty] | SEK0 | TREX
NSS-A214785930 | T-REX: Com Chop: Installation (partner and ESS) | 0% | 17 | 2026-12-23 | 2027-01-28 | 2026-12-11 | 2027-01-18 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | D03 | 1 | INST |  |  |  |  | 65 | [6 empty] | SEK0 | TREX
NSS-A214784620 | T-REX: P- Fast Chopper: Shipping | 0% | 5 | 2027-01-08 | 2027-01-14 | 23-Oct-26 | 29-Oct-26 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 50 | [6 empty] | SEK0 | TREX
NSS-A214784650 | T-REX: P- Fast Chopper: Qgate document submission phase | 0% | 10 | 2027-01-08 | 2027-01-21 | 23-Oct-26 | 2026-11-05 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 20 | [6 empty] | SEK0 | TREX
NSS-A214784660 | T-REX: P- Fast Chopper: Preparation of installation binder | 0% | 20 | 2027-01-08 | 2027-02-04 | 23-Oct-26 | 2026-11-19 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 30 | [6 empty] | SEK0 | TREX
NSS-A214786800 | T-REX: Thermal Polarization: Local SAT | 0% | 5 | 2027-01-12 | 2027-01-18 | 2026-12-21 | 2027-01-08 | -6 | SEK0 | SEK0 |  | SEK0 |  |  | -6 | E01-02 | 1 | COMM |  |  |  |  | 88 | [6 empty] | SEK0 | TREX
NSS-A214784630 | T-REX: P- Fast Chopper: Arrival Inspection | 0% | 5 | 2027-01-15 | 2027-01-21 | 30-Oct-26 | 2026-11-05 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 50 | [6 empty] | SEK0 | TREX
NSS-A214785360 | T-REX: Fan Chopper: Local SAT | 0% | 5 | 2027-01-19 | 2027-01-25 | 2026-11-19 | 2026-11-25 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 | E01-02 | 1 | COMM |  |  |  |  | 73 | [6 empty] | SEK0 | TREX
NSS-A214782950 | T-REX: Sample ex-container: Preparation for Testing / TRR (prep period+ sign off) | 0% | 10 | 2027-01-19 | 2027-02-01 | 2026-12-17 | 2027-01-13 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 | E01-02 | 1 | INST |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214784300 | T-REX:OoB Guide (151.5-163.1): IRR documents review by ESS | 0% | 10 | 2027-01-20 | 2027-02-02 | 2026-11-20 | 2026-12-03 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214787360 | T-REX: P- Fast Chopper: Quality gate review and approval | 0% | 20 | 2027-01-22 | 2027-02-18 | 2026-11-06 | 2026-12-03 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 |  |  |  |  | PROC.QGATE | 20 | [6 empty] | SEK0 | TREX
NSS-A214784640 | T-REX: P- Fast Chopper: Storage time | 0% | 30 | 2027-01-22 | 2027-03-04 | 2026-11-06 | 2026-12-17 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 20 | [6 empty] | SEK0 | TREX
NSS-A214783680 | T-REX: Primary Coll & Slits: Local SAT | 0% | 5 | 2027-01-26 | 2027-02-01 | 2027-01-21 | 2027-01-27 | -3 | SEK0 | SEK0 |  | SEK0 |  |  | -3 |  | 1 | COMM |  |  |  |  | 58 | [6 empty] | SEK0 | TREX
NSS-A214782730 | T-REX:BS:Installation E02 3 | 0% | 15 | 2027-01-26 | 2027-02-15 | 2026-11-26 | 2026-12-16 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | INST |  |  |  |  | 588 | [6 empty] | SEK0 | TREX
NSS-A214784970 | T-REX: M- Fast Chopper: Shipping | 0% | 5 | 2027-01-27 | 2027-02-02 | 2026-06-03 | 2026-06-09 | -139 | SEK0 | SEK0 |  | SEK0 |  |  | -139 |  | 1 | [5 empty] | 37 | [6 empty] | SEK0 | TREX
NSS-A214785000 | T-REX: M- Fast Chopper: Qgate document submission phase | 0% | 20 | 2027-01-27 | 2027-02-23 | 2026-06-03 | 2026-07-01 | -139 | SEK0 | SEK0 |  | SEK0 |  |  | -139 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214785010 | T-REX: M- Fast Chopper: Preparation of installation binder | 0% | 20 | 2027-01-27 | 2027-02-23 | 2026-06-03 | 2026-07-01 | -139 | SEK0 | SEK0 |  | SEK0 |  |  | -139 |  | 1 | [5 empty] | 22 | [6 empty] | SEK0 | TREX
NSS-A214788130 | T-REX: Polarization Flipper: Quality gate review and approval | 0% | 30 | 2027-01-27 | 2027-03-09 | 29-Oct-26 | 2026-12-09 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 |  |  |  |  | PROC.QGATE | 27 | [6 empty] | SEK0 | TREX
NSS-A214785940 | T-REX: Com Chop: Local SAT | 0% | 15 | 2027-01-29 | 2027-02-18 | 2027-01-19 | 2027-02-08 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | D03 | 1 | COMM |  |  |  |  | 65 | [6 empty] | SEK0 | TREX
NSS-A214781190 | T-REX: Sample Environment: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214781610 | T-REX: Polarization Analyser: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 | E01-02 | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214782960 | T-REX: Sample ex-container: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 | E01-02 | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214786290 | T-REX: Cave: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214786600 | T-REX: Control Hutch: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214786630 | T-REX: Cold Polarization: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 | E01-02 | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214786820 | T-REX: Thermal Polarization: Integrated SAT | 0% | 20 | 2027-02-02 | 2027-03-01 | 2027-01-14 | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 | E01-02 | 1 | COMM |  |  |  |  | 78 | [6 empty] | SEK0 | TREX
NSS-A214784980 | T-REX: M- Fast Chopper: Arrival Inspection | 0% | 5 | 2027-02-03 | 2027-02-09 | 2026-06-10 | 2026-06-16 | -139 | SEK0 | SEK0 |  | SEK0 |  |  | -139 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 37 | [6 empty] | SEK0 | TREX
NSS-A214787310 | T-REX:OoB Guide (151.5-163.1): Installation preparation | 0% | 5 | 2027-02-03 | 2027-02-09 | 2026-12-04 | 2026-12-10 | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 | [5 empty] | 67 | [6 empty] | SEK0 | TREX
NSS-A214784990 | T-REX: M- Fast Chopper: Storage time | 0% | 45 | 2027-02-03 | 2027-04-08 | 2026-06-10 | 2027-01-20 | -139 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214784310 | T-REX:OoB Guide (151.5-163.1): IRR/subTG4 (meeting) | 0% | 0 | 2027-02-03 |  | 2026-12-04 |  | -33 | SEK0 | SEK0 |  | SEK0 |  |  | -33 |  | 1 |  |  |  |  | INST.IRR | 67 | [6 empty] | SEK0 | TREX
NSS-A2147382590 | T-REX: Det boxes 2-4: FAT Report and Documentation | 0% | 5 | 2027-02-10 | 2027-02-16 | 2027-02-10 | 2027-02-16 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 90 | [6 empty] | SEK0 | TREX
NSS-A2147382580 | T-REX: Det boxes 2-4: Factory Acceptance Test (FAT) | 0% | 0 | 2027-02-10 |  | 2027-02-10 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | PROC.FAT | 90 | [6 empty] | SEK0 | TREX
NSS-A214782480 | T-REX:HS:Integrated SAT | 0% | 15 | 2027-02-12 | 2027-03-04 | 2027-03-04 | 2027-03-24 | 14 | SEK0 | SEK0 |  | SEK0 |  |  | 14 | BUN D03 | 1 | COMM |  |  |  |  | 20 | [6 empty] | SEK0 | TREX
NSS-A214782030 | T-REX: Detector Vessel + MG.TREX.1: Integrated SAT | 0% | 10 | 2027-02-16 | 2027-03-01 | 2027-01-28 | 2027-02-10 | -13 | SEK0 | SEK0 | CEP energisation as pred + CUP. ICS, ECDC missing as pred. | SEK0 |  |  | -13 | E01-02 | 1 | COMM |  |  |  |  | 68 | [6 empty] | SEK0 | TREX
NSS-A2147382600 | T-REX: Det boxes 2-4: FAT-closure of open points and approval | 0% | 5 | 2027-02-17 | 2027-02-23 | 2027-02-17 | 2027-02-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 90 | [6 empty] | SEK0 | TREX
NSS-A214784670 | T-REX: P- Fast Chopper: IRR documents review by ESS | 0% | 10 | 2027-02-19 | 2027-03-04 | 2026-12-04 | 2026-12-17 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 | [5 empty] | 20 | [6 empty] | SEK0 | TREX
NSS-A214782700 | T-REX:BS:Installation upper part D03 | 0% | 15 | 2027-02-19 | 2027-03-11 | 2027-02-09 | 2027-03-01 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | INST |  |  |  |  | 540 | [6 empty] | SEK0 | TREX
NSS-A214785960 | T-REX: Com Chop: Integrated SAT | 0% | 20 | 2027-02-19 | 2027-03-18 | 2027-02-09 | 2027-03-08 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | D03 | 1 | COMM |  |  |  |  | 65 | [6 empty] | SEK0 | TREX
NSS-A2147354680 | T-REX: Det boxes 2-4: Shipping to FZJ | 0% | 5 | 2027-02-24 | 2027-03-02 | 2027-02-24 | 2027-03-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 90 | [6 empty] | SEK0 | TREX
NSS-A214788030 | T-REX: Polarization Flipper: IRR documents review by ESS | 0% | 10 | 2027-02-24 | 2027-03-09 | 2026-11-26 | 2026-12-09 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | [5 empty] | 27 | [6 empty] | SEK0 | TREX
NSS-A214787430 | T-REX: M- Fast Chopper: Quality gate review and approval | 0% | 20 | 2027-02-24 | 2027-03-23 | 2026-11-13 | 2026-12-10 | -63 | SEK0 | SEK0 |  | SEK0 |  |  | -63 |  | 1 |  |  |  |  | PROC.QGATE | 12 | [6 empty] | SEK0 | TREX
NSS-A214785790 | T-REX: MG Detector: Integrated SAT Approval | 0% | 10 | 2027-03-02 | 2027-03-15 | 2027-02-11 | 2027-02-24 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 |  |  |  |  | COMM.SAT | 68 | [6 empty] | SEK0 | TREX
NSS-A2147354690 | T-REX: Det boxes 2-4: Arrival Inspection | 0% | 5 | 2027-03-03 | 2027-03-09 | 2027-03-03 | 2027-03-09 | 0 | SEK0 | SEK0 | What would be the successor? What will happened after arrival at FZJ? | SEK0 |  |  | 0 |  | 1 | [5 empty] | 90 | [6 empty] | SEK0 | TREX
NSS-A214784690 | T-REX: P- Fast Chopper: Installation (partner/supplier) | 0% | 20 | 2027-03-05 | 2027-04-05 | 2026-12-18 | 2027-01-28 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 | E01-02 | 1 | INST |  |  |  |  | 20 | [6 empty] | SEK0 | TREX
NSS-A214784680 | T-REX: P- Fast Chopper: IRR/subTG4 (meeting) | 0% | 0 | 2027-03-05 |  | 2026-12-18 |  | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 |  | 1 |  |  |  |  | INST.IRR | 20 | [6 empty] | SEK0 | TREX
NSS-A214781300 | T-REX: Translation Table: Integrated SAT | 0% | 20 | 2027-03-09 | 2027-04-07 | 2027-02-25 | 2027-03-24 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | E01-02 | 1 | COMM |  |  |  |  | 53 | [6 empty] | SEK0 | TREX
NSS-A214783700 | T-REX: Primary Coll & Slits: Integrated SAT | 0% | 20 | 2027-03-09 | 2027-04-07 | 2027-02-25 | 2027-03-24 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | E01-02 | 1 | COMM |  |  |  |  | 53 | [6 empty] | SEK0 | TREX
NSS-A214784150 | T-REX: Secondary RC: Integrated SAT approval | 0% | 20 | 2027-03-09 | 2027-04-07 | 2027-02-25 | 2027-03-24 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 | E01-02 | 1 | COMM |  |  |  | COMM.SAT | 53 | [6 empty] | SEK0 | TREX
NSS-A214788140 | T-REX: Polarization Flipper: IRR meeting preparation | 0% | 5 | 2027-03-10 | 2027-03-16 | 2026-12-10 | 2026-12-16 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | [5 empty] | 27 | [6 empty] | SEK0 | TREX
NSS-A214785020 | T-REX: M- Fast Chopper: IRR documents review by ESS | 0% | 10 | 2027-03-10 | 2027-03-23 | 2026-11-27 | 2026-12-10 | -63 | SEK0 | SEK0 |  | SEK0 |  |  | -63 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214782710 | T-REX:BS:Installation E02 1 | 0% | 15 | 2027-03-12 | 2027-04-05 | 2027-03-02 | 2027-03-22 | -8 | SEK0 | SEK0 |  | SEK0 |  |  | -8 |  | 1 | INST |  |  |  |  | 540 | [6 empty] | SEK0 | TREX
NSS-A214788150 | T-REX: Polarization Flipper: Installation preparation | 0% | 5 | 2027-03-17 | 2027-03-23 | 2026-12-17 | 2026-12-23 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | [5 empty] | 27 | [6 empty] | SEK0 | TREX
NSS-A214785370 | T-REX: Fan Chopper: TRR and integrated SAT | 0% | 10 | 2027-03-17 | 2027-04-01 | 2026-12-11 | 2027-01-07 | -58 | SEK0 | SEK0 |  | SEK0 |  |  | -58 |  | 1 | INST |  |  |  | COMM.TRR | 37 | [6 empty] | SEK0 | TREX
NSS-A214788040 | T-REX: Polarization Flipper: IRR/subTG4 (meeting) | 0% | 0 | 2027-03-17 |  | 2026-12-17 |  | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 |  |  |  |  | INST.IRR | 27 | [6 empty] | SEK0 | TREX
NSS-A214787440 | T-REX: M- Fast Chopper: IRR meeting preparation | 0% | 5 | 2027-03-24 | 2027-04-01 | 2026-12-11 | 2026-12-17 | -63 | SEK0 | SEK0 |  | SEK0 |  |  | -63 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214788050 | T-REX: Polarization Flipper: Installation (partner/supplier) | 0% | 20 | 2027-03-24 | 2027-04-22 | 2027-01-07 | 2027-02-03 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 | E01-02 | 1 | INST |  |  |  |  | 27 | [6 empty] | SEK0 | TREX
NSS-A214787450 | T-REX: M- Fast Chopper: Installation preparation | 0% | 5 | 2027-04-02 | 2027-04-08 | 2027-01-14 | 2027-01-20 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214785380 | T-REX: Fan Chopper: Integrated SAT approval | 0% | 20 | 2027-04-02 | 2027-04-29 | 2027-01-08 | 2027-02-04 | -58 | SEK0 | SEK0 |  | SEK0 |  |  | -58 | E01-02 | 1 | COMM |  |  |  | COMM.SAT | 37 | [6 empty] | SEK0 | TREX
NSS-A214785030 | T-REX: M- Fast Chopper: IRR/subTG4 (meeting) | 0% | 0 | 2027-04-02 |  | 2026-12-18 |  | -63 | SEK0 | SEK0 |  | SEK0 |  |  | -63 |  | 1 |  |  |  |  | INST.IRR | 12 | [6 empty] | SEK0 | TREX
NSS-A214784700 | T-REX: P- Fast Chopper: Local SAT | 0% | 5 | 2027-04-06 | 2027-04-12 | 2027-01-29 | 2027-02-04 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 | E01-02 | 1 | COMM |  |  |  |  | 20 | [6 empty] | SEK0 | TREX
NSS-A214784320 | T-REX:OoB Guide (151.5-163.1): Installation (partner/supplier) | 0% | 10 | 2027-04-09 | 2027-04-22 | 2027-01-21 | 2027-02-03 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 | E01-02 | 1 | INST |  |  |  |  | 27 | [6 empty] | SEK0 | TREX
NSS-A214785040 | T-REX: M- Fast Chopper: Installation (partner/supplier) | 0% | 10 | 2027-04-09 | 2027-04-22 | 2027-01-21 | 2027-02-03 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 | E01-02 | 1 | INST |  |  |  |  | 12 | [6 empty] | SEK0 | TREX
NSS-A214784710 | T-REX: P- Fast Chopper: TRR and integrated SAT | 0% | 10 | 2027-04-13 | 2027-04-26 | 2027-02-05 | 2027-02-18 | -45 | SEK0 | SEK0 | Assuming cooling water reqmt-RK | SEK0 |  |  | -45 | E01-02 | 1 | INST |  |  |  | COMM.TRR | 20 | [6 empty] | SEK0 | TREX
NSS-A214782720 | T-REX:BS:Installation E02 2 | 0% | 15 | 2027-04-13 | 2027-05-03 | 2027-03-23 | 2027-04-14 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | INST |  |  |  |  | 535 | [6 empty] | SEK0 | TREX
NSS-A214784330 | T-REX:OoB Guide (151.5-163.1): Local SAT | 0% | 5 | 2027-04-23 | 2027-04-29 | 2027-02-04 | 2027-02-10 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | COMM |  |  |  |  | 27 | [6 empty] | SEK0 | TREX
NSS-A214788060 | T-REX: Polarization Flipper: Integrated SAT | 0% | 5 | 2027-04-23 | 2027-04-29 | 2027-02-04 | 2027-02-10 | -54 | SEK0 | SEK0 | Sep 25: Refere to Notebook | SEK0 |  |  | -54 |  | 1 | COMM |  |  |  |  | 27 | [6 empty] | SEK0 | TREX
NSS-A214785060 | T-REX: M- Fast Chopper: TRR and integrated SAT | 0% | 10 | 2027-04-23 | 2027-05-10 | 2027-02-04 | 2027-02-17 | -54 | SEK0 | SEK0 | Assuming cooling water reqmt-RK | SEK0 |  |  | -54 | E01-02 | 1 | INST |  |  |  | COMM.TRR | 12 | [6 empty] | SEK0 | TREX
NSS-A214784720 | T-REX: P- Fast Chopper: Integrated SAT Approval | 0% | 20 | 2027-04-27 | 2027-05-26 | 2027-02-19 | 2027-03-18 | -45 | SEK0 | SEK0 |  | SEK0 |  |  | -45 | E01-02 | 1 | COMM |  |  |  | COMM.SAT | 20 | [6 empty] | SEK0 | TREX
NSS-A214784350 | T-REX:OoB Guide (151.5-163.1): Integrated SAT | 0% | 10 | 2027-04-30 | 2027-05-17 | 2027-02-25 | 2027-03-24 | -44 | SEK0 | SEK0 |  | SEK0 |  |  | -34 | E01-02 | 1 | COMM |  |  |  |  | 27 | [6 empty] | SEK0 | TREX
NSS-A214788080 | T-REX: Polarization Flipper: Integrated SAT Approval | 0% | 10 | 2027-04-30 | 2027-05-17 | 2027-02-25 | 2027-03-24 | -44 | SEK0 | SEK0 | Sep 25: is there any moveable component in flipper that needs mca? | SEK0 |  |  | -34 | E01-02 | 1 | COMM |  |  |  |  | 27 | [6 empty] | SEK0 | TREX
NSS-A2147354760 | T-REX: MG Det 2-4: Preparation of installation binder | 0% | 20 | 2027-04-30 | 2027-05-31 | 2027-04-30 | 31-May-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 55 | [6 empty] | SEK0 | TREX
NSS-A214782750 | T-REX:BS:Integrated SAT | 0% | 10 | 2027-05-04 | 2027-05-19 | 2027-04-15 | 2027-04-28 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | COMM |  |  |  |  | 535 | [6 empty] | SEK0 | TREX
NSS-A214785070 | T-REX: M- Fast Chopper: Integrated SAT approval | 0% | 20 | 2027-05-11 | 2027-06-07 | 2027-02-18 | 2027-03-17 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 | E01-02 | 1 | COMM |  |  |  | COMM.SAT | 12 | [6 empty] | SEK0 | TREX
NSS-A2147354770 | T-REX: MG Detector: IRR documents review by ESS | 0% | 10 | 2027-06-01 | 2027-06-14 | 2027-06-01 | 2027-06-14 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 55 | [6 empty] | SEK0 | TREX
NSS-A214786870 | T-REX: Integrated cold commissioning | 0% | 20 | 2027-06-08 | 2027-07-06 | 2027-03-25 | 2027-04-23 | -49 | SEK0 | SEK0 |  | SEK0 |  |  | -49 |  | 1 | COMM |  |  |  |  | 12 | [6 empty] | SEK0 | TREX
NSS-A214788820 | T-REX: Ready for cold Commissioning | 0% | 0 | 2027-06-08 |  | 2027-03-25 |  | -49 | SEK0 | SEK0 |  | SEK0 |  |  | -49 |  | 1 | [5 empty] | 122 | [6 empty] | SEK0 | TREX
NSS-A2147354790 | T-REX: MG Det 2-4: Installation preparation | 0% | 5 | 2027-06-17 | 2027-06-23 | 2027-06-17 | 2027-06-23 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 55 | [6 empty] | SEK0 | TREX
NSS-A2147354780 | T-REX: MG Detector: IRR/subTG4 (meeting) | 0% | 0 | 2027-06-17 |  | 2027-06-17 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 |  |  |  |  | INST.IRR | 55 | [6 empty] | SEK0 | TREX
NSS-A2147354800 | T-REX: MG Det 2-4: Installation | 0% | 15 | 2027-06-24 | 2027-07-15 | 2027-06-24 | 2027-07-15 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 55 | [6 empty] | SEK0 | TREX
NSS-A214786890 | T-REX: Preparation for TG5 review meeting (Float 2 months) | 0% | 40 | 2027-07-07 | 2027-09-28 | 2027-04-26 | 2027-06-22 | -49 | SEK0 | SEK0 |  | SEK0 |  |  | -49 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A2147354810 | T-REX: MG Detector: Local SAT | 0% | 5 | 2027-07-16 | 2027-08-19 | 2027-07-16 | 2027-08-19 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A2147354820 | T-REX: MG Det 2-4: Installation (ESS/common projects) | 0% | 10 | 2027-08-20 | 2027-09-02 | 2027-08-20 | 2027-09-02 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | INST |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A2147354830 | T-REX: MG Detector: Integrated SAT | 0% | 20 | 2027-09-03 | 2027-09-30 | 2027-09-03 | 2027-09-30 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214786910 | T-REX: TG5/SAR action closeouts and approval | 0% | 40 | 2027-09-29 | 2027-11-23 | 2027-06-23 | 2027-08-17 | -70 | SEK0 | SEK0 |  | SEK0 |  |  | -70 |  | 1 |  |  |  |  | COMM.SAR.A | 12 | [6 empty] | SEK0 | TREX
NSS-A214788870 | T-REX: All construction scope for the Instrument complete | 0% | 5 | 2027-10-01 | 2027-10-07 | 01-Oct-27 | 07-Oct-27 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | [5 empty] | 55 | [6 empty] | SEK0 | TREX
NSS-A214786930 | T-REX: Prep for i-SRR | 0% | 10 | 2027-11-24 | 2027-12-07 | 2027-08-18 | 2027-08-31 | -70 | SEK0 | SEK0 |  | SEK0 |  |  | -70 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214788310 | T-REX: Sample ex-container: FAT Report and Documentation | 0% | 12 | 06-okt-25* | 2025-10-21 | 2025-09-17 | 02-Oct-25 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | [5 empty] | 264 | [6 empty] | SEK0 | TREX
NSS-A214783930 | T-REX:OoB Guide (151.5-163.1): Detailed design | 0% | 70 | 18-Dec-25* | 2026-04-10 | 20-Oct-25 | 2026-02-06 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | Design |  |  |  |  | 47 | [6 empty] | SEK0 | TREX
NSS-A2147382610 | T-REX: Det boxes 2-4: Tendering process | 0% | 88 | 20-Nov-25* | 2026-04-08 | 2025-11-20 | 2026-04-08 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | PROC |  |  |  |  | 90 | [6 empty] | SEK0 | TREX
NSS-A2147354750 | T-REX: MG Det 2-4: Handover of the component from detector group | 0% | 0 | 30-Apr-27* |  | 2027-04-30 |  | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | PROC.DELIV |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214781670 | T-REX: IBG (HS): Installation (ESS/common projects) | 0% | 10 | 31-Jul-26* | 2026-08-13 | 20-Oct-25 | 31-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -10 | BUN D03 | 1 | INST |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214781850 | T-REX: IBG (fixed and remote): Installation (ESS/common projects) | 0% | 10 | 31-Jul-26* | 2026-08-13 | 20-Oct-25 | 31-Oct-25 | 0 | SEK0 | SEK0 | Sep 2025: Vacuum activities | SEK0 |  |  | -10 | BUN D03 | 1 | INST |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214782210 | T-REX: BBG:Installation (ESS/common projects) | 0% | 10 | 31-Jul-26* | 2026-08-13 | 20-Oct-25 | 31-Oct-25 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | -10 | BUN D03 | 1 | INST |  |  |  |  | 55 | [6 empty] | SEK0 | TREX
NSS-A214787990 | T-REX: Polarization Flipper: Arrival Inspection | 0% | 0 |  | 2026-07-13 |  | 2026-06-08 | -24 | SEK0 | SEK0 |  | SEK0 |  |  | -24 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 178 | [6 empty] | SEK0 | TREX
NSS-A214785780 | T-REX: Detector Vessel: Component delivered | 0% | 0 |  | 2026-07-14 |  | 2026-07-14 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 62 | [6 empty] | SEK0 | TREX
NSS-A214781520 | T-REX: Polarization Analyser: Arrival Inspection | 0% | 0 |  | 2026-08-21 |  | 2026-06-23 | -23 | SEK0 | SEK0 |  | SEK0 |  |  | -23 | E01-02 | 1 | PROC.DELIV |  |  |  |  | 159 | [6 empty] | SEK0 | TREX
NSS-A214785720 | T-REX: MG Detector: Local SAT | 0% | 0 |  | 2026-09-09 |  | 2026-09-09 | 0 | SEK0 | SEK0 |  | SEK0 |  |  | 0 |  | 1 | COMM |  |  |  |  | 182 | [6 empty] | SEK0 | TREX
NSS-A214783900 | T-REX:OoB Guide (96-151.5): Local SAT | 0% | 0 |  | 2026-09-25 |  | 2026-06-30 | -43 | SEK0 | SEK0 |  | SEK0 |  |  | -43 |  | 1 | COMM |  |  |  |  | 149 | [6 empty] | SEK0 | TREX
NSS-A214785150 | T-REX: Final TG3 Approval | 0% | 0 |  | 2026-10-07 |  | 2026-07-10 | -43 | SEK0 | SEK0 |  | SEK0 | Susanna_TG3 |  | -43 |  | 1 | [5 empty] | 281 | [6 empty] | SEK0 | TREX
NSS-A214785740 | T-REX: MG Detector: Integrated SAT | 0% | 0 |  | 2027-03-01 |  | 2027-02-10 | -13 | SEK0 | SEK0 |  | SEK0 |  |  | -13 |  | 1 | COMM |  |  |  |  | 68 | [6 empty] | SEK0 | TREX
NSS-A214785480 | T-REX: In-Bunker: ESS ready for CC (Integrated SAT) | 0% | 0 |  | 2027-03-04 |  | 2027-03-24 | 14 | SEK0 | SEK0 |  | SEK0 |  |  | 14 |  | 1 | [5 empty] | 75 | [6 empty] | SEK0 | TREX
NSS-A214785120 | T-REX: Final TG4 | 0% | 0 |  | 2027-04-02 |  | 2026-12-18 | -63 | SEK0 | SEK0 |  | SEK0 |  |  | -63 |  | 1 | [5 empty] | 167 | [6 empty] | SEK0 | TREX
NSS-A214785050 | T-REX: M- Fast Chopper: Local SAT | 0% | 0 |  | 2027-04-22 |  | 2027-02-03 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | COMM |  |  |  |  | 12 | [6 empty] | SEK0 | TREX
NSS-A214785490 | T-REX: Out of Bunker: Partners ready for CC (Local SAT) | 0% | 0 |  | 2027-04-29 |  | 2027-02-10 | -54 | SEK0 | SEK0 |  | SEK0 |  |  | -54 |  | 1 | [5 empty] | 37 | [6 empty] | SEK0 | TREX
NSS-A214785500 | T-REX: Out of Bunker: ESS ready for CC (Integrated SAT) | 0% | 0 |  | 2027-06-07 |  | 2027-03-24 | -49 | SEK0 | SEK0 |  | SEK0 |  |  | -49 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214786880 | T-REX: Instrument complete (TG5/SAR start) | 0% | 0 |  | 2027-07-06 |  | 2027-04-23 | -49 | SEK0 | SEK0 |  | SEK0 |  |  | -49 |  | 1 | [5 empty] | 12 | [6 empty] | SEK0 | TREX
NSS-A214786900 | T-REX: TG5/SAR meeting | 0% | 0 |  | 2027-09-28 |  | 2027-06-22 | -49 | SEK0 | SEK0 |  | SEK0 |  |  | -49 |  | 1 |  |  |  |  | COMM.SAR.M | 12 | [6 empty] | SEK0 | TREX
NSS-A214786920 | T-REX: TG5/SAR approval | 0% | 0 |  | 2027-11-23 |  | 2027-08-17 | -70 | SEK0 | SEK0 | Sep 25: Failure of chopper test and broken disk of of M-chopper (Fast chopper)- Refer notebook | SEK0 |  |  | -70 |  | 1 |  |  |  |  | Instruments.TG5 | 12 | [6 empty] | SEK0 | TREX
NSS-A214788830 | T-REX: TG5 | 0% | 0 |  | 2027-11-23 |  | 2027-08-17 | -70 | SEK0 | SEK0 |  | SEK0 |  |  | -70 |  | 1 | [5 empty] | 22 | [6 empty] | SEK0 | TREX

## CDR IRR vs replanning (hidden)
Activity ID | Activity Name | Activity % Complete | Original Duration | Budgeted Total Cost | Activity Count | Start | Finish | BL1 Start | BL1 Finish | Variance - BL1 Finish Date | Budgeted Nonlabor Cost | Budgeted Labor Cost | Earned Value Cost | Remaining Total Cost | Activity Notes | user_text8 | ESS 2023 Key Milestones | Variance - BL1 Start Date | NSS Area Code | Phase | ESS Activity Development Code | BL2 Finish | BL2 Start | ESS Milestone | Total Float | IK to Cash | In Kind | In Kind Country | In Kind Generate Cost | In Kind Planned Partner | In Kind TA status | Schedule Variance | Instrument
13-NSS-P09-25 Neutron Scattering Systems - P09-2025 Lockdown |  |  | 644 | SEK0 | 44 | 27-Aug-24 A | 2027-06-17 | 2024-08-27 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 115 | [6 empty] | SEK0
13-NSS-P09-25.1 NSS |  |  | 644 | SEK0 | 44 | 27-Aug-24 A | 2027-06-17 | 2024-08-27 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 115 | [6 empty] | SEK0
13-NSS-P09-25.1.7 NSS Instrument Construction |  |  | 644 | SEK0 | 44 | 27-Aug-24 A | 2027-06-17 | 2024-08-27 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 115 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15 Instrument T-REX |  |  | 644 | SEK0 | 44 | 27-Aug-24 A | 2027-06-17 | 2024-08-27 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 115 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2 Detail Plan |  |  | 644 | SEK0 | 44 | 27-Aug-24 A | 2027-06-17 | 2024-08-27 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 115 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.2 In-Bunker Guides |  |  | 19 | SEK0 | 2 | 27-Aug-24 A | 23-Sep-24 A | 2024-08-27 | 2024-09-23 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
13-NSS-P09-25.1.7.15.2.2.1.2.2 Guides (heavy shutter) |  |  | 0 | SEK0 | 1 | 27-Aug-24 A | 27-Aug-24 A | 2024-08-27 | 2024-08-27 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214781640 | T-REX: IBG (HS): IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 27-Aug-24 A |  | 2024-08-27 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.2.1.2.3 Guides (fixed and remote handling) |  |  | 0 | SEK0 | 1 | 23-Sep-24 A | 23-Sep-24 A | 2024-09-23 | 2024-09-23 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214781820 | T-REX: IBG (fixed and remote):IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 23-Sep-24 A |  | 2024-09-23 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.3 Heavy Shutter |  |  | 0 | SEK0 | 1 | 20-Sep-24 A | 20-Sep-24 A | 2024-09-20 | 2024-09-20 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [13 empty] | SEK0
NSS-A214782440 | T-REX:HS:IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 20-Sep-24 A |  | 2024-09-20 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | [7 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.5 Out of Bunker Guides |  |  | 432 | SEK0 | 8 | 26-Feb-25 A | 2027-02-03 | 2025-02-26 | 2026-09-15 | -91 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 67 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.5.1.5.1 Guides section 1 (40 - 96 m) |  |  | 73 | SEK0 | 2 | 25-Sep-25 A | 2026-01-20 | 2025-12-17 | 2025-12-17 | -14 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 59 | [6 empty] | 290 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.5.1.5.1.1 Guides section 1 A (40 - 96 m) |  |  | 0 | SEK0 | 1 | 25-Sep-25 A | 25-Sep-25 A | 2025-12-17 | 2025-12-17 | 59 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 59 | [13 empty] | SEK0
NSS-A214783080 | T-REX: OoB Guide 1 A: IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 25-Sep-25 A |  | 2025-12-17 |  | 59 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 59 | [5 empty] | INST.IRR | [7 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.5.1.5.1.2 Guides section 1 B (40 - 96 m) |  |  | 0 | SEK0 | 1 | 2026-01-20 | 2026-01-20 |  |  |  | SEK0 | SEK0 | SEK0 | SEK0 | [10 empty] | 287 | [6 empty] | SEK0
NSS-A2147409930 | T-REX: OoB Guide 1 B: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-20 |  |  |  |  | SEK0 | SEK0 | SEK0 | SEK0 | [9 empty] | INST.IRR | 287 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.5.1.5.2 Guides section 2 (28 - 40 m) |  |  | 218 | SEK0 | 2 | 26-Feb-25 A | 2026-02-18 | 2025-02-26 | 2026-01-29 | -14 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 219 | [6 empty] | SEK0
NSS-A214783390 | T-REX:OoB Guide (28-40): CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 26-Feb-25 A |  | 2025-02-26 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | TREX
NSS-A214783480 | T-REX:OoB Guide (28-40): IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-02-18 |  | 2026-01-29 |  | -14 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -14 | [5 empty] | INST.IRR | 219 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.5.1.5.3 Guides section 3 (96 - 151.5 m) |  |  | 124 | SEK0 | 2 | 2025-12-11 | 2026-06-25 | 2025-06-02 | 2026-01-29 | -99 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -116 | [6 empty] | 166 | [6 empty] | SEK0
NSS-A214783790 | T-REX:OoB Guide (96-151.5): CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-11 |  | 2025-06-02 |  | -116 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -116 | [5 empty] | ENG.CDR | 47 | [6 empty] | SEK0 | TREX
NSS-A214783880 | T-REX:OoB Guide (96-151.5): IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-06-25 |  | 2026-01-29 |  | -99 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -99 | [5 empty] | INST.IRR | 166 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.5.1.5.4 Guides section 4 (151.5 - 163.1) |  |  | 138 | SEK0 | 2 | 2026-06-11 | 2027-02-03 | 2025-12-17 | 2026-09-15 | -91 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -111 | [6 empty] | 67 | [6 empty] | SEK0
NSS-A214784220 | T-REX:OoB Guide (151.5-163.1): CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-06-11 |  | 2025-12-17 |  | -111 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -111 | [5 empty] | ENG.CDR | 47 | [6 empty] | SEK0 | TREX
NSS-A214784310 | T-REX:OoB Guide (151.5-163.1): IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-02-03 |  | 2026-09-15 |  | -91 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -91 | [5 empty] | INST.IRR | 67 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.6 Choppers |  |  | 305 | SEK0 | 6 | 2025-11-25 | 2027-04-02 | 2025-04-01 | 2026-09-21 | -127 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -143 | [6 empty] | 12 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.6.1.6.1 Fast Choppers |  |  | 18 | SEK0 | 2 | 2027-03-05 | 2027-04-02 | 2026-02-24 | 06-May-26 | -202 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -232 | [6 empty] | 12 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.6.1.6.1.1.6.1.1 P-Chopper |  |  | 0 | SEK0 | 1 | 2027-03-05 | 2027-03-05 | 2026-02-24 | 2026-02-24 | -232 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -232 | [6 empty] | 20 | [6 empty] | SEK0
NSS-A214784680 | T-REX: P- Fast Chopper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-03-05 |  | 2026-02-24 |  | -232 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -232 | [5 empty] | INST.IRR | 20 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.6.1.6.1.1.6.1.2 M-Chopper |  |  | 0 | SEK0 | 1 | 2027-04-02 | 2027-04-02 | 06-May-26 | 06-May-26 | -202 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -202 | [6 empty] | 12 | [6 empty] | SEK0
NSS-A214785030 | T-REX: M- Fast Chopper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-04-02 |  | 06-May-26 |  | -202 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -202 | [5 empty] | INST.IRR | 12 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.6.1.6.2 Fan Chopper |  |  | 224 | SEK0 | 2 | 2025-12-16 | 2026-12-15 | 2025-04-14 | 2026-09-01 | -75 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -149 | [6 empty] | 73 | [6 empty] | SEK0
NSS-A214785240 | T-REX: Fan Chopper:CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-16 |  | 2025-04-14 |  | -149 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -149 | [5 empty] | ENG.CDR | 73 | [6 empty] | SEK0 | TREX
NSS-A214785340 | T-REX: Fan Chopper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-12-15 |  | 2026-09-01 |  | -75 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -75 | [5 empty] | INST.IRR | 73 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.6.1.6.3 Background Chopper |  |  | 240 | SEK0 | 2 | 2025-11-25 | 2026-12-16 | 2025-04-01 | 2026-09-21 | -62 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -143 | [6 empty] | 65 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.6.1.6.3.1.6.3.1 Chopper Disks and Housing |  |  | 0 | SEK0 | 1 | 2025-11-25 | 2025-11-25 | 2025-04-01 | 2025-04-01 | -143 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -143 | [6 empty] | 65 | [6 empty] | SEK0
NSS-A214785530 | T-REX: BG Chopper (Disk & Housing): CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-11-25 |  | 2025-04-01 |  | -143 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -143 | [5 empty] | ENG.CDR | 65 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.6.1.6.3.1.6.3.2 Chopper Common Project (Spindles, Electronics, etc) |  |  | 0 | SEK0 | 1 | 2026-12-16 | 2026-12-16 | 2026-09-21 | 2026-09-21 | -62 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -62 | [6 empty] | 65 | [6 empty] | SEK0
NSS-A214785920 | T-REX: Com Chop: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-12-16 |  | 2026-09-21 |  | -62 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -62 | [5 empty] | INST.IRR | 65 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.7 Cave |  |  | 314 | SEK0 | 2 | 08-Nov-24 A | 2026-03-31 | 2024-11-08 | 2025-12-22 | -61 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 62 | [6 empty] | SEK0
NSS-A214786050 | T-REX: Cave: CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 08-Nov-24 A |  | 2024-11-08 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | TREX
NSS-A214786150 | T-REX: Cave: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-03-31 |  | 2025-12-22 |  | -61 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -61 | [5 empty] | INST.IRR | 62 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.8 Polarization Equipment |  |  | 296 | SEK0 | 9 | 2025-11-24 | 2027-03-17 | 2025-04-30 | 2026-09-04 | -128 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -123 | [6 empty] | 27 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.8.1.8.1 Cold |  |  | 0 | SEK0 | 1 | 2026-11-18 | 2026-11-18 | 2026-09-04 | 2026-09-04 | -53 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -53 | [6 empty] | 92 | [6 empty] | SEK0
NSS-A214786560 | T-REX: Cold Polarization: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-11-18 |  | 2026-09-04 |  | -53 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -53 | [5 empty] | INST.IRR | 92 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.8.1.8.2 Thermal |  |  | 227 | SEK0 | 2 | 2025-11-24 | 2026-11-26 | 2025-04-30 | 2026-06-11 | -99 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -123 | [6 empty] | 88 | [6 empty] | SEK0
NSS-A214786690 | T-REX: Thermal Polarization: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-11-24 |  | 2025-04-30 |  | -123 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -123 | [5 empty] | ENG.CDR | 88 | [6 empty] | SEK0 | TREX
NSS-A214786780 | T-REX: Thermal Polarization: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-11-26 |  | 2026-06-11 |  | -99 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -99 | [5 empty] | INST.IRR | 88 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.8.1.8.3 Translation Table |  |  | 181 | SEK0 | 2 | 2025-12-15 | 14-Oct-26 | 01-Oct-25 | 2026-07-03 | -53 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -53 | [6 empty] | 92 | [6 empty] | SEK0
NSS-A214781260 | T-REX: Translation Table: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 14-Oct-26 |  | 2026-07-03 |  | -53 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -53 | [5 empty] | INST.IRR | 92 | [6 empty] | SEK0 | TREX
NSS-A214786840 | T-REX: Translation Table: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-15 |  | 01-Oct-25 |  | -53 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -53 | [5 empty] | ENG.CDR | 92 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.8.1.8.4 Analyzer |  |  | 200 | SEK0 | 2 | 2025-12-19 | 2026-11-16 | 06-May-25 | 2026-04-27 | -121 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -139 | [6 empty] | 94 | [6 empty] | SEK0
NSS-A214781480 | T-REX: Polarization Analyser: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-19 |  | 06-May-25 |  | -139 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -139 | [5 empty] | ENG.CDR | 94 | [6 empty] | SEK0 | TREX
NSS-A214781570 | T-REX: Polarization Analyser: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-11-16 |  | 2026-04-27 |  | -121 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -121 | [5 empty] | INST.IRR | 94 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.8.1.8.41 Flipper |  |  | 281 | SEK0 | 2 | 2025-12-15 | 2027-03-17 | 07-May-25 | 2026-09-01 | -131 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -134 | [6 empty] | 27 | [6 empty] | SEK0
NSS-A214787950 | T-REX: Polarization Flipper: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-15 |  | 07-May-25 |  | -134 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -134 | [5 empty] | ENG.CDR | 113 | [6 empty] | SEK0 | TREX
NSS-A214788040 | T-REX: Polarization Flipper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-03-17 |  | 2026-09-01 |  | -131 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -131 | [5 empty] | INST.IRR | 27 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.9 Detector Vessel |  |  | 277 | SEK0 | 5 | 30-Apr-25 A | 2026-09-23 | 09-May-25 | 2026-06-12 | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 6 | [6 empty] | 122 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.9.1.9.1 Vessel |  |  | 0 | SEK0 | 1 | 2026-07-08 | 2026-07-08 | 2026-04-21 | 2026-04-21 | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [6 empty] | 62 | [6 empty] | SEK0
NSS-A214788190 | T-REX: Detector Vessel: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-07-08 |  | 2026-04-21 |  | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [5 empty] | INST.IRR | 62 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.9.1.9.2 False floor + detector support |  |  | 0 | SEK0 | 1 | 2026-08-26 | 2026-08-26 | 13-May-26 | 13-May-26 | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [6 empty] | 117 | [6 empty] | SEK0
NSS-A214782310 | T-REX: False floor and Det supp: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-08-26 |  | 13-May-26 |  | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [5 empty] | INST.IRR | 117 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.9.1.9.3 Radial collimator (drive) |  |  | 0 | SEK0 | 1 | 2026-09-09 | 2026-09-09 | 29-May-26 | 29-May-26 | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [6 empty] | 117 | [6 empty] | SEK0
NSS-A214782630 | T-REX: RC Drive: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-09-09 |  | 29-May-26 |  | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [5 empty] | INST.IRR | 117 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.9.1.9.5 Cadmium shielding |  |  | 277 | SEK0 | 2 | 30-Apr-25 A | 2026-09-23 | 09-May-25 | 2026-06-12 | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 6 | [6 empty] | 122 | [6 empty] | SEK0
NSS-A214783190 | T-REX: Cd Shielding: CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 30-Apr-25 A |  | 09-May-25 |  | 6 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 6 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | TREX
NSS-A214783280 | T-REX: Cd Shielding: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-09-23 |  | 2026-06-12 |  | -52 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -52 | [5 empty] | INST.IRR | 122 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.10 Primary Collimator & Slits |  |  | 212 | SEK0 | 2 | 2026-01-08 | 2026-12-08 | 2025-06-26 | 2026-07-08 | -89 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -110 | [6 empty] | 58 | [6 empty] | SEK0
NSS-A214783570 | T-REX: Primary Coll & Slits: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-08 |  | 2025-06-26 |  | -110 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -110 | [5 empty] | ENG.CDR | 59 | [6 empty] | SEK0 | TREX
NSS-A214788490 | T-REX: Primary Coll & Slits: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-12-08 |  | 2026-07-08 |  | -89 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -89 | [5 empty] | INST.IRR | 58 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.11 (Secondary) Radial Collimator (Blades) |  |  | 247 | SEK0 | 2 | 22-Apr-25 A | 28-May-26 | 2025-03-14 | 2026-06-18 | 15 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -25 | [6 empty] | 190 | [6 empty] | SEK0
NSS-A214783980 | T-REX: Secondary RC: CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 22-Apr-25 A |  | 2025-03-14 |  | -25 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -25 | [5 empty] | ENG.CDR | [7 empty] | SEK0 | TREX
NSS-A214784110 | T-REX: Secondary RC: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 28-May-26 |  | 2026-06-18 |  | 15 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 15 | [5 empty] | INST.IRR | 190 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.12 Beamstop |  |  | 177 | SEK0 | 2 | 2026-01-14 | 26-Oct-26 | 27-May-25 | 2026-03-18 | -132 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -132 | [6 empty] | 107 | [6 empty] | SEK0
NSS-A214784420 | T-REX: Beamstop: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-14 |  | 27-May-25 |  | -132 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -132 | [5 empty] | ENG.CDR | 107 | [6 empty] | SEK0 | TREX
NSS-A214784510 | T-REX: Beamstop: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 26-Oct-26 |  | 2026-03-18 |  | -132 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -132 | [5 empty] | INST.IRR | 107 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.13 Neutron Detector |  |  | 0 | SEK0 | 1 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 55 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.13.1.13.3 Detector |  |  | 0 | SEK0 | 1 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 55 | [6 empty] | SEK0
13-NSS-P09-25.1.7.15.2.13.1.13.3.1.13.3.41 MG T-REX 2-4 |  |  | 0 | SEK0 | 1 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [6 empty] | 55 | [6 empty] | SEK0
NSS-A2147354780 | T-REX: MG Detector: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-06-17 |  | 2027-06-17 |  | 0 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | 0 | [5 empty] | INST.IRR | 55 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.15 Control & Sample Hutch |  |  | 174 | SEK0 | 2 | 17-Oct-25 | 2026-07-10 | 2025-09-22 | 2026-06-12 | -19 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -19 | [6 empty] | 167 | [6 empty] | SEK0
NSS-A214786360 | T-REX: Control Hutch: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 17-Oct-25 |  | 2025-09-22 |  | -19 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -19 | [5 empty] | ENG.CDR | 167 | [6 empty] | SEK0 | TREX
NSS-A214786510 | T-REX: Control Hutch: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-07-10 |  | 2026-06-12 |  | -19 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -19 | [5 empty] | INST.IRR | 167 | [6 empty] | SEK0 | TREX
13-NSS-P09-25.1.7.15.2.16 Sample Environment |  |  | 162 | SEK0 | 2 | 2026-01-14 | 05-Oct-26 | 23-Oct-25 | 2026-06-30 | -49 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -49 | [6 empty] | 129 | [6 empty] | SEK0
NSS-A214781060 | T-REX: Sample Environment: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-14 |  | 23-Oct-25 |  | -49 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -49 | [5 empty] | ENG.CDR | 129 | [6 empty] | SEK0 | TREX
NSS-A214781150 | T-REX: Sample Environment: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 05-Oct-26 |  | 2026-06-30 |  | -49 | SEK0 | SEK0 | SEK0 | SEK0 |  |  |  | -49 | [5 empty] | INST.IRR | 129 | [6 empty] | SEK0 | TREX

## CDR IRR FAT vs replanning (hidden)
Activity ID | Activity Name | Activity % Complete | Original Duration | Budgeted Total Cost | Activity Count | Start | Finish | BL1 Start | BL1 Finish | Variance - BL1 Finish Date | Variance (months) | ESS Milestone
13-NSS-P09-25 Neutron Scattering Systems - P09-2025 Lockdown |  |  | 655 | SEK0 | 70 | 12-Aug-24 A | 2027-06-17 | 2024-08-12 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1 NSS |  |  | 655 | SEK0 | 70 | 12-Aug-24 A | 2027-06-17 | 2024-08-12 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1.7 NSS Instrument Construction |  |  | 655 | SEK0 | 70 | 12-Aug-24 A | 2027-06-17 | 2024-08-12 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1.7.15 Instrument T-REX |  |  | 655 | SEK0 | 70 | 12-Aug-24 A | 2027-06-17 | 2024-08-12 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1.7.15.2 Detail Plan |  |  | 655 | SEK0 | 70 | 12-Aug-24 A | 2027-06-17 | 2024-08-12 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1.7.15.2.2 In-Bunker Guides |  |  | 30 | SEK0 | 3 | 12-Aug-24 A | 23-Sep-24 A | 2024-08-12 | 2024-09-23 | 0 | 0
13-NSS-P09-25.1.7.15.2.2.1.2.2 Guides (heavy shutter) |  |  | 0 | SEK0 | 1 | 27-Aug-24 A | 27-Aug-24 A | 2024-08-27 | 2024-08-27 | 0 | 0
NSS-A214781640 | T-REX: IBG (HS): IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 27-Aug-24 A |  | 2024-08-27 |  | 0 | 0 | INST.IRR
13-NSS-P09-25.1.7.15.2.2.1.2.3 Guides (fixed and remote handling) |  |  | 30 | SEK0 | 2 | 12-Aug-24 A | 23-Sep-24 A | 2024-08-12 | 2024-09-23 | 0 | 0
NSS-A214781750 | T-REX: IBG (fixed and remote):Factory Acceptance Test (FAT) | 100% | 0 | SEK0 | 1 | 12-Aug-24 A |  | 2024-08-12 |  | 0 | 0 | PROC.FAT
NSS-A214781820 | T-REX: IBG (fixed and remote):IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 23-Sep-24 A |  | 2024-09-23 |  | 0 | 0 | INST.IRR
13-NSS-P09-25.1.7.15.2.3 Heavy Shutter |  |  | 0 | SEK0 | 1 | 20-Sep-24 A | 20-Sep-24 A | 2024-09-20 | 2024-09-20 | 0 | 0
NSS-A214782440 | T-REX:HS:IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 20-Sep-24 A |  | 2024-09-20 |  | 0 | 0 | INST.IRR
13-NSS-P09-25.1.7.15.2.5 Out of Bunker Guides |  |  | 432 | SEK0 | 13 | 26-Feb-25 A | 2027-02-03 | 2025-02-26 | 2026-09-15 | -91 | -4.55
13-NSS-P09-25.1.7.15.2.5.1.5.1 Guides section 1 (40 - 96 m) |  |  | 101 | SEK0 | 4 | 18-Aug-25 A | 2026-01-20 | 2025-09-08 | 2025-12-17 | -14 | -0.7
13-NSS-P09-25.1.7.15.2.5.1.5.1.1 Guides section 1 A (40 - 96 m) |  |  | 28 | SEK0 | 2 | 18-Aug-25 A | 25-Sep-25 A | 2025-09-08 | 2025-12-17 | 59 | 2.95
NSS-A214783010 | T-REX: OoB Guide 1 A: FAT | 100% | 0 | SEK0 | 1 | 18-Aug-25 A |  | 2025-09-08 |  | 15 | 0.75 | PROC.FAT
NSS-A214783080 | T-REX: OoB Guide 1 A: IRR/subTG4 (meeting) | 100% | 0 | SEK0 | 1 | 25-Sep-25 A |  | 2025-12-17 |  | 59 | 2.95 | INST.IRR
13-NSS-P09-25.1.7.15.2.5.1.5.1.2 Guides section 1 B (40 - 96 m) |  |  | 30 | SEK0 | 2 | 2025-11-25 | 2026-01-20 |  |  |  | 0
NSS-A2147409830 | T-REX: OoB Guide 1 B: FAT | 0% | 0 | SEK0 | 1 | 2025-11-25 |  |  |  |  | 0 | PROC.FAT
NSS-A2147409930 | T-REX: OoB Guide 1 B: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-20 |  |  |  |  | 0 | INST.IRR
13-NSS-P09-25.1.7.15.2.5.1.5.2 Guides section 2 (28 - 40 m) |  |  | 218 | SEK0 | 3 | 26-Feb-25 A | 2026-02-18 | 2025-02-26 | 2026-01-29 | -14 | -0.7
NSS-A214783390 | T-REX:OoB Guide (28-40): CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 26-Feb-25 A |  | 2025-02-26 |  | 0 | 0 | ENG.CDR
NSS-A214783410 | T-REX:OoB Guide (28-40): Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2025-11-06 |  | 17-Oct-25 |  | -14 | -0.7 | PROC.FAT
NSS-A214783480 | T-REX:OoB Guide (28-40): IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-02-18 |  | 2026-01-29 |  | -14 | -0.7 | INST.IRR
13-NSS-P09-25.1.7.15.2.5.1.5.3 Guides section 3 (96 - 151.5 m) |  |  | 124 | SEK0 | 3 | 2025-12-11 | 2026-06-25 | 2025-06-02 | 2026-01-29 | -99 | -4.95
NSS-A214783790 | T-REX:OoB Guide (96-151.5): CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-11 |  | 2025-06-02 |  | -116 | -5.8 | ENG.CDR
NSS-A214783810 | T-REX:OoB Guide (96-151.5): Factory Acceptance Test (FAT) Part 1 | 0% | 0 | SEK0 | 1 | 2026-03-16 |  | 2025-09-26 |  | -111 | -5.55 | PROC.FAT
NSS-A214783880 | T-REX:OoB Guide (96-151.5): IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-06-25 |  | 2026-01-29 |  | -99 | -4.95 | INST.IRR
13-NSS-P09-25.1.7.15.2.5.1.5.4 Guides section 4 (151.5 - 163.1) |  |  | 138 | SEK0 | 3 | 2026-06-11 | 2027-02-03 | 2025-12-17 | 2026-09-15 | -91 | -4.55
NSS-A214784220 | T-REX:OoB Guide (151.5-163.1): CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-06-11 |  | 2025-12-17 |  | -111 | -5.55 | ENG.CDR
NSS-A214784240 | T-REX:OoB Guide (151.5-163.1): Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 01-Oct-26 |  | 2026-04-23 |  | -91 | -4.55 | PROC.FAT
NSS-A214784310 | T-REX:OoB Guide (151.5-163.1): IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-02-03 |  | 2026-09-15 |  | -91 | -4.55 | INST.IRR
13-NSS-P09-25.1.7.15.2.6 Choppers |  |  | 305 | SEK0 | 11 | 2025-11-25 | 2027-04-02 | 2025-04-01 | 2026-09-21 | -127 | -6.35
13-NSS-P09-25.1.7.15.2.6.1.6.1 Fast Choppers |  |  | 93 | SEK0 | 4 | 2026-11-06 | 2027-04-02 | 2025-09-23 | 06-May-26 | -202 | -10.1
13-NSS-P09-25.1.7.15.2.6.1.6.1.1.6.1.1 P-Chopper |  |  | 64 | SEK0 | 2 | 2026-11-23 | 2027-03-05 | 2025-09-23 | 2026-02-24 | -232 | -11.6
NSS-A214784610 | T-REX: P- Fast Chopper: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-11-23 |  | 2025-09-23 |  | -268 | -13.4 | PROC.FAT
NSS-A214784680 | T-REX: P- Fast Chopper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-03-05 |  | 2026-02-24 |  | -232 | -11.6 | INST.IRR
13-NSS-P09-25.1.7.15.2.6.1.6.1.1.6.1.2 M-Chopper |  |  | 93 | SEK0 | 2 | 2026-11-06 | 2027-04-02 | 2025-12-19 | 06-May-26 | -202 | -10.1
NSS-A214784960 | T-REX: M- Fast Chopper: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-11-06 |  | 2025-12-19 |  | -194 | -9.7 | PROC.FAT
NSS-A214785030 | T-REX: M- Fast Chopper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-04-02 |  | 06-May-26 |  | -202 | -10.1 | INST.IRR
13-NSS-P09-25.1.7.15.2.6.1.6.2 Fan Chopper |  |  | 224 | SEK0 | 3 | 2025-12-16 | 2026-12-15 | 2025-04-14 | 2026-09-01 | -75 | -3.75
NSS-A214785240 | T-REX: Fan Chopper:CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-16 |  | 2025-04-14 |  | -149 | -7.45 | ENG.CDR
NSS-A214785270 | T-REX: Fan Chopper: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-09-01 |  | 2026-04-15 |  | -75 | -3.75 | PROC.FAT
NSS-A214785340 | T-REX: Fan Chopper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-12-15 |  | 2026-09-01 |  | -75 | -3.75 | INST.IRR
13-NSS-P09-25.1.7.15.2.6.1.6.3 Background Chopper |  |  | 240 | SEK0 | 4 | 2025-11-25 | 2026-12-16 | 2025-04-01 | 2026-09-21 | -62 | -3.1
13-NSS-P09-25.1.7.15.2.6.1.6.3.1.6.3.1 Chopper Disks and Housing |  |  | 70 | SEK0 | 2 | 2025-11-25 | 2026-03-17 | 2025-04-01 | 2025-12-05 | -62 | -3.1
NSS-A214785530 | T-REX: BG Chopper (Disk & Housing): CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-11-25 |  | 2025-04-01 |  | -143 | -7.15 | ENG.CDR
NSS-A214785560 | T-REX: BG Chopper (Disk & Housing): Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-03-17 |  | 2025-12-05 |  | -62 | -3.1 | PROC.FAT
13-NSS-P09-25.1.7.15.2.6.1.6.3.1.6.3.2 Chopper Common Project (Spindles, Electronics, etc) |  |  | 89 | SEK0 | 2 | 2026-07-16 | 2026-12-16 | 2026-04-15 | 2026-09-21 | -62 | -3.1
NSS-A214785850 | T-REX: Com Chop: Factory Acceptance Test (FAT) | 0% | 22 | SEK0 | 1 | 2026-07-16 | 2026-09-11 | 2026-04-15 | 19-May-26 | -62 | -3.1 | PROC.FAT
NSS-A214785920 | T-REX: Com Chop: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-12-16 |  | 2026-09-21 |  | -62 | -3.1 | INST.IRR
13-NSS-P09-25.1.7.15.2.7 Cave |  |  | 314 | SEK0 | 3 | 08-Nov-24 A | 2026-03-31 | 2024-11-08 | 2025-12-22 | -61 | -3.05
NSS-A214786050 | T-REX: Cave: CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 08-Nov-24 A |  | 2024-11-08 |  | 0 | 0 | ENG.CDR
NSS-A214786150 | T-REX: Cave: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-03-31 |  | 2025-12-22 |  | -61 | -3.05 | INST.IRR
NSS-A214787660 | T-REX: Cave: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-01-27 |  | 2025-09-30 |  | -75 | -3.75 | PROC.FAT
13-NSS-P09-25.1.7.15.2.8 Polarization Equipment |  |  | 296 | SEK0 | 13 | 2025-11-24 | 2027-03-17 | 2025-04-30 | 2026-09-04 | -128 | -6.4
13-NSS-P09-25.1.7.15.2.8.1.8.1 Cold |  |  | 0 | SEK0 | 1 | 2026-11-18 | 2026-11-18 | 2026-09-04 | 2026-09-04 | -53 | -2.65
NSS-A214786560 | T-REX: Cold Polarization: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-11-18 |  | 2026-09-04 |  | -53 | -2.65 | INST.IRR
13-NSS-P09-25.1.7.15.2.8.1.8.2 Thermal |  |  | 227 | SEK0 | 3 | 2025-11-24 | 2026-11-26 | 2025-04-30 | 2026-06-11 | -99 | -4.95
NSS-A214786690 | T-REX: Thermal Polarization: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-11-24 |  | 2025-04-30 |  | -123 | -6.15 | ENG.CDR
NSS-A214786780 | T-REX: Thermal Polarization: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-11-26 |  | 2026-06-11 |  | -99 | -4.95 | INST.IRR
NSS-A214787750 | T-REX: Thermal Polarization: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-06-15 |  | 2026-01-20 |  | -99 | -4.95 | PROC.FAT
13-NSS-P09-25.1.7.15.2.8.1.8.3 Translation Table |  |  | 181 | SEK0 | 3 | 2025-12-15 | 14-Oct-26 | 01-Oct-25 | 2026-07-03 | -53 | -2.65
NSS-A214781260 | T-REX: Translation Table: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 14-Oct-26 |  | 2026-07-03 |  | -53 | -2.65 | INST.IRR
NSS-A214786840 | T-REX: Translation Table: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-15 |  | 01-Oct-25 |  | -53 | -2.65 | ENG.CDR
NSS-A214787770 | T-REX: Translation Table: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-06-10 |  | 2026-03-20 |  | -53 | -2.65 | PROC.FAT
13-NSS-P09-25.1.7.15.2.8.1.8.4 Analyzer |  |  | 200 | SEK0 | 3 | 2025-12-19 | 2026-11-16 | 06-May-25 | 2026-04-27 | -121 | -6.05
NSS-A214781480 | T-REX: Polarization Analyser: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-19 |  | 06-May-25 |  | -139 | -6.95 | ENG.CDR
NSS-A214781570 | T-REX: Polarization Analyser: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-11-16 |  | 2026-04-27 |  | -121 | -6.05 | INST.IRR
NSS-A214787870 | T-REX: Polarization Analyser: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-06-22 |  | 2025-12-11 |  | -121 | -6.05 | PROC.FAT
13-NSS-P09-25.1.7.15.2.8.1.8.41 Flipper |  |  | 281 | SEK0 | 3 | 2025-12-15 | 2027-03-17 | 07-May-25 | 2026-09-01 | -131 | -6.55
NSS-A214787950 | T-REX: Polarization Flipper: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2025-12-15 |  | 07-May-25 |  | -134 | -6.7 | ENG.CDR
NSS-A214788040 | T-REX: Polarization Flipper: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-03-17 |  | 2026-09-01 |  | -131 | -6.55 | INST.IRR
NSS-A214788110 | T-REX: Polarization Flipper: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-06-08 |  | 2025-12-05 |  | -116 | -5.8 | PROC.FAT
13-NSS-P09-25.1.7.15.2.9 Detector Vessel |  |  | 447 | SEK0 | 9 | 24-Sep-24 A | 2026-09-23 | 2024-09-24 | 2026-06-12 | -52 | -2.6
13-NSS-P09-25.1.7.15.2.9.1.9.1 Vessel |  |  | 0 | SEK0 | 1 | 2026-07-08 | 2026-07-08 | 2026-04-21 | 2026-04-21 | -52 | -2.6
NSS-A214788190 | T-REX: Detector Vessel: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-07-08 |  | 2026-04-21 |  | -52 | -2.6 | INST.IRR
13-NSS-P09-25.1.7.15.2.9.1.9.2 False floor + detector support |  |  | 427 | SEK0 | 2 | 24-Sep-24 A | 2026-08-26 | 2024-09-24 | 13-May-26 | -52 | -2.6
NSS-A214782310 | T-REX: False floor and Det supp: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-08-26 |  | 13-May-26 |  | -52 | -2.6 | INST.IRR
NSS-A214788200 | T-REX: False floor and Det supp: Factory Acceptance Test (FAT) | 100% | 0 | SEK0 | 1 | 24-Sep-24 A |  | 2024-09-24 |  | 0 | 0 | PROC.FAT
13-NSS-P09-25.1.7.15.2.9.1.9.3 Radial collimator (drive) |  |  | 293 | SEK0 | 2 | 02-May-25 A | 2026-09-09 | 2025-12-10 | 29-May-26 | -52 | -2.6
NSS-A214782630 | T-REX: RC Drive: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-09-09 |  | 29-May-26 |  | -52 | -2.6 | INST.IRR
NSS-A214788250 | T-REX: RC Drive: Factory Acceptance Test (FAT) | 100% | 0 | SEK0 | 1 | 02-May-25 A |  | 2025-12-10 |  | 134 | 6.7 | PROC.FAT
13-NSS-P09-25.1.7.15.2.9.1.9.4 Sample exchange container |  |  | 0 | SEK0 | 1 | 06-Oct-25 | 06-Oct-25 | 2025-08-19 | 2025-08-19 | -34 | -1.7
NSS-A214788300 | T-REX: Sample ex-container: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 06-Oct-25 |  | 2025-08-19 |  | -34 | -1.7 | PROC.FAT
13-NSS-P09-25.1.7.15.2.9.1.9.5 Cadmium shielding |  |  | 277 | SEK0 | 3 | 30-Apr-25 A | 2026-09-23 | 09-May-25 | 2026-06-12 | -52 | -2.6
NSS-A214783190 | T-REX: Cd Shielding: CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 30-Apr-25 A |  | 09-May-25 |  | 6 | 0.3 | ENG.CDR
NSS-A214783280 | T-REX: Cd Shielding: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-09-23 |  | 2026-06-12 |  | -52 | -2.6 | INST.IRR
NSS-A214788370 | T-REX: Cd Shielding: Factory Acceptance Test (FAT) | 0% | 5 | SEK0 | 1 | 2026-04-23 | 2026-04-29 | 2025-11-25 | 2025-12-01 | -95 | -4.75 | PROC.FAT
13-NSS-P09-25.1.7.15.2.10 Primary Collimator & Slits |  |  | 212 | SEK0 | 3 | 2026-01-08 | 2026-12-08 | 2025-06-26 | 2026-07-08 | -89 | -4.45
NSS-A214783570 | T-REX: Primary Coll & Slits: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-08 |  | 2025-06-26 |  | -110 | -5.5 | ENG.CDR
NSS-A214788440 | T-REX: Primary Coll & Slits: Factory Acceptance Test (FAT) | 0% | 5 | SEK0 | 1 | 2026-08-17 | 2026-08-21 | 2026-03-09 | 2026-03-13 | -89 | -4.45 | PROC.FAT
NSS-A214788490 | T-REX: Primary Coll & Slits: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-12-08 |  | 2026-07-08 |  | -89 | -4.45 | INST.IRR
13-NSS-P09-25.1.7.15.2.11 (Secondary) Radial Collimator (Blades) |  |  | 247 | SEK0 | 3 | 22-Apr-25 A | 28-May-26 | 2025-03-14 | 2026-06-18 | 15 | 0.75
NSS-A214783980 | T-REX: Secondary RC: CDR/subTG3 (meeting) | 100% | 0 | SEK0 | 1 | 22-Apr-25 A |  | 2025-03-14 |  | -25 | -1.25 | ENG.CDR
NSS-A214784110 | T-REX: Secondary RC: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 28-May-26 |  | 2026-06-18 |  | 15 | 0.75 | INST.IRR
NSS-A214788520 | T-REX: Secondary RC: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2025-11-07 |  | 2025-11-28 |  | 15 | 0.75 | PROC.FAT
13-NSS-P09-25.1.7.15.2.12 Beamstop |  |  | 177 | SEK0 | 3 | 2026-01-14 | 26-Oct-26 | 27-May-25 | 2026-03-18 | -132 | -6.6
NSS-A214784420 | T-REX: Beamstop: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-14 |  | 27-May-25 |  | -132 | -6.6 | ENG.CDR
NSS-A214784510 | T-REX: Beamstop: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 26-Oct-26 |  | 2026-03-18 |  | -132 | -6.6 | INST.IRR
NSS-A214788590 | T-REX: Beamstop: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-06-23 |  | 2025-11-27 |  | -132 | -6.6 | PROC.FAT
13-NSS-P09-25.1.7.15.2.13 Neutron Detector |  |  | 87 | SEK0 | 2 | 2027-02-10 | 2027-06-17 | 2026-08-31 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1.7.15.2.13.1.13.21 Detector Boxs 2-4 |  |  | 0 | SEK0 | 1 | 2027-02-10 | 2027-02-10 | 2026-08-31 | 2026-08-31 | -107 | -5.35
NSS-A2147382580 | T-REX: Det boxes 2-4: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2027-02-10 |  | 2026-08-31 |  | -107 | -5.35 | PROC.FAT
13-NSS-P09-25.1.7.15.2.13.1.13.3 Detector |  |  | 0 | SEK0 | 1 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 0 | 0
13-NSS-P09-25.1.7.15.2.13.1.13.3.1.13.3.41 MG T-REX 2-4 |  |  | 0 | SEK0 | 1 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 2027-06-17 | 0 | 0
NSS-A2147354780 | T-REX: MG Detector: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2027-06-17 |  | 2027-06-17 |  | 0 | 0 | INST.IRR
13-NSS-P09-25.1.7.15.2.15 Control & Sample Hutch |  |  | 174 | SEK0 | 3 | 17-Oct-25 | 2026-07-10 | 2025-09-22 | 2026-06-12 | -19 | -0.95
NSS-A214786360 | T-REX: Control Hutch: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 17-Oct-25 |  | 2025-09-22 |  | -19 | -0.95 | ENG.CDR
NSS-A214786510 | T-REX: Control Hutch: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 2026-07-10 |  | 2026-06-12 |  | -19 | -0.95 | INST.IRR
NSS-A214788660 | T-REX: Control Hutch: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-04-01 |  | 2026-03-05 |  | -19 | -0.95 | PROC.FAT
13-NSS-P09-25.1.7.15.2.16 Sample Environment |  |  | 162 | SEK0 | 3 | 2026-01-14 | 05-Oct-26 | 23-Oct-25 | 2026-06-30 | -49 | -2.45
NSS-A214781060 | T-REX: Sample Environment: CDR/subTG3 (meeting) | 0% | 0 | SEK0 | 1 | 2026-01-14 |  | 23-Oct-25 |  | -49 | -2.45 | ENG.CDR
NSS-A214781150 | T-REX: Sample Environment: IRR/subTG4 (meeting) | 0% | 0 | SEK0 | 1 | 05-Oct-26 |  | 2026-06-30 |  | -49 | -2.45 | INST.IRR
NSS-A214788730 | T-REX: Sample Environment: Factory Acceptance Test (FAT) | 0% | 0 | SEK0 | 1 | 2026-06-01 |  | 2026-03-17 |  | -49 | -2.45 | PROC.FAT

## Milestones (hidden)
Activity ID | Activity Name | Activity % Complete | Start date (Sep 24) | Start date (April 25) | Variance - BL1 Start Date | Variance start date (month)
NSS-A2147510270 | MAGIC: XYZ: Factory Acceptance Test (FAT) | 0% | 2024-11-26 | 2025-05-20 | -112 | -5.6
NSS-A214757070 | MAGIC:Polarizer: CDR (meeting) | 0% | 2024-12-09 | 2025-06-04 | -111 | -5.55
NSS-A214756690 | MAGIC:OoB VH & Supp Sec 1: CDR (meeting) | 0% | 2025-02-05 | 2025-06-19 | -90 | -4.5
NSS-A214757350 | MAGIC:RF SF: CDR (meeting) | 0% | 2025-02-10 | 2025-07-02 | -95 | -4.75
NSS-A2147510050 | MAGIC: Good Lift: Factory Acceptance Test (FAT) | 0% | 2025-03-11 | 2025-08-20 | -109 | -5.45
NSS-A214756020 | MAGIC:Guid+VH+Supp (in-bunker):Factory Acceptance Test (FAT) | 0% | 2025-03-14 | 2026-01-13 | -198 | -9.9
NSS-A214757790 | MAGIC: Sample St: CDR (meeting) | 0% | 2025-04-14 | 2025-09-01 | -73 | -3.65
NSS-A214758640 | MAGIC: Det A: Factory Acceptance Test (FAT) | 0% | 2025-05-12 | 2025-12-05 | -145 | -7.25
NSS-A214758050 | MAGIC:Supp-RC+Det A: CDR (meeting) | 0% | 2025-06-10 | 2025-09-30 | -59 | -2.95
NSS-A214756290 | MAGIC:BWF:Factory Acceptance Test (FAT) | 0% | 2025-07-25 | 2025-11-20 | -84 | -4.2

## Procurement (hidden)
Activity Name | Activity % Complete | Start date (Sep 24) | Finish date (Sep 24) | Start date (April 25) | Finish date (April 25) | Variance - BL1 Start Date | Variance - BL1 Finish Date | Variance finish date (month)
MAGIC: Analyzer Seg 1: Procurement and manufacturing of the Component | 82.24% | 2024-04-02 | 2025-07-25 | 02-Apr-24 A | 2025-07-25 | 0 | 0 | 0 | In manufacturing? Contract in place?
MAGIC: XYZ: Procurement and manufacturing of the Component | 75% | 2024-04-02 | 2024-11-25 | 02-Apr-24 A | 19-May-25 | 0 | -112 | -5.6
MAGIC:Guid+VH+Supp: Procurement of the Component | 70% | 2024-06-03 | 2025-03-13 | 03-Jun-24 A | 17-Apr-25 A | 0 | -25 | -1.25
MAGIC: RC: Procurement and manufacturing of Radial Collimator | 68.81% | 2024-09-16 | 2025-06-17 | 16-Sep-24 A | 2025-09-08 | 0 | -38 | -1.9
MAGIC: Analyzer: Seg 2: Procurement and manufacturing of the Component | 0% | 2024-11-06 | 2026-04-15 | 2025-07-28 | 2026-04-16 | -171 | -1 | -0.05
MAGIC:BWF:Procurement and manufacturing of the Component | 6.67% | 2024-12-04 | 2025-07-24 | 15-Apr-25 A | 2025-11-19 | -84 | -84 | -4.2
MAGIC:Polarizer: Procurement and manufacturing of the Component | 0% | 2025-01-13 | 2025-06-09 | 2025-06-27 | 2025-11-13 | -112 | -112 | -5.6
MAGIC:RF SF: Procurement and manufacturing of the Component | 0% | 2025-02-24 | 2025-07-08 | 2025-07-16 | 2025-11-18 | -95 | -95 | -4.75
MAGIC:OoB VH & Supp Sec 1: Procurement of OoB housing and supports | 0% | 2025-02-26 | 23-Oct-25 | 2025-07-11 | 30-Oct-25 | -90 | -5 | -0.25 | In manufacturing? Contract in place?
MAGIC:OoB VH & Supp Sec 2: Procurement of OoB housing and supports | 0% |  |  | 2025-07-15 | 2025-11-03 |  |  | 0
MAGIC:OoB VH & Supp Sec 3: Procurement of OoB housing and supports | 0% |  |  | 2025-08-18 | 2025-11-07 |  |  | 0
MAGIC: Sample St: Procurement and manufacturing of the Component | 0% | 2025-04-30 | 2025-09-09 | 2025-09-15 | 2026-02-03 | -93 | -93 | -4.65
MAGIC: Supp- Analzr+Det B: Procurement and manufacturing of the Component | 0% | 2025-09-15 | 2026-02-17 | 2025-07-25 | 2025-12-11 | 36 | 36 | 1.8 | In manufacturing? Contract in place?
MAGIC:Supp-RC+Det A: Procurement and manufacturing of the Component | 0% | 2025-06-25 | 2025-11-11 | 14-Oct-25 | 2026-03-18 | -79 | -79 | -3.95 | -79 | -79

## Sheet4 (hidden)
Activity ID | Activity Name | Activity % Complete | Original Duration | Start (juni lockdown) | Finish (juni lockdown) | Start (juni lockdown) | Finish (juni lockdown) | Start (december lockdown) | Finish (december lockdown) | Variance start date | Variance finish date
13-NSS-P06-24.1.7.16.16.11 Technology groups/Common Projects |  |  | 318 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.1 Common Electrical Project |  |  | 188 | [6 empty] | 0 | 0
NSS-A2147186560 | Common electrical project offer accepted | 0% | 0 |  | 2024-08-21 |  | 2024-08-21 |  | 2025-01-30 | 0 | -117
13-NSS-P06-24.1.7.16.16.11.1.1 CEP milestones to be met by Instrument for start of Detail design |  |  | 18 | [6 empty] | 0 | 0
NSS-A2147186570 | MIRACLES: CEP: Updated PID released in CHESS | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186580 | MIRACLES: CEP: Updated EPL model available | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186590 | MIRACLES: CEP: FBS/LBS is incorporated within the EPL model | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186600 | MIRACLES: CEP: Cave prelim design complete | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186610 | MIRACLES: CEP: CEP feedthroughs into cave agreed. | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186620 | MIRACLES: CEP: nstrument components/systems incorporated into the EPL model | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186630 | MIRACLES: CEP: All Rack/box positions incorporated within the EPL model. (with FBS in model) | 0% | 18 | 2024-07-01 | 2024-08-21 | 2024-07-01 | 2024-08-21 | 2025-01-07 | 2025-01-30 | -137 | -117
NSS-A2147186690 | MIRACLES: CEP: All CEP requirement milestones completed | 0% | 0 |  | 2024-08-21 |  | 2024-08-21 |  | 2025-01-30 | 0 | -117
13-NSS-P06-24.1.7.16.16.11.1.2 CEP milestones to be met by Instrument for start of Installation |  |  | 0 | [6 empty] | 0 | 0
NSS-A2147186640 | MIRACLES: CEP:Cave installed and complete | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186650 | MIRACLES: CEP:Guide installations complete | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186660 | MIRACLES: CEP:Shield wall complete | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186670 | MIRACLES: CEP:Instrument ready for CEP installations | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186680 | MIRACLES: CEP: Approximate delivery of cabinets/racks provided | 0% | 0 | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 |  | -137 | 0
NSS-A2147186740 | MIRACLES: CEP:All CEP Installation reqmt milestones completed | 0% | 0 |  | 2024-07-01 |  | 2024-07-01 |  | 2025-01-07 | 0 | -137
13-NSS-P06-24.1.7.16.16.11.1.3 CEP Detailed Design |  |  | 100 | [6 empty] | 0 | 0
NSS-A2147186700 | MIRACLES: CEP: Detailed design (Inst zone) | 0% | 100 | 2024-08-22 | 2025-01-23 | 2024-08-22 | 2025-01-23 | 2025-01-31 | 2025-06-30 | -117 | -113
NSS-A2147186710 | MIRACLES: CEP: Detailed design (Bunker zone) | 0% | 60 | 2024-08-22 | 2024-11-13 | 2024-08-22 | 2024-11-13 | 2025-01-31 | 2025-04-28 | -117 | -119
13-NSS-P06-24.1.7.16.16.11.1.4 CEP Installation |  |  | 186 | [6 empty] | 0 | 0
NSS-A2147186750 | MIRACLES: CEP: Installation (Inst zone)- Infrastructure (cave) | 0% | 25 | 03-Jul-24* | 2024-09-03 | 2024-07-03 | 2024-09-03 | 2025-01-07 | 2025-02-10 | -135 | -115
NSS-A2147186760 | MIRACLES: CEP: Installation (Inst zone)- Cabling (cave) | 0% | 20 | 2024-09-04 | 2024-10-01 | 2024-09-04 | 2024-10-01 | 2025-02-11 | 2025-03-10 | -115 | -115
NSS-A2147186770 | MIRACLES: Inst Installation (Inst zone)- Level 3 cable termination (cave) complete (Incom link from Inst) | 0% | 0 | 2024-10-02 |  | 2024-10-02 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186800 | MIRACLES: Inst Installation (Inst zone)- Component (inside cave) ready for SAT (outgoing link to Inst) | 0% | 0 | 2024-10-02 |  | 2024-10-02 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186730 | MIRACLES: CEP: Installation (Bunker zone) | 0% | 50 | 2024-11-14 | 2025-02-06 | 2024-11-14 | 2025-02-06 | 2025-04-29 | 2025-07-14 | -119 | -113
NSS-A2147186720 | MIRACLES: CEP: Installation (Inst zone)- Infrastructure (excluding cave) | 0% | 30 | 2025-01-24 | 2025-03-06 | 2025-01-24 | 2025-03-06 | 2025-07-01 | 2025-09-08 | -113 | -133
NSS-A2147187280 | MIRACLES: CEP: Installation (Inst zone)- Cabling (excluding cave) | 0% | 25 | 2025-03-07 | 2025-04-10 | 2025-03-07 | 2025-04-10 | 2025-09-09 | 2025-10-13 | -133 | -133
NSS-A2147187290 | MIRACLES: Inst Installation (Inst zone)- false floors | 0% | 5 | 2025-04-11 | 2025-04-17 | 2025-04-11 | 2025-04-17 | 2025-10-14 | 2025-10-20 | -133 | -133
NSS-A2147187330 | MIRACLES:Inst Installation (Inst zone)- Level 3 cable termination (excluding cave) complete | 0% | 0 | 2025-04-11 |  | 2025-04-11 |  | 2025-10-14 |  | -133 | 0
NSS-A2147187300 | MIRACLES: Inst Installation (Inst zone)- Racks and cabinets installation complete | 0% | 0 | 2025-04-22 |  | 2025-04-22 |  | 2025-10-21 |  | -131 | 0
NSS-A2147187310 | MIRACLES: CEP: Level 2 termination | 0% | 5 | 2025-04-22 | 2025-04-28 | 2025-04-22 | 2025-04-28 | 2025-10-21 | 2025-10-27 | -131 | -131
NSS-A2147187320 | MIRACLES: CEP: Energization of racks | 0% | 5 | 2025-04-29 | 2025-05-06 | 2025-04-29 | 2025-05-06 | 2025-10-28 | 2025-11-03 | -131 | -130
NSS-A2147187340 | Component ready for testing at site | 0% | 0 | 2025-05-07 |  | 2025-05-07 |  | 2025-11-04 |  | -130 | 0
13-NSS-P06-24.1.7.16.16.11.7 Common Shielding Project |  |  | 225 | [6 empty] | 0 | 0
NSS-A2147187120 | Detailed Design | 0% | 225 | 2024-07-01 | 2025-07-02 | 2024-07-01 | 2025-07-02 | 2025-01-07 | 2026-01-07 | -137 | -136
NSS-A2147187130 | Manufacturing and Procurment | 0% | 225 | 2024-07-01 | 2025-07-02 | 2024-07-01 | 2025-07-02 | 2025-01-07 | 2026-01-07 | -137 | -136
NSS-A2147187140 | Installation | 0% | 175 | 2024-07-01 | 2025-04-14 | 2024-07-01 | 2025-04-14 | 2025-01-07 | 2025-10-15 | -137 | -133
13-NSS-P06-24.1.7.16.16.11.2 Common Utilities Project |  |  | 200 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.2.1 CUP milestones to be met by Instrument for start of Detail design |  |  | 0 | [6 empty] | 0 | 0
NSS-A2147187040 | Updated PID released in CHESS | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187050 | Updated EPL model available | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187060 | FBS/LBS is incorporated within the EPL model | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187070 | Cave prelim design complete | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187080 | CUP feedthroughs into cave agreed. | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187090 | Instrument components/systems incorporated into the EPL model | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187100 | All components requiring utility interface incorporated within the EPL model. (with FBS in model) | 0% | 0 | 01-Jul-24* |  | 2024-07-01 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147187110 | All CUP requirement milestones completed | 0% | 0 |  | 2024-07-01 |  | 2024-07-01 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.6 Design |  |  | 65 | [6 empty] | 0 | 0
NSS-A2147349840 | MIRACLES CUP: Preliminary design phase | 0% | 15 | 2024-07-01 | 2024-08-16 | 2024-07-01 | 2024-08-16 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349790 | MIRACLES CUP: Detailed design phase (Piping) | 0% | 50 | 2024-08-19 | 2024-10-25 | 2024-08-19 | 2024-10-25 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349830 | MIRACLES CUP: PDR (Piping) | 0% | 0 | 2024-08-19 |  | 2024-08-19 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147349850 | MIRACLES CUP: Detail design phase for skids | 0% | 35 | 2024-08-19 | 2024-10-04 | 2024-08-19 | 2024-10-04 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349860 | MIRACLES CUP: CDR for skids and approval | 0% | 10 | 2024-10-07 | 2024-10-18 | 2024-10-07 | 2024-10-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349820 | MIRACLES CUP: CDR (Piping) | 0% | 0 | 2024-10-28 |  | 2024-10-28 |  | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.7 Manufacturing and Delivery |  |  | 45 | [6 empty] | 0 | 0
NSS-A2147349870 | MIRACLES CUP: Procurement and Order placement for skids | 0% | 30 | 2024-10-21 | 2024-11-29 | 2024-10-21 | 2024-11-29 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349900 | MIRACLES CUP: Procurement and Order placement (Piping) | 0% | 40 | 2024-10-28 | 2024-12-20 | 2024-10-28 | 2024-12-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349880 | MIRACLES CUP: Delivery of skids to ESS | 0% | 5 | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-06 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.8 Installation Preparation and Reviews |  |  | 120 | [6 empty] | 0 | 0
NSS-A2147349750 | MIRACLES CUP: Procurement and Installation (Piping & Skids)-CUP ESTIA | 0% | 120 | 2024-10-21 | 2025-04-23 | 2024-10-21 | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349920 | MIRACLES CUP: IRR preparation (skids) | 0% | 15 | 2024-12-02 | 2024-12-20 | 2024-12-02 | 2024-12-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349810 | MIRACLES CUP: IRR preparation (piping) | 0% | 20 | 2025-01-07 | 2025-02-03 | 2025-01-07 | 2025-02-03 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349740 | MIRACLES CUP: IRR (skids and piping) | 0% | 0 | 2025-02-04 |  | 2025-02-04 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147349760 | MIRACLES CUP: IPL work | 0% | 55 | 2025-02-04 | 2025-04-23 | 2025-02-04 | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349950 | MIRACLES CUP: Installation preparation | 0% | 10 | 2025-02-04 | 2025-02-17 | 2025-02-04 | 2025-02-17 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.4 Installation phase |  |  | 45 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.2.4.1 Bunker zone |  |  | 15 | [6 empty] | 0 | 0
NSS-A2147349930 | MIRACLES CUP: Installation of supports for vacuum manifold | 0% | 15 | 2025-02-18 | 2025-03-10 | 2025-02-18 | 2025-03-10 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349940 | MIRACLES CUP: Installation of piping for In bunker components | 0% | 15 | 2025-02-18 | 2025-03-10 | 2025-02-18 | 2025-03-10 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.4.5 Instrument zone |  |  | 45 | [6 empty] | 0 | 0
NSS-A2147349890 | MIRACLES CUP: Installation phase for skids | 0% | 10 | 2025-02-18 | 2025-03-03 | 2025-02-18 | 2025-03-03 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349960 | MIRACLES CUP: Installation phase-Cave exterior | 0% | 30 | 2025-02-18 | 2025-03-31 | 2025-02-18 | 2025-03-31 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349980 | MIRACLES CUP: Installation phase-Galleries Level 90 | 0% | 20 | 2025-02-18 | 2025-03-17 | 2025-02-18 | 2025-03-17 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349970 | MIRACLES CUP: Installation phase-Cave interior | 0% | 15 | 2025-04-01 | 2025-04-23 | 2025-04-01 | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.2.5 Final inspections and commissioning |  |  | 20 | [6 empty] | 0 | 0
NSS-A2147349910 | MIRACLES CUP: All installations complete | 0% | 0 |  | 2025-04-23 |  | 2025-04-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349990 | MIRACLES CUP: Mechanical inspection of installations | 0% | 5 | 2025-04-24 | 2025-04-30 | 2025-04-24 | 2025-04-30 | #N/A | #N/A | #N/A | #N/A
NSS-A2147350000 | MIRACLES CUP: Pressure testing and Quality control | 0% | 5 | 2025-05-02 | 2025-05-08 | 2025-05-02 | 2025-05-08 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349780 | MIRACLES CUP: Commissioning & final documentation | 0% | 10 | 2025-05-09 | 2025-05-22 | 2025-05-09 | 2025-05-22 | #N/A | #N/A | #N/A | #N/A
NSS-A2147349770 | MIRACLES CUP: Documentation released (scope complete - feed into SRR) | 0% | 0 | 2025-05-23 |  | 2025-05-23 |  | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.3 Motion Control and Automation |  |  | 253 | [6 empty] | 0 | 0
NSS-A2147186780 | MCA MIRACLES: offer accepted and project kicked off | 0% | 5 | 16-Sep-24* | 2024-09-20 | 2024-09-16 | 2024-09-20 | 2025-01-07 | 2025-01-13 | -82 | -82
NSS-A2147186790 | MCA MIRACLES: Sheet 4 of Table of Motion fully filled | 0% | 0 | 16-Sep-24* |  | 2024-09-16 |  | 2025-01-07 |  | -82 | 0
13-NSS-P06-24.1.7.16.16.11.3.1 D03 Hall (Bunker Zone) |  |  | 130 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.3.1.4 Junction boxes |  |  | 48 | [6 empty] | 0 | 0
NSS-A2147350250 | MCA MIRACLES: Design, Eplan of junction box (for switches)) | 0% | 15 | 2024-09-23 | 2024-10-11 | 2024-09-23 | 2024-10-11 | 2025-01-14 | 2025-02-03 | -82 | -82
NSS-A2147350260 | MCA MIRACLES: Procurement of junction box (for switches) | 0% | 30 | 2024-10-14 | 2024-11-22 | 2024-10-14 | 2024-11-22 | 2025-02-04 | 2025-03-17 | -82 | -82
NSS-A2147350270 | MCA MIRACLES: Installation of junction box (for switches)) | 0% | 3 | 2024-11-25 | 2024-11-27 | 2024-11-25 | 2024-11-27 | 2025-03-18 | 2025-03-20 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.1.3 Wall boxes |  |  | 56 | [6 empty] | 0 | 0
NSS-A2147350130 | MCA MIRACLES: Design , Eplan of wall boxes (pneumatic box ) | 0% | 15 | 2024-09-30 | 2024-10-18 | 2024-09-30 | 2024-10-18 | 2025-01-21 | 2025-02-10 | -82 | -82
NSS-A2147350140 | MCA MIRACLES: Procurement and adaptation of wall boxes (pneumatic box ) | 0% | 36 | 2024-10-21 | 2024-12-09 | 2024-10-21 | 2024-12-09 | 2025-02-11 | 2025-04-01 | -82 | -82
NSS-A2147350150 | MCA MIRACLES: Installation of wall boxes (pneumatic box ) | 0% | 5 | 2024-12-10 | 2024-12-16 | 2024-12-10 | 2024-12-16 | 2025-04-02 | 2025-04-08 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.1.5 Cabinets |  |  | 56 | [6 empty] | 0 | 0
NSS-A2147350100 | MCA MIRACLES: Design, Eplan of cabinet 1 (shutter cabinet) | 0% | 15 | 2024-10-07 | 2024-10-25 | 2024-10-07 | 2024-10-25 | 2025-01-28 | 2025-02-17 | -82 | -82
NSS-A2147350110 | MCA MIRACLES: Procurement of cabinet 1 (shutter cabinet) | 0% | 36 | 2024-10-28 | 2024-12-16 | 2024-10-28 | 2024-12-16 | 2025-02-18 | 2025-04-08 | -82 | -82
NSS-A2147350120 | MCA MIRACLES: Installation of cabinet 1 (shutter cabinet) link pred install false floor | 0% | 5 | 2024-12-17 | 2025-01-07 | 2024-12-17 | 2025-01-07 | 2025-04-09 | 2025-04-15 | -82 | -71
13-NSS-P06-24.1.7.16.16.11.3.1.6 MCA L3 and energization |  |  | 60 | [6 empty] | 0 | 0
NSS-A2147350160 | MCA MIRACLES: Design of all MCA cables, cable data base (CDB), label list | 0% | 15 | 2024-10-28 | 2024-11-15 | 2024-10-28 | 2024-11-15 | 2025-02-18 | 2025-03-10 | -82 | -82
NSS-A2147350170 | MCA MIRACLES: Procurement and labelling of all MCA cables | 0% | 30 | 2024-11-18 | 2025-01-13 | 2024-11-18 | 2025-01-13 | 2025-03-11 | 2025-04-23 | -82 | -73
NSS-A2147350180 | MCA MIRACLES: Termination and testing of all installed cables | 0% | 10 | 2025-01-14 | 2025-01-27 | 2025-01-14 | 2025-01-27 | 2025-04-24 | 2025-05-08 | -73 | -74
NSS-A2147350430 | MCA MIRACLES: Final energization of cabinets Bunker Zone | 0% | 5 | 2025-01-28 | 2025-02-03 | 2025-01-28 | 2025-02-03 | 2025-05-09 | 2025-05-15 | -74 | -74
13-NSS-P06-24.1.7.16.16.11.3.1.1 MCA control system setup Bunker Zone |  |  | 45 | [6 empty] | 0 | 0
NSS-A2147350370 | MCA MIRACLES: Setting up of control systems (not related to ICS) | 0% | 10 | 2025-02-04 | 2025-02-17 | 2025-02-04 | 2025-02-17 | 2025-05-16 | 2025-06-02 | -74 | -76
NSS-A2147350380 | MCA MIRACLES: Commissioning of subsystem related to respective cabinets | 0% | 15 | 2025-02-18 | 2025-03-10 | 2025-02-18 | 2025-03-10 | 2025-06-03 | 2025-06-25 | -76 | -78
NSS-A2147350390 | MCA MIRACLES: Configuration of interfaces to EPICS/NICOS in bunker | 0% | 10 | 2025-03-11 | 2025-03-24 | 2025-03-11 | 2025-03-24 | 2025-06-26 | 2025-07-09 | -78 | -78
NSS-A2147350540 | MCA MIRACLES: Local SAT D03 with ECDC/ICS for motion control testing with EPICS/NICOS | 0% | 10 | 2025-03-25 | 2025-04-07 | 2025-03-25 | 2025-04-07 | 2025-07-10 | 2025-08-20 | -78 | -98
13-NSS-P06-24.1.7.16.16.11.3.3 E02 Hall (Instrument Zone)-if applicable for MCA |  |  | 88 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.3.3.4 Junction boxes |  |  | 9 | [6 empty] | 0 | 0
NSS-A2147350190 | MCA MIRACLES: Design, Eplan of junction box (for switches) | 0% | 2 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2025-01-07 | 2025-01-08 | -137 | -137
NSS-A2147350200 | MCA MIRACLES: Procurement of junction box(for switches) | 0% | 5 | 2024-07-03 | 2024-07-09 | 2024-07-03 | 2024-07-09 | 2025-01-09 | 2025-01-15 | -137 | -137
NSS-A2147350210 | MCA MIRACLES: Installation of junction box(for switches) | 0% | 2 | 2024-07-10 | 2024-07-11 | 2024-07-10 | 2024-07-11 | 2025-01-16 | 2025-01-17 | -137 | -137
13-NSS-P06-24.1.7.16.16.11.3.3.3 Wall boxes |  |  | 48 | [6 empty] | 0 | 0
NSS-A2147350220 | MCA MIRACLES: Design , Eplan of wall boxes (pneumatic box ) | 0% | 12 | 2024-07-01 | 2024-08-13 | 2024-07-01 | 2024-08-13 | 2025-01-07 | 2025-01-22 | -137 | -117
NSS-A2147350230 | MCA MIRACLES: Procurement of wall boxes (pneumatic box ) | 0% | 34 | 2024-08-14 | 2024-09-30 | 2024-08-14 | 2024-09-30 | 2025-01-23 | 2025-03-11 | -117 | -117
NSS-A2147350240 | MCA MIRACLES: Installation of wall boxes (pneumatic box ) | 0% | 2 | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-02 | 2025-03-12 | 2025-03-13 | -117 | -117
13-NSS-P06-24.1.7.16.16.11.3.3.2 Cabinets |  |  | 22 | [6 empty] | 0 | 0
NSS-A2147350310 | MCA MIRACLES: Design, Eplan of cabinet 2.1 (EC node wall box) | 0% | 15 | 2024-07-01 | 2024-08-16 | 2024-07-01 | 2024-08-16 | 2025-01-07 | 2025-01-27 | -137 | -117
NSS-A2147350320 | MCA MIRACLES: Procurement of cabinet 2.1 (EC node wall box) | 0% | 6 | 2024-08-19 | 2024-08-26 | 2024-08-19 | 2024-08-26 | 2025-01-28 | 2025-02-04 | -117 | -117
NSS-A2147350330 | MCA MIRACLES: Installation of cabinet 2.1 (EC node wall box) | 0% | 1 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2025-02-05 | 2025-02-05 | -117 | -117
13-NSS-P06-24.1.7.16.16.11.3.3.1 MCA L3 and energization |  |  | 63 | [6 empty] | 0 | 0
NSS-A2147350280 | MCA MIRACLES: Design of all MCA cables, cable data base (CDB), label list | 0% | 5 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-05 | 2025-01-07 | 2025-01-13 | -137 | -137
NSS-A2147350290 | MCA MIRACLES: Procurement and labelling of all MCA cables | 0% | 30 | 2024-07-08 | 2024-09-13 | 2024-07-08 | 2024-09-13 | 2025-01-14 | 2025-02-24 | -137 | -117
NSS-A2147350300 | MCA MIRACLES: Termination of all installed cables E02 | 0% | 10 | 2024-10-03 | 2024-10-16 | 2024-10-03 | 2024-10-16 | 2025-03-14 | 2025-03-27 | -117 | -117
NSS-A2147350500 | MCA MIRACLES: Final energization of cabinets E02 Hall instrument Zone | 0% | 5 | 2024-10-17 | 2024-10-23 | 2024-10-17 | 2024-10-23 | 2025-03-28 | 2025-04-03 | -117 | -117
13-NSS-P06-24.1.7.16.16.11.3.3.5 MCA control system setup E02 Instrument Zone |  |  | 88 | [6 empty] | 0 | 0
NSS-A2147350480 | MCA MIRACLES: Temporary energization of MCA cabinets E02 | 0% | 5 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-05 | 2025-01-07 | 2025-01-13 | -137 | -137
NSS-A2147350450 | MCA MIRACLES: Setting up of control systems | 0% | 5 | 2024-07-08 | 2024-07-12 | 2024-07-08 | 2024-07-12 | 2025-01-14 | 2025-01-20 | -137 | -137
NSS-A2147350460 | MCA MIRACLES: Commissioning of subsystem related to respective cabinets | 0% | 10 | 2024-10-24 | 2024-11-06 | 2024-10-24 | 2024-11-06 | 2025-04-04 | 2025-04-17 | -117 | -117
NSS-A2147350470 | MCA MIRACLES: Configuration of interfaces to EPICS/NICOS E02 | 0% | 5 | 2024-11-07 | 2024-11-13 | 2024-11-07 | 2024-11-13 | 2025-04-22 | 2025-04-28 | -119 | -119
NSS-A2147350530 | MCA MIRACLES: Local SAT EO2 with ECDC/ICS for motion control testing with EPICS/NICOS | 0% | 10 | 2024-11-14 | 2024-11-27 | 2024-11-14 | 2024-11-27 | 2025-04-29 | 2025-05-13 | -119 | -120
13-NSS-P06-24.1.7.16.16.11.3.2 E01 Hall (Instrument Zone) |  |  | 198 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.3.2.4 Junction boxes |  |  | 55 | [6 empty] | 0 | 0
NSS-A2147350010 | MCA MIRACLES: Design, Eplan of junction boxes (connection plates, switch boxes) | 0% | 22 | 2024-10-14 | 2024-11-12 | 2024-10-14 | 2024-11-12 | 2025-02-04 | 2025-03-05 | -82 | -82
NSS-A2147350020 | MCA MIRACLES: Procurement of junction boxes (connection plates, switch boxes) | 0% | 15 | 2024-11-13 | 2024-12-03 | 2024-11-13 | 2024-12-03 | 2025-03-06 | 2025-03-26 | -82 | -82
NSS-A2147350030 | MCA MIRACLES: Installation of junction boxes (connection plates, switch boxes) | 0% | 3 | 2025-01-09 | 2025-01-13 | 2025-01-09 | 2025-01-13 | 2025-04-17 | 2025-04-23 | -71 | -73
13-NSS-P06-24.1.7.16.16.11.3.2.3 Wall boxes |  |  | 50 | [6 empty] | 0 | 0
NSS-A2147350070 | MCA MIRACLES: Design, Eplan of wall boxes (pneumatic box, shutter operator panel ) | 0% | 15 | 2024-10-21 | 2024-11-08 | 2024-10-21 | 2024-11-08 | 2025-02-11 | 2025-03-03 | -82 | -82
NSS-A2147350080 | MCA MIRACLES: Procurement of wall boxes (pneumatic box , shutter operator panel ) | 0% | 30 | 2024-11-11 | 2024-12-20 | 2024-11-11 | 2024-12-20 | 2025-03-04 | 2025-04-14 | -82 | -82
NSS-A2147350090 | MCA MIRACLES: Installation of wall boxes (pneumatic box, shutter operator panel ) | 0% | 5 | 2025-01-07 | 2025-01-13 | 2025-01-07 | 2025-01-13 | 2025-04-15 | 2025-04-23 | -71 | -73
13-NSS-P06-24.1.7.16.16.11.3.2.5 Cabinet 3 |  |  | 35 | [6 empty] | 0 | 0
NSS-A2147350040 | MCA MIRACLES: Design, Eplan of cabinet 3 | 0% | 15 | 2024-10-28 | 2024-11-15 | 2024-10-28 | 2024-11-15 | 2025-02-18 | 2025-03-10 | -82 | -82
NSS-A2147350050 | MCA MIRACLES: Procurement of cabinet 3 | 0% | 15 | 2024-11-18 | 2024-12-06 | 2024-11-18 | 2024-12-06 | 2025-03-11 | 2025-03-31 | -82 | -82
NSS-A2147350060 | MCA MIRACLES: Installation of cabinet 3 | 0% | 5 | 2024-12-09 | 2024-12-13 | 2024-12-09 | 2024-12-13 | 2025-04-01 | 2025-04-07 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.2.2 Cabinet 2 |  |  | 35 | [6 empty] | 0 | 0
NSS-A2147350550 | MCA MIRACLES: Design, Eplan of cabinet 2 | 0% | 15 | 2024-11-04 | 2024-11-22 | 2024-11-04 | 2024-11-22 | 2025-02-25 | 2025-03-17 | -82 | -82
NSS-A2147350560 | MCA MIRACLES: Procurement of cabinet 2 | 0% | 15 | 2024-11-25 | 2024-12-13 | 2024-11-25 | 2024-12-13 | 2025-03-18 | 2025-04-07 | -82 | -82
NSS-A2147350570 | MCA MIRACLES: Installation of cabinet 2 | 0% | 5 | 2024-12-16 | 2024-12-20 | 2024-12-16 | 2024-12-20 | 2025-04-08 | 2025-04-14 | -82 | -82
13-NSS-P06-24.1.7.16.16.11.3.2.6 MCA L3 and energization |  |  | 108 | [6 empty] | 0 | 0
NSS-A2147350400 | MCA MIRACLES: Design of all MCA cables, cable data base (CDB), label list | 0% | 5 | 2024-11-25 | 2024-11-29 | 2024-11-25 | 2024-11-29 | 2025-03-18 | 2025-03-24 | -82 | -82
NSS-A2147350410 | MCA MIRACLES: Procurement and labelling of all MCA cables | 0% | 30 | 2024-12-02 | 2025-01-27 | 2024-12-02 | 2025-01-27 | 2025-03-25 | 2025-05-08 | -82 | -74
NSS-A2147350420 | MCA MIRACLES: Termination of all installed cables E01 | 0% | 10 | 2025-01-14 | 2025-01-27 | 2025-01-14 | 2025-01-27 | 2025-04-24 | 2025-05-08 | -73 | -74
NSS-A2147350510 | MCA MIRACLES: Final energization of cabinets E01 Hall instrument zone | 0% | 5 | 2025-05-07 | 2025-05-13 | 2025-05-07 | 2025-05-13 | 2025-11-04 | 2025-11-10 | -130 | -130
13-NSS-P06-24.1.7.16.16.11.3.2.1 MCA control system setup E01 Instrument Zone |  |  | 60 | [6 empty] | 0 | 0
NSS-A2147350340 | MCA MIRACLES: Setting up of control systems | 0% | 10 | 2025-05-14 | 2025-05-27 | 2025-05-14 | 2025-05-27 | 2025-11-11 | 2025-11-24 | -130 | -130
NSS-A2147350350 | MCA MIRACLES: Commissioning of subsystem related to respective cabinets | 0% | 30 | 2025-05-28 | 2025-07-14 | 2025-05-28 | 2025-07-14 | 2025-11-25 | 2026-01-19 | -130 | -136
NSS-A2147350360 | MCA MIRACLES: Configuration of interfaces to EPICS/NICOS E01 succ local sat with duration (how g with pred from ics, ecd | 0% | 10 | 2025-07-15 | 2025-08-25 | 2025-07-15 | 2025-08-25 | 2026-01-20 | 2026-02-02 | -136 | -116
NSS-A2147350520 | MCA MIRACLES: Local SAT E01 with ECDC/ICS for motion control testing with EPICS/NICOS | 0% | 10 | 2025-08-26 | 2025-09-08 | 2025-08-26 | 2025-09-08 | 2026-02-03 | 2026-02-16 | -116 | -116
13-NSS-P06-24.1.7.16.16.11.4 Detector project |  |  | 261 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.4.7 Detector Racks |  |  | 261 | [6 empty] | 0 | 0
NSS-A2147186370 | Preliminary design review (PDR) and approval | 0% | 15 | 2024-10-16 | 2024-11-05 | 2024-10-16 | 2024-11-05 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187350 | Scope transfer agreed and project kicked off with Det Group | 0% | 0 | 16-okt-24* |  | 2024-10-16 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186320 | Tender/offer issuance | 0% | 5 | 2024-11-06 | 2024-11-12 | 2024-11-06 | 2024-11-12 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186330 | Tender review,selection and award of contract completed | 0% | 40 | 2024-11-13 | 2025-01-22 | 2024-11-13 | 2025-01-22 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186380 | Detailed design phase for the Racks | 0% | 30 | 2025-01-23 | 2025-03-05 | 2025-01-23 | 2025-03-05 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186340 | Submission of docs to ESS for CDR/TG3 | 0% | 20 | 2025-02-20 | 2025-03-19 | 2025-02-20 | 2025-03-19 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186350 | CDR/sub-TG3 review | 0% | 0 |  | 2025-03-19 |  | 2025-03-19 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186360 | CDR/sub-TG3 approval | 0% | 20 | 2025-03-20 | 2025-04-16 | 2025-03-20 | 2025-04-16 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186410 | Procurement and manufacturing | 0% | 60 | 17-Apr-25* | 2025-07-18 | 2025-04-17 | 2025-07-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186420 | Factory Acceptance Test (FAT) | 0% | 5 | 18-Aug-25* | 2025-08-22 | 2025-08-18 | 2025-08-22 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186430 | FAT approval and documentation | 0% | 10 | 25-Aug-25* | 2025-09-05 | 2025-08-25 | 2025-09-05 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186530 | Shipping period for the components | 0% | 10 | 2025-09-08 | 2025-09-19 | 2025-09-08 | 2025-09-19 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186460 | IRR document submission phase | 0% | 15 | 2025-09-08 | 2025-09-26 | 2025-09-08 | 2025-09-26 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186390 | Pre-installation testing of detectors with ECDC and ICS | 0% | 30 | 2025-09-22 | 2025-10-31 | 2025-09-22 | 2025-10-31 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186400 | Handing over of Level 3 cables to CEP | 0% | 2 | 2025-09-22 | 2025-09-23 | 2025-09-22 | 2025-09-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186450 | Delivery of Racks and cables | 0% | 0 | 2025-09-22 |  | 2025-09-22 |  | #N/A | #N/A | #N/A | #N/A
NSS-A2147186470 | Instrument readiness review (IRR) | 0% | 0 |  | 2025-09-26 |  | 2025-09-26 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186550 | Detector racks TG4 approved | 0% | 0 |  | 2025-09-26 |  | 2025-09-26 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186490 | Installation of Racks | 0% | 3 | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-05 | 2026-09-18 | 2026-09-24 | -230 | -232
NSS-A2147186500 | Level 3 cable termination | 0% | 3 | 2025-11-06 | 2025-11-10 | 2025-11-06 | 2025-11-10 | 2026-10-09 | 2026-10-15 | -242 | -244
NSS-A2147186540 | Test readiness review (TRR) and approval | 0% | 2 | 2025-11-11 | 2025-11-12 | 2025-11-11 | 2025-11-12 | 2026-10-16 | 2026-10-29 | -244 | -252
NSS-A2147186510 | System Acceptance Test (SAT)- along with detectors | 0% | 15 | 2025-11-13 | 2025-12-03 | 2025-11-13 | 2025-12-03 | #N/A | #N/A | #N/A | #N/A
NSS-A2147186520 | SAT approval | 0% | 3 | 2025-12-04 | 2025-12-08 | 2025-12-04 | 2025-12-08 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.5 Chopper project |  |  | 201 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.5.7 Chopper Rack 1-3 |  |  | 201 | [6 empty] | 0 | 0
NSS-A2147187160 | Delivery of Chopper Rack | 100% | 5 | 14-Aug-23 A | 18-Aug-23 A | 2023-08-14 | 2023-08-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187150 | Quality gate review and approval | 0% | 20 | 2024-07-01 | 2024-08-23 | 2024-07-01 | 2024-08-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187170 | Submission of docs to ESS for Quality gate and IRR/sub-TG4 | 0% | 20 | 2024-07-01 | 2024-08-23 | 2024-07-01 | 2024-08-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187180 | Installation Readiness Review (IRR) | 0% | 0 |  | 2024-08-23 |  | 2024-08-23 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187190 | IRR Approval | 0% | 20 | 2024-08-26 | 2024-09-20 | 2024-08-26 | 2024-09-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187270 | TG4 | 0% | 0 |  | 2024-09-20 |  | 2024-09-20 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187200 | Installation of Chopper Rack | 0% | 20 | 2024-09-23 | 2024-10-18 | 2024-09-23 | 2024-10-18 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187210 | CEP interface ( earthing and bonding connections) | 0% | 10 | 2024-09-23 | 2024-10-04 | 2024-09-23 | 2024-10-04 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187250 | CUP interface | 0% | 10 | 2024-09-23 | 2024-10-04 | 2024-09-23 | 2024-10-04 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187260 | Pre-installation testing at site with ECDC and ICS | 0% | 5 | 2024-09-23 | 2024-09-27 | 2024-09-23 | 2024-09-27 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187240 | Test readiness review (TRR) and approval | 0% | 5 | 2024-10-21 | 2024-10-25 | 2024-10-21 | 2024-10-25 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187220 | System Acceptance Test (SAT) | 0% | 5 | 2024-10-28 | 2024-11-01 | 2024-10-28 | 2024-11-01 | #N/A | #N/A | #N/A | #N/A
NSS-A2147187230 | SAT approval | 0% | 10 | 2024-11-04 | 2024-11-15 | 2024-11-04 | 2024-11-15 | #N/A | #N/A | #N/A | #N/A
13-NSS-P06-24.1.7.16.16.11.6 Beam Monitor project |  |  | 211 | [6 empty] | 0 | 0
13-NSS-P06-24.1.7.16.16.11.6.1 Beam monitors |  |  | 211 | [6 empty] | 0 | 0
NSS-A2147186990 | Contract signed and order placed | 0% | 5 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-05 | 2025-01-07 | 2025-01-13 | -137 | -137
NSS-A2147187000 | Detailed design phase for the Beam monitor including electronics | 0% | 30 | 2024-07-08 | 2024-09-13 | 2024-07-08 | 2024-09-13 | 2025-01-14 | 2025-02-24 | -137 | -117
NSS-A2147187010 | Design documents submitted for review | 0% | 10 | 2024-08-26 | 2024-09-06 | 2024-08-26 | 2024-09-06 | 2025-02-04 | 2025-02-17 | -117 | -117
NSS-A2147187020 | CDR and approval | 0% | 10 | 2024-09-09 | 2024-09-20 | 2024-09-09 | 2024-09-20 | 2025-02-18 | 2025-03-03 | -117 | -117
NSS-A2147187030 | Manufacturing and Procurement | 0% | 50 | 2024-09-23 | 2024-11-29 | 2024-09-23 | 2024-11-29 | 2025-03-04 | 2025-05-15 | -117 | -120
NSS-A2147186810 | Factory Acceptance Test (FAT) | 0% | 5 | 2024-12-02 | 2024-12-06 | 2024-12-02 | 2024-12-06 | 2025-05-16 | 2025-05-22 | -120 | -120
NSS-A2147186850 | Submission of docs to ESS for Quality gate and IRR | 0% | 56 | 2024-12-09 | 2025-03-11 | 2024-12-09 | 2025-03-11 | 2025-05-23 | 2025-09-11 | -120 | -133
NSS-A2147186940 | FAT Report and Documentation | 0% | 15 | 2024-12-09 | 2025-01-13 | 2024-12-09 | 2025-01-13 | 2025-05-23 | 2025-06-17 | -120 | -112
NSS-A2147186820 | FAT- closure of open points and approval | 0% | 20 | 2024-12-16 | 2025-01-27 | 2024-12-16 | 2025-01-27 | 2025-06-03 | 2025-07-02 | -122 | -113
NSS-A2147186830 | Quality gate review and approval | 0% | 32 | 2025-01-17 | 2025-03-03 | 2025-01-17 | 2025-03-03 | 2025-06-24 | 2025-09-03 | -113 | -133
NSS-A2147186980 | Testing of beam monitors prior to shipment and related documentation | 0% | 20 | 2025-01-28 | 2025-02-24 | 2025-01-28 | 2025-02-24 | 2025-07-03 | 2025-08-27 | -113 | -133
NSS-A2147186920 | Shipping period for the Beam monitors | 0% | 10 | 2025-02-25 | 2025-03-10 | 2025-02-25 | 2025-03-10 | 2025-08-28 | 2025-09-10 | -133 | -133
NSS-A2147186840 | Delivery of Beam monitor, electronics and racks | 0% | 0 |  | 2025-03-11 |  | 2025-03-11 |  | 2025-09-11 | 0 | -133
NSS-A2147186860 | Instrument readiness review (IRR) | 0% | 0 |  | 2025-03-11 |  | 2025-03-11 |  | 2025-09-11 | 0 | -133
NSS-A2147186870 | IRR approval | 0% | 20 | 2025-03-12 | 2025-04-08 | 2025-03-12 | 2025-04-08 | 2025-09-12 | 2025-10-09 | -133 | -133
NSS-A2147186970 | TG4 completed for Beam monitors and racks | 0% | 0 |  | 2025-04-08 |  | 2025-04-08 |  | 2025-10-09 | 0 | -133
NSS-A2147186880 | Installation of Beam monitors and racks | 0% | 10 | 2025-04-09 | 2025-04-24 | 2025-04-09 | 2025-04-24 | 2025-10-10 | 2025-10-23 | -133 | -131
NSS-A2147186890 | CEP interface | 0% | 15 | 2025-04-09 | 2025-05-02 | 2025-04-09 | 2025-05-02 | 2025-10-10 | 2025-10-30 | -133 | -130
NSS-A2147186950 | CUP interface | 0% | 10 | 2025-04-09 | 2025-04-24 | 2025-04-09 | 2025-04-24 | 2025-10-10 | 2025-10-23 | -133 | -131
NSS-A2147186960 | ECDC-ICS integration (EPICS/NICOS) and Pre installation testing | 0% | 10 | 2025-04-09 | 2025-04-24 | 2025-04-09 | 2025-04-24 | 2025-10-10 | 2025-10-23 | -133 | -131
NSS-A2147186930 | Test readiness review (TRR) and approval | 0% | 10 | 2025-05-05 | 2025-05-16 | 2025-05-05 | 2025-05-16 | 2025-10-31 | 2025-11-13 | -130 | -130
NSS-A2147186900 | System Acceptance Test (SAT) | 0% | 5 | 2025-05-19 | 2025-05-23 | 2025-05-19 | 2025-05-23 | 2025-11-14 | 2025-11-20 | -130 | -130
NSS-A2147186910 | SAT approval | 0% | 10 | 2025-05-26 | 2025-06-11 | 2025-05-26 | 2025-06-11 | 2025-11-21 | 2025-12-04 | -130 | -127
Formulas:
Variance start date = IF([Start (juni lockdown)]<>0&[Finish (juni lockdown)]<>0,+NETWORKDAYS([Start (december lockdown)],[Start (juni lockdown)]),"")
Variance finish date = IF([Finish (juni lockdown)]<>0&[Finish (december lockdown)]<>0,+NETWORKDAYS([Finish (december lockdown)],[Finish (juni lockdown)]),"")