## Slide 1: BEER ICEB
CRITICAL PATHS, SCHEDULE ETC

## Slide 2: Schedule adherence
Most months – BEER is above average on schedule accuracy
Chart: Started activities: Planned vs Achieved
| 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748
Planned start | 5 | 4 | 7 | 4 | 1 | 4 | 2 | 6 | 12 | 6
Achieved start | 3 | 2 | 5 | 4 | 1 | 4 | 1 | 5 | 11 | 5
% starts achieved | 0.6 | 0.5 | 0.71429 | 1 | 1 | 1 | 0.5 | 0.83333 | 0.91667 | 0.83333
% starts achieved NSS | 0.88 | 0.6 | 0.68 | 0.56198 | 0.7651 | 0.81928 | 0.65476 | 0.59494 | 0.57488 | 0.74
Chart: Finished activites: Planned vs Achieved
| 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748
Planned finish | 2 | 6 | 2 | 5 | 1 | 4 | 2 | 5 | 13 | 10
Achieved finish | 1 | 5 | 1 | 5 | 0 | 4 | 0 | 4 | 10 | 9
% finish achieved | 0.5 | 0.83333 | 0.5 | 1 | 0 | 1 | 0 | 0.8 | 0.76923 | 0.9
% finish achieved NSS | 0.74 | 0.55 | 0.56 | 0.52381 | 0.65823 | 0.80374 | 0.57396 | 0.63277 | 0.62946 | 0.68
ICEB in May-25
Notes: June and july – development code, not in the NPR report

## Slide 3: Schedule adherence
Lower than before
Chart: Started activities: Planned vs Achieved
| 45778 | 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082 | 46113
Planned start | 15 | 9 | 1 | 12 | 13 | 10 | 12 | 2 | 8 | 8
Achieved start | 9 | 9 | 1 | 9 | 7 | 2 | 9 | 2 | 2 | 4
% starts achieved | 0.6 | 1 | 1 | 0.75 | 0.53846 | 0.2 | 0.75 | 1 | 0.25 | 0.5
% starts achieved NSS | 0.68 | 0.65 | 0.65 | 0.56 | 0.52 | 0.7 | 0.61 | 0.64 | 0.59 | 0.64
Chart: Finished activites: Planned vs Achieved
| 45778 | 45809 | 45870 | 45901 | 45931 | 45962 | 46023 | 46054 | 46082 | 46113
Planned finish | 14 | 7 | 3 | 11 | 15 | 13 | 9 | 4 | 4 | 8
Achieved finish | 10 | 7 | 1 | 4 | 6 | 6 | 7 | 2 | 0 | 0
% finish achieved | 0.71429 | 1 | 0.33333 | 0.36364 | 0.4 | 0.46154 | 0.77778 | 0.5 | 0 | 0
% finish achieved NSS | 0.64 | 0.61 | 0.58 | 0.46 | 0.49 | 0.62 | 0.52 | 0.51 | 0.63 | 0.56
Notes: June and july – development code, not in the NPR report

## Slide 4: Lookout - future activities
There’s a lot in the pipeline..
Chart: Planned starts
| 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357
Planned start | 2 | 8 | 8 | 7 | 5 | 17 | 26 | 18 | 17 | 11 | 9
Achieved start | 2 | 2 | 4
Chart: Planned finishes
| 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357
Planned finish | 4 | 4 | 8 | 13 | 8 | 14 | 15 | 34 | 13 | 19 | 5
Achieved finish | 2 | 0 | 0

## Slide 5: TG5 Approval dates
This table shows the TG5 date from the replanning. All instruments have had their TG5 date slip. Additionally, we have seen schedule compression and several milestones slipping.
For several instrument, one partner scope is driving the completion of the instrument project.
*combined TG5/SAR and iSRR meeting
Tranche 2 and 3 - Since the replanning
Instrument | Replanning close-out | March 26 lockdown | Slip (months)
BEER | 05-aug-26 | 02-jun-27 | -10,3
ESTIA | 05-dec-25 | 18-aug-26* | -7,35
TREX | 23-jun-27 | 07-dec-27 | -4,9
MAGIC | 13-jan-27 | 26-May-27 | -4,55
HEIMDAL | 20-May-27 | 24-sep-27 | -3,55
CSPEC | 26-aug-27 | 16-nov-27 | -2,9
SKADI | 07-dec-26 | 19-feb-27 | -2,2
FREIA | 23-feb-27 | 13-apr-27 | -1,65
MIRACLES | 11-jun-27 | 17-aug-27 | -1,35
PAC.17
Notes: In two years, Beer has moved 10 months.
Activity Name
New schedule baseline
TG5 (Replanning)
TG5 PMB (Baseline)
ESTIA: Final TG5 Jun 2024
2025-12-05
2024-05-02
BEER: Final TG5 Jun 2024
2026-08-17
2024-03-28
FREIA: Final TG5 Jun 2024
2027-02-23
2025-12-08
MIRACLES: Final TG5 Jun 2024
2027-06-14
2025-12-16
MAGIC: Final TG5 Sep 2024
2027-01-13
2025-03-17
CSPEC: Final TG5 Sep 2024
2027-08-26
2026-04-02
SKADI: Final TG5 Jan 2025
2026-12-16
2025-08-18
T-REX: Final TG5 Jan 2025
2027-06-14
2026-06-30
HEIMDAL: Final TG5 Jan 2025
2027-05-20
2026-02-02

## Slide 6
Beer Critical Paths
Data from P6 August 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
*Dependant on pre-alignement of chopper support before bunker closing in 2025. Chopper installation completed in first bunker opening after BOT.
2025
2027
No. 1 - Critical Path
(0 days TF)
No. 4 - Critical Path
(36 days TF)
No. 2 - Critical Path
(19 days TF)
No. 3 - Critical Path
(21 days TF)
Today
2025
2026
2027
66 days
85 days
201 days
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Aug 2025 - Oct 2025
81 days
Aug 2025 - Nov 2025
Sample Tower Support: Design phase (Hereon)
77 days
Nov 2025 - Mar 2026
Sample Tower Support: Procurement and Manufacturing phase (Hereon)
50 days
Mar 2026 - May 2026
Sample Tower Support, Hexapod and Rotary Stage: Installation phase (Hereon)
96 days
May 2026 - Sep 2026
MCA: Energization and Commissioning phase for sub-systems (Hereon)
81 days
Aug 2025 - Nov 2025
Detector Support: Design phase (Hereon)
83 days
Nov 2025 - Mar 2026
Detector Support: Procurement and Manufacturing phase (Hereon)
43 days
Mar 2026 - May 2026
Detector Support: Installation phase (Hereon)
Supports for guides and choppers: Design phase (Hereon)
Supports for guides and choppers: Procurement and Manufacturing phase (Hereon)
Nov 2025 - Sep 2026
In-bunker choppers, bispectral switch and heavy shutter : Installation and commissioning phase (Hereon)*
Aug 2025 - Nov 2025
133 days
bunker closed
Jan 2026 - Jul 2026
185 days
Aug 2025 - Apr 2026
RCM: Manufacturing phase (Hereon)
49 days
Apr 2026 - Jun 2026
RCM, Detector and BM: Installation phase (Hereon)
50 days
Jun 2026 - Sep 2026
MCA: Energization and Commissioning phase for sub-systems (Hereon)
TG5/SAR approval
Mar 3, 2027
Start of CC
Oct 1, 2026
Final TG3
Feb 13, 2026
Last ICEB
Notes: 2025-07
TG5 delayed 1 month
Sample tower design delayed 2 months
RCM manufacturing delayed 1 month
Detector Support design delayed 2 months
2025-06
Delay on design for supports for guide and choppers 1,5 months.
2025-04
All design are delayed
CEP - Start installation beginning of Nov - > to be finalized in February
2025-03
Linked to bunker opening. Chopper supports delayed
Sample tower supports 3 months delay
2024-10
MCA, CEP and ICS has been added
The cave is no longer the 1st CP. Sample tower and detector support is now driving

## Slide 7
Beer Critical Paths
Data from P6 May 2026
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
2026
2027
No. 3 - Critical Path
(56 days TF)
No. 1 - Critical Path
(0 days TF)
No. 2 - Critical Path
(45 days TF)
No. 4 - Critical Path
(67 days TF)
Today
2026
2027
50 days
Q2
Q3
Q4
Q1
Q2
81 days
May 2026 - Aug 2026
Sample Tower Support: Procurement and Manufacturing phase (Hereon)
15 days
Aug 2026 - Sep 2026
Sample Tower Support, Hexapod and Rotary Stage: Installation phase (Hereon)
48 days
Sep 2026 - Nov 2026
MCA: Commissioning phase for sub-systems (Hereon)
97 days
May 2026 - Sep 2026
Detector Support: Design phase (Hereon)
65 days
Aug 2026 - Nov 2026
Detector Support: Procurement and Manufacturing phase (Hereon)
68 days
Nov 2026 - Feb 2027
Detector (incl. supports) and RCM: Installation and commissioning phase (Hereon & ESS)
Jul 2026 - Oct 2026
In-bunker choppers, bispectral switch and MCA : Installation phase (Hereon)
97 days
May 2026 - Sep 2026
Detector+ BM: Manufacturing phase incl. delivery (Hereon)
5 days
Feb 2027 - Feb 2027
Final integrated testing
Back into CP01 with 56 days float
Nov 18
0 days
63 days
May 2026 - Jul 2026
Supports for guides and choppers (array 1): Procurement and Manufacturing phase (Hereon)
Back into CP01 with 45 days float
Dec 1
0 days
Back into CP01 with 67 days float
Sep 14
0 days
10 days
Oct 2026 - Oct 2026
MCA: Commissioning phase for sub-systems
30 days
Oct 2026 - Dec 2026
Chopper: Commissioning phase
Q3
TG5/SAR approval
Jul 8, 2027
Cold Commissioning of TG5 scope complete
Feb 26, 2027
Final TG3
Nov 24, 2026
0 days
0 days
0 days
Notes: 2026-05
Det support: 25 days delayed
2026-02
Det support: 40 days delayed
Supports for guides and choppers: 39 days delayed
TG5: 18 days delayed
2026-01
Sample tower 40 days delay (in December period)
Detector support: 17 days delay in the period (55days in the last couple of months)
Chopper supports: 10 days delay in the period
Detector: 60 days delay (in December period)
2025-10
Sample tower design delayed 2 months
Sample tower manufacturing delayed 1 months
Detector support design delayed 3 months
Detector support manufacturing delayed 1,5 months
Final TG3 delayed 3 months
2025-07
TG5 delayed 1 month
Sample tower design delayed 2 months
RCM manufacturing delayed 1 month
Detector Support design delayed 2 months
2025-06
Delay on design for supports for guide and choppers 1,5 months.
2025-04
All design are delayed
CEP - Start installation beginning of Nov - > to be finalized in February
2025-03
Linked to bunker opening. Chopper supports delayed
Sample tower supports 3 months delay
2024-10
MCA, CEP and ICS has been added
The cave is no longer the 1st CP. Sample tower and detector support is now driving

## Slide 8: Estimated TG5/SAR approval dates
2026
2029
Extrapolated (using each instruments own slip rate**)
Extrapolated (using average slip rate*)
June 2024 (Replanning close out)
April 2026 lockdown
Today
2026
2027
Q3
Q4
Q1
Q2
Q3
May 2028
0 days
BeerTG5/SAR approval
Oct 2027
0 days
BeerTG5/SAR approval
Aug 2026
0 days
BeerTG5/SAR approval
2028
Q4
Q1
Q2
Q3
Q4
Q1
Dec 2029
0 days
.
Dec 2029
0 days
.
Dec 2029
0 days
.
Dec 2029
0 days
.
Dec 2029
0 days
.
2029
Q2
Q3
Q4
Jun 2027
0 days
BeerTG5/SAR approval
Dec 2029
0 days
.
*5 working days (T2T3 instrument average slip per month)
**9 working days (Beer average slip per month)
Note, tentative date (from progress meetings in May): 8th of July

## Slide 9: NSS Replanning Evaluation
BEER ICEB – Follow up

## Slide 10: Activities with > ≈4 months delay
Comparing June 2024 with April 2025 and August 2025
Activity Name | Start date (Aug 25) | Finish date (Aug 25) | Start date (April 25) | Finish date (April 25) | Start date (June 24) | Finish date (June 24) | Variance finish date (month)
BEER: In-Bunker Guides Chopper section: CDR/TG3 Closure of open points and approval | 27-Jun-25 | 11-July-25 | 26-May-25 | 11-jun-25 | 04-sep-24 | 17-sep-24 | - 10,7
BEER: Supports for Guides and Choppers: CDR/TG3 Closure of open points and approval | 13-Sep-24 A | 31-Oct-25 | 13-Sep-24 A | 18-jul-25 | 09-sep-24 | 20-sep-24 | - 14,55
BEER: Supports for Guides and Choppers: Factory Acceptance Test (FAT) | 17-Nov-25 | 27-Nov-25 | 27-Oct-25 | 31-Oct-25 | 25-mar-25 | 31-mar-25 | - 8,7
BEER: Cave: FAT closure of open pts and approval | 17-Sep-25 | 30-Sep-25 | 03-sep-25 | 16-sep-25 | 14-feb-25 | 27-feb-25 | - 7,7
BEER: RCM: Factory Acceptance Test (FAT) | 04-Mar-26 | 24-Mar-26 | 24-nov-25 | 15-dec-25 | 29-jan-25 | 19-feb-25 | - 14,25
BEER: Sample Tower Support: CDR/TG3 Closure of open points and approval | 10-Nov-25 | 21-Nov-25 | 09-sep-25 | 22-sep-25 | 24-apr-25 | 08-May-25 | - 7,1
** Support plan has been updated into 3 sections and the presented date is the latest section, First Array

## Slide 11: Dates keep on moving to the right…
Chart: time (progress collection)
| 45552 | 45819 | 45849
BEER: In-Bunker Guides Chopper section: CDR/TG3 Closure of open points and approval | 45444 | 45748 | 45870
BEER: Supports for Guides and Choppers: Factory Acceptance Test (FAT) | 45444 | 45748 | 45870
BEER: Cave: FAT closure of open pts and approval | 45444 | 45748 | 45870
BEER: RCM: Factory Acceptance Test (FAT) | 45444 | 45748 | 45870
BEER: Sample Tower Support: CDR/TG3 Closure of open points and approval | 45444 | 45748 | 45870
BEER: Supports for Guides and Choppers: CDR/TG3 Closure of open points and approval | 45444 | 45748 | 45870

## Slide 12
Beer Critical Paths
Data from P6 August 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
*Dependant on pre-alignement of chopper support before bunker closing in 2025. Chopper installation completed in first bunker opening after BOT.
2025
2027
No. 1 - Critical Path
(0 days TF)
No. 4 - Critical Path
(36 days TF)
No. 2 - Critical Path
(19 days TF)
No. 3 - Critical Path
(21 days TF)
Today
2025
2026
2027
66 days
85 days
201 days
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Aug 2025 - Oct 2025
81 days
Aug 2025 - Nov 2025
Sample Tower Support: Design phase (Hereon)
77 days
Nov 2025 - Mar 2026
Sample Tower Support: Procurement and Manufacturing phase (Hereon)
50 days
Mar 2026 - May 2026
Sample Tower Support, Hexapod and Rotary Stage: Installation phase (Hereon)
96 days
May 2026 - Sep 2026
MCA: Energization and Commissioning phase for sub-systems (Hereon)
81 days
Aug 2025 - Nov 2025
Detector Support: Design phase (Hereon)
83 days
Nov 2025 - Mar 2026
Detector Support: Procurement and Manufacturing phase (Hereon)
43 days
Mar 2026 - May 2026
Detector Support: Installation phase (Hereon)
Supports for guides and choppers: Design phase (Hereon)
Supports for guides and choppers: Procurement and Manufacturing phase (Hereon)
Nov 2025 - Sep 2026
In-bunker choppers, bispectral switch and heavy shutter : Installation and commissioning phase (Hereon)*
Aug 2025 - Nov 2025
133 days
bunker closed
Jan 2026 - Jul 2026
185 days
Aug 2025 - Apr 2026
RCM: Manufacturing phase (Hereon)
49 days
Apr 2026 - Jun 2026
RCM, Detector and BM: Installation phase (Hereon)
50 days
Jun 2026 - Sep 2026
MCA: Energization and Commissioning phase for sub-systems (Hereon)
TG5/SAR approval
Mar 3, 2027
Start of CC
Oct 1, 2026
Final TG3
Feb 13, 2026
Notes: 2025-07
TG5 delayed 1 month
Sample tower design delayed 2 months
RCM manufacturing delayed 1 month
Detector Support design delayed 2 months
2025-06
Delay on design for supports for guide and choppers 1,5 months.
2025-04
All design are delayed
CEP - Start installation beginning of Nov - > to be finalized in February
2025-03
Linked to bunker opening. Chopper supports delayed
Sample tower supports 3 months delay
2024-10
MCA, CEP and ICS has been added
The cave is no longer the 1st CP. Sample tower and detector support is now driving

## Slide 13: Agenda
BEER replanning evaluation
Replanning recap and updates
Replanning evaluation
Schedule adherence
Earned value
Critical paths
Bunker access

## Slide 14: Beer replanning finalized in June 2024
Chart: Number of activites
| Number of activities before replanning (P6) | Number of activities after replanning (P6)
ESTIA | 89 | 430
SKADI | 53 | 592
BEER | 105 | 569
FREIA | 58 | 764
HEIMDAL | 89 | 828
MIRACLES | 95 | 708
MAGIC | 97 | 833
TREX | 209 | 981
CSPEC | 165 | 1034
VESPA | 109 | 1093
COMMON PROJECTS T2T3 | 715 | 2095
More details in P6 : TA milestones + detailed plan
We have more information in P6.
How can we use this information:
to plan/coordinate (installation, commissioning etc.)
keep track of progress (updating monthly instrument dashboards with replanning dates)
make informed decisions about priorities
BEER has 312 open activities in P6:
70 TA activities
242 activities from detailed plan

## Slide 15: Simplified view of the P6 landscape
Linking an instrument plan to common projects and technology groups
ICS – control
ICS – network
ICS – PSS
CEP
MCA
CUP
Detectors
(BM, Detector integration, Detector… )
Choppers
Vacuum
Instrument plan
Output:
Installation team
Q-gate team
Controllers
….

## Slide 16: Common projects replanning T2T3
Linked to P6 instrument plans
Information has been sent out in the NSS Progress Report
*Draft plan in place linked to the instrument plan. Further review might be needed with wp manager and instrument teams
Instrument | CEP | MCA | CUP | Choppers | Detectors | BM | ICS Network | ICS PSS
ESTIA | YES | YES | YES | YES | YES: MB | YES | YES | YES
SKADI | YES | YES* | YES | YES (Racks) | N/A | YES* | YES* | YES*
BEER | YES | YES* | YES | YES | N/A | YES* | YES* | YES*
MAGIC | YES | YES* | YES | YES | N/A |  | YES* | YES*
FREIA | YES | YES* | YES | YES (Racks) | YES: MB |  | YES* | YES*
HEIMDAL | YES | YES* | YES | YES | N/A |  | YES* | YES*
MIRACLES | YES | YES* | YES | YES (Racks) | N/A |  | YES* | YES*
CSPEC | YES | YES* | YES | N/A | YES: He3 |  | YES* | YES*
T-REX | YES | YES* | YES | YES | YES: MG |  | YES* | YES*
VESPA |  |  |  |  |  |  |  | 

## Slide 17: Schedule adherence
Most months – BEER is above average on schedule accuracy
Chart: Started activities: Planned vs Achieved
| 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748
Planned start | 5 | 4 | 7 | 4 | 1 | 4 | 2 | 6 | 12 | 6
Achieved start | 3 | 2 | 5 | 4 | 1 | 4 | 1 | 5 | 11 | 5
% starts achieved | 0.6 | 0.5 | 0.71429 | 1 | 1 | 1 | 0.5 | 0.83333 | 0.91667 | 0.83333
% starts achieved NSS | 0.88 | 0.6 | 0.68 | 0.56198 | 0.7651 | 0.81928 | 0.65476 | 0.59494 | 0.57488 | 0.74
Chart: Finished activites: Planned vs Achieved
| 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748
Planned finish | 2 | 6 | 2 | 5 | 1 | 4 | 2 | 5 | 13 | 10
Achieved finish | 1 | 5 | 1 | 5 | 0 | 4 | 0 | 4 | 10 | 9
% finish achieved | 0.5 | 0.83333 | 0.5 | 1 | 0 | 1 | 0 | 0.8 | 0.76923 | 0.9
% finish achieved NSS | 0.74 | 0.55 | 0.56 | 0.52381 | 0.65823 | 0.80374 | 0.57396 | 0.63277 | 0.62946 | 0.68
Notes: June and july – development code, not in the NPR report

## Slide 18: Critical paths T2T3
When a delay impacts the end date of a project
  We measure float towards the instrument’s TG5
  The first critical path has 0 float. If there’s a delay of 1 month, TG5 will shift 1 month.
  If the second critical path has 2 months float, it will push TG5 if there’s a delay of more than 2 months.
  The length of an activity reflects the start and the end of an activity, not the amount of time spent during that time period.
  The critical paths reflect the activities that are critical from a schedule perspective, not necessarily critical from a scientific or technical perspective.
  Activities on the critical paths should a priority for all of us!

## Slide 19
2025
2027
No. 1 - Critical Path
(0 days TF)
No. 2 - Critical Path
(16 days TF)
No. 3 - Critical Path
(20 days TF)
No. 4 - Critical Path
(120 days TF)
Today
2025
2026
2027
79 days
Supports for guides and choppers: Design phase (Hereon)
88 days
Supports for guides and choppers: Procurement and Manufacturing phase (Hereon)
213 days
Nov 2025 - Sep 2026
In-bunker choppers, bispectral switch and heavy shutter : Installation and commissioning phase (Hereon)*
Jul 2025 - Nov 2025
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Apr 2025 - Jul 2025
125 days
Apr 2025 - Sep 2025
Sample Tower Support: Design phase (Hereon)
93 days
Sep 2025 - Jan 2026
Sample Tower Support: Procurement and Manufacturing phase (Hereon)
45 days
Jan 2026 - Apr 2026
Sample Tower Support, Hexapod and Rotary Stage: Installation phase (Hereon)
101 days
Apr 2026 - Aug 2026
MCA: Energization and Commissioning phase for sub-systems (Hereon)
125 days
Apr 2025 - Sep 2025
Detector Support: Design phase (Hereon)
129 days
Sep 2025 - Mar 2026
Detector Support: Procurement and Manufacturing phase (Hereon)
43 days
Mar 2026 - May 2026
Detector Support: Installation and Commissioning phase (Hereon)
41 days
May 2026 - Jul 2026
Detector, BM, RC** and MCA: Installation and Commissioning phase (Hereon)
121 days
Apr 2025 - Sep 2025
Cave: Manufacturing phase (NPI)
105 days
May 2025 - Oct 2025
Cave: Installation phase (NPI)
91 days
Oct 2025 - Feb 2026
CEP, CUP and ICS: Installation and Energization (ESS)
TG5/SAR approval
Feb 16, 2027
Start of CC
Sep 15, 2026
Final TG3
Dec 1, 2025
Beer Critical Paths
Data from P6 April 2025 lockdown
Design phase ends at CDR approval
Procurement and Manufacturing phase ends at FAT closure of open points
Installation and Commissioning phase ends at SAT approval
TF: number days of total float to Instrument’s TG5
*Dependant on pre-alignement of chopper support before bunker closing in 2025. Chopper installation completed in June 2026 (first bunker opening after BOT)
**RCM manufacturing has 13 days float
Notes: 2025-04
All design are delayed
CEP - Start installation beginning of Nov - > to be finalized in February
2025-03
Linked to bunker opening. Chopper supports delayed
Sample tower supports 3 months delay
2024-10
MCA, CEP and ICS has been added
The cave is no longer the 1st CP. Sample tower and detector support is now driving

## Slide 20: Key milestones

## Slide 21: Activities with > ≈4 months delay
Comparing June 2024 with April 2025
Activity Name | Start date (April 25) | Finish date (April 25) | Start date (June 24) | Finish date (June 24) | Variance finish date (month)
BEER: In-Bunker Guides Chopper section: CDR/TG3 Closure of open points and approval | 26-May-25 | 11-jun-25 | 04-sep-24 | 17-sep-24 | -8,7
BEER: Supports for Guides and Choppers: CDR/TG3 Closure of open points and approval | 13-Sep-24 A | 18-jul-25 | 09-sep-24 | 20-sep-24 | -9,85
BEER: Supports for Guides and Choppers: Factory Acceptance Test (FAT) | 27-Oct-25 | 31-Oct-25 | 25-mar-25 | 31-mar-25 | -6,35
BEER: Cave: FAT closure of open pts and approval | 03-sep-25 | 16-sep-25 | 14-feb-25 | 27-feb-25 | -6,8
BEER: RCM: Factory Acceptance Test (FAT) | 24-nov-25 | 15-dec-25 | 29-jan-25 | 19-feb-25 | -9,3
BEER: Sample Tower Support: CDR/TG3 Closure of open points and approval | 09-sep-25 | 22-sep-25 | 24-apr-25 | 08-May-25 | -3,65

## Slide 22: Earned value
Scheduled (in the replanning June 2024) vs. performed (April 2025)
NPI: Cave, hutch behind schedule, but progressing well
Hereon: Choppers and Neutron Optic support behind schedule
Budget for CEP, CUP and MCA to be transferred when CR:s have been agreed.
To note: Some budget holder for Hereon “Tollgates and milestones” were missing links in the replanning and were planned for June/Oct 25 and started in 2024 (TG3.3 Detectors and Support plus Radial Collimators & TG4.7 BBG, BWI, Choppers and Neutron optics in bunker and support)

## Slide 23: Earned value
Scheduled in replanning (blue) vs. performed (red)
vs.

## Slide 24: Bunker next steps
  Closing roof D03 side – after summer
  West access is extended to Aug 29th,
  Roof installation starts September 1st
  Extra access before BOT currently mid Oct - mid Dec 2025. Under discussion.
  Post BOT access:
  First access after BOT: summer 2026
  Second access after BOT: xmas 2026
  Third access after BOT: summer 2027