## Slide 1: TAC 13
Hector Novella
Deputy project manager
www.europeanspallationsource.se
2016-04
Parallel Sessions - Integrated Control System
ICS project replanning

## Slide 2: ICS project replanning TAC 13
Outline
ICS planning process
ICS planning implementation
ICS planning status

## Slide 3: ICS project replanning TAC 13
Outline
ICS planning process
  Boundaries
  Scheduling process
  System life cycle stages and milestones
  Top level scope decomposition
ICS planning implementation
ICS planning status

## Slide 4: ICS planning process Foundations
Based on ESS Process for Planning (ESS-0019598)
  Conformant with ISO/IEC 15288 (Systems Engineering)
Approach taken:
  ICS construction planning is Schedule oriented (vs Cost) and Time oriented (vs Resource).
  Top-down approach for most of the plan, with some refinements bottom-up.
  Rolling out detail in stages.
  One plan (work packages or work units are integrated).
  Automated scheduling (supported by Primavera et al.).
  Deliverable or Milestone-focused (seeking robustness to uncertainties)
Notes:   Deliverable or Milestone-focused. Seeking robustness to uncertainties (scope adaptation to meet time and budget)

## Slide 5: Boundaries ICS planning process
Fixed budget for ICS. 50% cash, 50% IKC.
ICS budget may be distributed among Work Packages according to ICS criteria.
ESS Integrated Master Schedule is our reference to report on the same milestones.
ESS top level requirements for reliability and availability set the quality level of ICS deliverables.

## Slide 6: Scheduling process ICS planning process
Plan from the top down
  Start thinking about the overall project deliverables
  Break down into greater detail
Add tasks and milestones
  Outlining deliverables and activities (in a measurable way)
  Timescale in relation to detail
  Key milestones at key decision points
Enter work against tasks
  Best-guess (“duration” in exceptional cases; “work” = ManMonth)
  Large-duration: rolling wave / estimated (late tasks)
Link related tasks together (logical sequence)
  Benefit from L1, L1b, L2, L2b milestones
Resource load the schedule
  IKC, personnel, services (consulting, travel, etc.)
Notes: Milestone levels:
L1: ESS Project 0
L1b: Shared among divisions
L2: ICS Project 14 relevant
L2b: Shared among Work Packages

## Slide 7: System life cycle stages and milestones ICS planning process
ISO/IEC-15288 Systems Engineering.
When no other external milestone applies.
Phase (system stages) | Milestone (end of phase)
… | 
Requirements | SRR: System Requirements Review
Design | PDR: Preliminary Design Review
 | CDR: Critical Design Review
Development (from design to complete system) | TRR: Test Readiness Review
Integration and Test (conformance to requirements) | SAR: System Acceptance Review
Production (system into operation, resolve problems from Integration and Test) | 
 | ORR: Operational Readiness Review
Operation & Maintenance | (yearly? maintenance review)
Disposal | …
Construction Phase
Initial Ops
Operations Phase

## Slide 8: Top level scope decomposition ICS planning process
Work package 01 Management and administration
Work package 06 Equipment
Work package 07 Control system infrastructure
Work package 09 Personnel safety systems
Work package 05 Machine protection
Work package 03 Software core
Work package 02 Software Applications
Work package 08 Physics
Work package 04 Hardware core
Work package 14 Test Stands
Work package 13 Integration - Conventional facilities
Work package 10 Integration - Accelerator
Work package 11 Integration - Target
Work package 12 Integration - Instruments
Work package 20 Installation

## Slide 9: ICS project replanning TAC 13
Outline
ICS planning process
ICS planning implementation
  Rationale under ICS planning
  Graphical example
  PSS correlated overview
  MP correlated overview
  CS integration correlated overview
  Beam on Target challenges
  High level schedule – Project ICS
ICS planning status
Further ToDo:s

## Slide 10: ICS planning implementation Overview
input
ICS Project Charter*
input
ICS Concept
output
output
output
ICS Planning
ICS Requirements*
ICS Schedule*
ICS Project Mgmt Plan**
* Ongoing
** Pending

## Slide 11: Rationale under ICS planning ICS planning implementation
To help seeing the relation of ICS activities with the rest of ESS systems, we can categorize them according to what is needed to switch-on the Machine.
ICS critical activities are:
  PSS (Personnel Safety System)
  MPS (Machine Protection System) integration
  CS (Control System) integration
ICS enabling activities are:
  Software core systems
  CS development
  Hardware core systems
  Infrastructure
ICS complementing activities are:
  Operations oriented applications
  Physics oriented applications
High Dependencies on other Division’s specifications
Minimum Viable Product to guarantee Beam on Target for ICS activities
Notes: This will give us an idea of prioritization.

## Slide 12: Beam on Target challenges ICS planning implementation
Under ICS perspective, BoT milestone implies some constraints:
PSS, MPS and control systems integration are a must.
  The scope for BoT is directly related to the effort needed in ICS.
  We believe that a scope of Low Power Beam on Target without instruments is still feasible and compatible with today’s ICS plans.
  After that BoT, a transient period with iterative extension will be needed to:
      Accommodate to a High Power Beam and Operational Modes.
      Accommodate new Neutron Scattering Systems.
  For the future success of ESS as a research facility, Operator Applications and Physics Oriented Applications is a must and requires continuous activity.
Notes: Just READ

## Slide 13: High Level Schedule – Project ICS ICS planning implementation
First Installations
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
Global & Project MS
First Beam on Target
Handover Completed
WP Integrations
WP Personnel Safety
WP Machine Protection
WP SW, HW & Infrastructure
Accelerator PSS-2 complete
Beam Interlock System installation started
Timing system components ready for procurement
Temporary control room operational
Accelerator PSS-1
Target PSS complete
1st Bldg integration complete
Controls ready for
integrated testing
#1
#2
#3
#4
#5
#6
Beam Interlock System ready
for High power beam commissioning
#1: Isrc+LEBT
#2: +RFQ+MEBT
#3: +DTL1
#4: +DTL2-4
#5: +NCFE+... to DUMP
#6: to TARGET
NMX controls ready
for cold commissioning
Notes: In this presentation, skip this fast.

## Slide 14: ICS project replanning TAC 13
Outline
ICS planning process
ICS planning implementation
ICS planning status
  Project Plan Optimization
  Conclusions

## Slide 15: ICS planning status Overview
WP | Title | Work package manager | Status | Artefacts | In P6
01 | Administration | Henrik Carling | Done | 75 | Done
02 | Software Applications | Leandro Fernandez | Ongoing |  | 
03 | Software Core | Susanne Regnell | Ongoing |  | 
04 | Hardware core | Timo Korhonen | Ongoing |  | 
05 | Machine protection system | Annika Nordt | Done | 260 | Ongoing
06 | Equipment | Timo Korhonen | Not applicable |  | 
07 | Control system infrastructure | Remy Mudingay | Done | 160 | Ongoing
08 | Physics | Garry Trahern | Done | 150 | Done
09 | Personnel safety system | Stuart Birch | Done | 250 | 
10 | Integration accelerator | Han Lee | Ongoing |  | 
11 | Integration target | Benedetto Gallese | Done | 275 | Done
12 | Integration NSS | David Brodrick | Ongoing |  | 
13 | Integration CF | Nick Levchenko | Done | 610 | Done
14 | Test stands | Daniel Piso | Pending |  | 
20 | Installation | Henrik Carling | Pending |  | 
Achievements:
Beginning to have a hierarchy of milestones.
Raised internal awareness of the importance of consistency in the plan
(EVM reports)
Some WP are now better oriented towards deliverable products and/or review milestones. Making them more robust to uncertainties.
Main missing element:
Traceable list of deliverables.
Notes: Unfortunately, not everything that I would like is done. For example:
  We still lack comprehensive milestones inside the WP:s.
  We still lack a clear view of our scope of work, reflected in deliverables traceable in the plan.
Everything takes time and not everything is yet in the MS Projects:
  I still need to synchronize some data from P6 (it is not so straightforward).
  I still need to update some MS Projects with data from the Excel files we were working up until now.
  Then I would like to define L2 (ICS level), L2b (between ICS WPs) and L3 (inside a WP) milestones.
  I would also like to include the Deliverables for each WP.
  Finally, I would like to simplify the way the activities are expressed, to make our monthly reports more consistent and predictable. (with the use of milestones and deliverable linkage).

## Slide 16: Project plan optimization ICS planning status

## Slide 17: Conclusions ICS planning status
The previous slides show part of the work done during the last 4 months.
ICS construction cost estimates do not include all research and development costs from other areas/labs that are needed to support ICS.
Furthermore, since significant R&D activities to support ICS remain to be completed and technical uncertainties persist, the cost of ICS could grow and completion could take longer.
To avoid cost increases and schedule delays ICS is trying to improve on management and oversight. With emphasis on having an integrated management team.
Independent reviews are expected to be effective on examining both the construction project and its supporting external activities (R&D, IKC).
Focus on (1) planning for the complexities associated with assembling and installing the linac controls along with the target and instrument controls in stages, and (2) refining the cost estimations as soon as new data is disclosed. Supported on more systems engineering focus within ICS work package managers; in order to better identify the full scope of ICS and realistically estimate the project’s engineering complexities.
Project management decisions could be affected by unrealistic budgets (IKC) or the fast-track construction strategy imposing substantial cost pressures.