## Slide 1: Integrated Control System Infrastructure and Main Control Room TAC 13
Remy Mudingay
ESS/ICS
2016-04

## Slide 2: Content
Introduction
Control System Infrastructure Scope
Control Room Work Unit
Control Room Project
Standard
Working Group
Standard
MCR location
Documentation

## Slide 3: Control System Infrastructure WP 7 Scope
The scope of this work package is to design, develop and procure the IT infrastructure required for the Control System to operate.
It has the following work units:
Control Room 7.1
  Design and implementation of the centralized ESS Control Room, which allows the Accelerator, Target, Neutron Instruments and Conventional Facilities to be monitored and controlled from the same room.
Data Centre 7.2
  Provide servers and file storage infrastructure required for normal operation during development, commissioning and operations phase.
Control System Networks 7.3
  Design and implementation of the networks between IO Controllers, Control Room(s) and Data Centre.
  Covers the efforts and material required for connecting devices to the ICS through to the IO Controllers.
Notes:   Is the scope for the infrastructure work package appropriate and precise enough?

## Slide 4
Main Control Room

## Slide 5: Control Room Work Unit
In-Kind agreement with Norway
  IFE (Institute for Energy Technology)
  Three Stages (Technical Annexes)
    Stage 1 – (2015 Q4/2016 Q2)
      Preliminary/Conceptual Design
      Semi-monthly meetings
        Accomplishments
        Activities for the next period
        Comments/Changes/Concerns/Risks
        Action items
    Stage 2 TBD (2016 Q3/2017 Q3)
      Detailed Design
    Stage 3 TBD (2018 Q1/2019 Q2)
      V&V
      Main Control Room (MCR) realisation

## Slide 6: Control Room Stage 1 ISO 11064 Ergonomic design of Control Centres
Phase C: Conceptual Design 2016-05-09
Phase B: Analysis & Definition 2016-03-16
Phased approach
Participatory process
Best practice
  High level functions
  Task analysis
  Task synthesis + link analysis
  Diagrams/functional arrangements
  Workstation layouts
  Room layout
  CAD model
  User group
  Visit and documentation
  - other facilities.
  Done: (CERN, PSI, Diamond)
      Phase A: Clarification 2016-01-29
✔
Environment
Machine
(Hardware & Software)
Operations & Management
Human
Objectives
Design Process
Preliminary Design 2016-06-17
Review

## Slide 7: Clarification Phase – Completed Stage 1, Phase A
Interviews
Deliverable
Safety and Security
Operation and Control
Work organization
Work environment
Requirements
Constraints
Summary report
ESS-0052323

## Slide 8: Clarification Phase Participants Stage 1, Phase A
Interview Type | Stakeholders |  |  |  |  |  |  |  | 
Division | AD | CF | EIS | ESH | ICS | NSS | Operations | Target | Technical Coordinator
Operator Experience | 2 |  |  |  | 2 |  |  |  | 
Requirements & Constraints | 3 | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1
Target control, Cooling, Target Safety System (TSS)
Beam Physics, Diagnostics, Instrumentation, Cryogenics
Conventional Facilities, Building Management System (BMS)
Commissioning, Operations
Personnel Safety System (PSS), Machine Protection System (MPS), Beam Permit System(BPS)
Electronics and I&C
OpenXAL, Control System Infrastructure, Alarm Design
Fire protection, Security
Neutron Instruments
Technical coordination.

## Slide 9: Clarification Phase - MCR Functions Stage 1, ISO 11064 Phase A
Division | System/Sub-system
CF | BMS Electrical SCADA Security access Fire alarms Mobile and Radio ELV systems
ICS | Control System Infrastructure Alarm Personal Safety System Key Exchange Machine Protection System Beam Permit System
NSS | Neutron Instruments CCTV Shutter status
Target | Target Safety System Key Exchange Motion of the Target Wheel Helium flow
Division | System/Sub-system
Accelerator | Beam RF Systems Diagnostics Instrumentation Physics Source Vacuum … Cryogenics Accelerator Cryo Plant (ACCP) Target Moderator Cryo Plant (TMCP) Test and Instrument Cryo Plant (TICP) Flow Temperature Vibration
ESH | Fire protection Alarm signals Safety Ionizing radiation monitors Security Communication

## Slide 10: Analysis & Definition Phase Stage 1, ISO 11064 Phase B
User Reference Group ESS (URGE)
Staff | Division | Previous experience
Linda Coney | Target | FNAL, RAL, MICE
Emanual Laface | ICS | CERN
Marc Munoz | Accelerator | Daresbury, SLS, Alba
Annika Nordt | ICS | CERN
Thomas Shea | Accelerator | SNS, BNL, LANL
Workshop – scenario analysis (Functional & Task based)
Scenario Analyses
ESS-0052323

## Slide 11: Control Room Project summary
14.7.1 ICS Control Room work unit
  ISO 11064 Ergonomic design of Control Centres
  In-kind Stage 1:
    Phase A - Control room requirements (Done)
      Safety & Security
      Operation & Control
      Work organization
    Phase B - Functional & Task analysis (In Review)
    Phase C - Preliminary Design (Next)
  In-kind Stage 2: Detailed Design & Temporary Control Hardware
  In-Kind Stage 3: Main Control Room Hardware
The Norwegian Institute for Energy Technology (IFE) in Halden (In-kind contribution)
Interviews
Requirements
Constraints
Summary report
ESS-0052323
output
output

## Slide 12: Control Room project
MCR proper
129m2
Glass wall
Coffee/Lounge & Kitchenette Area
27m2 (22+5)
Shared
Meeting room
34m2
Total space: 206m2 + 29m2 Server room/COMMS room*

## Slide 13
Control System Data Centre
and Network

## Slide 14: Control System Data Centre
Servers
  Virtualisation infrastructure
    IO Controller
    PV Access gateway (pva2pva)
    Server Applications
      Monitoring
      Control System Services
      RDBMS/Database
      DHCP
        CSentry
      NTP
      Channel Archiver
      Logs
      Post-mortem
  Storage
    NFS
    Distributed
    Backup
      Online
      Offline
Data Centre 7.2
  Provide servers and file storage infrastructure required for normal operation during development, commissioning and operations phase.

## Slide 15: Control System Network
Fibre backbone
  Network
  Timing system
Structured cabling
  COMMS room to µTCA/iPC/IO device
Network devices
Cyber security implementations & policy
Control System Networks 7.3
  Design and implementation of the networks between IO Controllers, Control Room(s) and Data Centre.
  Covers the efforts and material required for connecting devices to the ICS through to the IO Controllers.

## Slide 16: Control System Infrastructure Needs & Timeline
2016
2017
2018
2019
Security Assessment
In-kind
Proto-typing:
Controls network
Virtualization platform (VP)
Performance/Stress & evaluation tests
Storage & VP
Applications
  Proxy
  DPI
  IDS
  EPICS gateway
Procurement
Use of RATS facility for acceptance testing
Network
Desktop computers
Storage and compute Servers
Performance/Stress & evaluation tests
Accelerator installation
Wifi in the tunnel
Remote connectivity
Site
Accelerator installation & integration
Temp. Server room
Temp Control room
  connectivity
ICS Lab
Remote connectivity
Collaboration ICS/IT /DMSC conducive
ESS Lund
Procurement
Use of RATS facility acceptance testing
Installation and
Network
Storage and compute Servers
Site
Neutron Instruments
Target
Target integration
Procurement
Network
Desktop computers
Storage and compute Servers
Performance/Stress & evaluation tests
Site
Neutron Instruments
Commissioning of all systems
Main Control room
  Connectivity
2nd Controls Server room
Where
What
When
Notes: 2016 – Working primarily in the ICS lab – Tunavägen – to proto-type both accelerator and neutron instruments control system network. Some procurement of network switches is planned Q1-Q2 2016. Other baseline metrics also needs to be identified for storage and computer needs for the EPICS control system.
2017 – Design for the controls infrastructure is completed and we move towards procuring hardware. Remote connectivity will be needed for the acceptance testing and verification at the RATS facility. Installation of the accelerator begins in earnest Q4 2017 for networks. Storage and computing for the controls network will commence Q2/Q3 2017. Site internet connectivity would be “nice to have” by the end of Q4 2017.
2018 – Accelerator installation and testing spills over throughout 2018 but work on the preparation of Target and neutron instruments begins in Q3 2018 but via the RATS facility.
2019 – Installation of Target and neutron instruments begins in Q2-Q3 2019. Some work will occur on the main control room (network) and a second sever room for controls which will mirror the CUB server room, at least for the control system.

## Slide 17: Accelerator Commissioning
Naming convention
Standard Rack
Standard Rack dimensions
Rack layout – COMMS room
ISO/IEC 11801 for generic cabling …
Standardisation ESS-0052535

## Slide 18: Regulatory requirements ICS Plan for Cyber Security
TRA
SA
Integrated Control System
  IEC 62443 Network and System security for industrial-process measurement and control
    Security assurance levels
    System security requirements and security assurance levels
Threat/Risk Assessment (TRA)
Security Assurance (SA)
Assets
Risk
Counter measures
Vulnerabilities
Threats
Assurance Techniques
Evaluation
Assurance
Confidence
Owners
produce
require
create
Gives evidence
identify
require
minimizes
to
ESS Cyber Security workshop: Feb 2016

## Slide 19: Control System Network fibre termination
Klystron gallery
Cryo
building
Central utility
Server hall
Target building
Beam lines
Control room
Substation
Substation
Dedicated COMMS room
Shared COMMS (NSS &| IT)
Cabinet
50 rack rows
2017: COMMS room
Temporary Server room
2016: Available now
2019: Server/computer room &
COMMS room

## Slide 20: ICS Network Architecture
H05
Primary Substation
COMMS room
G02
Gallery Building
COMMS room
G04
Cryogenic Plant
COMMS room
D04
Lab/Exp. Hall 2
COMMS room
D07
Lab 1B /Exp. Hall 1
COMMS room
D08
Lab 1A /Exp. Hall 1
COMMS room
E02
Beam line gallery
COMMS room
E04
Lab 3B /Exp. Hall 3
COMMS room
Route A
Route B
B01
Campus
COMMS room
H01
Server Hall
Central Utility Building
D02
MCR ICS Computer Room
D02
MCR

## Slide 21: Conceptual ESS Control System Network
Main Control Room
DMZ
ESS Network
Core Network
CA network
CA network
CA network
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW: EPICS PV Gateway (pva2pva)
Red: Accelerator
Yellow: Target & Cryogenics
Orange & Violet: Experimental halls
Blue: Conventional facilities
PVGW
PVGW
CA network
CA network
CA network
CA network
CA network
CA network